## Work Order Details
Data Extract Date | WorkOrderKey | Work Order Description | Work Type | Work Criticality | EquipmentRef | Work Order Status | Condition For Work | Status Date | Target Finish Date | Schedule Start Date | Schedule Finish Date | Work Order Priority | Department | Discipline | Work Order Remaining Hours
2019-03-31 | 2 | Work Order Description - 2 - CM | CM | 4 | 657378 | WSCHD | NORM-OPS | 2017-07-11 | 2018-12-09 | 2019-06-29 | 2019-07-02 | 4 | MAINTENANCE | MECHANICAL | 26.9167
2019-03-31 | 6 | Work Order Description - 6 - CM | CM | 4 | 436047 | SCHD | NORM-OPS | 2018-11-13 | 2019-08-26 | 2019-03-09 | 2019-04-13 | 4 | INTEGRITY | CONSTRUCTION | 31
2019-03-31 | 8 | Work Order Description - 8 - CM | CM | 4 | 499836 | WSCHD | TPS | 2018-06-08 | 2019-05-14 | 2020-05-03 | 2020-05-05 | 3 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 12 | Work Order Description - 12 - CM | CM | 4 | 450548 | SCHD | NORM-OPS | 2018-11-13 | 2019-09-18 | 2019-04-13 | 2019-04-15 | 4 | ENGINEERING | CONSTRUCTION | 49
2019-03-31 | 29 | Work Order Description - 29 - CM | CM | 4 | 497327 | WSCHD | NORM-OPS | 2017-07-06 | 2019-12-31 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 99 | Work Order Description - 99 - CM | CM | 4 | 247829 | WSCHD | TPS | 2017-07-17 | 2019-06-12 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 106 | Work Order Description - 106 - CM | CM | 4 | 327894 | WSCHD | TPS | 2017-07-17 | 2019-12-06 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 17
2019-03-31 | 118 | Work Order Description - 118 - PSCM | PSCM | 1 | 246202 | WSCHD | NORM-OPS | 2015-10-29 | 2020-12-27 | 2020-05-02 | 2020-05-02 | 2 | INTEGRITY | MECHANICAL | 5
2019-03-31 | 127 | Work Order Description - 127 - CM | CM | 4 | 215445 | WSCHD | NORM-OPS | 2013-04-06 | 2019-07-01 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | SAFETY | 19
2019-03-31 | 131 | Work Order Description - 131 - CM | CM | 4 | 326056 | WSCHD | TPS | 2017-07-17 | 2019-01-08 | 2020-12-01 | 2020-12-01 | 2 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 134 | Work Order Description - 134 - PSPM | PSPM | 1 | 361100 | WSCHD | EQUIP-ISOL | 2015-10-15 | 2022-01-01 | 2019-09-30 | 2019-09-30 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 135 | Work Order Description - 135 - PSPM | PSPM | 1 | 399547 | WSCHD | EQUIP-ISOL | 2015-10-15 | 2020-03-29 | 2021-12-26 | 2021-12-26 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 136 | Work Order Description - 136 - PSPM | PSPM | 1 | 260932 | WSCHD | EQUIP-ISOL | 2015-10-15 | 2020-01-01 | 2019-09-30 | 2019-09-30 | 1 | INTEGRITY | INSPECTION | 0.016667
2019-03-31 | 137 | Work Order Description - 137 - CM | CM | 4 | 408340 | SCHD | NORM-OPS | 2019-03-31 | 2020-06-13 | 2019-03-30 | 2019-05-05 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 138 | Work Order Description - 138 - CM | CM | 4 | 322142 | WSCHD | TPS | 2015-08-27 | 2019-11-16 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 139 | Work Order Description - 139 - CM | CM | 4 | 327971 | WSCHD | TPS | 2011-11-27 | 2019-12-17 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 140 | Work Order Description - 140 - CM | CM | 3 | 502857 | WSCHD | TPS | 2015-08-27 | 2019-05-01 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 141 | Work Order Description - 141 - CM | CM | 3 | 501333 | WSCHD | TPS | 2015-08-27 | 2019-07-22 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 142 | Work Order Description - 142 - CM | CM | 3 | 33545 | WPLAN | TPS | 2017-07-26 | 2019-07-27 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 143 | Work Order Description - 143 - CM | CM | 3 | 501028 | WPLAN | TPS | 2017-07-26 | 2019-11-13 | 2020-05-02 | 2020-05-02 | 2 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 147 | Work Order Description - 147 - CM | CM | 4 | 303827 | SCHD | TPS | 2018-09-06 | 2019-12-16 | 2019-07-13 | 2019-07-13 | 2 | INTEGRITY | MECHANICAL | 30
2019-03-31 | 179 | Work Order Description - 179 - CM | CM | 4 | 321199 | WSCHD | SYS-ISOL | 2017-07-06 | 2019-07-01 | 2019-04-27 | 2019-05-10 | 4 | INTEGRITY | SERVICES | 420
2019-03-31 | 184 | Work Order Description - 184 - CM | CM | 4 | 471166 | WSCHD | TPS | 2018-06-08 | 2019-10-19 | 2020-05-02 | 2022-03-06 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 186 | Work Order Description - 186 - CM | CM | 4 | 657423 | WPLAN | NORM-OPS | 2017-12-11 | 2019-12-11 | 2019-06-29 | 2019-07-01 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 196 | Work Order Description - 196 - CM | CM | 4 | 472264 | SCHD | NORM-OPS | 2018-09-06 | 2019-06-25 | 2019-05-18 | 2019-05-18 | 2 | INTEGRITY | SERVICES | 57
2019-03-31 | 200 | Work Order Description - 200 - CM | CM | 4 | 527177 | SCHD | NORM-OPS | 2018-06-21 | 2019-03-13 | 2019-07-13 | 2019-07-18 | 4 | INTEGRITY | CONSTRUCTION | 120
2019-03-31 | 225 | Work Order Description - 225 - CM | CM | 4 | 657124 | WSCHD | NORM-OPS | 2011-09-25 | 2019-01-27 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 252 | Work Order Description - 252 - PSPM | PSPM | 1 | 399837 | WSCHD | EQUIP-ISOL | 2015-10-15 | 2019-06-01 | 2020-09-26 | 2020-09-26 | 1 | INTEGRITY | INSPECTION | 0.016667
2019-03-31 | 254 | Work Order Description - 254 - CM | CM | 3 | 674778 | WSCHD | NORM-OPS | 2017-07-07 | 2019-10-06 | 2019-09-14 | 2019-09-17 | 2 | MAINTENANCE | MECHANICAL | 44
2019-03-31 | 258 | Work Order Description - 258 - CM | CM | 3 | 531852 | WSCHD | NORM-OPS | 2017-07-08 | 2019-06-23 | 2019-09-07 | 2019-09-08 | 2 | INTEGRITY | MECHANICAL | 28
2019-03-31 | 259 | Work Order Description - 259 - CM | CM | 3 | 362499 | WSCHD | NORM-OPS | 2011-12-02 | 2019-03-18 | 2021-03-06 | 2021-03-09 | 2 | INTEGRITY | MECHANICAL | 50
2019-03-31 | 261 | Work Order Description - 261 - CM | CM | 3 | 246202 | WSCHD | NORM-OPS | 2011-12-06 | 2020-01-10 | 2021-03-06 | 2021-03-07 | 2 | INTEGRITY | MECHANICAL | 27
2019-03-31 | 266 | Work Order Description - 266 - CM | CM | 4 | 48057 | WSCHD | NORM-OPS | 2017-07-21 | 2019-08-05 | 2019-11-01 | 2019-11-01 | 3 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 270 | Work Order Description - 270 - PSPM | PSPM | 1 | 19020 | WSCHD | TPS | 2011-12-15 | 2020-06-02 | 2020-05-02 | 2020-05-03 | 2 | INTEGRITY | INSPECTION | 25
2019-03-31 | 276 | Work Order Description - 276 - CM | CM | 4 | 584332 | SCHD | TPS | 2018-09-06 | 2019-08-04 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 294 | Work Order Description - 294 - CM | CM | 4 | 497321 | SCHD | NORM-OPS | 2019-03-24 | 2020-03-20 | 2019-04-06 | 2019-04-07 | 3 | INTEGRITY | FABRIC | 63
2019-03-31 | 302 | Work Order Description - 302 - CM | CM | 4 | 215331 | WSCHD | NORM-OPS | 2012-02-17 | 2019-09-05 | 2019-06-08 | 2019-06-09 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 305 | Work Order Description - 305 - CM | CM | 4 | 500736 | WSCHD | SYS-ISOL | 2012-12-27 | 2019-02-23 | 2021-03-06 | 2021-03-07 | 3 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 307 | Work Order Description - 307 - CM | CM | 4 | 361924 | WSCHD | TPS | 2016-03-22 | 2019-01-09 | 2019-05-24 | 2019-05-29 | 4 | MAINTENANCE | MECHANICAL | 104
2019-03-31 | 308 | Work Order Description - 308 - CM | CM | 4 | 361925 | WSCHD | TPS | 2015-08-27 | 2019-03-06 | 2019-05-24 | 2019-05-25 | 4 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 314 | Work Order Description - 314 - CM | CM | 4 | 57534 | WSCHD | NORM-OPS | 2012-04-13 | 2019-03-14 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 322 | Work Order Description - 322 - CM | CM | 3 | 678463 | WSCHD | NORM-OPS | 2012-03-08 | 2019-06-22 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | CONSTRUCTION | 26
2019-03-31 | 345 | Work Order Description - 345 - CM | CM | 4 | 480105 | WSCHD | NORM-OPS | 2012-04-15 | 2019-08-16 | 2019-08-16 | 2019-08-16 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 353 | Work Order Description - 353 - CM | CM | 3 | 138449 | WSCHD | SYS-ISOL | 2012-05-07 | 2019-05-05 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 358 | Work Order Description - 358 - CM | CM | 3 | 545260 | WSCHD | TPS | 2015-08-27 | 2019-08-15 | 2019-07-24 | 2019-07-24 | 2 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 361 | Work Order Description - 361 - CM | CM | 3 | 545222 | WSCHD | TPS | 2015-08-27 | 2019-07-24 | 2019-07-24 | 2019-07-24 | 2 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 372 | Work Order Description - 372 - CM | CM | 4 | 311601 | SCHD | TPS | 2018-05-31 | 2019-04-10 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 373 | Work Order Description - 373 - CM | CM | 3 | 520152 | WSCHD | NORM-OPS | 2017-06-23 | 2019-05-29 | 2019-07-27 | 2019-07-31 | 4 | MAINTENANCE | MECHANICAL | 56
2019-03-31 | 382 | Work Order Description - 382 - CM | CM | 4 | 418023 | WSCHD | NORM-OPS | 2017-07-21 | 2019-05-08 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 46
2019-03-31 | 389 | Work Order Description - 389 - CM | CM | 4 | 471536 | WSCHD | NORM-OPS | 2012-05-27 | 2019-01-03 | 2019-05-25 | 2019-05-27 | 2 | MAINTENANCE | INSTRUMENTS | 15
2019-03-31 | 394 | Work Order Description - 394 - PM | PM | 4 | 401355 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-05-06 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 396 | Work Order Description - 396 - PM | PM | 4 | 677399 | WSCHD | EQUIP-ISOL | 2012-06-01 | 2018-12-18 | 2019-05-04 | 2019-05-06 | 3 | INTEGRITY | MECHANICAL | 48
2019-03-31 | 415 | Work Order Description - 415 - CM | CM | 3 | 363635 | WSCHD | TPS | 2015-08-27 | 2019-01-12 | 2020-03-07 | 2020-03-09 | 2 | INTEGRITY | CONSTRUCTION | 28
2019-03-31 | 418 | Work Order Description - 418 - BR | BR | 4 | 501158 | WSCHD | SUBSYS-ISOL | 2015-08-27 | 2019-09-02 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 456 | Work Order Description - 456 - CM | CM | 4 | 259083 | SCHD | NORM-OPS | 2018-07-18 | 2019-06-23 | 2020-02-15 | 2020-02-15 | 3 | MAINTENANCE | INSTRUMENTS | 54
2019-03-31 | 465 | Work Order Description - 465 - CM | CM | 4 | 448089 | WPLAN | NORM-OPS | 2019-03-06 | 2021-02-24 | 2021-01-12 | 2021-01-12 | 4 | INTEGRITY | FABRIC | 42
2019-03-31 | 471 | Work Order Description - 471 - CM | CM | 3 | 479579 | WSCHD | NORM-OPS | 2019-03-25 | 2019-07-31 | 2019-06-01 | 2019-06-01 | 4 | INTEGRITY | CONSTRUCTION | 147
2019-03-31 | 474 | Work Order Description - 474 - CM | CM | 4 | 495496 | WSCHD | SYS-ISOL | 2012-09-03 | 2019-02-24 | 2020-05-02 | 2020-05-06 | 2 | MAINTENANCE | MECHANICAL | 60
2019-03-31 | 479 | Work Order Description - 479 - CM | CM | 3 | 411140 | WSCHD | SYS-ISOL | 2012-09-09 | 2019-02-09 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 494 | Work Order Description - 494 - CM | CM | 4 | 272739 | WSCHD | NORM-OPS | 2012-09-30 | 2019-01-30 | 2019-04-13 | 2019-04-15 | 3 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 504 | Work Order Description - 504 - CM | CM | 3 | 499512 | WSCHD | TPS | 2018-06-21 | 2019-02-02 | 2020-05-02 | 2020-05-05 | 3 | MAINTENANCE | MECHANICAL | 45
2019-03-31 | 509 | Work Order Description - 509 - PM | PM | 4 | 261853 | WSCHD | EQUIP-ISOL | 2015-10-14 | 2019-05-19 | 2019-07-27 | 2019-07-27 | 2 | MAINTENANCE | INSTRUMENTS | 0.016667
2019-03-31 | 513 | Work Order Description - 513 - CM | CM | 4 | 363627 | WSCHD | NORM-OPS | 2012-10-11 | 2019-07-04 | 2019-08-31 | 2019-09-02 | 2 | INTEGRITY | INSTRUMENTS | 43
2019-03-31 | 514 | Work Order Description - 514 - CM | CM | 4 | 51688 | WSCHD | NORM-OPS | 2012-10-15 | 2019-02-27 | 2019-08-31 | 2019-09-03 | 2 | MAINTENANCE | INSTRUMENTS | 52
2019-03-31 | 556 | Work Order Description - 556 - CM | CM | 3 | 405099 | WSCHD | SYS-ISOL | 2012-11-14 | 2019-05-15 | 2019-05-04 | 2019-05-05 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 586 | Work Order Description - 586 - CM | CM | 3 | 326114 | WSCHD | TPS | 2018-06-25 | 2019-08-03 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 587 | Work Order Description - 587 - CM | CM | 4 | 33824 | WSCHD | TPS | 2015-06-10 | 2019-05-29 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 588 | Work Order Description - 588 - CM | CM | 4 | 322272 | WSCHD | TPS | 2015-06-10 | 2019-01-26 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 589 | Work Order Description - 589 - CM | CM | 4 | 503262 | WSCHD | TPS | 2015-06-10 | 2019-12-23 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 591 | Work Order Description - 591 - PM | PM | 3 | 360533 | WSCHD | PACK-ISOL | 2012-11-27 | 2019-03-07 | 2019-12-28 | 2019-12-28 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 592 | Work Order Description - 592 - PM | PM | 3 | 53288 | WSCHD | PACK-ISOL | 2012-11-27 | 2019-12-14 | 2019-12-28 | 2019-12-28 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 597 | Work Order Description - 597 - PM | PM | 3 | 53614 | WSCHD | PACK-ISOL | 2012-11-27 | 2019-07-07 | 2019-12-28 | 2019-12-28 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 598 | Work Order Description - 598 - PM | PM | 3 | 360304 | WSCHD | PACK-ISOL | 2012-11-27 | 2019-11-05 | 2019-12-28 | 2019-12-28 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 599 | Work Order Description - 599 - CM | CM | 4 | 17540 | WSCHD | NORM-OPS | 2012-11-27 | 2019-04-15 | 2019-04-27 | 2019-05-01 | 3 | MAINTENANCE | CONSTRUCTION | 68
2019-03-31 | 604 | Work Order Description - 604 - CM | CM | 4 | 26917 | SCHD | TPS | 2018-09-06 | 2019-06-24 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 104
2019-03-31 | 626 | Work Order Description - 626 - CM | CM | 4 | 57928 | WSCHD | NORM-OPS | 2012-12-10 | 2020-04-01 | 2020-09-30 | 2020-10-01 | 4 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 628 | Work Order Description - 628 - CM | CM | 4 | 403817 | SCHD | NORM-OPS | 2018-06-21 | 2019-11-15 | 2019-06-30 | 2019-06-30 | 4 | INTEGRITY | CONSTRUCTION | 21
2019-03-31 | 653 | Work Order Description - 653 - CM | CM | 4 | 324569 | WSCHD | TPS | 2018-06-07 | 2020-01-24 | 2020-05-03 | 2020-05-04 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 654 | Work Order Description - 654 - CM | CM | 3 | 51662 | WSCHD | NORM-OPS | 2017-06-23 | 2019-07-01 | 2019-12-28 | 2019-12-30 | 3 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 655 | Work Order Description - 655 - CM | CM | 3 | 545266 | WSCHD | TPS | 2018-08-05 | 2019-02-07 | 2020-05-02 | 2020-05-06 | 3 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 680 | Work Order Description - 680 - CM | CM | 1 | 51662 | WPLAN | SYS-ISOL | 2017-06-13 | 2019-04-24 | 2019-11-02 | 2019-11-02 | 3 | MAINTENANCE | CONSTRUCTION | 14
2019-03-31 | 682 | Work Order Description - 682 - CM | CM | 1 | 545266 | WPLAN | SYS-ISOL | 2017-06-13 | 2019-04-24 | 2019-07-27 | 2019-07-28 | 3 | MAINTENANCE | CONSTRUCTION | 21
2019-03-31 | 683 | Work Order Description - 683 - CM | CM | 4 | 491044 | WSCHD | TPS | 2018-06-15 | 2019-04-12 | 2020-05-02 | 2020-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 794 | Work Order Description - 794 - CM | CM | 3 | 657409 | WSCHD | NORM-OPS | 2013-02-02 | 2019-03-12 | 2019-11-02 | 2019-11-02 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 798 | Work Order Description - 798 - CM | CM | 3 | 51561 | WSCHD | NORM-OPS | 2013-01-30 | 2020-04-01 | 2019-12-21 | 2019-12-23 | 2 | MAINTENANCE | MECHANICAL | 52
2019-03-31 | 804 | Work Order Description - 804 - CM | CM | 4 | 305371 | WSCHD | NORM-OPS | 2013-02-04 | 2019-07-26 | 2019-09-28 | 2019-09-28 | 4 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 809 | Work Order Description - 809 - CM | CM | 3 | 319242 | WSCHD | TPS | 2013-02-04 | 2019-10-19 | 2020-12-01 | 2020-12-01 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 813 | Work Order Description - 813 - CM | CM | 2 | 681466 | WSCHD | NORM-OPS | 2013-02-07 | 2019-08-19 | 2019-05-04 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 814 | Work Order Description - 814 - CM | CM | 2 | 681467 | WSCHD | NORM-OPS | 2013-02-07 | 2019-09-21 | 2019-05-04 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 815 | Work Order Description - 815 - CM | CM | 2 | 356483 | WSCHD | NORM-OPS | 2013-02-07 | 2019-09-22 | 2019-05-04 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 816 | Work Order Description - 816 - CM | CM | 2 | 681468 | WSCHD | NORM-OPS | 2013-02-07 | 2019-06-27 | 2019-05-04 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 817 | Work Order Description - 817 - CM | CM | 2 | 671335 | WSCHD | NORM-OPS | 2013-02-07 | 2019-05-09 | 2019-05-04 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 841 | Work Order Description - 841 - CM | CM | 4 | 492026 | WSCHD | NORM-OPS | 2013-09-29 | 2019-01-03 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 843 | Work Order Description - 843 - CM | CM | 4 | 478268 | SCHD | NORM-OPS | 2018-09-06 | 2020-01-14 | 2020-04-04 | 2020-04-04 | 4 | INTEGRITY | MECHANICAL | 11
2019-03-31 | 847 | Work Order Description - 847 - PSPM | PSPM | 1 | 399838 | WSCHD | EQUIP-ISOL | 2015-10-15 | 2019-05-16 | 2019-09-16 | 2019-09-16 | 1 | INTEGRITY | CONSTRUCTION | 0.016667
2019-03-31 | 848 | Work Order Description - 848 - PSPM | PSPM | 1 | 260931 | WSCHD | EQUIP-ISOL | 2015-10-15 | 2019-09-01 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | CONSTRUCTION | 0.016667
2019-03-31 | 849 | Work Order Description - 849 - PSPM | PSPM | 1 | 399546 | WSCHD | EQUIP-ISOL | 2015-10-15 | 2019-09-01 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | CONSTRUCTION | 0.016667
2019-03-31 | 850 | Work Order Description - 850 - PSPM | PSPM | 1 | 248093 | WSCHD | EQUIP-ISOL | 2015-10-15 | 2019-07-20 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | CONSTRUCTION | 0.016667
2019-03-31 | 851 | Work Order Description - 851 - PSPM | PSPM | 1 | 361099 | WSCHD | EQUIP-ISOL | 2015-10-15 | 2019-07-21 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | CONSTRUCTION | 0.016667
2019-03-31 | 852 | Work Order Description - 852 - PSPM | PSPM | 1 | 248094 | WSCHD | EQUIP-ISOL | 2015-10-15 | 2022-11-01 | 2020-09-26 | 2020-09-26 | 1 | INTEGRITY | CONSTRUCTION | 0.016667
2019-03-31 | 865 | Work Order Description - 865 - CM | CM | 4 | 478267 | SCHD | NORM-OPS | 2018-09-06 | 2019-03-31 | 2020-04-04 | 2020-04-04 | 4 | INTEGRITY | MECHANICAL | 11
2019-03-31 | 866 | Work Order Description - 866 - CM | CM | 4 | 551215 | SCHD | NORM-OPS | 2018-09-06 | 2019-01-28 | 2020-04-04 | 2020-04-04 | 4 | INTEGRITY | MECHANICAL | 11
2019-03-31 | 878 | Work Order Description - 878 - CM | CM | 3 | 471062 | WSCHD | NORM-OPS | 2017-06-23 | 2019-07-01 | 2020-04-04 | 2020-04-05 | 3 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 879 | Work Order Description - 879 - CM | CM | 3 | 418397 | WSCHD | NORM-OPS | 2013-03-05 | 2019-12-06 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 882 | Work Order Description - 882 - CM | CM | 4 | 245666 | WSCHD | NORM-OPS | 2013-03-06 | 2019-10-01 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 884 | Work Order Description - 884 - CM | CM | 4 | 361881 | WSCHD | NORM-OPS | 2013-03-07 | 2019-03-26 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 893 | Work Order Description - 893 - CM | CM | 3 | 51662 | WSCHD | NORM-OPS | 2015-05-28 | 2019-07-01 | 2019-08-05 | 2019-08-05 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 897 | Work Order Description - 897 - BR | BR | 4 | 418145 | WSCHD | NORM-OPS | 2017-06-22 | 2019-05-05 | 2019-05-25 | 2019-05-27 | 3 | MAINTENANCE | CONSTRUCTION | 22
2019-03-31 | 912 | Work Order Description - 912 - CM | CM | 3 | 215916 | SCHD | NORM-OPS | 2018-07-18 | 2020-01-16 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 941 | Work Order Description - 941 - CM | CM | 3 | 654921 | WPLAN | TPS | 2017-07-26 | 2019-08-10 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 942 | Work Order Description - 942 - CM | CM | 3 | 122809 | WPLAN | TPS | 2017-07-26 | 2019-06-27 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 943 | Work Order Description - 943 - CM | CM | 4 | 450548 | SCHD | NORM-OPS | 2018-11-13 | 2019-08-05 | 2019-06-30 | 2019-07-02 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 944 | Work Order Description - 944 - CM | CM | 3 | 293804 | WPLAN | TPS | 2017-07-26 | 2019-10-18 | 2020-05-02 | 2020-05-02 | 2 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 952 | Work Order Description - 952 - CM | CM | 3 | 546702 | WSCHD | TPS | 2018-06-15 | 2019-06-19 | 2019-09-28 | 2019-09-28 | 2 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 953 | Work Order Description - 953 - BR | BR | 4 | 359578 | WPLAN | TPS | 2018-01-17 | 2019-11-26 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 959 | Work Order Description - 959 - CM | CM | 4 | 56319 | WSCHD | NORM-OPS | 2018-06-08 | 2019-07-07 | 2020-05-02 | 2020-05-02 | 4 | INTEGRITY | CONSTRUCTION | 4.5
2019-03-31 | 972 | Work Order Description - 972 - CM | CM | 3 | 29419 | SCHD | TPS | 2018-09-06 | 2019-12-08 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 973 | Work Order Description - 973 - CM | CM | 3 | 29418 | SCHD | TPS | 2018-09-06 | 2019-12-14 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 60
2019-03-31 | 978 | Work Order Description - 978 - PM | PM | 3 | 57144 | WSCHD | PACK-ISOL | 2013-04-30 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 981 | Work Order Description - 981 - CM | CM | 4 | 418148 | WSCHD | NORM-OPS | 2019-02-20 | 2020-01-09 | 2019-05-25 | 2019-05-26 | 2 | MAINTENANCE | MECHANICAL | 10.8
2019-03-31 | 990 | Work Order Description - 990 - CM | CM | 4 | 227221 | WSCHD | NORM-OPS | 2013-05-09 | 2019-07-01 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | MECHANICAL | 17
2019-03-31 | 997 | Work Order Description - 997 - CM | CM | 4 | 674251 | WSCHD | NORM-OPS | 2013-06-06 | 2019-10-30 | 2019-11-01 | 2019-11-01 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 1003 | Work Order Description - 1003 - CM | CM | 3 | 322378 | WSCHD | TPS | 2015-06-09 | 2018-12-22 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 1005 | Work Order Description - 1005 - CM | CM | 3 | 327955 | WSCHD | TPS | 2018-06-08 | 2019-05-27 | 2020-05-03 | 2020-05-04 | 3 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 1006 | Work Order Description - 1006 - CM | CM | 3 | 33874 | WPLAN | TPS | 2017-07-26 | 2019-01-05 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 1007 | Work Order Description - 1007 - CM | CM | 3 | 245876 | WSCHD | SYS-ISOL | 2018-06-08 | 2020-01-13 | 2020-05-03 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 1008 | Work Order Description - 1008 - CM | CM | 3 | 323085 | SCHD | TPS | 2019-01-30 | 2019-04-09 | 2020-05-03 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 1010 | Work Order Description - 1010 - CM | CM | 3 | 327384 | WSCHD | TPS | 2013-05-15 | 2019-06-14 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 1011 | Work Order Description - 1011 - CM | CM | 3 | 500939 | WSCHD | NORM-OPS | 2013-05-15 | 2019-10-16 | 2019-05-25 | 2019-05-26 | 2 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 1012 | Work Order Description - 1012 - CM | CM | 3 | 322526 | WSCHD | SYS-ISOL | 2013-05-15 | 2019-11-13 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 13
2019-03-31 | 1014 | Work Order Description - 1014 - CM | CM | 3 | 500960 | WSCHD | TPS | 2015-06-09 | 2019-06-15 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 1015 | Work Order Description - 1015 - CM | CM | 3 | 500944 | WSCHD | TPS | 2015-06-09 | 2019-02-04 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 1016 | Work Order Description - 1016 - CM | CM | 4 | 214934 | WPLAN | TPS | 2017-07-26 | 2019-07-06 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 1017 | Work Order Description - 1017 - CM | CM | 4 | 293636 | WPLAN | TPS | 2017-07-26 | 2018-12-20 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 1018 | Work Order Description - 1018 - CM | CM | 3 | 247636 | WSCHD | SYS-ISOL | 2013-05-17 | 2020-01-14 | 2020-05-02 | 2020-05-04 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 1020 | Work Order Description - 1020 - CM | CM | 4 | 326781 | WSCHD | TPS | 2015-06-11 | 2019-11-02 | 2020-05-02 | 2020-05-02 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 1021 | Work Order Description - 1021 - CM | CM | 3 | 226527 | WSCHD | NORM-OPS | 2015-06-09 | 2019-10-28 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 1022 | Work Order Description - 1022 - CM | CM | 3 | 226528 | WSCHD | NORM-OPS | 2015-06-09 | 2019-12-04 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 1023 | Work Order Description - 1023 - CM | CM | 3 | 226420 | WSCHD | TPS | 2015-06-09 | 2019-01-21 | 2020-05-02 | 2020-05-02 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 1026 | Work Order Description - 1026 - CM | CM | 4 | 322705 | WSCHD | SYS-ISOL | 2015-06-10 | 2019-08-13 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 1027 | Work Order Description - 1027 - CM | CM | 4 | 322712 | WSCHD | SYS-ISOL | 2017-07-21 | 2019-03-20 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | CONSTRUCTION | 4
2019-03-31 | 1028 | Work Order Description - 1028 - CM | CM | 4 | 327570 | WSCHD | SYS-ISOL | 2017-07-21 | 2019-08-11 | 2019-09-07 | 2019-09-08 | 3 | MAINTENANCE | MECHANICAL | 4.8167
2019-03-31 | 1029 | Work Order Description - 1029 - CM | CM | 4 | 322774 | WSCHD | SYS-ISOL | 2017-07-21 | 2019-01-17 | 2019-09-28 | 2019-09-28 | 3 | MAINTENANCE | CONSTRUCTION | 4.8167
2019-03-31 | 1031 | Work Order Description - 1031 - CM | CM | 4 | 327568 | WSCHD | SYS-ISOL | 2015-06-10 | 2019-04-20 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 1032 | Work Order Description - 1032 - CM | CM | 3 | 323090 | WSCHD | TPS | 2013-05-20 | 2019-07-15 | 2020-05-02 | 2020-05-02 | 2 | MAINTENANCE | CONSTRUCTION | 6
2019-03-31 | 1033 | Work Order Description - 1033 - CM | CM | 3 | 226417 | WSCHD | TPS | 2013-05-20 | 2019-11-23 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | CONSTRUCTION | 12
2019-03-31 | 1034 | Work Order Description - 1034 - CM | CM | 4 | 399608 | WSCHD | SYS-ISOL | 2017-02-12 | 2019-11-22 | 2019-09-07 | 2019-09-09 | 2 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 1036 | Work Order Description - 1036 - CM | CM | 4 | 659870 | WPLAN | NORM-OPS | 2018-08-04 | 2019-11-14 | 2019-09-01 | 2019-09-15 | 2 | INTEGRITY | CONSTRUCTION | 218
2019-03-31 | 1037 | Work Order Description - 1037 - CM | CM | 4 | 314549 | WPLAN | NORM-OPS | 2018-05-27 | 2019-05-27 | 2019-05-04 | 2019-05-06 | 3 | MAINTENANCE | MECHANICAL | 34
2019-03-31 | 1039 | Work Order Description - 1039 - CM | CM | 4 | 541967 | SCHD | TPS | 2018-09-06 | 2019-07-10 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 1046 | Work Order Description - 1046 - CM | CM | 4 | 33996 | WSCHD | SUBSYS-ISOL | 2018-06-21 | 2019-05-27 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 1056 | Work Order Description - 1056 - CM | CM | 4 | 83100 | WPLAN | NORM-OPS | 2018-08-20 | 2020-08-17 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 1080 | Work Order Description - 1080 - CM | CM | 4 | 665126 | WPLAN | NORM-OPS | 2018-10-08 | 2020-08-17 | 2019-07-13 | 2019-07-14 | 4 | INTEGRITY | MECHANICAL | 8
2019-03-31 | 1084 | Work Order Description - 1084 - CM | CM | 3 | 502628 | WSCHD | PACK-ISOL | 2013-09-29 | 2019-07-30 | 2020-05-02 | 2020-05-04 | 4 | MAINTENANCE | MECHANICAL | 29
2019-03-31 | 1085 | Work Order Description - 1085 - CM | CM | 3 | 247130 | WSCHD | TPS | 2013-06-04 | 2019-02-10 | 2021-06-05 | 2021-06-06 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 1122 | Work Order Description - 1122 - CM | CM | 4 | 666102 | WSCHD | NORM-OPS | 2013-06-12 | 2020-01-12 | 2019-08-17 | 2019-08-17 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 1157 | Work Order Description - 1157 - PRJ | PRJ | 2 | 403916 | SCHD | NORM-OPS | 2018-09-06 | 2019-07-29 | 2020-03-14 | 2020-03-14 | 3 | INTEGRITY | CONSTRUCTION | 160
2019-03-31 | 1228 | Work Order Description - 1228 - CM | CM | 3 | 578833 | SCHD | TPS | 2018-05-30 | 2019-01-22 | 2019-07-13 | 2019-07-13 | 4 | WELLS | MECHANICAL | 30
2019-03-31 | 1264 | Work Order Description - 1264 - CM | CM | 3 | 322548 | WSCHD | TPS | 2015-06-11 | 2019-06-06 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 6.9
2019-03-31 | 1288 | Work Order Description - 1288 - CM | CM | 4 | 602950 | SCHD | NORM-OPS | 2018-06-21 | 2019-11-01 | 2018-06-01 | 2018-06-01 | 3 | INTEGRITY | SUBSEA | 12
2019-03-31 | 1303 | Work Order Description - 1303 - CM | CM | 3 | 51659 | WSCHD | NORM-OPS | 2013-07-17 | 2019-12-14 | 2019-06-29 | 2019-07-04 | 3 | MAINTENANCE | INSTRUMENTS | 32
2019-03-31 | 1305 | Work Order Description - 1305 - CM | CM | 3 | 545261 | WSCHD | NORM-OPS | 2013-07-18 | 2019-11-01 | 2019-06-29 | 2019-07-04 | 3 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 1323 | Work Order Description - 1323 - CM | CM | 3 | 188479 | SCHD | SYS-ISOL | 2018-07-18 | 2019-08-21 | 2019-07-20 | 2019-07-20 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 1341 | Work Order Description - 1341 - CM | CM | 4 | 519820 | WSCHD | NORM-OPS | 2013-07-31 | 2019-11-04 | 2019-06-22 | 2019-06-22 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 1376 | Work Order Description - 1376 - CM | CM | 3 | 267673 | WPLAN | NORM-OPS | 2018-02-16 | 2019-03-31 | 2020-03-07 | 2020-03-09 | 4 | INTEGRITY | CONSTRUCTION | 29
2019-03-31 | 1392 | Work Order Description - 1392 - CM | CM | 3 | 50992 | WSCHD | TPS | 2013-08-28 | 2019-12-28 | 2020-05-02 | 2020-05-15 | 3 | MAINTENANCE | INSTRUMENTS | 96
2019-03-31 | 1394 | Work Order Description - 1394 - CM | CM | 3 | 247283 | WSCHD | TPS | 2018-06-08 | 2019-07-14 | 2020-05-03 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 1419 | Work Order Description - 1419 - PSCM | PSCM | 1 | 361927 | WSCHD | TPS | 2015-07-31 | 2020-01-01 | 2019-05-25 | 2019-05-28 | 3 | MAINTENANCE | MECHANICAL | 37
2019-03-31 | 1427 | Work Order Description - 1427 - CM | CM | 3 | 463338 | SCHD | TPS | 2018-09-06 | 2019-07-25 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 63
2019-03-31 | 1436 | Work Order Description - 1436 - CM | CM | 3 | 33597 | WPLAN | TPS | 2018-06-03 | 2019-05-28 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 1453 | Work Order Description - 1453 - BR | BR | 3 | 215022 | WSCHD | SUBSYS-ISOL | 2015-06-09 | 2020-01-03 | 2019-05-04 | 2019-05-05 | 4 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 1457 | Work Order Description - 1457 - CM | CM | 2 | 671179 | WSCHD | TPS | 2017-11-17 | 2019-02-26 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 1466 | Work Order Description - 1466 - PRJ | PRJ | 3 | 671787 | WSCHD | NORM-OPS | 2013-09-11 | 2019-05-30 | 2019-04-27 | 2019-04-28 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 1486 | Work Order Description - 1486 - CM | CM | 3 | 323291 | WSCHD | NORM-OPS | 2017-08-25 | 2019-09-17 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 1487 | Work Order Description - 1487 - CM | CM | 4 | 217953 | SCHD | NORM-OPS | 2018-09-06 | 2019-08-16 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 56
2019-03-31 | 1493 | Work Order Description - 1493 - CM | CM | 4 | 265963 | SCHD | TPS | 2018-09-06 | 2019-10-08 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 1494 | Work Order Description - 1494 - CM | CM | 4 | 17680 | WSCHD | TPS | 2013-10-04 | 2019-11-13 | 2020-12-31 | 2021-01-01 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 1508 | Work Order Description - 1508 - CM | CM | 2 | 308495 | WSCHD | NORM-OPS | 2018-02-09 | 2019-04-30 | 2019-05-25 | 2019-05-29 | 3 | MAINTENANCE | CONSTRUCTION | 62
2019-03-31 | 1511 | Work Order Description - 1511 - CM | CM | 4 | 76032 | WPLAN | NORM-OPS | 2017-09-06 | 2019-11-27 | 2019-07-13 | 2019-07-15 | 4 | INTEGRITY | MECHANICAL | 25
2019-03-31 | 1520 | Work Order Description - 1520 - CM | CM | 4 | 361985 | WSCHD | NORM-OPS | 2014-01-20 | 2020-01-18 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | SERVICES | 2
2019-03-31 | 1539 | Work Order Description - 1539 - CM | CM | 4 | 356957 | WSCHD | NORM-OPS | 2013-10-21 | 2019-06-20 | 2019-11-02 | 2019-11-03 | 3 | MAINTENANCE | INSTRUMENTS | 11
2019-03-31 | 1543 | Work Order Description - 1543 - BR | BR | 4 | 261322 | WSCHD | NORM-OPS | 2013-11-05 | 2019-06-02 | 2019-08-31 | 2019-08-31 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 1567 | Work Order Description - 1567 - CM | CM | 4 | 308651 | WSCHD | NORM-OPS | 2013-10-29 | 2019-07-01 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 1569 | Work Order Description - 1569 - CM | CM | 4 | 671700 | WSCHD | NORM-OPS | 2013-10-29 | 2019-07-01 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 1570 | Work Order Description - 1570 - CM | CM | 4 | 674890 | WSCHD | NORM-OPS | 2013-10-29 | 2019-07-01 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 1571 | Work Order Description - 1571 - CM | CM | 4 | 357299 | WSCHD | NORM-OPS | 2013-10-29 | 2019-07-01 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 1574 | Work Order Description - 1574 - CM | CM | 3 | 215026 | WSCHD | SUBSYS-ISOL | 2017-07-07 | 2019-07-19 | 2019-09-07 | 2019-09-08 | 3 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 1578 | Work Order Description - 1578 - CM | CM | 4 | 363329 | WSCHD | NORM-OPS | 2013-11-24 | 2019-07-24 | 2019-10-25 | 2019-10-27 | 2 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 1579 | Work Order Description - 1579 - CM | CM | 4 | 536648 | WSCHD | NORM-OPS | 2013-11-24 | 2019-02-01 | 2019-09-07 | 2019-09-09 | 2 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 1593 | Work Order Description - 1593 - BR | BR | 4 | 161216 | WSCHD | TPS | 2018-06-16 | 2020-01-10 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 1594 | Work Order Description - 1594 - CM | CM | 3 | 501915 | WSCHD | NORM-OPS | 2013-11-06 | 2019-01-06 | 2019-05-04 | 2019-05-05 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 1617 | Work Order Description - 1617 - CM | CM | 3 | 35553 | SCHD | TPS | 2018-09-06 | 2019-12-27 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 23
2019-03-31 | 1622 | Work Order Description - 1622 - CM | CM | 3 | 319731 | WSCHD | TPS | 2013-11-14 | 2019-03-06 | 2020-05-02 | 2020-05-02 | 2 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 1624 | Work Order Description - 1624 - CM | CM | 3 | 319731 | WSCHD | TPS | 2013-11-13 | 2018-12-12 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 1677 | Work Order Description - 1677 - CM | CM | 4 | 125761 | WPLAN | NORM-OPS | 2015-10-05 | 2019-10-04 | 2019-09-01 | 2019-09-02 | 4 | INTEGRITY | CONSTRUCTION | 36
2019-03-31 | 1679 | Work Order Description - 1679 - CM | CM | 3 | 326740 | WSCHD | PACK-ISOL | 2013-11-25 | 2019-05-19 | 2020-05-02 | 2020-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 1683 | Work Order Description - 1683 - CM | CM | 3 | 501412 | WSCHD | TPS | 2014-08-04 | 2019-12-19 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | CONSTRUCTION | 2
2019-03-31 | 1685 | Work Order Description - 1685 - PM | PM | 3 | 409660 | WSCHD | PACK-ISOL | 2013-11-27 | 2019-05-21 | 2019-09-28 | 2019-09-28 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 1686 | Work Order Description - 1686 - PM | PM | 3 | 360542 | WSCHD | PACK-ISOL | 2013-11-27 | 2019-10-05 | 2019-09-28 | 2019-09-28 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 1687 | Work Order Description - 1687 - PM | PM | 3 | 360543 | WSCHD | PACK-ISOL | 2013-11-27 | 2019-12-05 | 2019-09-28 | 2019-09-28 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 1688 | Work Order Description - 1688 - PM | PM | 3 | 54310 | WSCHD | PACK-ISOL | 2013-11-27 | 2019-01-29 | 2019-09-01 | 2019-09-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 1697 | Work Order Description - 1697 - CM | CM | 3 | 404640 | WSCHD | NORM-OPS | 2018-03-21 | 2020-01-01 | 2020-06-13 | 2020-06-16 | 4 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 1706 | Work Order Description - 1706 - CM | CM | 3 | 353456 | WSCHD | NORM-OPS | 2013-12-03 | 2019-11-02 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 1707 | Work Order Description - 1707 - CM | CM | 3 | 553383 | WSCHD | NORM-OPS | 2017-06-23 | 2019-10-08 | 2019-09-28 | 2019-09-28 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 1719 | Work Order Description - 1719 - CM | CM | 2 | 50802 | WPLAN | TPS | 2017-07-26 | 2019-07-20 | 2020-05-03 | 2020-05-07 | 2 | INTEGRITY | MECHANICAL | 44
2019-03-31 | 1722 | Work Order Description - 1722 - CM | CM | 4 | 575115 | WPLAN | NORM-OPS | 2018-02-14 | 2019-05-25 | 2019-08-31 | 2019-09-04 | 4 | INTEGRITY | CONSTRUCTION | 64
2019-03-31 | 1751 | Work Order Description - 1751 - CM | CM | 4 | 33412 | WPLAN | NORM-OPS | 2014-03-30 | 2020-09-01 | 2019-04-27 | 2019-04-27 | 4 | INTEGRITY | CONSTRUCTION | 14
2019-03-31 | 1764 | Work Order Description - 1764 - CM | CM | 3 | 547538 | WSCHD | TPS | 2015-06-11 | 2019-03-08 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 1768 | Work Order Description - 1768 - CM | CM | 2 | 33632 | WSCHD | TPS | 2015-06-10 | 2019-01-04 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 1773 | Work Order Description - 1773 - PM | PM | 4 | 408340 | SCHD | EQUIP-ISOL | 2019-03-22 | 2020-01-14 | 2019-03-30 | 2019-04-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 1775 | Work Order Description - 1775 - PSPM | PSPM | 1 | 248425 | WSCHD | EQUIP-ISOL | 2015-10-15 | 2019-05-16 | 2019-11-30 | 2019-11-30 | 1 | INTEGRITY | CONSTRUCTION | 0.016667
2019-03-31 | 1783 | Work Order Description - 1783 - CM | CM | 3 | 363226 | WSCHD | PACK-ISOL | 2018-06-07 | 2019-08-18 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | CONSTRUCTION | 12
2019-03-31 | 1792 | Work Order Description - 1792 - CM | CM | 3 | 461046 | SCHD | TPS | 2018-09-06 | 2019-08-30 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 1809 | Work Order Description - 1809 - CM | CM | 3 | 460949 | SCHD | TPS | 2018-09-06 | 2019-10-11 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 1834 | Work Order Description - 1834 - CM | CM | 4 | 650444 | WSCHD | NORM-OPS | 2014-01-19 | 2019-02-20 | 2019-04-21 | 2019-04-21 | 4 | OPERATIONS | MEDIC | 1
2019-03-31 | 1840 | Work Order Description - 1840 - CM | CM | 3 | 226434 | WSCHD | TPS | 2015-06-09 | 2019-05-02 | 2020-05-02 | 2020-05-05 | 2 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 1845 | Work Order Description - 1845 - CM | CM | 3 | 375795 | WPLAN | TPS | 2018-12-17 | 2019-12-20 | 2019-07-13 | 2019-07-20 | 4 | MAINTENANCE | CONSTRUCTION | 96
2019-03-31 | 1861 | Work Order Description - 1861 - CM | CM | 4 | 375585 | SCHD | SYS-ISOL | 2018-06-21 | 2019-05-30 | 2019-07-13 | 2019-07-19 | 4 | INTEGRITY | CONSTRUCTION | 205
2019-03-31 | 1864 | Work Order Description - 1864 - CM | CM | 3 | 245877 | WSCHD | TPS | 2015-06-09 | 2019-05-28 | 2020-05-02 | 2020-05-05 | 3 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 1865 | Work Order Description - 1865 - CM | CM | 3 | 493009 | WSCHD | TPS | 2017-07-27 | 2019-09-30 | 2020-05-02 | 2020-05-05 | 3 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 1866 | Work Order Description - 1866 - CM | CM | 3 | 327377 | WSCHD | TPS | 2018-06-15 | 2019-07-01 | 2020-05-02 | 2020-05-08 | 3 | MAINTENANCE | MECHANICAL | 97
2019-03-31 | 1867 | Work Order Description - 1867 - CM | CM | 3 | 33919 | WSCHD | TPS | 2018-06-15 | 2019-07-01 | 2020-05-02 | 2020-05-05 | 3 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 1868 | Work Order Description - 1868 - CM | CM | 3 | 33920 | WSCHD | TPS | 2018-06-15 | 2019-07-01 | 2020-05-02 | 2020-05-05 | 3 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 1873 | Work Order Description - 1873 - CM | CM | 3 | 138447 | WSCHD | SYS-ISOL | 2017-07-21 | 2018-12-17 | 2020-12-01 | 2020-12-03 | 3 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 1877 | Work Order Description - 1877 - CM | CM | 4 | 402284 | WSCHD | NORM-OPS | 2019-03-25 | 2019-09-15 | 2020-05-02 | 2020-05-02 | 4 | INTEGRITY | FABRIC | 12
2019-03-31 | 1905 | Work Order Description - 1905 - CM | CM | 4 | 666084 | WPLAN | NORM-OPS | 2017-05-21 | 2019-03-08 | 2019-05-01 | 2019-05-01 | 4 | INTEGRITY | SUBSEA | 6
2019-03-31 | 1940 | Work Order Description - 1940 - CM | CM | 4 | 267676 | WSCHD | NORM-OPS | 2014-02-22 | 2018-12-01 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | SAFETY | 1
2019-03-31 | 1942 | Work Order Description - 1942 - CM | CM | 3 | 228868 | SCHD | SYS-ISOL | 2018-09-06 | 2019-12-21 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | MECHANICAL | 57
2019-03-31 | 1946 | Work Order Description - 1946 - CM | CM | 4 | 268043 | WSCHD | NORM-OPS | 2017-07-06 | 2020-01-20 | 2019-04-20 | 2019-04-23 | 3 | DRILLING | DRILLING | 44
2019-03-31 | 1948 | Work Order Description - 1948 - CM | CM | 3 | 55898 | SCHD | SYS-ISOL | 2018-09-06 | 2018-12-31 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | MECHANICAL | 55
2019-03-31 | 1960 | Work Order Description - 1960 - CM | CM | 4 | 470367 | SCHD | NORM-OPS | 2018-09-06 | 2019-10-03 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 27
2019-03-31 | 1978 | Work Order Description - 1978 - CM | CM | 4 | 674888 | WSCHD | NORM-OPS | 2017-07-21 | 2019-10-01 | 2019-09-28 | 2019-09-28 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 1979 | Work Order Description - 1979 - CM | CM | 3 | 29132 | SCHD | TPS | 2018-07-06 | 2019-06-04 | 2019-07-13 | 2019-07-13 | 2 | INTEGRITY | INSTRUMENTS | 16
2019-03-31 | 2011 | Work Order Description - 2011 - CM | CM | 4 | 602950 | SCHD | NORM-OPS | 2018-06-21 | 2019-11-01 | 2019-05-01 | 2019-09-25 | 4 | INTEGRITY | SUBSEA | 6
2019-03-31 | 2020 | Work Order Description - 2020 - CM | CM | 3 | 495413 | WPLAN | TPS | 2017-07-26 | 2020-01-17 | 2019-05-04 | 2019-05-06 | 3 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 2021 | Work Order Description - 2021 - BR | BR | 3 | 247759 | WPLAN | TPS | 2017-07-26 | 2020-01-16 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 2022 | Work Order Description - 2022 - CM | CM | 3 | 357262 | WSCHD | NORM-OPS | 2017-07-06 | 2019-01-05 | 2019-09-07 | 2019-09-08 | 2 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 2065 | Work Order Description - 2065 - CM | CM | 3 | 308865 | WSCHD | NORM-OPS | 2014-03-29 | 2020-04-01 | 2019-12-06 | 2019-12-06 | 3 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 2078 | Work Order Description - 2078 - CM | CM | 4 | 468114 | WSCHD | NORM-OPS | 2015-08-27 | 2019-01-19 | 2019-05-03 | 2019-05-03 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 2091 | Work Order Description - 2091 - CM | CM | 4 | 295923 | WPLAN | NORM-OPS | 2018-02-27 | 2019-02-03 | 2019-06-01 | 2019-06-01 | 3 | INTEGRITY | CONSTRUCTION | 23.5
2019-03-31 | 2110 | Work Order Description - 2110 - CM | CM | 2 | 321199 | WSCHD | NORM-OPS | 2017-07-06 | 2019-03-29 | 2019-08-31 | 2019-09-01 | 4 | MAINTENANCE | MECHANICAL | 100
2019-03-31 | 2111 | Work Order Description - 2111 - CM | CM | 4 | 80527 | WPLAN | TPS | 2018-12-17 | 2019-09-08 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 2126 | Work Order Description - 2126 - CM | CM | 3 | 314298 | WSCHD | SUBSYS-ISOL | 2017-07-05 | 2019-06-11 | 2019-04-06 | 2019-04-09 | 3 | MAINTENANCE | CONSTRUCTION | 165
2019-03-31 | 2135 | Work Order Description - 2135 - CM | CM | 2 | 546611 | WSCHD | NORM-OPS | 2017-07-21 | 2020-04-01 | 2021-09-26 | 2021-09-26 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 2151 | Work Order Description - 2151 - CM | CM | 3 | 306212 | SCHD | TPS | 2018-09-06 | 2019-10-29 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 2152 | Work Order Description - 2152 - CM | CM | 3 | 541965 | SCHD | TPS | 2018-09-06 | 2019-09-07 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 17
2019-03-31 | 2160 | Work Order Description - 2160 - CM | CM | 4 | 213813 | WSCHD | NORM-OPS | 2014-04-18 | 2018-12-21 | 2019-06-22 | 2019-06-22 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 2166 | Work Order Description - 2166 - PM | PM | 3 | 360354 | WSCHD | PACK-ISOL | 2014-04-22 | 2019-04-26 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 2191 | Work Order Description - 2191 - CM | CM | 4 | 320250 | SCHD | TPS | 2019-02-13 | 2021-02-06 | 2019-07-20 | 2019-07-20 | 4 | INTEGRITY | FABRIC | 36
2019-03-31 | 2193 | Work Order Description - 2193 - CM | CM | 2 | 357090 | WSCHD | NORM-OPS | 2017-07-21 | 2019-04-30 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 2265 | Work Order Description - 2265 - CM | CM | 3 | 520043 | WSCHD | TPS | 2017-07-21 | 2019-02-01 | 2020-05-02 | 2020-05-04 | 2 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 2284 | Work Order Description - 2284 - CM | CM | 4 | 501537 | SCHD | TPS | 2018-09-06 | 2019-08-23 | 2019-07-13 | 2019-07-13 | 2 | INTEGRITY | INSTRUMENTS | 12
2019-03-31 | 2285 | Work Order Description - 2285 - CM | CM | 4 | 491060 | SCHD | NORM-OPS | 2018-07-06 | 2019-10-17 | 2019-06-08 | 2019-06-08 | 2 | INTEGRITY | INSTRUMENTS | 12
2019-03-31 | 2286 | Work Order Description - 2286 - CM | CM | 4 | 402744 | SCHD | NORM-OPS | 2018-07-06 | 2019-07-02 | 2019-06-08 | 2019-06-08 | 2 | INTEGRITY | INSTRUMENTS | 1
2019-03-31 | 2305 | Work Order Description - 2305 - CM | CM | 3 | 460679 | SCHD | TPS | 2018-09-06 | 2019-01-27 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 2306 | Work Order Description - 2306 - CM | CM | 3 | 460680 | SCHD | TPS | 2018-09-06 | 2018-12-05 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 2307 | Work Order Description - 2307 - CM | CM | 3 | 29087 | SCHD | TPS | 2018-07-18 | 2019-11-12 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 2310 | Work Order Description - 2310 - PM | PM | 4 | 362499 | WSCHD | EQUIP-ISOL | 2014-05-19 | 2019-03-28 | 2019-09-28 | 2019-09-29 | 2 | INTEGRITY | INSTRUMENTS | 7
2019-03-31 | 2334 | Work Order Description - 2334 - CM | CM | 4 | 215921 | SCHD | NORM-OPS | 2019-02-13 | 2021-02-10 | 2020-02-11 | 2020-02-11 | 4 | INTEGRITY | FABRIC | 68
2019-03-31 | 2371 | Work Order Description - 2371 - BR | BR | 3 | 672480 | SCHD | NORM-OPS | 2019-02-21 | 2019-12-31 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 2393 | Work Order Description - 2393 - CM | CM | 3 | 375637 | SCHD | SYS-ISOL | 2019-02-13 | 2019-06-13 | 2019-05-05 | 2019-05-11 | 4 | MAINTENANCE | CONSTRUCTION | 399
2019-03-31 | 2394 | Work Order Description - 2394 - CM | CM | 2 | 375637 | WPLAN | SYS-ISOL | 2018-05-31 | 2020-01-01 | 2019-05-31 | 2019-06-11 | 4 | MAINTENANCE | CONSTRUCTION | 190
2019-03-31 | 2414 | Work Order Description - 2414 - PSPM | PSPM | 1 | 399545 | WSCHD | EQUIP-ISOL | 2015-10-15 | 2022-08-01 | 2021-06-27 | 2021-06-27 | 1 | INTEGRITY | CONSTRUCTION | 0.016667
2019-03-31 | 2429 | Work Order Description - 2429 - PRJ | PRJ | 4 | 227867 | WPLAN | NORM-OPS | 2017-05-23 | 2019-06-14 | 2019-04-28 | 2019-06-17 | 4 | MAINTENANCE | INSTRUMENTS | 168
2019-03-31 | 2432 | Work Order Description - 2432 - CM | CM | 4 | 21141 | SCHD | TPS | 2018-05-30 | 2019-10-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 83
2019-03-31 | 2453 | Work Order Description - 2453 - PM | PM | 4 | 541013 | WSCHD | NORM-OPS | 2017-07-21 | 2019-04-20 | 2020-06-30 | 2020-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 2467 | Work Order Description - 2467 - CM | CM | 4 | 321318 | WPLAN | TPS | 2017-07-26 | 2020-06-01 | 2020-05-01 | 2020-05-01 | 3 | MAINTENANCE | CONSTRUCTION | 54
2019-03-31 | 2475 | Work Order Description - 2475 - CM | CM | 4 | 403918 | WSCHD | NORM-OPS | 2019-03-25 | 2020-07-31 | 2020-03-14 | 2020-03-14 | 2 | INTEGRITY | CONSTRUCTION | 56
2019-03-31 | 2499 | Work Order Description - 2499 - PM | PM | 2 | 113097 | SCHD | PACK-ISOL | 2018-06-21 | 2019-07-06 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 2506 | Work Order Description - 2506 - CM | CM | 4 | 312996 | SCHD | PACK-ISOL | 2018-09-06 | 2019-07-11 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 2512 | Work Order Description - 2512 - CM | CM | 3 | 322680 | WSCHD | TPS | 2014-09-18 | 2019-10-31 | 2019-09-07 | 2019-09-08 | 4 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 2553 | Work Order Description - 2553 - CM | CM | 3 | 650644 | WPLAN | TPS | 2014-07-16 | 2020-09-01 | 2020-05-02 | 2020-05-07 | 4 | MAINTENANCE | CONSTRUCTION | 225
2019-03-31 | 2554 | Work Order Description - 2554 - BR | BR | 3 | 327539 | WSCHD | TPS | 2014-09-21 | 2019-07-15 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 2556 | Work Order Description - 2556 - CM | CM | 4 | 403918 | WSCHD | TPS | 2019-03-25 | 2020-07-30 | 2020-03-14 | 2020-03-14 | 4 | INTEGRITY | CONSTRUCTION | 150
2019-03-31 | 2633 | Work Order Description - 2633 - CM | CM | 4 | 312438 | SCHD | TPS | 2018-10-09 | 2019-02-27 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 2640 | Work Order Description - 2640 - CM | CM | 3 | 677989 | WPLAN | NORM-OPS | 2018-08-25 | 2019-03-31 | 2019-05-25 | 2019-05-25 | 4 | INTEGRITY | CONSTRUCTION | 53
2019-03-31 | 2677 | Work Order Description - 2677 - CM | CM | 4 | 321218 | WRISKQ | NORM-OPS | 2019-03-25 | 2020-03-06 |  |  | 3 | INTEGRITY | FABRIC | 198
2019-03-31 | 2684 | Work Order Description - 2684 - CM | CM | 4 | 25400 | SCHD | NORM-OPS | 2019-03-29 | 2020-12-16 | 2020-02-29 | 2020-02-29 | 4 | INTEGRITY | FABRIC | 90
2019-03-31 | 2722 | Work Order Description - 2722 - CM | CM | 3 | 33598 | WSCHD | TPS | 2017-07-27 | 2019-03-08 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 2766 | Work Order Description - 2766 - CM | CM | 3 | 501363 | SCHD | TPS | 2019-02-13 | 2021-02-06 | 2019-06-29 | 2019-06-29 | 4 | INTEGRITY | FABRIC | 100
2019-03-31 | 2767 | Work Order Description - 2767 - CM | CM | 3 | 520071 | WSCHD | NORM-OPS | 2015-08-28 | 2020-04-01 | 2019-09-02 | 2019-09-02 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 2790 | Work Order Description - 2790 - PM | PM | 3 | 51172 | WSCHD | EQUIP-ISOL | 2018-06-08 | 2019-06-08 | 2020-05-02 | 2020-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 26
2019-03-31 | 2801 | Work Order Description - 2801 - CM | CM | 4 | 368321 | SCHD | NORM-OPS | 2019-03-05 | 2020-11-13 | 2019-03-30 | 2019-04-02 | 4 | INTEGRITY | FABRIC | 1
2019-03-31 | 2811 | Work Order Description - 2811 - CM | CM | 3 | 48100 | WSCHD | TPS | 2015-08-28 | 2019-07-01 | 2020-05-02 | 2020-05-05 | 3 | MAINTENANCE | OPERATIONS | 26
2019-03-31 | 2850 | Work Order Description - 2850 - PM | PM | 3 | 595920 | WSCHD | EQUIP-ISOL | 2018-06-08 | 2019-01-25 | 2020-05-03 | 2020-05-06 | 2 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 2852 | Work Order Description - 2852 - BR | BR | 2 | 520071 | WSCHD | NORM-OPS | 2015-08-28 | 2020-04-01 | 2019-09-02 | 2019-09-02 | 3 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 2880 | Work Order Description - 2880 - CM | CM | 3 | 479226 | SCHD | NORM-OPS | 2018-07-06 | 2019-05-13 | 2020-01-18 | 2020-01-18 | 3 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 2916 | Work Order Description - 2916 - CM | CM | 2 | 375669 | SCHD | SUBSYS-ISOL | 2018-06-21 | 2019-09-08 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | MECHANICAL | 23
2019-03-31 | 2917 | Work Order Description - 2917 - CM | CM | 3 | 360707 | WSCHD | NORM-OPS | 2017-07-21 | 2019-05-14 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | INSTRUMENTS | 11
2019-03-31 | 2919 | Work Order Description - 2919 - CM | CM | 4 | 215324 | WPLAN | NORM-OPS | 2017-07-26 | 2019-06-27 | 2020-05-02 | 2020-05-05 | 2 | MAINTENANCE | MECHANICAL | 39
2019-03-31 | 2927 | Work Order Description - 2927 - PM | PM | 3 | 57185 | WSCHD | EQUIP-ISOL | 2017-07-21 | 2019-06-12 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 2930 | Work Order Description - 2930 - PM | PM | 4 | 546655 | WSCHD | EQUIP-ISOL | 2015-08-28 | 2019-01-27 | 2019-08-31 | 2019-08-31 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 2941 | Work Order Description - 2941 - PM | PM | 2 | 670468 | INPRG | PACK-ISOL | 2019-03-09 | 2019-08-25 | 2019-03-09 | 2019-03-16 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 2949 | Work Order Description - 2949 - PM | PM | 3 | 53403 | WSCHD | EQUIP-ISOL | 2015-10-14 | 2019-10-12 | 2019-09-24 | 2019-09-24 | 1 | MAINTENANCE | INSTRUMENTS | 0.016667
2019-03-31 | 2950 | Work Order Description - 2950 - PM | PM | 4 | 671635 | WSCHD | EQUIP-ISOL | 2015-10-14 | 2019-10-15 | 2019-09-24 | 2019-09-24 | 1 | MAINTENANCE | INSTRUMENTS | 0.016667
2019-03-31 | 2951 | Work Order Description - 2951 - PM | PM | 3 | 57070 | WSCHD | EQUIP-ISOL | 2015-10-14 | 2019-11-02 | 2019-09-24 | 2019-09-24 | 1 | MAINTENANCE | INSTRUMENTS | 0.016667
2019-03-31 | 2963 | Work Order Description - 2963 - CM | CM | 3 | 51533 | WSCHD | TPS | 2017-10-05 | 2019-02-18 | 2020-05-02 | 2020-05-06 | 3 | MAINTENANCE | MECHANICAL | 63
2019-03-31 | 2964 | Work Order Description - 2964 - CM | CM | 3 | 546695 | WSCHD | TPS | 2017-08-22 | 2019-08-02 | 2020-05-02 | 2020-05-05 | 3 | MAINTENANCE | MECHANICAL | 43
2019-03-31 | 2965 | Work Order Description - 2965 - CM | CM | 3 | 33775 | WSCHD | TPS | 2015-06-11 | 2018-12-24 | 2020-05-02 | 2020-05-05 | 3 | MAINTENANCE | MECHANICAL | 41
2019-03-31 | 2969 | Work Order Description - 2969 - CM | CM | 4 | 495243 | WSCHD | NORM-OPS | 2014-10-06 | 2019-07-30 | 2019-12-28 | 2019-12-29 | 4 | MAINTENANCE | MECHANICAL | 13
2019-03-31 | 2970 | Work Order Description - 2970 - CM | CM | 4 | 495243 | WSCHD | NORM-OPS | 2014-10-06 | 2019-07-22 | 2019-12-28 | 2019-12-29 | 4 | MAINTENANCE | MECHANICAL | 13
2019-03-31 | 2971 | Work Order Description - 2971 - CM | CM | 3 | 520139 | WSCHD | TPS | 2015-08-28 | 2019-11-07 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 2972 | Work Order Description - 2972 - CM | CM | 3 | 248071 | WSCHD | SYS-ISOL | 2015-08-28 | 2019-06-03 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 2973 | Work Order Description - 2973 - CM | CM | 4 | 681342 | WSCHD | NORM-OPS | 2017-07-21 | 2019-09-07 | 2019-09-28 | 2019-09-28 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 2974 | Work Order Description - 2974 - CM | CM | 4 | 681341 | WSCHD | NORM-OPS | 2017-07-06 | 2019-05-28 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 3005 | Work Order Description - 3005 - CM | CM | 4 | 404642 | WSCHD | NORM-OPS | 2017-07-21 | 2019-05-24 | 2019-12-28 | 2020-01-02 | 3 | MAINTENANCE | MECHANICAL | 107
2019-03-31 | 3053 | Work Order Description - 3053 - CM | CM | 1 | 17814 | WSCHD | TPS | 2017-12-07 | 2020-07-02 | 2020-05-02 | 2020-05-03 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 3123 | Work Order Description - 3123 - CM | CM | 4 | 128229 | SCHD | NORM-OPS | 2018-09-06 | 2019-04-01 | 2019-02-16 | 2019-02-16 | 3 | INTEGRITY | SERVICES | 77
2019-03-31 | 3125 | Work Order Description - 3125 - CM | CM | 4 | 408345 | WPLAN | PACK-ISOL | 2014-12-21 | 2019-04-01 | 2019-08-31 | 2019-09-01 | 3 | INTEGRITY | CONSTRUCTION | 10
2019-03-31 | 3145 | Work Order Description - 3145 - CM | CM | 3 | 215018 | WSCHD | SYS-ISOL | 2017-07-05 | 2020-01-05 | 2019-05-01 | 2019-05-02 | 2 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 3146 | Work Order Description - 3146 - CM | CM | 3 | 51172 | WSCHD | SYS-ISOL | 2018-06-08 | 2019-04-17 | 2020-05-03 | 2020-05-06 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 3159 | Work Order Description - 3159 - CM | CM | 3 | 405042 | WSCHD | NORM-OPS | 2017-07-07 | 2019-08-01 | 2019-04-27 | 2019-04-28 | 2 | MAINTENANCE | OPERATIONS | 28
2019-03-31 | 3219 | Work Order Description - 3219 - CM | CM | 4 | 464999 | SCHD | PACK-ISOL | 2018-09-06 | 2019-05-02 | 2019-09-14 | 2019-09-14 | 3 | WELLS | MECHANICAL | 17
2019-03-31 | 3220 | Work Order Description - 3220 - CM | CM | 4 | 578829 | SCHD | PACK-ISOL | 2018-06-21 | 2020-01-24 | 2019-09-21 | 2019-09-21 | 3 | WELLS | MECHANICAL | 58
2019-03-31 | 3237 | Work Order Description - 3237 - PM | PM | 3 | 54483 | WSCHD | PACK-ISOL | 2014-11-24 | 2019-02-20 | 2019-09-01 | 2019-09-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 3238 | Work Order Description - 3238 - PM | PM | 3 | 360535 | WSCHD | PACK-ISOL | 2014-11-24 | 2020-01-11 | 2019-09-01 | 2019-09-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 3239 | Work Order Description - 3239 - PM | PM | 3 | 360536 | WSCHD | PACK-ISOL | 2014-11-24 | 2019-12-06 | 2019-09-01 | 2019-09-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 3240 | Work Order Description - 3240 - PM | PM | 3 | 53258 | WSCHD | PACK-ISOL | 2014-11-24 | 2019-10-14 | 2019-09-01 | 2019-09-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 3243 | Work Order Description - 3243 - PM | PM | 3 | 53612 | WSCHD | PACK-ISOL | 2014-11-24 | 2019-04-30 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 3244 | Work Order Description - 3244 - PM | PM | 3 | 54976 | WSCHD | PACK-ISOL | 2014-11-24 | 2019-08-20 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 3247 | Work Order Description - 3247 - PM | PM | 3 | 653324 | WSCHD | PACK-ISOL | 2014-11-24 | 2018-12-11 | 2019-09-01 | 2019-09-01 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 3248 | Work Order Description - 3248 - PM | PM | 3 | 54117 | WSCHD | PACK-ISOL | 2014-11-24 | 2018-12-20 | 2019-09-01 | 2019-09-01 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 3249 | Work Order Description - 3249 - PM | PM | 3 | 653317 | WSCHD | PACK-ISOL | 2014-11-24 | 2019-09-04 | 2019-09-01 | 2019-09-01 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 3281 | Work Order Description - 3281 - CM | CM | 4 | 307984 | WSCHD | NORM-OPS | 2017-07-21 | 2019-04-02 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | SERVICES | 1
2019-03-31 | 3294 | Work Order Description - 3294 - CM | CM | 4 | 686448 | WPLAN | SYS-ISOL | 2018-05-08 | 2020-05-06 | 2019-07-13 | 2019-07-14 | 4 | INTEGRITY | MECHANICAL | 11
2019-03-31 | 3309 | Work Order Description - 3309 - CM | CM | 4 | 247987 | WSCHD | TPS | 2017-07-21 | 2019-02-27 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 3318 | Work Order Description - 3318 - PSPM | PSPM | 1 | 260936 | WSCHD | EQUIP-ISOL | 2014-12-09 | 2019-05-01 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 3354 | Work Order Description - 3354 - CM | CM | 4 | 50760 | WSCHD | NORM-OPS | 2017-08-10 | 2019-06-02 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | INSTRUMENTS | 14
2019-03-31 | 3362 | Work Order Description - 3362 - CM | CM | 3 | 464175 | SCHD | NORM-OPS | 2018-07-18 | 2019-08-03 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 34
2019-03-31 | 3367 | Work Order Description - 3367 - CM | CM | 4 | 478042 | SCHD | NORM-OPS | 2018-07-06 | 2020-01-07 | 2020-04-04 | 2020-04-04 | 3 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 3382 | Work Order Description - 3382 - CM | CM | 4 | 315789 | SCHD | NORM-OPS | 2019-02-13 | 2021-02-06 | 2019-04-06 | 2019-04-06 | 4 | INTEGRITY | FABRIC | 0
2019-03-31 | 3386 | Work Order Description - 3386 - CM | CM | 4 | 360934 | WSCHD | PACK-ISOL | 2017-07-11 | 2019-08-29 | 2020-05-02 | 2020-05-07 | 3 | MAINTENANCE | INSTRUMENTS | 49
2019-03-31 | 3411 | Work Order Description - 3411 - CM | CM | 4 | 326764 | WSCHD | TPS | 2015-01-24 | 2019-12-08 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 3412 | Work Order Description - 3412 - CM | CM | 4 | 410366 | WSCHD | TPS | 2015-01-24 | 2019-03-26 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 3433 | Work Order Description - 3433 - PSPM | PSPM | 1 | 547543 | WSCHD | SUBSYS-ISOL | 2016-11-28 | 2022-04-01 | 2020-03-07 | 2020-03-07 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 3450 | Work Order Description - 3450 - PM | PM | 2 | 670211 | SCHD | PACK-ISOL | 2018-06-21 | 2019-11-30 | 2019-05-31 | 2019-05-31 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 3451 | Work Order Description - 3451 - PM | PM | 2 | 670212 | SCHD | PACK-ISOL | 2018-06-21 | 2019-05-13 | 2019-05-31 | 2019-05-31 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 3534 | Work Order Description - 3534 - CM | CM | 2 | 308202 | WSCHD | SYS-ISOL | 2018-01-31 | 2018-12-01 | 2020-05-02 | 2020-05-04 | 2 | MAINTENANCE | MECHANICAL | 40
2019-03-31 | 3536 | Work Order Description - 3536 - CM | CM | 3 | 375795 | WPLAN | TPS | 2018-08-20 | 2020-08-17 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 3540 | Work Order Description - 3540 - CM | CM | 3 | 21114 | SCHD | TPS | 2018-09-06 | 2019-11-04 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 43
2019-03-31 | 3549 | Work Order Description - 3549 - CM | CM | 3 | 502862 | WSCHD | SYS-ISOL | 2015-01-18 | 2019-06-02 | 2020-05-02 | 2020-05-06 | 3 | MAINTENANCE | MECHANICAL | 71
2019-03-31 | 3550 | Work Order Description - 3550 - CM | CM | 3 | 666265 | WSCHD | SYS-ISOL | 2015-06-11 | 2019-06-10 | 2020-05-02 | 2020-05-04 | 2 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 3551 | Work Order Description - 3551 - CM | CM | 3 | 308897 | WSCHD | SYS-ISOL | 2015-01-11 | 2019-08-18 | 2020-05-02 | 2020-05-04 | 4 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 3565 | Work Order Description - 3565 - CM | CM | 3 | 501258 | WSCHD | SYS-ISOL | 2017-07-07 | 2019-02-01 | 2019-05-04 | 2019-05-06 | 3 | MAINTENANCE | CONSTRUCTION | 36
2019-03-31 | 3566 | Work Order Description - 3566 - CM | CM | 3 | 501235 | WSCHD | SUBSYS-ISOL | 2017-07-07 | 2019-02-04 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | CONSTRUCTION | 22
2019-03-31 | 3570 | Work Order Description - 3570 - CM | CM | 4 | 55937 | SCHD | NORM-OPS | 2018-09-06 | 2019-10-24 | 2020-02-29 | 2020-02-29 | 3 | INTEGRITY | CONSTRUCTION | 182
2019-03-31 | 3610 | Work Order Description - 3610 - PM | PM | 4 | 595921 | WSCHD | EQUIP-ISOL | 2018-06-08 | 2019-07-16 | 2020-05-03 | 2020-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 3611 | Work Order Description - 3611 - PM | PM | 4 | 540746 | SCHD | EQUIP-ISOL | 2018-12-21 | 2018-12-19 | 2020-05-03 | 2020-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 3663 | Work Order Description - 3663 - CM | CM | 4 | 669388 | SCHD | NORM-OPS | 2018-06-21 | 2019-11-11 | 2019-04-21 | 2019-04-23 | 4 | MAINTENANCE | DRILLING | 13
2019-03-31 | 3843 | Work Order Description - 3843 - CM | CM | 4 | 501769 | WSCHD | SYS-ISOL | 2015-01-31 | 2019-03-14 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 3844 | Work Order Description - 3844 - CM | CM | 4 | 323161 | WSCHD | TPS | 2015-01-31 | 2019-07-12 | 2019-06-01 | 2019-06-02 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 3846 | Work Order Description - 3846 - CM | CM | 4 | 490381 | WSCHD | NORM-OPS | 2015-01-29 | 2019-11-07 | 2019-06-15 | 2019-06-15 | 4 | MAINTENANCE | SERVICES | 1
2019-03-31 | 3901 | Work Order Description - 3901 - CM | CM | 4 | 546068 | WSCHD | NORM-OPS | 2017-07-21 | 2019-05-17 | 2019-05-25 | 2019-05-26 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 3904 | Work Order Description - 3904 - CM | CM | 3 | 659338 | SCHD | SYS-ISOL | 2018-06-21 | 2020-03-04 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 3988 | Work Order Description - 3988 - CM | CM | 2 | 321115 | WSCHD | NORM-OPS | 2015-02-15 | 2019-10-01 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 3994 | Work Order Description - 3994 - CM | CM | 4 | 477563 | SCHD | TPS | 2018-09-06 | 2020-01-12 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 4066 | Work Order Description - 4066 - CM | CM | 3 | 568873 | SCHD | TPS | 2018-09-06 | 2020-01-10 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 4072 | Work Order Description - 4072 - CM | CM | 4 | 469182 | SCHD | PACK-ISOL | 2018-12-21 | 2019-11-11 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | CONSTRUCTION | 12
2019-03-31 | 4075 | Work Order Description - 4075 - CM | CM | 2 | 469183 | WSCHD | PACK-ISOL | 2018-06-07 | 2019-06-12 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | CONSTRUCTION | 12
2019-03-31 | 4090 | Work Order Description - 4090 - PM | PM | 4 | 357335 | WSCHD | EQUIP-ISOL | 2017-07-21 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 4144 | Work Order Description - 4144 - CM | CM | 4 | 669235 | SCHD | NORM-OPS | 2019-03-15 | 2021-03-13 | 2019-09-28 | 2019-09-29 | 4 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 4145 | Work Order Description - 4145 - CM | CM | 4 | 124424 | WPLAN | NORM-OPS | 2017-09-06 | 2019-01-27 | 2019-09-29 | 2019-09-30 | 4 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 4162 | Work Order Description - 4162 - CM | CM | 3 | 35886 | SCHD | TPS | 2018-09-06 | 2019-11-16 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 25
2019-03-31 | 4243 | Work Order Description - 4243 - CM | CM | 4 | 323263 | WSCHD | TPS | 2015-03-12 | 2020-01-03 | 2020-05-02 | 2020-05-07 | 2 | MAINTENANCE | MECHANICAL | 88
2019-03-31 | 4262 | Work Order Description - 4262 - CM | CM | 4 | 408320 | WSCHD | NORM-OPS | 2017-07-21 | 2019-03-12 | 2019-06-15 | 2019-06-15 | 4 | OPERATIONS | OPERATIONS | 1
2019-03-31 | 4345 | Work Order Description - 4345 - CM | CM | 3 | 357127 | WSCHD | NORM-OPS | 2017-07-21 | 2019-09-24 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 4350 | Work Order Description - 4350 - CM | CM | 4 | 261320 | WSCHD | NORM-OPS | 2015-08-28 | 2019-10-01 | 2019-08-31 | 2019-09-03 | 4 | MAINTENANCE | MECHANICAL | 56
2019-03-31 | 4364 | Work Order Description - 4364 - CM | CM | 3 | 463174 | SCHD | TPS | 2018-09-06 | 2019-02-28 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 127
2019-03-31 | 4373 | Work Order Description - 4373 - CM | CM | 3 | 261935 | WSCHD | TPS | 2018-08-31 | 2019-08-10 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 4377 | Work Order Description - 4377 - CM | CM | 4 | 490502 | SCHD | NORM-OPS | 2018-09-06 | 2019-10-08 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 37
2019-03-31 | 4383 | Work Order Description - 4383 - CM | CM | 3 | 392462 | WPLAN | SYS-ISOL | 2018-08-20 | 2020-08-17 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 4390 | Work Order Description - 4390 - PSCM | PSCM | 1 | 494090 | WSCHD | SYS-ISOL | 2018-06-08 | 2020-08-01 | 2020-05-03 | 2020-05-06 | 3 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 4421 | Work Order Description - 4421 - PM | PM | 3 | 359313 | WSCHD | NORM-OPS | 2017-07-21 | 2019-01-24 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 4430 | Work Order Description - 4430 - CM | CM | 4 | 19142 | WPLAN | PACK-ISOL | 2015-04-27 | 2019-08-15 | 2019-08-31 | 2019-08-31 | 4 | INTEGRITY | CONSTRUCTION | 0.1
2019-03-31 | 4436 | Work Order Description - 4436 - CM | CM | 1 | 210544 | WPLAN | TPS | 2018-02-14 | 2020-09-01 | 2020-05-02 | 2020-05-07 | 4 | INTEGRITY | CONSTRUCTION | 47.5
2019-03-31 | 4439 | Work Order Description - 4439 - CM | CM | 4 | 191685 | WSCHD | NORM-OPS | 2015-08-28 | 2019-01-10 | 2019-06-29 | 2019-06-30 | 3 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 4443 | Work Order Description - 4443 - CM | CM | 3 | 55322 | SCHD | TPS | 2018-09-06 | 2019-06-24 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 112
2019-03-31 | 4464 | Work Order Description - 4464 - CM | CM | 3 | 661048 | WSCHD | NORM-OPS | 2017-07-21 | 2019-08-20 | 2019-04-27 | 2019-04-28 | 2 | WELLS | WELLS | 7
2019-03-31 | 4498 | Work Order Description - 4498 - CM | CM | 4 | 501087 | SCHD | NORM-OPS | 2018-09-06 | 2019-07-27 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | MECHANICAL | 33
2019-03-31 | 4504 | Work Order Description - 4504 - CM | CM | 3 | 33908 | WSCHD | SYS-ISOL | 2018-06-08 | 2019-07-10 | 2020-05-03 | 2020-05-05 | 2 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 4512 | Work Order Description - 4512 - CM | CM | 3 | 314379 | WSCHD | NORM-OPS | 2018-06-08 | 2020-04-01 | 2020-05-03 | 2020-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 4516 | Work Order Description - 4516 - CM | CM | 3 | 375637 | WPLAN | NORM-OPS | 2018-08-20 | 2020-08-17 | 2020-07-28 | 2020-08-12 | 4 | MAINTENANCE | MECHANICAL | 100
2019-03-31 | 4517 | Work Order Description - 4517 - CM | CM | 3 | 375637 | WPLAN | NORM-OPS | 2018-08-20 | 2020-08-17 | 2020-07-28 | 2020-07-30 | 4 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 4527 | Work Order Description - 4527 - PM | PM | 3 | 491977 | SCHD | SUBSYS-ISOL | 2018-09-06 | 2019-11-28 | 2020-01-04 | 2020-01-04 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 4535 | Work Order Description - 4535 - CM | CM | 3 | 435781 | WPLAN | SYS-ISOL | 2018-10-08 | 2020-08-17 | 2019-07-13 | 2019-07-14 | 4 | INTEGRITY | MECHANICAL | 19
2019-03-31 | 4633 | Work Order Description - 4633 - CM | CM | 3 | 25356 | SCHD | TPS | 2018-09-06 | 2019-01-28 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 66
2019-03-31 | 4647 | Work Order Description - 4647 - PSPM | PSPM | 1 | 399558 | WSCHD | PACK-ISOL | 2015-04-28 | 2020-01-01 | 2019-11-30 | 2019-11-30 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 4649 | Work Order Description - 4649 - PSPM | PSPM | 1 | 653313 | WSCHD | PACK-ISOL | 2016-09-02 | 2020-01-01 | 2020-01-25 | 2020-01-25 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 4663 | Work Order Description - 4663 - BR | BR | 3 | 58332 | WSCHD | TPS | 2015-05-15 | 2018-12-06 | 2019-08-31 | 2019-09-05 | 3 | MAINTENANCE | MECHANICAL | 53
2019-03-31 | 4665 | Work Order Description - 4665 - PSPM | PSPM | 1 | 248095 | WSCHD | EQUIP-ISOL | 2015-10-15 | 2022-08-01 | 2020-05-02 | 2020-05-02 | 1 | INTEGRITY | CONSTRUCTION | 0.016667
2019-03-31 | 4695 | Work Order Description - 4695 - CM | CM | 3 | 411162 | WSCHD | TPS | 2018-06-08 | 2019-10-06 | 2020-05-03 | 2020-05-03 | 2 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 4700 | Work Order Description - 4700 - CM | CM | 4 | 671829 | SCHD | NORM-OPS | 2019-03-08 | 2019-06-22 | 2019-04-13 | 2019-04-15 | 3 | MAINTENANCE | INSTRUMENTS | 37
2019-03-31 | 4702 | Work Order Description - 4702 - PRJ | PRJ | 4 | 404767 | WSCHD | NORM-OPS | 2017-07-21 | 2019-03-28 | 2019-12-30 | 2019-12-30 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 4764 | Work Order Description - 4764 - PSPM | PSPM | 1 | 248132 | WSCHD | EQUIP-ISOL | 2015-11-02 | 2021-01-01 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | CONSTRUCTION | 0.016667
2019-03-31 | 4774 | Work Order Description - 4774 - BR | BR | 4 | 138124 | WSCHD | NORM-OPS | 2017-07-21 | 2019-09-13 | 2019-10-05 | 2019-10-05 | 4 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 4804 | Work Order Description - 4804 - CM | CM | 3 | 479579 | SCHD | NORM-OPS | 2018-10-09 | 2019-10-01 | 2020-03-28 | 2020-03-28 | 3 | INTEGRITY | FABRIC | 66
2019-03-31 | 4834 | Work Order Description - 4834 - CM | CM | 3 | 383796 | WPLAN | TPS | 2018-08-20 | 2020-08-17 | 2019-07-13 | 2019-07-15 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 4839 | Work Order Description - 4839 - PSCM | PSCM | 1 | 50802 | WPLAN | TPS | 2016-08-11 | 2020-09-01 | 2020-05-02 | 2020-05-02 | 2 | INTEGRITY | CONSTRUCTION | 0.1
2019-03-31 | 4844 | Work Order Description - 4844 - CM | CM | 4 | 697913 | WPLAN | NORM-OPS | 2018-05-03 | 2019-03-28 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | CONSTRUCTION | 0.1
2019-03-31 | 4847 | Work Order Description - 4847 - CM | CM | 3 | 449075 | WMATL | SYS-ISOL | 2017-09-11 | 2019-08-21 | 2019-07-13 | 2019-07-14 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 4853 | Work Order Description - 4853 - CM | CM | 3 | 686448 | WPLAN | SYS-ISOL | 2018-08-20 | 2020-08-17 | 2019-07-13 | 2019-07-14 | 4 | INTEGRITY | MECHANICAL | 8
2019-03-31 | 4856 | Work Order Description - 4856 - CM | CM | 4 | 126953 | WPLAN | NORM-OPS | 2018-08-20 | 2020-08-17 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 4901 | Work Order Description - 4901 - CM | CM | 4 | 216158 | WPLAN | NORM-OPS | 2016-02-05 | 2019-01-07 | 2020-03-07 | 2020-03-07 | 3 | DRILLING | CONSTRUCTION | 90
2019-03-31 | 4912 | Work Order Description - 4912 - CM | CM | 3 | 449120 | WPLAN | SYS-ISOL | 2018-08-20 | 2020-08-17 | 2019-07-13 | 2019-07-16 | 4 | MAINTENANCE | MECHANICAL | 50
2019-03-31 | 4913 | Work Order Description - 4913 - PSCM | PSCM | 1 | 520311 | WSCHD | SYS-ISOL | 2017-07-21 | 2019-07-01 | 2020-01-01 | 2020-01-03 | 4 | MAINTENANCE | MECHANICAL | 43
2019-03-31 | 4922 | Work Order Description - 4922 - CM | CM | 4 | 45250 | WSCHD | TPS | 2016-04-11 | 2019-12-09 | 2020-01-01 | 2020-01-02 | 3 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 5012 | Work Order Description - 5012 - CM | CM | 4 | 407438 | WSCHD | NORM-OPS | 2015-08-28 | 2019-09-26 | 2019-09-30 | 2019-10-01 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 5013 | Work Order Description - 5013 - CM | CM | 4 | 546931 | WSCHD | NORM-OPS | 2015-08-28 | 2019-07-30 | 2019-09-30 | 2019-10-01 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 5019 | Work Order Description - 5019 - CM | CM | 1 | 572012 | WPLAN | TPS | 2018-02-14 | 2020-09-01 | 2020-05-02 | 2020-05-05 | 3 | INTEGRITY | CONSTRUCTION | 42
2019-03-31 | 5020 | Work Order Description - 5020 - CM | CM | 1 | 572012 | WPLAN | TPS | 2018-02-14 | 2020-09-01 | 2020-05-02 | 2020-05-03 | 3 | INTEGRITY | CONSTRUCTION | 20
2019-03-31 | 5033 | Work Order Description - 5033 - PSPM | PSPM | 1 | 677996 | WSCHD | SUBSYS-ISOL | 2018-06-14 | 2019-07-06 | 2019-06-01 | 2019-06-04 | 1 | INTEGRITY | MECHANICAL | 1
2019-03-31 | 5064 | Work Order Description - 5064 - PSCM | PSCM | 1 | 671265 | SCHD | PACK-ISOL | 2018-11-11 | 2020-08-01 | 2019-07-06 | 2019-07-07 | 4 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 5069 | Work Order Description - 5069 - CM | CM | 3 | 404691 | SCHD | NORM-OPS | 2018-11-30 | 2019-09-13 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 19
2019-03-31 | 5070 | Work Order Description - 5070 - CM | CM | 1 | 17814 | WPLAN | TPS | 2016-08-14 | 2020-06-11 | 2020-05-02 | 2020-05-02 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 5073 | Work Order Description - 5073 - PSPM | PSPM | 1 | 248300 | WSCHD | EQUIP-ISOL | 2015-06-17 | 2020-08-01 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 5146 | Work Order Description - 5146 - PSCM | PSCM | 1 | 50981 | WSCHD | SUBSYS-ISOL | 2018-07-03 | 2019-05-01 | 2019-08-02 | 2019-08-02 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 5147 | Work Order Description - 5147 - CM | CM | 3 | 325831 | WPLAN | TPS | 2017-07-26 | 2019-09-06 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 5148 | Work Order Description - 5148 - CM | CM | 3 | 494339 | WPLAN | TPS | 2017-07-26 | 2019-09-06 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 5162 | Work Order Description - 5162 - CM | CM | 4 | 368215 | WSCHD | NORM-OPS | 2015-08-28 | 2019-04-04 | 2019-06-01 | 2019-06-04 | 4 | MAINTENANCE | ELECTRICAL | 42
2019-03-31 | 5172 | Work Order Description - 5172 - CM | CM | 3 | 34006 | WSCHD | SYS-ISOL | 2015-06-25 | 2019-09-06 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 5173 | Work Order Description - 5173 - CM | CM | 1 | 17814 | WPLAN | TPS | 2018-02-14 | 2020-09-01 | 2020-05-02 | 2020-05-04 | 2 | INTEGRITY | CONSTRUCTION | 51
2019-03-31 | 5190 | Work Order Description - 5190 - CM | CM | 4 | 99434 | SCHD | NORM-OPS | 2018-06-21 | 2019-03-08 | 2019-09-01 | 2019-09-29 | 2 | MAINTENANCE | MECHANICAL | 62
2019-03-31 | 5197 | Work Order Description - 5197 - CM | CM | 1 | 17814 | WPLAN | TPS | 2015-12-23 | 2020-07-24 | 2020-05-02 | 2020-05-02 | 3 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 5200 | Work Order Description - 5200 - CM | CM | 3 | 686448 | WPLAN | TPS | 2018-08-20 | 2020-08-17 | 2019-07-13 | 2019-10-05 | 4 | INTEGRITY | MECHANICAL | 29
2019-03-31 | 5201 | Work Order Description - 5201 - CM | CM | 3 | 686448 | WPLAN | SYS-ISOL | 2018-08-20 | 2020-08-17 | 2019-07-13 | 2019-07-14 | 4 | INTEGRITY | MECHANICAL | 18
2019-03-31 | 5216 | Work Order Description - 5216 - CM | CM | 3 | 12611 | SCHD | TPS | 2018-09-06 | 2019-06-19 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 52
2019-03-31 | 5227 | Work Order Description - 5227 - CM | CM | 3 | 490120 | WSCHD | NORM-OPS | 2015-07-06 | 2020-04-01 | 2021-09-25 | 2021-09-28 | 4 | MAINTENANCE | MECHANICAL | 54
2019-03-31 | 5230 | Work Order Description - 5230 - CM | CM | 3 | 36120 | SCHD | PACK-ISOL | 2018-09-06 | 2019-02-12 | 2019-09-28 | 2019-09-28 | 3 | WELLS | MECHANICAL | 37
2019-03-31 | 5238 | Work Order Description - 5238 - CM | CM | 3 | 397036 | WPLAN | SUBSYS-ISOL | 2018-05-08 | 2019-08-01 | 2019-07-13 | 2019-07-14 | 4 | INTEGRITY | MECHANICAL | 18
2019-03-31 | 5241 | Work Order Description - 5241 - CM | CM | 4 | 327687 | WSCHD | TPS | 2018-06-08 | 2019-09-06 | 2020-05-03 | 2020-05-04 | 4 | MAINTENANCE | CONSTRUCTION | 16
2019-03-31 | 5246 | Work Order Description - 5246 - PSPM | PSPM | 1 | 677994 | WSCHD | SUBSYS-ISOL | 2015-11-02 | 2021-08-01 | 2019-12-28 | 2019-12-28 | 1 | INTEGRITY | INSTRUMENTS | 0.016667
2019-03-31 | 5354 | Work Order Description - 5354 - CM | CM | 4 | 572012 | WPLAN | NORM-OPS | 2018-12-31 | 2020-09-01 | 2019-05-04 | 2019-05-04 | 3 | INTEGRITY | CONSTRUCTION | 6
2019-03-31 | 5372 | Work Order Description - 5372 - PM | PM | 3 | 496768 | WSCHD | SUBSYS-ISOL | 2015-07-16 | 2019-12-06 | 2019-09-28 | 2019-09-28 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 5373 | Work Order Description - 5373 - PM | PM | 3 | 481328 | WSCHD | SUBSYS-ISOL | 2015-07-16 | 2019-02-15 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 5434 | Work Order Description - 5434 - PM | PM | 4 | 272335 | WSCHD | NORM-OPS | 2015-07-27 | 2019-01-28 | 2019-04-13 | 2019-04-14 | 2 | OPERATIONS | OPERATIONS | 8
2019-03-31 | 5436 | Work Order Description - 5436 - PSPM | PSPM | 1 | 54112 | WSCHD | PACK-ISOL | 2015-07-22 | 2019-06-01 | 2020-12-26 | 2020-12-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 5466 | Work Order Description - 5466 - CM | CM | 3 | 245376 | WSCHD | TPS | 2018-06-08 | 2019-03-24 | 2020-05-03 | 2020-05-04 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 5467 | Work Order Description - 5467 - CM | CM | 4 | 499837 | WSCHD | TPS | 2018-06-08 | 2019-12-17 | 2020-05-03 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 5468 | Work Order Description - 5468 - CM | CM | 4 | 438325 | WSCHD | TPS | 2018-06-08 | 2019-10-14 | 2020-05-03 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 5514 | Work Order Description - 5514 - CM | CM | 1 | 17814 | WPLAN | SYS-ISOL | 2018-02-14 | 2020-09-01 | 2020-05-02 | 2020-05-08 | 3 | INTEGRITY | CONSTRUCTION | 99
2019-03-31 | 5515 | Work Order Description - 5515 - CM | CM | 4 | 368329 | WPLAN | TPS | 2016-10-24 | 2020-09-01 | 2020-05-02 | 2020-05-03 | 3 | INTEGRITY | CONSTRUCTION | 12
2019-03-31 | 5516 | Work Order Description - 5516 - CM | CM | 1 | 17814 | WPLAN | SYS-ISOL | 2018-02-14 | 2020-09-01 | 2020-05-02 | 2020-05-03 | 3 | INTEGRITY | CONSTRUCTION | 7
2019-03-31 | 5524 | Work Order Description - 5524 - CM | CM | 3 | 322377 | WSCHD | TPS | 2018-06-21 | 2019-12-24 | 2020-05-03 | 2020-05-05 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 5526 | Work Order Description - 5526 - CM | CM | 4 | 472796 | SCHD | NORM-OPS | 2019-01-27 | 2020-01-08 | 2019-11-09 | 2019-11-09 | 3 | INTEGRITY | FABRIC | 147
2019-03-31 | 5527 | Work Order Description - 5527 - CM | CM | 3 | 327241 | WSCHD | TPS | 2018-06-21 | 2019-10-16 | 2020-05-03 | 2020-05-04 | 3 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 5561 | Work Order Description - 5561 - CM | CM | 4 | 361880 | WSCHD | TPS | 2018-06-08 | 2019-03-30 | 2020-05-03 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 5563 | Work Order Description - 5563 - CM | CM | 4 | 228839 | INPRG | NORM-OPS | 2018-08-08 | 2019-02-01 | 2019-05-05 | 2019-05-21 | 4 | INTEGRITY | CONSTRUCTION | 20.25
2019-03-31 | 5567 | Work Order Description - 5567 - CM | CM | 4 | 652140 | WSCHD | NORM-OPS | 2018-04-05 | 2019-09-06 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 5569 | Work Order Description - 5569 - CM | CM | 3 | 525033 | WSCHD | TPS | 2018-06-12 | 2019-03-06 | 2020-05-02 | 2020-05-04 | 3 | MAINTENANCE | CONSTRUCTION | 10
2019-03-31 | 5594 | Work Order Description - 5594 - CM | CM | 4 | 546611 | WSCHD | NORM-OPS | 2015-08-07 | 2020-04-01 | 2020-03-06 | 2020-03-06 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 5599 | Work Order Description - 5599 - CM | CM | 3 | 51662 | WSCHD | NORM-OPS | 2017-05-08 | 2019-09-06 | 2019-10-05 | 2019-10-05 | 4 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 5606 | Work Order Description - 5606 - BR | BR | 4 | 322640 | WSCHD | SYS-ISOL | 2015-08-07 | 2019-09-06 | 2019-08-17 | 2019-08-20 | 4 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 5610 | Work Order Description - 5610 - CM | CM | 4 | 322935 | WSCHD | TPS | 2018-08-05 | 2019-09-06 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | CONSTRUCTION | 4
2019-03-31 | 5611 | Work Order Description - 5611 - CM | CM | 4 | 501419 | WSCHD | TPS | 2018-08-05 | 2019-09-06 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 5613 | Work Order Description - 5613 - CM | CM | 4 | 34105 | WSCHD | SYS-ISOL | 2018-06-21 | 2019-09-06 | 2020-05-03 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 5619 | Work Order Description - 5619 - CM | CM | 2 | 58163 | SCHD | TPS | 2018-12-05 | 2019-04-07 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 5620 | Work Order Description - 5620 - CM | CM | 2 | 327532 | WSCHD | NORM-OPS | 2015-08-28 | 2020-01-22 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 5628 | Work Order Description - 5628 - CM | CM | 1 | 210544 | WPLAN | TPS | 2018-02-14 | 2020-09-01 | 2020-05-02 | 2020-05-05 | 2 | INTEGRITY | CONSTRUCTION | 105
2019-03-31 | 5629 | Work Order Description - 5629 - CM | CM | 3 | 436047 | SCHD | NORM-OPS | 2018-08-14 | 2019-08-14 | 2019-05-25 | 2019-05-27 | 4 | INTEGRITY | CONSTRUCTION | 42
2019-03-31 | 5630 | Work Order Description - 5630 - CM | CM | 3 | 527507 | INPRG | NORM-OPS | 2018-09-12 | 2019-07-26 | 2019-03-09 | 2019-03-14 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 5652 | Work Order Description - 5652 - CM | CM | 4 | 572012 | WPLAN | NORM-OPS | 2016-07-09 | 2020-09-01 | 2019-09-07 | 2019-09-07 | 2 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 5708 | Work Order Description - 5708 - CM | CM | 4 | 572012 | WPLAN | TPS | 2016-04-16 | 2020-09-01 | 2020-05-02 | 2020-05-02 | 2 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 5711 | Work Order Description - 5711 - CM | CM | 2 | 450548 | WPLAN | NORM-OPS | 2015-09-22 | 2020-01-05 | 2019-07-13 | 2019-07-16 | 3 | INTEGRITY | CONSTRUCTION | 25
2019-03-31 | 5713 | Work Order Description - 5713 - CM | CM | 4 | 172651 | WPLAN | NORM-OPS | 2017-07-05 | 2020-09-01 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 5723 | Work Order Description - 5723 - PRJ | PRJ | 4 | 575063 | WSCHD | NORM-OPS | 2017-07-21 | 2019-04-12 | 2019-07-27 | 2019-07-27 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 5765 | Work Order Description - 5765 - CM | CM | 4 | 479579 | SCHD | NORM-OPS | 2018-10-09 | 2019-07-01 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | FABRIC | 90
2019-03-31 | 5767 | Work Order Description - 5767 - CM | CM | 3 | 547760 | WSCHD | TPS | 2018-06-21 | 2019-06-09 | 2020-05-02 | 2020-05-08 | 3 | MAINTENANCE | MECHANICAL | 65
2019-03-31 | 5768 | Work Order Description - 5768 - PSCM | PSCM | 1 | 399584 | WSCHD | TPS | 2018-06-15 | 2019-08-01 | 2020-05-02 | 2020-05-07 | 3 | MAINTENANCE | MECHANICAL | 101
2019-03-31 | 5769 | Work Order Description - 5769 - CM | CM | 4 | 327716 | WSCHD | TPS | 2015-08-23 | 2019-09-06 | 2019-06-01 | 2019-06-03 | 4 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 5808 | Work Order Description - 5808 - CM | CM | 2 | 33427 | WSCHD | NORM-OPS | 2015-09-08 | 2019-04-28 | 2019-07-27 | 2019-07-28 | 3 | MAINTENANCE | MECHANICAL | 23
2019-03-31 | 5824 | Work Order Description - 5824 - CM | CM | 3 | 411138 | WSCHD | SYS-ISOL | 2015-08-29 | 2019-05-28 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 5825 | Work Order Description - 5825 - CM | CM | 3 | 409745 | WSCHD | SYS-ISOL | 2015-08-29 | 2019-03-15 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 5826 | Work Order Description - 5826 - CM | CM | 3 | 247130 | WSCHD | SYS-ISOL | 2015-08-29 | 2019-11-17 | 2020-12-01 | 2020-12-01 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 5835 | Work Order Description - 5835 - CM | CM | 4 | 490862 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-24 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 40
2019-03-31 | 5838 | Work Order Description - 5838 - CM | CM | 3 | 138124 | WSCHD | NORM-OPS | 2017-07-21 | 2019-01-10 | 2019-10-05 | 2019-10-14 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 5840 | Work Order Description - 5840 - CM | CM | 3 | 138124 | WSCHD | NORM-OPS | 2017-07-21 | 2019-01-27 | 2019-10-19 | 2019-10-19 | 3 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 5863 | Work Order Description - 5863 - CM | CM | 4 | 326466 | WSCHD | TPS | 2017-07-21 | 2019-02-14 | 2019-06-01 | 2019-06-02 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 5867 | Work Order Description - 5867 - CM | CM | 4 | 494196 | WSCHD | TPS | 2018-05-31 | 2019-04-06 | 2020-05-03 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 3.5
2019-03-31 | 6367 | Work Order Description - 6367 - CM | CM | 3 | 503101 | WSCHD | TPS | 2015-09-04 | 2019-09-06 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 6370 | Work Order Description - 6370 - CM | CM | 4 | 358306 | WSCHD | NORM-OPS | 2015-09-13 | 2019-12-17 | 2019-05-11 | 2019-05-12 | 2 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 6372 | Work Order Description - 6372 - CM | CM | 3 | 308129 | WSCHD | NORM-OPS | 2017-07-21 | 2019-06-21 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | INSTRUMENTS | 22.5
2019-03-31 | 6380 | Work Order Description - 6380 - CM | CM | 4 | 19019 | WSCHD | NORM-OPS | 2017-07-21 | 2019-08-12 | 2019-06-15 | 2019-06-15 | 3 | INTEGRITY | SERVICES | 1
2019-03-31 | 6381 | Work Order Description - 6381 - CM | CM | 2 | 480203 | WSCHD | NORM-OPS | 2017-07-06 | 2019-08-18 | 2019-04-18 | 2019-04-19 | 3 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 6402 | Work Order Description - 6402 - CM | CM | 4 | 408345 | WSCHD | NORM-OPS | 2017-07-21 | 2019-07-01 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 6403 | Work Order Description - 6403 - CM | CM | 4 | 408345 | WSCHD | NORM-OPS | 2017-07-21 | 2019-07-01 | 2019-09-28 | 2019-09-30 | 3 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 6450 | Work Order Description - 6450 - CM | CM | 4 | 450550 | SCHD | NORM-OPS | 2018-08-14 | 2019-01-11 | 2019-05-25 | 2019-05-31 | 4 | INTEGRITY | CONSTRUCTION | 49
2019-03-31 | 6471 | Work Order Description - 6471 - CM | CM | 4 | 481743 | SCHD | NORM-OPS | 2019-01-22 | 2020-01-21 | 2019-04-06 | 2019-04-06 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 6514 | Work Order Description - 6514 - PSCM | PSCM | 1 | 51162 | WSCHD | TPS | 2018-06-08 | 2020-08-01 | 2020-05-03 | 2020-05-05 | 2 | MAINTENANCE | MECHANICAL | 29
2019-03-31 | 6515 | Work Order Description - 6515 - CM | CM | 3 | 322522 | WSCHD | TPS | 2015-09-27 | 2018-12-13 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 6516 | Work Order Description - 6516 - CM | CM | 3 | 327383 | WSCHD | TPS | 2015-09-27 | 2019-06-26 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 6519 | Work Order Description - 6519 - PM | PM | 3 | 410689 | WSCHD | EQUIP-ISOL | 2015-09-29 | 2019-05-04 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 6527 | Work Order Description - 6527 - CM | CM | 4 | 324498 | WSCHD | NORM-OPS | 2015-09-25 | 2019-04-08 | 2019-09-07 | 2019-09-08 | 2 | MAINTENANCE | MECHANICAL | 23
2019-03-31 | 6538 | Work Order Description - 6538 - CM | CM | 2 | 663482 | WPLAN | TPS | 2018-10-10 | 2019-09-13 | 2019-07-13 | 2019-07-19 | 4 | INTEGRITY | MECHANICAL | 84
2019-03-31 | 6540 | Work Order Description - 6540 - CM | CM | 2 | 669622 | WPLAN | NORM-OPS | 2018-10-08 | 2019-09-13 | 2019-07-13 | 2019-07-18 | 4 | INTEGRITY | MECHANICAL | 60
2019-03-31 | 6542 | Work Order Description - 6542 - CM | CM | 4 | 368215 | WSCHD | NORM-OPS | 2017-07-21 | 2019-09-06 | 2019-06-01 | 2019-06-04 | 4 | MAINTENANCE | ELECTRICAL | 63
2019-03-31 | 6609 | Work Order Description - 6609 - PM | PM | 4 | 128080 | SCHD | SUBSYS-ISOL | 2018-06-21 | 2020-12-26 | 2019-08-10 | 2019-08-10 | 4 | INTEGRITY | INSPECTION | 3
2019-03-31 | 6632 | Work Order Description - 6632 - BR | BR | 4 | 658088 | WSCHD | NORM-OPS | 2015-10-09 | 2019-09-06 | 2019-04-20 | 2019-04-24 | 4 | MAINTENANCE | MECHANICAL | 35
2019-03-31 | 6633 | Work Order Description - 6633 - CM | CM | 3 | 308732 | WSCHD | NORM-OPS | 2017-07-21 | 2020-01-22 | 2019-04-20 | 2019-04-21 | 2 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 6673 | Work Order Description - 6673 - CM | CM | 3 | 308157 | WSCHD | SYS-ISOL | 2015-10-09 | 2019-05-11 | 2020-05-03 | 2020-05-04 | 2 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 6676 | Work Order Description - 6676 - CM | CM | 4 | 558310 | WSCHD | NORM-OPS | 2018-11-16 | 2021-11-03 | 2019-05-25 | 2019-06-11 | 4 | INTEGRITY | FABRIC | 295.5
2019-03-31 | 6682 | Work Order Description - 6682 - PSCM | PSCM | 1 | 403562 | SCHD | NORM-OPS | 2018-08-08 | 2019-11-01 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | FABRIC | 280
2019-03-31 | 6685 | Work Order Description - 6685 - CM | CM | 4 | 479487 | SCHD | NORM-OPS | 2018-10-09 | 2019-07-01 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | FABRIC | 1
2019-03-31 | 6696 | Work Order Description - 6696 - PM | PM | 3 | 409792 | WSCHD | EQUIP-ISOL | 2017-11-06 | 2019-02-24 | 2019-10-26 | 2019-10-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 6697 | Work Order Description - 6697 - PM | PM | 3 | 53372 | WSCHD | EQUIP-ISOL | 2017-11-06 | 2019-05-25 | 2019-10-26 | 2019-10-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 6698 | Work Order Description - 6698 - PM | PM | 3 | 410251 | WSCHD | EQUIP-ISOL | 2017-11-06 | 2019-06-02 | 2019-09-28 | 2019-09-28 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 6699 | Work Order Description - 6699 - PM | PM | 3 | 308533 | WSCHD | EQUIP-ISOL | 2017-11-06 | 2018-12-15 | 2020-12-26 | 2020-12-26 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 6700 | Work Order Description - 6700 - PM | PM | 3 | 57068 | WSCHD | EQUIP-ISOL | 2017-11-06 | 2019-08-30 | 2020-12-26 | 2020-12-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 6701 | Work Order Description - 6701 - PM | PM | 3 | 54247 | WSCHD | EQUIP-ISOL | 2017-11-06 | 2019-06-25 | 2020-12-26 | 2020-12-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 6702 | Work Order Description - 6702 - PM | PM | 3 | 674803 | WSCHD | EQUIP-ISOL | 2017-11-06 | 2019-10-17 | 2020-12-26 | 2020-12-26 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 6715 | Work Order Description - 6715 - CM | CM | 1 | 17814 | WPLAN | TPS | 2018-02-14 | 2020-09-01 | 2020-05-02 | 2020-05-04 | 3 | INTEGRITY | CONSTRUCTION | 66
2019-03-31 | 6735 | Work Order Description - 6735 - CM | CM | 4 | 490534 | SCHD | NORM-OPS | 2018-06-21 | 2019-10-29 | 2019-04-20 | 2019-04-20 | 4 | INTEGRITY | INSTRUMENTS | 46
2019-03-31 | 6779 | Work Order Description - 6779 - CM | CM | 3 | 545260 | WSCHD | NORM-OPS | 2015-10-13 | 2020-01-11 | 2019-05-25 | 2019-05-29 | 4 | MAINTENANCE | MECHANICAL | 62
2019-03-31 | 6785 | Work Order Description - 6785 - CM | CM | 1 | 247220 | WPLAN | NORM-OPS | 2016-04-16 | 2019-06-23 | 2019-05-04 | 2019-05-09 | 4 | INTEGRITY | CONSTRUCTION | 72
2019-03-31 | 6805 | Work Order Description - 6805 - CM | CM | 4 | 410520 | WSCHD | SYS-ISOL | 2016-08-19 | 2019-09-06 | 2019-06-24 | 2019-06-24 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 6873 | Work Order Description - 6873 - CM | CM | 4 | 172651 | WPLAN | TPS | 2016-07-09 | 2019-04-01 | 2019-05-25 | 2019-05-25 | 3 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 6951 | Work Order Description - 6951 - CM | CM | 3 | 322842 | WSCHD | TPS | 2018-06-08 | 2020-01-18 | 2020-05-03 | 2020-05-04 | 2 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 6955 | Work Order Description - 6955 - CM | CM | 4 | 368215 | WSCHD | NORM-OPS | 2015-11-11 | 2019-05-02 | 2019-06-01 | 2019-06-11 | 4 | MAINTENANCE | ELECTRICAL | 85
2019-03-31 | 6956 | Work Order Description - 6956 - CM | CM | 3 | 327715 | WSCHD | TPS | 2017-10-11 | 2019-02-11 | 2019-11-30 | 2019-12-02 | 4 | MAINTENANCE | CONSTRUCTION | 36
2019-03-31 | 6958 | Work Order Description - 6958 - CM | CM | 3 | 322846 | WPLAN | TPS | 2017-07-26 | 2019-10-28 | 2020-01-01 | 2020-01-02 | 3 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 6963 | Work Order Description - 6963 - CM | CM | 4 | 450548 | WPLAN | NORM-OPS | 2015-11-16 | 2019-05-31 | 2019-09-01 | 2019-09-02 | 4 | INTEGRITY | CONSTRUCTION | 28
2019-03-31 | 6966 | Work Order Description - 6966 - CM | CM | 3 | 50981 | WPLAN | TPS | 2017-07-26 | 2020-01-17 | 2020-05-02 | 2020-05-04 | 3 | MAINTENANCE | CONSTRUCTION | 29
2019-03-31 | 6968 | Work Order Description - 6968 - CM | CM | 3 | 489325 | WSCHD | TPS | 2018-06-15 | 2019-01-31 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 6978 | Work Order Description - 6978 - CM | CM | 4 | 320453 | WSCHD | NORM-OPS | 2015-12-04 | 2019-12-31 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 6980 | Work Order Description - 6980 - CM | CM | 4 | 553378 | WSCHD | NORM-OPS | 2017-06-26 | 2020-01-01 | 2019-12-28 | 2019-12-28 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 6981 | Work Order Description - 6981 - CM | CM | 4 | 652883 | WSCHD | NORM-OPS | 2015-11-05 | 2019-09-06 | 2019-12-28 | 2019-12-28 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 6982 | Work Order Description - 6982 - CM | CM | 4 | 354188 | WSCHD | NORM-OPS | 2017-06-26 | 2020-01-01 | 2019-12-28 | 2019-12-28 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 6983 | Work Order Description - 6983 - CM | CM | 4 | 260238 | WSCHD | NORM-OPS | 2015-11-14 | 2019-07-01 | 2019-12-28 | 2019-12-28 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 6985 | Work Order Description - 6985 - PM | PM | 3 | 409817 | WSCHD | EQUIP-ISOL | 2015-11-04 | 2020-01-11 | 2019-12-28 | 2019-12-29 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 7079 | Work Order Description - 7079 - CM | CM | 3 | 499518 | WSCHD | NORM-OPS | 2018-06-15 | 2019-03-03 | 2020-05-02 | 2020-05-02 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 7098 | Work Order Description - 7098 - PRJ | PRJ | 4 | 580382 | WSCHD | PACK-ISOL | 2017-09-15 | 2019-02-22 | 2019-05-25 | 2019-05-27 | 4 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 7115 | Work Order Description - 7115 - CM | CM | 4 | 469709 | SCHD | NORM-OPS | 2018-09-06 | 2019-10-17 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 7126 | Work Order Description - 7126 - CM | CM | 4 | 321697 | WSCHD | TPS | 2015-11-11 | 2019-09-06 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | CONSTRUCTION | 16
2019-03-31 | 7128 | Work Order Description - 7128 - CM | CM | 3 | 260490 | WSCHD | TPS | 2018-06-15 | 2019-01-29 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 7129 | Work Order Description - 7129 - CM | CM | 3 | 227235 | WSCHD | TPS | 2015-11-11 | 2019-05-01 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 7133 | Work Order Description - 7133 - CM | CM | 3 | 399771 | WSCHD | TPS | 2017-07-21 | 2019-11-26 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 7175 | Work Order Description - 7175 - CM | CM | 3 | 54304 | WSCHD | NORM-OPS | 2017-07-21 | 2019-12-21 | 2019-05-11 | 2019-05-12 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 7195 | Work Order Description - 7195 - PM | PM | 3 | 653616 | WSCHD | PACK-ISOL | 2015-11-16 | 2019-10-14 | 2019-05-25 | 2019-05-26 | 2 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 7224 | Work Order Description - 7224 - CM | CM | 4 | 327788 | WSCHD | TPS | 2015-11-25 | 2019-06-04 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | CONSTRUCTION | 16
2019-03-31 | 7228 | Work Order Description - 7228 - CM | CM | 4 | 495412 | WSCHD | TPS | 2015-11-25 | 2019-01-19 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 7232 | Work Order Description - 7232 - CM | CM | 4 | 185316 | SCHD | NORM-OPS | 2018-07-18 | 2019-08-26 | 2019-10-12 | 2019-10-12 | 4 | INTEGRITY | MECHANICAL | 30
2019-03-31 | 7259 | Work Order Description - 7259 - PM | PM | 2 | 408300 | WSCHD | EQUIP-ISOL | 2015-11-18 | 2019-04-11 | 2019-05-04 | 2019-05-04 | 2 | INTEGRITY | ELECTRICAL | 7
2019-03-31 | 7264 | Work Order Description - 7264 - CM | CM | 4 | 368215 | WSCHD | NORM-OPS | 2016-09-22 | 2019-01-26 | 2019-05-25 | 2019-06-01 | 4 | MAINTENANCE | ELECTRICAL | 49
2019-03-31 | 7265 | Work Order Description - 7265 - CM | CM | 4 | 358420 | WSCHD | NORM-OPS | 2016-09-22 | 2019-09-12 | 2019-05-25 | 2019-05-30 | 4 | MAINTENANCE | ELECTRICAL | 35
2019-03-31 | 7267 | Work Order Description - 7267 - CM | CM | 4 | 54178 | WSCHD | NORM-OPS | 2017-04-30 | 2020-01-03 | 2019-05-25 | 2019-05-30 | 4 | MAINTENANCE | ELECTRICAL | 35
2019-03-31 | 7289 | Work Order Description - 7289 - PM | PM | 4 | 399872 | WSCHD | EQUIP-ISOL | 2015-12-06 | 2019-08-13 | 2020-05-02 | 2020-05-03 | 1 | INTEGRITY | CONSTRUCTION | 30
2019-03-31 | 7323 | Work Order Description - 7323 - CM | CM | 4 | 496734 | WPLAN | NORM-OPS | 2017-05-30 | 2020-07-31 | 2019-06-01 | 2019-06-04 | 3 | INTEGRITY | CONSTRUCTION | 98
2019-03-31 | 7326 | Work Order Description - 7326 - PSCM | PSCM | 1 | 545892 | WSCHD | NORM-OPS | 2015-11-30 | 2019-11-23 | 2019-07-27 | 2019-07-28 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 7328 | Work Order Description - 7328 - PSCM | PSCM | 1 | 653275 | WSCHD | NORM-OPS | 2015-11-30 | 2019-11-23 | 2019-07-27 | 2019-07-31 | 4 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 7347 | Work Order Description - 7347 - CM | CM | 4 | 481808 | WSCHD | NORM-OPS | 2019-03-25 | 2018-12-18 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 7365 | Work Order Description - 7365 - PM | PM | 4 | 355393 | WSCHD | EQUIP-ISOL | 2015-12-20 | 2019-06-21 | 2019-07-27 | 2019-07-28 | 2 | INTEGRITY | MECHANICAL | 10
2019-03-31 | 7383 | Work Order Description - 7383 - PM | PM | 3 | 363635 | WSCHD | EQUIP-ISOL | 2015-12-11 | 2019-03-25 | 2020-05-02 | 2020-05-02 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 7470 | Work Order Description - 7470 - CM | CM | 4 | 403920 | SCHD | NORM-OPS | 2018-09-06 | 2019-05-15 | 2020-04-04 | 2020-04-04 | 3 | INTEGRITY | FABRIC | 335
2019-03-31 | 7477 | Work Order Description - 7477 - CM | CM | 4 | 546068 | WSCHD | NORM-OPS | 2017-07-11 | 2019-04-11 | 2019-06-01 | 2019-06-06 | 3 | MAINTENANCE | SERVICES | 89
2019-03-31 | 7478 | Work Order Description - 7478 - CM | CM | 4 | 652220 | WSCHD | NORM-OPS | 2017-07-11 | 2019-08-25 | 2019-04-27 | 2019-05-02 | 3 | MAINTENANCE | SERVICES | 89
2019-03-31 | 7491 | Work Order Description - 7491 - CM | CM | 3 | 540665 | WSCHD | NORM-OPS | 2015-12-08 | 2019-09-06 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | OPERATIONS | 1
2019-03-31 | 7578 | Work Order Description - 7578 - CM | CM | 3 | 308100 | WSCHD | NORM-OPS | 2015-12-13 | 2019-07-01 | 2019-07-06 | 2019-07-08 | 3 | MAINTENANCE | SERVICES | 21
2019-03-31 | 7595 | Work Order Description - 7595 - PRJ | PRJ | 4 | 497446 | WSCHD | NORM-OPS | 2017-07-21 | 2019-08-18 | 2019-07-28 | 2019-07-28 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 7602 | Work Order Description - 7602 - CM | CM | 4 | 479577 | SCHD | NORM-OPS | 2019-02-13 | 2019-08-14 | 2019-03-30 | 2019-03-30 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 7638 | Work Order Description - 7638 - CM | CM | 3 | 501919 | WSCHD | TPS | 2018-10-19 | 2019-12-09 | 2019-05-25 | 2019-05-26 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 7643 | Work Order Description - 7643 - CM | CM | 4 | 503933 | SCHD | NORM-OPS | 2018-09-06 | 2020-01-10 | 2019-06-29 | 2019-06-29 | 2 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 7648 | Work Order Description - 7648 - PRJ | PRJ | 4 | 547341 | WSCHD | NORM-OPS | 2017-07-21 | 2018-12-05 | 2021-06-30 | 2021-06-30 | 4 | OPERATIONS | OPERATIONS | 0.1
2019-03-31 | 7685 | Work Order Description - 7685 - CM | CM | 4 | 547803 | WSCHD | TPS | 2015-12-18 | 2019-05-20 | 2019-05-04 | 2019-05-06 | 3 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 7695 | Work Order Description - 7695 - CM | CM | 4 | 661010 | WSCHD | NORM-OPS | 2016-02-28 | 2019-12-03 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | DRILLING | 1
2019-03-31 | 7698 | Work Order Description - 7698 - CM | CM | 4 | 462436 | SCHD | NORM-OPS | 2018-06-21 | 2019-10-16 | 2019-05-18 | 2019-05-18 | 4 | MAINTENANCE | MECHANICAL | 52
2019-03-31 | 7700 | Work Order Description - 7700 - CM | CM | 4 | 419551 | WSCHD | NORM-OPS | 2015-12-18 | 2019-04-14 | 2019-04-20 | 2019-04-21 | 4 | DRILLING | DRILLING | 16
2019-03-31 | 7709 | Work Order Description - 7709 - CM | CM | 4 | 500455 | WSCHD | NORM-OPS | 2015-12-18 | 2019-04-14 | 2019-06-01 | 2019-06-05 | 4 | MAINTENANCE | ELECTRICAL | 28
2019-03-31 | 7729 | Work Order Description - 7729 - PM | PM | 3 | 256411 | SCHD | NORM-OPS | 2018-06-21 | 2019-05-05 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 7731 | Work Order Description - 7731 - CM | CM | 4 | 368215 | WSCHD | NORM-OPS | 2015-12-18 | 2018-12-08 | 2019-09-28 | 2019-10-01 | 4 | MAINTENANCE | ELECTRICAL | 21
2019-03-31 | 7745 | Work Order Description - 7745 - CM | CM | 4 | 66687 | WSCHD | SYS-ISOL | 2015-12-20 | 2019-10-26 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | DRILLING | 6
2019-03-31 | 7761 | Work Order Description - 7761 - CM | CM | 4 | 479226 | SCHD | NORM-OPS | 2018-07-06 | 2019-03-26 | 2020-01-04 | 2020-01-04 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 7762 | Work Order Description - 7762 - CM | CM | 4 | 465446 | SCHD | NORM-OPS | 2018-07-18 | 2019-07-11 | 2019-09-14 | 2019-09-14 | 3 | WELLS | MECHANICAL | 1
2019-03-31 | 7793 | Work Order Description - 7793 - PM | PM | 3 | 188463 | SCHD | SUBSYS-ISOL | 2018-09-06 | 2019-03-10 | 2020-01-04 | 2020-01-04 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 7804 | Work Order Description - 7804 - CM | CM | 2 | 107572 | SCHD | SYS-ISOL | 2019-03-29 | 2020-01-24 | 2019-08-10 | 2019-08-11 | 3 | MAINTENANCE | INSTRUMENTS | 110
2019-03-31 | 7813 | Work Order Description - 7813 - PRJ | PRJ | 4 | 294959 | WSCHD | NORM-OPS | 2017-07-21 | 2019-02-15 | 2019-12-28 | 2019-12-28 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 7844 | Work Order Description - 7844 - CM | CM | 3 | 404914 | WSCHD | NORM-OPS | 2016-01-01 | 2019-01-05 | 2019-08-31 | 2019-09-02 | 3 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 7850 | Work Order Description - 7850 - PRJ | PRJ | 4 | 575063 | WSCHD | NORM-OPS | 2017-07-21 | 2019-08-18 | 2021-06-30 | 2021-06-30 | 4 | ENGINEERING | CONSTRUCTION | 1
2019-03-31 | 7860 | Work Order Description - 7860 - CM | CM | 4 | 246887 | WSCHD | TPS | 2018-08-05 | 2019-09-06 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 7871 | Work Order Description - 7871 - CM | CM | 4 | 368215 | WSCHD | NORM-OPS | 2016-01-05 | 2019-11-12 | 2019-09-28 | 2019-10-04 | 4 | MAINTENANCE | ELECTRICAL | 42
2019-03-31 | 7893 | Work Order Description - 7893 - PSPM | PSPM | 1 | 361881 | WSCHD | SUBSYS-ISOL | 2016-01-26 | 2019-01-02 | 2020-03-07 | 2020-03-08 | 1 | MAINTENANCE | OPERATIONS | 12
2019-03-31 | 7895 | Work Order Description - 7895 - PSPM | PSPM | 1 | 361917 | WSCHD | SUBSYS-ISOL | 2018-08-05 | 2019-04-01 | 2020-05-02 | 2020-05-03 | 1 | MAINTENANCE | OPERATIONS | 12
2019-03-31 | 7896 | Work Order Description - 7896 - PSPM | PSPM | 1 | 520071 | WSCHD | SUBSYS-ISOL | 2018-08-05 | 2019-04-01 | 2020-05-02 | 2020-05-03 | 1 | MAINTENANCE | OPERATIONS | 12
2019-03-31 | 8021 | Work Order Description - 8021 - CM | CM | 4 | 403920 | SCHD | NORM-OPS | 2019-01-22 | 2020-01-08 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 8024 | Work Order Description - 8024 - CM | CM | 4 | 403920 | SCHD | NORM-OPS | 2019-01-22 | 2020-01-08 | 2020-02-29 | 2020-02-29 | 3 | INTEGRITY | FABRIC | 392
2019-03-31 | 8027 | Work Order Description - 8027 - CM | CM | 4 | 403920 | WPLAN | NORM-OPS | 2016-02-05 | 2019-10-01 | 2019-06-22 | 2019-06-22 | 4 | INTEGRITY | FABRIC | 316
2019-03-31 | 8034 | Work Order Description - 8034 - CM | CM | 4 | 403920 | SCHD | NORM-OPS | 2019-01-31 | 2020-01-08 | 2019-08-03 | 2019-08-03 | 3 | INTEGRITY | FABRIC | 120
2019-03-31 | 8053 | Work Order Description - 8053 - CM | CM | 4 | 403920 | SCHD | NORM-OPS | 2019-01-22 | 2020-01-08 | 2020-01-25 | 2020-01-25 | 3 | INTEGRITY | FABRIC | 196
2019-03-31 | 8088 | Work Order Description - 8088 - CM | CM | 1 | 479578 | SCHD | NORM-OPS | 2019-03-02 | 2020-02-28 | 2019-04-07 | 2019-04-07 | 3 | INTEGRITY | CONSTRUCTION | 72
2019-03-31 | 8089 | Work Order Description - 8089 - CM | CM | 3 | 226643 | WSCHD | TPS | 2018-06-20 | 2019-07-04 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 8090 | Work Order Description - 8090 - CM | CM | 4 | 479577 | SCHD | NORM-OPS | 2018-09-06 | 2019-01-18 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | MECHANICAL | 120
2019-03-31 | 8093 | Work Order Description - 8093 - CM | CM | 3 | 499750 | WSCHD | TPS | 2018-06-20 | 2019-05-04 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 8094 | Work Order Description - 8094 - CM | CM | 3 | 493399 | WSCHD | TPS | 2018-06-20 | 2019-11-23 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 8100 | Work Order Description - 8100 - PRJ | PRJ | 3 | 653434 | WSCHD | TPS | 2018-09-26 | 2019-07-23 | 2020-05-02 | 2020-05-04 | 3 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 8124 | Work Order Description - 8124 - CM | CM | 3 | 273658 | WSCHD | TPS | 2018-06-27 | 2019-11-02 | 2020-03-23 | 2020-03-29 | 3 | INTEGRITY | MECHANICAL | 122
2019-03-31 | 8125 | Work Order Description - 8125 - CM | CM | 3 | 273658 | WSCHD | TPS | 2018-05-14 | 2019-02-04 | 2020-05-02 | 2020-05-04 | 3 | INTEGRITY | MECHANICAL | 6
2019-03-31 | 8151 | Work Order Description - 8151 - CM | CM | 3 | 56478 | WSCHD | NORM-OPS | 2016-01-12 | 2018-12-18 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 8246 | Work Order Description - 8246 - CM | CM | 2 | 480203 | WSCHD | NORM-OPS | 2016-01-21 | 2019-01-16 | 2019-05-25 | 2019-05-27 | 3 | MAINTENANCE | ELECTRICAL | 16
2019-03-31 | 8252 | Work Order Description - 8252 - PSPM | PSPM | 1 | 681802 | WSCHD | NORM-OPS | 2016-01-18 | 2020-01-01 | 2019-07-27 | 2019-07-28 | 1 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 8290 | Work Order Description - 8290 - CM | CM | 3 | 399803 | WSCHD | NORM-OPS | 2017-07-21 | 2019-01-18 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 8298 | Work Order Description - 8298 - CM | CM | 3 | 305225 | WSCHD | NORM-OPS | 2016-02-13 | 2019-01-03 | 2019-06-01 | 2019-06-04 | 3 | MAINTENANCE | INSTRUMENTS | 55
2019-03-31 | 8407 | Work Order Description - 8407 - CM | CM | 1 | 17814 | WPLAN | TPS | 2016-08-14 | 2020-09-01 | 2020-04-04 | 2020-04-04 | 4 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 8422 | Work Order Description - 8422 - CM | CM | 4 | 368329 | WPLAN | NORM-OPS | 2016-06-26 | 2020-09-01 | 2019-07-27 | 2019-08-01 | 4 | INTEGRITY | CONSTRUCTION | 84
2019-03-31 | 8431 | Work Order Description - 8431 - CM | CM | 3 | 377005 | SCHD | SYS-ISOL | 2018-06-21 | 2019-06-18 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 8614 | Work Order Description - 8614 - CM | CM | 3 | 249448 | WSCHD | NORM-OPS | 2016-02-13 | 2019-10-08 | 2019-10-05 | 2019-10-06 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 8615 | Work Order Description - 8615 - CM | CM | 4 | 545266 | WSCHD | TPS | 2016-02-11 | 2019-10-08 | 2020-05-02 | 2020-05-06 | 4 | MAINTENANCE | MECHANICAL | 63
2019-03-31 | 8616 | Work Order Description - 8616 - BR | BR | 3 | 531852 | WSCHD | NORM-OPS | 2017-07-05 | 2019-10-17 | 2019-09-07 | 2019-09-09 | 3 | INTEGRITY | MECHANICAL | 10
2019-03-31 | 8617 | Work Order Description - 8617 - CM | CM | 3 | 490011 | WSCHD | TPS | 2018-06-08 | 2019-10-12 | 2020-05-03 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 8618 | Work Order Description - 8618 - CM | CM | 3 | 34123 | WPLAN | TPS | 2017-07-26 | 2019-10-14 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 8619 | Work Order Description - 8619 - CM | CM | 3 | 545732 | WSCHD | PACK-ISOL | 2017-07-06 | 2019-10-01 | 2019-11-30 | 2019-12-05 | 2 | MAINTENANCE | MECHANICAL | 77
2019-03-31 | 8721 | Work Order Description - 8721 - CM | CM | 3 | 247109 | WSCHD | TPS | 2016-02-05 | 2019-04-28 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 8731 | Work Order Description - 8731 - CM | CM | 3 | 51688 | WSCHD | NORM-OPS | 2016-05-11 | 2019-10-08 | 2019-09-28 | 2019-09-28 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 8732 | Work Order Description - 8732 - PM | PM | 3 | 552989 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-07-25 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 8737 | Work Order Description - 8737 - CM | CM | 3 | 227428 | WPLAN | SYS-ISOL | 2017-07-26 | 2019-10-08 | 2020-05-03 | 2020-05-04 | 4 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 8740 | Work Order Description - 8740 - CM | CM | 3 | 499565 | WSCHD | TPS | 2018-06-21 | 2019-01-27 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 8741 | Work Order Description - 8741 - CM | CM | 3 | 499566 | WSCHD | TPS | 2018-06-21 | 2020-01-01 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 8743 | Work Order Description - 8743 - CM | CM | 3 | 313086 | SCHD | SYS-ISOL | 2018-09-06 | 2019-02-11 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 106
2019-03-31 | 8747 | Work Order Description - 8747 - PM | PM | 2 | 595904 | WSCHD | EQUIP-ISOL | 2016-02-27 | 2019-03-16 | 2019-04-27 | 2019-05-01 | 2 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 8759 | Work Order Description - 8759 - CM | CM | 4 | 51688 | WSCHD | NORM-OPS | 2016-02-18 | 2019-10-08 | 2019-05-25 | 2019-05-27 | 4 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 8766 | Work Order Description - 8766 - CM | CM | 3 | 499458 | WSCHD | NORM-OPS | 2016-02-11 | 2019-10-08 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 8809 | Work Order Description - 8809 - CM | CM | 3 | 545266 | WSCHD | NORM-OPS | 2017-07-07 | 2019-10-10 | 2019-05-25 | 2019-05-27 | 3 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 8822 | Work Order Description - 8822 - PSCM | PSCM | 1 | 479578 | SCHD | NORM-OPS | 2018-10-09 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 4 | INTEGRITY | FABRIC | 203
2019-03-31 | 8856 | Work Order Description - 8856 - CM | CM | 3 | 308202 | WSCHD | TPS | 2018-01-31 | 2019-07-04 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 8871 | Work Order Description - 8871 - CM | CM | 4 | 318334 | WSCHD | NORM-OPS | 2016-02-21 | 2019-01-09 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 8872 | Work Order Description - 8872 - CM | CM | 3 | 652244 | WSCHD | NORM-OPS | 2017-06-23 | 2019-07-01 | 2019-06-24 | 2019-06-25 | 3 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 8873 | Work Order Description - 8873 - CM | CM | 4 | 51662 | WSCHD | PACK-ISOL | 2017-06-23 | 2019-07-01 | 2019-08-31 | 2019-08-31 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 8878 | Work Order Description - 8878 - CM | CM | 4 | 477030 | WSCHD | SYS-ISOL | 2018-06-08 | 2020-01-07 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | CONSTRUCTION | 3.2667
2019-03-31 | 8879 | Work Order Description - 8879 - CM | CM | 4 | 490436 | WSCHD | NORM-OPS | 2017-06-23 | 2019-08-16 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | SERVICES | 6
2019-03-31 | 8936 | Work Order Description - 8936 - BR | BR | 3 | 19008 | WSCHD | SUBSYS-ISOL | 2016-03-03 | 2019-12-29 | 2019-09-07 | 2019-09-11 | 2 | INTEGRITY | MECHANICAL | 50
2019-03-31 | 8945 | Work Order Description - 8945 - CM | CM | 4 | 237407 | WPLAN | NORM-OPS | 2016-03-27 | 2019-01-07 | 2019-05-01 | 2019-05-05 | 3 | INTEGRITY | CONSTRUCTION | 126
2019-03-31 | 8946 | Work Order Description - 8946 - PSPM | PSPM | 1 | 248424 | WSCHD | EQUIP-ISOL | 2016-02-16 | 2019-07-01 | 2020-12-26 | 2020-12-26 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 8965 | Work Order Description - 8965 - CM | CM | 4 | 481745 | SCHD | NORM-OPS | 2018-10-09 | 2019-07-01 | 2019-06-15 | 2019-06-15 | 3 | INTEGRITY | FABRIC | 112
2019-03-31 | 9014 | Work Order Description - 9014 - CM | CM | 3 | 58397 | WSCHD | NORM-OPS | 2017-08-10 | 2019-10-08 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 9024 | Work Order Description - 9024 - CM | CM | 3 | 327540 | WSCHD | SUBSYS-ISOL | 2016-02-25 | 2019-02-24 | 2019-09-07 | 2019-09-08 | 3 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 9080 | Work Order Description - 9080 - CM | CM | 3 | 314873 | WSCHD | TPS | 2018-11-13 | 2019-11-13 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 9085 | Work Order Description - 9085 - CM | CM | 4 | 228839 | SCHD | NORM-OPS | 2018-08-25 | 2019-11-28 | 2019-06-01 | 2019-06-08 | 3 | INTEGRITY | CONSTRUCTION | 86
2019-03-31 | 9114 | Work Order Description - 9114 - CM | CM | 3 | 29092 | SCHD | TPS | 2018-07-18 | 2019-10-14 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 9
2019-03-31 | 9115 | Work Order Description - 9115 - CM | CM | 1 | 661010 | WPLAN | NORM-OPS | 2016-08-14 | 2019-03-24 | 2019-04-27 | 2019-05-28 | 2 | DRILLING | DRILLING | 441
2019-03-31 | 9127 | Work Order Description - 9127 - PSCM | PSCM | 1 | 56319 | WSCHD | SYS-ISOL | 2018-06-08 | 2019-11-01 | 2020-05-03 | 2020-05-05 | 3 | INTEGRITY | MECHANICAL | 1
2019-03-31 | 9172 | Work Order Description - 9172 - PM | PM | 2 | 595906 | WSCHD | EQUIP-ISOL | 2016-02-27 | 2019-05-15 | 2019-07-06 | 2019-07-10 | 2 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 9179 | Work Order Description - 9179 - CM | CM | 4 | 447441 | SCHD | NORM-OPS | 2018-07-06 | 2019-11-24 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | MECHANICAL | 29
2019-03-31 | 9183 | Work Order Description - 9183 - CM | CM | 4 | 29041 | SCHD | NORM-OPS | 2018-06-21 | 2019-01-11 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 9236 | Work Order Description - 9236 - CM | CM | 3 | 666130 | WSCHD | NORM-OPS | 2016-03-08 | 2019-11-01 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | INSTRUMENTS | 22
2019-03-31 | 9253 | Work Order Description - 9253 - CM | CM | 4 | 315837 | SCHD | NORM-OPS | 2018-09-06 | 2019-07-28 | 2020-05-02 | 2020-05-02 | 3 | INTEGRITY | CONSTRUCTION | 9
2019-03-31 | 9255 | Work Order Description - 9255 - CM | CM | 4 | 315837 | SCHD | NORM-OPS | 2019-02-13 | 2021-02-10 | 2019-08-17 | 2019-08-17 | 4 | INTEGRITY | FABRIC | 72
2019-03-31 | 9376 | Work Order Description - 9376 - CM | CM | 4 | 314949 | WSCHD | NORM-OPS | 2016-03-17 | 2018-12-22 | 2019-04-20 | 2019-04-24 | 3 | MAINTENANCE | DRILLING | 32
2019-03-31 | 9387 | Work Order Description - 9387 - CM | CM | 4 | 303827 | SCHD | SYS-ISOL | 2018-09-06 | 2020-01-09 | 2019-05-04 | 2019-05-04 | 4 | INTEGRITY | MECHANICAL | 31
2019-03-31 | 9419 | Work Order Description - 9419 - CM | CM | 3 | 138449 | WPLAN | SYS-ISOL | 2018-05-13 | 2019-10-15 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | INSTRUMENTS | 31
2019-03-31 | 9452 | Work Order Description - 9452 - CM | CM | 3 | 308494 | WSCHD | SUBSYS-ISOL | 2016-03-14 | 2019-12-31 | 2019-04-06 | 2019-04-11 | 4 | MAINTENANCE | MECHANICAL | 52
2019-03-31 | 9456 | Work Order Description - 9456 - CM | CM | 2 | 127783 | SCHD | SYS-ISOL | 2018-06-21 | 2019-01-12 | 2019-07-13 | 2019-07-17 | 4 | INTEGRITY | CONSTRUCTION | 53
2019-03-31 | 9459 | Work Order Description - 9459 - CM | CM | 3 | 308494 | WSCHD | SUBSYS-ISOL | 2017-07-05 | 2019-02-02 | 2019-04-06 | 2019-04-09 | 4 | MAINTENANCE | MECHANICAL | 35
2019-03-31 | 9510 | Work Order Description - 9510 - CM | CM | 3 | 18981 | WSCHD | NORM-OPS | 2019-03-22 | 2019-01-24 | 2019-05-25 | 2019-05-25 | 2 | INTEGRITY | CONSTRUCTION | 156
2019-03-31 | 9511 | Work Order Description - 9511 - PM | PM | 4 | 55936 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-20 | 2019-04-20 | 2 | INTEGRITY | INSPECTION | 272
2019-03-31 | 9516 | Work Order Description - 9516 - CM | CM | 1 | 17814 | WPLAN | TPS | 2018-01-24 | 2020-03-15 | 2020-05-02 | 2020-05-02 | 4 | INTEGRITY | CONSTRUCTION | 4
2019-03-31 | 9518 | Work Order Description - 9518 - CM | CM | 2 | 321199 | WSCHD | NORM-OPS | 2016-03-25 | 2019-07-01 | 2020-03-07 | 2020-03-08 | 4 | MAINTENANCE | INSTRUMENTS | 19
2019-03-31 | 9521 | Work Order Description - 9521 - CM | CM | 3 | 254953 | SCHD | TPS | 2018-09-06 | 2019-09-14 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 9582 | Work Order Description - 9582 - CM | CM | 4 | 545222 | WSCHD | NORM-OPS | 2017-07-21 | 2019-06-23 | 2019-07-20 | 2019-07-20 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 9584 | Work Order Description - 9584 - CM | CM | 3 | 321921 | WSCHD | NORM-OPS | 2017-07-21 | 2019-07-01 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 9649 | Work Order Description - 9649 - CM | CM | 3 | 189241 | SCHD | NORM-OPS | 2018-07-06 | 2019-09-25 | 2019-06-08 | 2019-06-08 | 3 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 9650 | Work Order Description - 9650 - CM | CM | 3 | 189240 | SCHD | NORM-OPS | 2018-06-21 | 2019-07-09 | 2019-06-15 | 2019-06-15 | 3 | MAINTENANCE | MECHANICAL | 41
2019-03-31 | 9674 | Work Order Description - 9674 - PSPM | PSPM | 1 | 361182 | WSCHD | EQUIP-ISOL | 2016-03-25 | 2020-03-30 | 2020-05-02 | 2020-05-02 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 9692 | Work Order Description - 9692 - CM | CM | 2 | 480203 | WSCHD | NORM-OPS | 2017-10-16 | 2019-04-23 | 2019-04-18 | 2019-04-19 | 2 | MAINTENANCE | MECHANICAL | 13
2019-03-31 | 9694 | Work Order Description - 9694 - CM | CM | 3 | 375585 | SCHD | SUBSYS-ISOL | 2019-01-07 | 2019-10-24 | 2019-07-13 | 2019-07-15 | 3 | INTEGRITY | CONSTRUCTION | 112
2019-03-31 | 9696 | Work Order Description - 9696 - CM | CM | 4 | 70841 | WPLAN | SYS-ISOL | 2018-01-24 | 2020-03-26 | 2019-12-01 | 2019-12-10 | 4 | INTEGRITY | CONSTRUCTION | 84
2019-03-31 | 9697 | Work Order Description - 9697 - CM | CM | 4 | 128231 | SCHD | NORM-OPS | 2018-09-06 | 2020-01-11 | 2019-08-03 | 2019-08-03 | 2 | MAINTENANCE | INSTRUMENTS | 40
2019-03-31 | 9701 | Work Order Description - 9701 - CM | CM | 3 | 249422 | WSCHD | NORM-OPS | 2016-04-03 | 2019-09-06 | 2019-11-30 | 2019-12-01 | 4 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 9704 | Work Order Description - 9704 - PSPM | PSPM | 1 | 361917 | WSCHD | NORM-OPS | 2017-01-26 | 2019-07-17 | 2020-05-02 | 2020-05-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 9705 | Work Order Description - 9705 - PSPM | PSPM | 1 | 520071 | WSCHD | NORM-OPS | 2016-07-24 | 2019-05-06 | 2020-04-11 | 2020-04-11 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 9723 | Work Order Description - 9723 - BR | BR | 4 | 404984 | WSCHD | NORM-OPS | 2017-07-21 | 2019-12-14 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 9724 | Work Order Description - 9724 - CM | CM | 4 | 58398 | WSCHD | NORM-OPS | 2017-07-21 | 2019-09-30 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 9734 | Work Order Description - 9734 - CM | CM | 4 | 659557 | WPLAN | TPS | 2018-12-17 | 2019-07-08 | 2019-07-13 | 2019-07-14 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 9754 | Work Order Description - 9754 - CM | CM | 3 | 496734 | WPLAN | PACK-ISOL | 2018-01-17 | 2019-04-01 | 2019-11-02 | 2019-11-02 | 3 | INTEGRITY | CONSTRUCTION | 19
2019-03-31 | 9759 | Work Order Description - 9759 - CM | CM | 4 | 460160 | SCHD | NORM-OPS | 2018-09-06 | 2019-10-26 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 45
2019-03-31 | 9769 | Work Order Description - 9769 - CM | CM | 3 | 74956 | SCHD | NORM-OPS | 2018-12-27 | 2019-11-08 | 2019-09-06 | 2019-09-12 | 4 | INTEGRITY | CONSTRUCTION | 98
2019-03-31 | 9786 | Work Order Description - 9786 - CM | CM | 3 | 19008 | WSCHD | TPS | 2018-12-19 | 2019-02-21 | 2019-06-01 | 2019-06-06 | 4 | INTEGRITY | CONSTRUCTION | 4
2019-03-31 | 9794 | Work Order Description - 9794 - CM | CM | 3 | 409743 | WSCHD | SUBSYS-ISOL | 2017-07-07 | 2019-06-12 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 9796 | Work Order Description - 9796 - CM | CM | 3 | 460960 | SCHD | NORM-OPS | 2018-09-06 | 2019-04-22 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 9805 | Work Order Description - 9805 - PSPM | PSPM | 1 | 362499 | WSCHD | SUBSYS-ISOL | 2016-04-04 | 2020-01-01 | 2021-06-19 | 2021-06-19 | 1 | INTEGRITY | INSTRUMENTS | 5
2019-03-31 | 9806 | Work Order Description - 9806 - PSPM | PSPM | 1 | 363611 | WSCHD | SUBSYS-ISOL | 2016-04-04 | 2019-07-01 | 2021-06-19 | 2021-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 9808 | Work Order Description - 9808 - PSPM | PSPM | 1 | 50795 | WSCHD | SUBSYS-ISOL | 2016-04-04 | 2020-01-01 | 2021-06-19 | 2021-06-19 | 1 | INTEGRITY | INSTRUMENTS | 2
2019-03-31 | 9809 | Work Order Description - 9809 - PSPM | PSPM | 1 | 19024 | WSCHD | SUBSYS-ISOL | 2016-04-04 | 2020-01-01 | 2021-06-19 | 2021-06-20 | 1 | INTEGRITY | INSTRUMENTS | 3
2019-03-31 | 9810 | Work Order Description - 9810 - PSPM | PSPM | 1 | 363528 | WSCHD | SUBSYS-ISOL | 2016-04-04 | 2019-07-01 | 2021-06-19 | 2021-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 9906 | Work Order Description - 9906 - PSPM | PSPM | 1 | 361921 | WSCHD | SUBSYS-ISOL | 2016-07-24 | 2024-01-01 | 2021-06-19 | 2021-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 9935 | Work Order Description - 9935 - CM | CM | 4 | 670468 | WPLAN | NORM-OPS | 2017-12-21 | 2019-11-03 | 2020-07-28 | 2020-07-29 | 4 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 9966 | Work Order Description - 9966 - CM | CM | 4 | 661010 | WSCHD | NORM-OPS | 2016-04-13 | 2018-12-08 | 2019-04-27 | 2019-04-29 | 3 | DRILLING | DRILLING | 26
2019-03-31 | 9967 | Work Order Description - 9967 - CM | CM | 4 | 661010 | WSCHD | NORM-OPS | 2016-04-13 | 2019-05-15 | 2019-04-27 | 2019-04-29 | 3 | DRILLING | DRILLING | 26
2019-03-31 | 10023 | Work Order Description - 10023 - CM | CM | 3 | 500964 | WSCHD | TPS | 2018-06-08 | 2019-04-07 | 2020-05-03 | 2020-05-05 | 3 | MAINTENANCE | MECHANICAL | 80
2019-03-31 | 10024 | Work Order Description - 10024 - CM | CM | 3 | 33921 | WSCHD | TPS | 2018-06-21 | 2019-01-21 | 2020-05-02 | 2020-05-04 | 3 | MAINTENANCE | MECHANICAL | 80
2019-03-31 | 10025 | Work Order Description - 10025 - CM | CM | 3 | 33922 | WSCHD | TPS | 2018-06-08 | 2019-02-28 | 2020-05-03 | 2020-05-05 | 3 | MAINTENANCE | MECHANICAL | 80
2019-03-31 | 10026 | Work Order Description - 10026 - CM | CM | 3 | 322543 | WSCHD | TPS | 2018-06-08 | 2019-03-28 | 2020-05-03 | 2020-05-05 | 3 | MAINTENANCE | MECHANICAL | 80
2019-03-31 | 10027 | Work Order Description - 10027 - CM | CM | 3 | 322500 | WSCHD | TPS | 2018-06-08 | 2019-01-15 | 2020-05-03 | 2020-05-08 | 3 | MAINTENANCE | MECHANICAL | 96
2019-03-31 | 10042 | Work Order Description - 10042 - CM | CM | 3 | 357058 | WSCHD | NORM-OPS | 2016-04-13 | 2020-01-10 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 10047 | Work Order Description - 10047 - PSCM | PSCM | 1 | 536566 | WSCHD | SYS-ISOL | 2018-06-08 | 2019-07-01 | 2019-04-27 | 2019-04-30 | 2 | MAINTENANCE | CONSTRUCTION | 39
2019-03-31 | 10083 | Work Order Description - 10083 - CM | CM | 4 | 496734 | WPLAN | NORM-OPS | 2017-05-23 | 2020-04-10 | 2019-06-01 | 2019-06-04 | 4 | INTEGRITY | CONSTRUCTION | 49
2019-03-31 | 10084 | Work Order Description - 10084 - CM | CM | 3 | 308098 | WSCHD | NORM-OPS | 2017-11-20 | 2019-04-13 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 10207 | Work Order Description - 10207 - CM | CM | 4 | 520179 | WSCHD | NORM-OPS | 2016-04-20 | 2019-10-08 | 2019-10-26 | 2019-10-27 | 4 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 10267 | Work Order Description - 10267 - CM | CM | 4 | 105279 | WPLAN | SYS-ISOL | 2018-11-06 | 2020-01-01 | 2019-07-13 | 2019-07-14 | 3 | MAINTENANCE | FABRIC | 10
2019-03-31 | 10330 | Work Order Description - 10330 - CM | CM | 4 | 55322 | SCHD | NORM-OPS | 2018-09-06 | 2019-03-09 | 2019-06-15 | 2019-06-15 | 3 | MAINTENANCE | INSTRUMENTS | 32
2019-03-31 | 10345 | Work Order Description - 10345 - PM | PM | 3 | 387964 | SCHD | EQUIP-ISOL | 2018-06-01 | 2019-03-17 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 10346 | Work Order Description - 10346 - PM | PM | 3 | 668430 | SCHD | EQUIP-ISOL | 2018-06-01 | 2019-10-19 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 10348 | Work Order Description - 10348 - CM | CM | 4 | 472772 | SCHD | NORM-OPS | 2018-09-06 | 2019-08-27 | 2019-09-14 | 2019-09-14 | 2 | MAINTENANCE | MECHANICAL | 56
2019-03-31 | 10370 | Work Order Description - 10370 - CM | CM | 4 | 249340 | WSCHD | NORM-OPS | 2017-07-21 | 2019-10-25 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 10371 | Work Order Description - 10371 - CM | CM | 4 | 652373 | WSCHD | NORM-OPS | 2016-04-30 | 2019-01-05 | 2019-07-27 | 2019-07-27 | 4 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 10374 | Work Order Description - 10374 - CM | CM | 3 | 462622 | SCHD | TPS | 2018-09-06 | 2019-04-14 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 10375 | Work Order Description - 10375 - CM | CM | 3 | 462625 | SCHD | TPS | 2018-07-18 | 2019-07-19 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 10376 | Work Order Description - 10376 - CM | CM | 3 | 29086 | SCHD | TPS | 2018-09-06 | 2019-11-27 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 10380 | Work Order Description - 10380 - PM | PM | 3 | 53601 | WSCHD | PACK-ISOL | 2016-04-28 | 2019-02-27 | 2020-12-26 | 2020-12-26 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 10402 | Work Order Description - 10402 - CM | CM | 4 | 575063 | WSCHD | NORM-OPS | 2016-04-30 | 2019-02-12 | 2020-09-19 | 2020-09-19 | 4 | INTEGRITY | SERVICES | 1
2019-03-31 | 10414 | Work Order Description - 10414 - CM | CM | 4 | 575063 | WSCHD | NORM-OPS | 2016-04-30 | 2019-09-05 | 2019-08-17 | 2019-08-17 | 4 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 10415 | Work Order Description - 10415 - CM | CM | 4 | 575063 | WSCHD | NORM-OPS | 2016-04-29 | 2019-11-18 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 10418 | Work Order Description - 10418 - CM | CM | 2 | 267673 | WPLAN | NORM-OPS | 2017-02-07 | 2019-04-29 | 2019-04-27 | 2019-04-29 | 4 | INTEGRITY | CONSTRUCTION | 40
2019-03-31 | 10436 | Work Order Description - 10436 - CM | CM | 4 | 463641 | SCHD | TPS | 2018-09-06 | 2019-05-26 | 2019-09-28 | 2019-09-28 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 10826 | Work Order Description - 10826 - CM | CM | 3 | 308893 | WSCHD | TPS | 2018-06-08 | 2019-01-25 | 2020-05-03 | 2020-05-06 | 2 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 10829 | Work Order Description - 10829 - CM | CM | 4 | 500476 | SCHD | NORM-OPS | 2019-03-31 | 2019-07-06 | 2019-04-20 | 2019-04-21 | 3 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 10850 | Work Order Description - 10850 - CM | CM | 4 | 217608 | SCHD | NORM-OPS | 2018-06-21 | 2019-09-10 | 2019-09-01 | 2019-09-01 | 4 | MAINTENANCE | CONSTRUCTION | 3
2019-03-31 | 10898 | Work Order Description - 10898 - CM | CM | 4 | 352926 | WSCHD | NORM-OPS | 2017-07-21 | 2019-10-01 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 10918 | Work Order Description - 10918 - CM | CM | 4 | 541966 | SCHD | TPS | 2018-09-06 | 2019-10-07 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 10923 | Work Order Description - 10923 - CM | CM | 3 | 188007 | WSCHD | NORM-OPS | 2019-01-28 | 2020-01-15 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | MECHANICAL | 149
2019-03-31 | 10935 | Work Order Description - 10935 - CM | CM | 3 | 395510 | SCHD | NORM-OPS | 2019-02-13 | 2018-12-08 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 10949 | Work Order Description - 10949 - CM | CM | 3 | 214994 | WSCHD | NORM-OPS | 2017-07-07 | 2019-10-19 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 10950 | Work Order Description - 10950 - CM | CM | 3 | 214992 | WSCHD | NORM-OPS | 2017-07-07 | 2019-04-12 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 10958 | Work Order Description - 10958 - CM | CM | 3 | 51481 | WSCHD | NORM-OPS | 2016-08-05 | 2020-04-01 | 2019-04-27 | 2019-05-01 | 3 | MAINTENANCE | MECHANICAL | 41
2019-03-31 | 10959 | Work Order Description - 10959 - CM | CM | 3 | 321682 | WSCHD | PACK-ISOL | 2018-06-08 | 2019-05-08 | 2020-05-03 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 10971 | Work Order Description - 10971 - CM | CM | 2 | 267676 | WSCHD | NORM-OPS | 2017-07-21 | 2019-05-29 | 2019-05-25 | 2019-05-26 | 4 | MAINTENANCE | SAFETY | 7
2019-03-31 | 10972 | Work Order Description - 10972 - CM | CM | 3 | 325754 | WSCHD | NORM-OPS | 2017-07-06 | 2019-10-28 | 2019-06-15 | 2019-06-18 | 2 | MAINTENANCE | MECHANICAL | 41
2019-03-31 | 10982 | Work Order Description - 10982 - PRJ | PRJ | 4 | 596073 | WSCHD | NORM-OPS | 2017-07-21 | 2019-05-14 | 2019-06-15 | 2019-06-15 | 4 | OPERATIONS | MEDIC | 1
2019-03-31 | 10985 | Work Order Description - 10985 - CM | CM | 3 | 514303 | SCHD | TPS | 2018-09-06 | 2019-07-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 11028 | Work Order Description - 11028 - PSPM | PSPM | 1 | 309627 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-07-01 | 2019-05-04 | 2019-05-04 | 1 | INTEGRITY | MECHANICAL | 26
2019-03-31 | 11038 | Work Order Description - 11038 - CM | CM | 4 | 451342 | SCHD | NORM-OPS | 2019-03-09 | 2019-09-06 | 2019-03-09 | 2019-03-18 | 3 | INTEGRITY | FABRIC | 185
2019-03-31 | 11134 | Work Order Description - 11134 - PRJ | PRJ | 3 | 399771 | WSCHD | NORM-OPS | 2016-07-08 | 2019-05-03 | 2019-04-20 | 2019-04-22 | 4 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 11147 | Work Order Description - 11147 - CM | CM | 3 | 248905 | WSCHD | SUBSYS-ISOL | 2017-07-06 | 2020-01-08 | 2019-04-27 | 2019-05-01 | 3 | MAINTENANCE | MECHANICAL | 45
2019-03-31 | 11148 | Work Order Description - 11148 - CM | CM | 4 | 126954 | SCHD | NORM-OPS | 2018-06-21 | 2019-06-18 | 2020-07-28 | 2020-07-29 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 11149 | Work Order Description - 11149 - CM | CM | 4 | 126954 | SCHD | NORM-OPS | 2018-06-21 | 2019-09-18 | 2020-07-28 | 2020-07-29 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 11164 | Work Order Description - 11164 - CM | CM | 3 | 495472 | WSCHD | TPS | 2016-05-23 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 11165 | Work Order Description - 11165 - CM | CM | 3 | 495475 | WSCHD | TPS | 2016-05-23 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 11166 | Work Order Description - 11166 - CM | CM | 3 | 247793 | WSCHD | TPS | 2016-05-23 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 11167 | Work Order Description - 11167 - CM | CM | 3 | 214983 | WSCHD | TPS | 2016-05-23 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 11168 | Work Order Description - 11168 - CM | CM | 3 | 327567 | WSCHD | NORM-OPS | 2017-07-05 | 2019-05-29 | 2019-09-07 | 2019-09-08 | 3 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 11169 | Work Order Description - 11169 - CM | CM | 3 | 327566 | WSCHD | NORM-OPS | 2017-07-05 | 2019-06-08 | 2019-09-07 | 2019-09-08 | 3 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 11170 | Work Order Description - 11170 - CM | CM | 3 | 327564 | WSCHD | NORM-OPS | 2017-07-05 | 2019-06-22 | 2019-09-07 | 2019-09-08 | 3 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 11171 | Work Order Description - 11171 - CM | CM | 3 | 322753 | WSCHD | NORM-OPS | 2017-07-05 | 2019-12-05 | 2019-09-07 | 2019-09-08 | 3 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 11172 | Work Order Description - 11172 - CM | CM | 4 | 519836 | WSCHD | SUBSYS-ISOL | 2016-06-20 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 11173 | Work Order Description - 11173 - CM | CM | 3 | 520198 | WSCHD | SUBSYS-ISOL | 2016-05-24 | 2019-09-06 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 11179 | Work Order Description - 11179 - CM | CM | 4 | 128338 | SCHD | NORM-OPS | 2018-10-09 | 2019-07-01 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | FABRIC | 98
2019-03-31 | 11224 | Work Order Description - 11224 - PRJ | PRJ | 3 | 368329 | WSCHD | NORM-OPS | 2019-02-20 | 2019-09-08 | 2019-06-22 | 2019-06-22 | 4 | OPERATIONS | OPERATIONS | 0.016667
2019-03-31 | 11234 | Work Order Description - 11234 - CM | CM | 3 | 215391 | WSCHD | TPS | 2016-06-03 | 2019-04-21 | 2020-05-02 | 2020-05-05 | 3 | MAINTENANCE | CONSTRUCTION | 37
2019-03-31 | 11276 | Work Order Description - 11276 - BR | BR | 3 | 494164 | WSCHD | SUBSYS-ISOL | 2017-07-05 | 2019-03-18 | 2019-09-07 | 2019-09-08 | 3 | MAINTENANCE | CONSTRUCTION | 14
2019-03-31 | 11351 | Work Order Description - 11351 - CM | CM | 3 | 25407 | SCHD | NORM-OPS | 2018-09-06 | 2019-08-27 | 2019-08-17 | 2019-08-17 | 4 | INTEGRITY | FABRIC | 594
2019-03-31 | 11397 | Work Order Description - 11397 - CM | CM | 3 | 25390 | SCHD | NORM-OPS | 2019-03-15 | 2020-02-26 | 2020-02-15 | 2020-02-15 | 3 | INTEGRITY | FABRIC | 10
2019-03-31 | 11408 | Work Order Description - 11408 - CM | CM | 4 | 501446 | SCHD | NORM-OPS | 2018-10-04 | 2019-07-01 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | FABRIC | 333
2019-03-31 | 11409 | Work Order Description - 11409 - CM | CM | 4 | 501446 | SCHD | NORM-OPS | 2018-10-04 | 2019-07-01 | 2019-04-27 | 2019-04-27 | 4 | INTEGRITY | FABRIC | 254
2019-03-31 | 11415 | Work Order Description - 11415 - PM | PM | 3 | 249449 | WSCHD | EQUIP-ISOL | 2016-06-03 | 2019-03-01 | 2019-09-07 | 2019-09-13 | 2 | MAINTENANCE | MECHANICAL | 90
2019-03-31 | 11542 | Work Order Description - 11542 - PM | PM | 3 | 74996 | SCHD | PACK-ISOL | 2018-06-01 | 2019-05-14 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 11558 | Work Order Description - 11558 - PM | PM | 2 | 531916 | WSCHD | NORM-OPS | 2018-10-12 | 2019-01-22 | 2019-05-11 | 2019-05-11 | 1 | INTEGRITY | SUBSEA | 0
2019-03-31 | 11568 | Work Order Description - 11568 - PSCM | PSCM | 1 | 33921 | WSCHD | TPS | 2018-06-21 | 2020-08-01 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 11575 | Work Order Description - 11575 - CM | CM | 4 | 273658 | SCHD | NORM-OPS | 2019-03-13 | 2019-06-07 | 2019-04-13 | 2019-04-14 | 3 | INTEGRITY | MECHANICAL | 5
2019-03-31 | 11580 | Work Order Description - 11580 - CM | CM | 4 | 368329 | WPLAN | NORM-OPS | 2017-07-04 | 2019-07-17 | 2019-08-24 | 2019-08-24 | 3 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 11584 | Work Order Description - 11584 - CM | CM | 3 | 361596 | WSCHD | SUBSYS-ISOL | 2017-07-07 | 2019-11-27 | 2019-09-07 | 2019-09-08 | 3 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 11623 | Work Order Description - 11623 - CM | CM | 3 | 188367 | SCHD | TPS | 2018-09-06 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 42
2019-03-31 | 11641 | Work Order Description - 11641 - CM | CM | 4 | 494338 | WSCHD | NORM-OPS | 2016-07-15 | 2019-12-31 | 2019-04-06 | 2019-04-07 | 4 | MAINTENANCE | MECHANICAL | 17
2019-03-31 | 11652 | Work Order Description - 11652 - CM | CM | 4 | 287682 | WSCHD | NORM-OPS | 2017-07-21 | 2020-01-18 | 2019-12-30 | 2019-12-30 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 11655 | Work Order Description - 11655 - CM | CM | 4 | 520365 | WSCHD | TPS | 2018-06-08 | 2019-06-09 | 2020-05-03 | 2020-05-07 | 3 | MAINTENANCE | MECHANICAL | 50
2019-03-31 | 11659 | Work Order Description - 11659 - CM | CM | 4 | 226533 | WSCHD | TPS | 2016-08-05 | 2019-10-09 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 11663 | Work Order Description - 11663 - PM | PM | 3 | 262306 | WSCHD | EQUIP-ISOL | 2016-06-09 | 2018-12-10 | 2020-03-07 | 2020-03-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 11664 | Work Order Description - 11664 - PM | PM | 3 | 54434 | WSCHD | EQUIP-ISOL | 2016-06-09 | 2019-07-13 | 2020-03-07 | 2020-03-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 11665 | Work Order Description - 11665 - PM | PM | 3 | 53504 | WSCHD | EQUIP-ISOL | 2016-06-09 | 2018-12-21 | 2020-03-07 | 2020-03-07 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 11666 | Work Order Description - 11666 - PSPM | PSPM | 1 | 357587 | WSCHD | SUBSYS-ISOL | 2017-07-21 | 2019-07-01 | 2020-03-07 | 2020-03-07 | 1 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 11689 | Work Order Description - 11689 - PM | PM | 3 | 210544 | SCHD | SUBSYS-ISOL | 2018-09-07 | 2019-04-01 | 2019-11-01 | 2019-11-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 11697 | Work Order Description - 11697 - CM | CM | 4 | 33556 | WSCHD | SUBSYS-ISOL | 2016-07-06 | 2019-08-27 | 2019-07-06 | 2019-07-08 | 3 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 11706 | Work Order Description - 11706 - CM | CM | 2 | 375680 | SCHD | SYS-ISOL | 2019-01-07 | 2019-12-07 | 2019-07-13 | 2019-07-15 | 3 | MAINTENANCE | MECHANICAL | 38
2019-03-31 | 11708 | Work Order Description - 11708 - CM | CM | 3 | 327248 | WPLAN | SUBSYS-ISOL | 2017-07-26 | 2019-08-07 | 2019-07-06 | 2019-07-11 | 3 | MAINTENANCE | MECHANICAL | 72
2019-03-31 | 11711 | Work Order Description - 11711 - CM | CM | 4 | 375636 | WPLAN | NORM-OPS | 2018-08-20 | 2020-08-17 | 2020-07-28 | 2020-07-30 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 11713 | Work Order Description - 11713 - CM | CM | 4 | 375636 | WPLAN | NORM-OPS | 2018-08-20 | 2020-08-17 | 2020-07-28 | 2020-07-29 | 4 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 11718 | Work Order Description - 11718 - CM | CM | 4 | 375636 | WPLAN | NORM-OPS | 2018-08-20 | 2020-08-17 | 2020-07-28 | 2020-07-30 | 4 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 11724 | Work Order Description - 11724 - CM | CM | 4 | 267676 | WSCHD | NORM-OPS | 2016-06-12 | 2019-05-11 | 2020-06-27 | 2020-06-27 | 4 | INTEGRITY | SERVICES | 1
2019-03-31 | 11726 | Work Order Description - 11726 - CM | CM | 2 | 527378 | SCHD | NORM-OPS | 2018-06-21 | 2019-11-11 | 2019-05-03 | 2019-05-05 | 3 | INTEGRITY | CONSTRUCTION | 35
2019-03-31 | 11731 | Work Order Description - 11731 - CM | CM | 4 | 267676 | WSCHD | NORM-OPS | 2016-06-13 | 2019-10-24 | 2019-04-13 | 2019-04-13 | 4 | OPERATIONS | OPERATIONS | 1
2019-03-31 | 11773 | Work Order Description - 11773 - CM | CM | 3 | 399408 | SCHD | NORM-OPS | 2018-11-02 | 2019-11-25 | 2019-08-03 | 2019-08-05 | 4 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 11877 | Work Order Description - 11877 - PSCM | PSCM | 1 | 325633 | SCHD | NORM-OPS | 2018-09-06 | 2019-04-01 | 2020-01-04 | 2020-01-04 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 11884 | Work Order Description - 11884 - CM | CM | 3 | 493008 | WSCHD | SYS-ISOL | 2019-02-23 | 2019-10-29 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 11887 | Work Order Description - 11887 - CM | CM | 2 | 126053 | SCHD | NORM-OPS | 2018-06-21 | 2019-09-14 | 2019-08-31 | 2019-09-01 | 4 | MAINTENANCE | MECHANICAL | 17
2019-03-31 | 11942 | Work Order Description - 11942 - PSPM | PSPM | 1 | 595635 | WSCHD | EQUIP-ISOL | 2016-06-21 | 2020-01-04 | 2019-12-20 | 2019-12-22 | 1 | MAINTENANCE | INSTRUMENTS | 17
2019-03-31 | 11956 | Work Order Description - 11956 - CM | CM | 1 | 570144 | SCHD | NORM-OPS | 2019-03-22 | 2019-07-01 | 2019-04-20 | 2019-04-26 | 3 | INTEGRITY | SERVICES | 147
2019-03-31 | 11969 | Work Order Description - 11969 - CM | CM | 1 | 204611 | WSCHD | NORM-OPS | 2018-04-17 | 2019-10-01 | 2019-06-01 | 2019-06-03 | 4 | INTEGRITY | DRILLING | 54
2019-03-31 | 11982 | Work Order Description - 11982 - CM | CM | 3 | 502380 | WPLAN | SUBSYS-ISOL | 2017-07-26 | 2019-12-31 | 2019-04-13 | 2019-04-21 | 3 | MAINTENANCE | MECHANICAL | 71
2019-03-31 | 12005 | Work Order Description - 12005 - CM | CM | 3 | 489974 | WPLAN | SUBSYS-ISOL | 2017-07-26 | 2019-12-29 | 2019-04-13 | 2019-04-22 | 3 | MAINTENANCE | MECHANICAL | 109
2019-03-31 | 12015 | Work Order Description - 12015 - PSCM | PSCM | 1 | 666277 | WSCHD | TPS | 2018-06-26 | 2020-08-02 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 12051 | Work Order Description - 12051 - CM | CM | 4 | 659495 | SCHD | NORM-OPS | 2018-06-21 | 2019-03-23 | 2019-05-04 | 2019-05-09 | 4 | INTEGRITY | CONSTRUCTION | 56
2019-03-31 | 12074 | Work Order Description - 12074 - CM | CM | 3 | 215004 | WSCHD | NORM-OPS | 2016-07-06 | 2019-08-26 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 12075 | Work Order Description - 12075 - CM | CM | 3 | 357282 | WSCHD | SYS-ISOL | 2017-07-19 | 2019-02-20 | 2019-08-03 | 2019-08-04 | 3 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 12105 | Work Order Description - 12105 - CM | CM | 3 | 541238 | WSCHD | TPS | 2018-06-08 | 2019-09-12 | 2020-05-03 | 2020-05-03 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 12112 | Work Order Description - 12112 - CM | CM | 3 | 677996 | WSCHD | NORM-OPS | 2018-06-20 | 2019-09-20 | 2019-04-27 | 2019-04-29 | 3 | INTEGRITY | CONSTRUCTION | 22
2019-03-31 | 12115 | Work Order Description - 12115 - CM | CM | 3 | 464221 | SCHD | NORM-OPS | 2019-02-13 | 2020-02-12 | 2019-08-17 | 2019-08-17 | 3 | INTEGRITY | FABRIC | 80
2019-03-31 | 12118 | Work Order Description - 12118 - CM | CM | 3 | 25392 | SCHD | TPS | 2018-09-06 | 2019-03-26 | 2019-07-13 | 2019-07-13 | 4 | INTEGRITY | MECHANICAL | 237
2019-03-31 | 12126 | Work Order Description - 12126 - CM | CM | 4 | 72765 | WPLAN | SYS-ISOL | 2018-11-05 | 2020-01-01 | 2019-06-01 | 2019-06-01 | 3 | INTEGRITY | FABRIC | 56
2019-03-31 | 12129 | Work Order Description - 12129 - PRJ | PRJ | 4 | 76038 | SCHD | NORM-OPS | 2018-06-21 | 2019-12-02 | 2019-09-18 | 2020-03-28 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 12150 | Work Order Description - 12150 - BR | BR | 3 | 327249 | WPLAN | SUBSYS-ISOL | 2017-07-26 | 2019-12-31 | 2019-08-03 | 2019-08-10 | 3 | MAINTENANCE | MECHANICAL | 86
2019-03-31 | 12157 | Work Order Description - 12157 - CM | CM | 4 | 556357 | SCHD | NORM-OPS | 2018-09-06 | 2020-01-16 | 2020-06-13 | 2020-06-13 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 12164 | Work Order Description - 12164 - PM | PM | 4 | 480203 | WSCHD | PACK-ISOL | 2016-07-01 | 2019-09-23 | 2019-04-10 | 2019-04-11 | 3 | MAINTENANCE | MECHANICAL | 112
2019-03-31 | 12174 | Work Order Description - 12174 - CM | CM | 3 | 652769 | SCHD | TPS | 2018-12-05 | 2019-02-23 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 12184 | Work Order Description - 12184 - CM | CM | 4 | 70841 | WPLAN | NORM-OPS | 2017-05-24 | 2019-08-16 | 2020-05-02 | 2020-05-04 | 2 | INTEGRITY | CONSTRUCTION | 35
2019-03-31 | 12185 | Work Order Description - 12185 - CM | CM | 3 | 435896 | WPLAN | TPS | 2018-08-20 | 2019-08-19 | 2019-07-13 | 2019-07-14 | 3 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 12215 | Work Order Description - 12215 - CM | CM | 3 | 51131 | WSCHD | NORM-OPS | 2016-09-21 | 2019-09-06 | 2019-05-18 | 2019-05-19 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 12218 | Work Order Description - 12218 - CM | CM | 3 | 519871 | WSCHD | SUBSYS-ISOL | 2016-07-28 | 2019-10-29 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 6
2019-03-31 | 12219 | Work Order Description - 12219 - CM | CM | 3 | 495420 | WSCHD | SUBSYS-ISOL | 2016-07-29 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 12220 | Work Order Description - 12220 - CM | CM | 3 | 215014 | WSCHD | SUBSYS-ISOL | 2016-07-29 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 6
2019-03-31 | 12221 | Work Order Description - 12221 - CM | CM | 3 | 215013 | WSCHD | SUBSYS-ISOL | 2016-07-29 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 12222 | Work Order Description - 12222 - CM | CM | 3 | 247762 | WSCHD | SUBSYS-ISOL | 2016-07-29 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 12223 | Work Order Description - 12223 - CM | CM | 3 | 247761 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 12224 | Work Order Description - 12224 - CM | CM | 3 | 214976 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 4
2019-03-31 | 12226 | Work Order Description - 12226 - CM | CM | 4 | 215182 | WSCHD | TPS | 2016-08-05 | 2019-09-06 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | CONSTRUCTION | 4
2019-03-31 | 12227 | Work Order Description - 12227 - CM | CM | 3 | 325903 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 12228 | Work Order Description - 12228 - CM | CM | 4 | 675036 | WSCHD | NORM-OPS | 2016-07-15 | 2019-11-07 | 2019-04-20 | 2019-04-21 | 4 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 12229 | Work Order Description - 12229 - CM | CM | 3 | 247785 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 12230 | Work Order Description - 12230 - CM | CM | 3 | 357260 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 4 | MAINTENANCE | CONSTRUCTION | 11
2019-03-31 | 12232 | Work Order Description - 12232 - CM | CM | 3 | 245657 | WSCHD | SUBSYS-ISOL | 2016-07-12 | 2019-09-06 | 2019-09-14 | 2019-09-14 | 4 | MAINTENANCE | CONSTRUCTION | 9
2019-03-31 | 12234 | Work Order Description - 12234 - CM | CM | 3 | 215029 | WSCHD | SUBSYS-ISOL | 2016-07-30 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 6
2019-03-31 | 12235 | Work Order Description - 12235 - CM | CM | 3 | 519879 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 6
2019-03-31 | 12236 | Work Order Description - 12236 - CM | CM | 3 | 501293 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 12237 | Work Order Description - 12237 - CM | CM | 3 | 495476 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 6
2019-03-31 | 12238 | Work Order Description - 12238 - CM | CM | 3 | 519932 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 6
2019-03-31 | 12239 | Work Order Description - 12239 - CM | CM | 3 | 495470 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 6
2019-03-31 | 12264 | Work Order Description - 12264 - CM | CM | 3 | 245657 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 4 | MAINTENANCE | CONSTRUCTION | 12
2019-03-31 | 12265 | Work Order Description - 12265 - BR | BR | 3 | 19009 | WSCHD | SUBSYS-ISOL | 2016-07-17 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 4 | INTEGRITY | CONSTRUCTION | 11
2019-03-31 | 12266 | Work Order Description - 12266 - CM | CM | 3 | 531854 | WSCHD | SUBSYS-ISOL | 2016-07-17 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | INTEGRITY | CONSTRUCTION | 6
2019-03-31 | 12267 | Work Order Description - 12267 - CM | CM | 3 | 531853 | WSCHD | SUBSYS-ISOL | 2016-07-17 | 2019-09-06 | 2019-09-07 | 2019-09-09 | 4 | INTEGRITY | CONSTRUCTION | 16
2019-03-31 | 12269 | Work Order Description - 12269 - BR | BR | 3 | 19008 | WSCHD | SUBSYS-ISOL | 2016-07-17 | 2019-09-06 | 2019-09-07 | 2019-09-10 | 4 | INTEGRITY | CONSTRUCTION | 22
2019-03-31 | 12270 | Work Order Description - 12270 - BR | BR | 3 | 531852 | WSCHD | SUBSYS-ISOL | 2016-07-17 | 2019-09-06 | 2019-09-07 | 2019-09-10 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 12271 | Work Order Description - 12271 - CM | CM | 3 | 214842 | WSCHD | SUBSYS-ISOL | 2016-07-17 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 4
2019-03-31 | 12275 | Work Order Description - 12275 - PM | PM | 4 | 249644 | WSCHD | EQUIP-ISOL | 2016-07-08 | 2019-09-04 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 12312 | Work Order Description - 12312 - PSPM | PSPM | 1 | 361211 | WSCHD | EQUIP-ISOL | 2016-07-08 | 2020-07-28 | 2020-05-02 | 2020-05-03 | 1 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 12319 | Work Order Description - 12319 - PSCM | PSCM | 1 | 322938 | WSCHD | TPS | 2018-06-08 | 2020-08-01 | 2020-05-03 | 2020-05-04 | 3 | MAINTENANCE | CONSTRUCTION | 20
2019-03-31 | 12321 | Work Order Description - 12321 - CM | CM | 3 | 247763 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-02-01 | 2019-09-07 | 2019-09-08 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 12328 | Work Order Description - 12328 - BR | BR | 3 | 248432 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 4
2019-03-31 | 12329 | Work Order Description - 12329 - CM | CM | 3 | 495418 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 12330 | Work Order Description - 12330 - CM | CM | 3 | 215012 | WSCHD | SUBSYS-ISOL | 2016-07-29 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 12331 | Work Order Description - 12331 - CM | CM | 3 | 519838 | WPLAN | SUBSYS-ISOL | 2018-11-15 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 12332 | Work Order Description - 12332 - CM | CM | 3 | 495421 | WSCHD | SUBSYS-ISOL | 2016-07-29 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 6
2019-03-31 | 12333 | Work Order Description - 12333 - CM | CM | 3 | 519870 | WSCHD | SUBSYS-ISOL | 2016-07-29 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 12345 | Work Order Description - 12345 - CM | CM | 3 | 51880 | WPLAN | TPS | 2017-07-26 | 2019-02-22 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 12444 | Work Order Description - 12444 - PM | PM | 4 | 479824 | SCHD | EQUIP-ISOL | 2018-09-06 | 2020-11-06 | 2020-05-09 | 2020-05-09 | 1 | INTEGRITY | DRILLING | 4
2019-03-31 | 12539 | Work Order Description - 12539 - CM | CM | 3 | 33833 | WSCHD | NORM-OPS | 2018-06-15 | 2019-09-06 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 12540 | Work Order Description - 12540 - CM | CM | 3 | 503309 | WSCHD | NORM-OPS | 2018-06-15 | 2019-09-06 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 12541 | Work Order Description - 12541 - CM | CM | 3 | 33834 | WSCHD | TPS | 2018-06-08 | 2019-09-06 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | CONSTRUCTION | 14
2019-03-31 | 12543 | Work Order Description - 12543 - CM | CM | 4 | 480135 | WSCHD | NORM-OPS | 2016-07-14 | 2019-09-06 | 2019-08-24 | 2019-08-31 | 4 | MAINTENANCE | CONSTRUCTION | 99
2019-03-31 | 12544 | Work Order Description - 12544 - CM | CM | 4 | 480134 | WSCHD | NORM-OPS | 2016-07-16 | 2019-09-06 | 2019-08-24 | 2019-08-31 | 4 | INTEGRITY | CONSTRUCTION | 99
2019-03-31 | 12573 | Work Order Description - 12573 - CM | CM | 4 | 215325 | WPLAN | NORM-OPS | 2017-07-26 | 2018-12-05 | 2019-08-24 | 2019-08-25 | 4 | MAINTENANCE | CONSTRUCTION | 49
2019-03-31 | 12587 | Work Order Description - 12587 - CM | CM | 4 | 308564 | INPRG | NORM-OPS | 2019-03-23 | 2019-11-10 | 2019-03-30 | 2019-03-31 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 12588 | Work Order Description - 12588 - CM | CM | 4 | 308564 | SCHD | NORM-OPS | 2019-03-22 | 2019-05-26 | 2019-03-30 | 2019-03-31 | 3 | MAINTENANCE | MECHANICAL | 117
2019-03-31 | 12590 | Work Order Description - 12590 - CM | CM | 4 | 308564 | SCHD | NORM-OPS | 2019-02-26 | 2020-01-10 | 2019-03-30 | 2019-04-07 | 3 | MAINTENANCE | SERVICES | 32.5
2019-03-31 | 12596 | Work Order Description - 12596 - CM | CM | 4 | 675037 | WSCHD | NORM-OPS | 2016-07-14 | 2019-12-31 | 2019-05-25 | 2019-05-26 | 3 | MAINTENANCE | MECHANICAL | 56
2019-03-31 | 12598 | Work Order Description - 12598 - CM | CM | 4 | 675037 | WSCHD | NORM-OPS | 2016-07-14 | 2019-12-31 | 2019-05-25 | 2019-05-31 | 3 | MAINTENANCE | MECHANICAL | 196
2019-03-31 | 12600 | Work Order Description - 12600 - CM | CM | 4 | 675037 | WSCHD | NORM-OPS | 2016-07-14 | 2019-12-31 | 2019-05-25 | 2019-05-26 | 3 | MAINTENANCE | MECHANICAL | 56
2019-03-31 | 12602 | Work Order Description - 12602 - CM | CM | 4 | 675037 | WSCHD | NORM-OPS | 2016-07-16 | 2019-12-31 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 12626 | Work Order Description - 12626 - CM | CM | 4 | 520843 | WSCHD | NORM-OPS | 2016-08-23 | 2019-09-06 | 2019-05-04 | 2019-05-06 | 4 | MAINTENANCE | CONSTRUCTION | 23
2019-03-31 | 12638 | Work Order Description - 12638 - CM | CM | 2 | 479226 | SCHD | NORM-OPS | 2018-07-06 | 2019-12-26 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 12691 | Work Order Description - 12691 - PSPM | PSPM | 1 | 357616 | WSCHD | PACK-ISOL | 2017-11-10 | 2019-06-01 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 12692 | Work Order Description - 12692 - PSPM | PSPM | 1 | 357618 | WSCHD | PACK-ISOL | 2016-07-20 | 2019-06-01 | 2019-10-26 | 2019-10-26 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 13030 | Work Order Description - 13030 - CM | CM | 3 | 363614 | WSCHD | TPS | 2018-11-30 | 2019-12-12 | 2020-05-02 | 2020-05-03 | 2 | INTEGRITY | MECHANICAL | 1
2019-03-31 | 13041 | Work Order Description - 13041 - CM | CM | 4 | 138562 | WSCHD | SUBSYS-ISOL | 2016-07-25 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | SERVICES | 5
2019-03-31 | 13045 | Work Order Description - 13045 - CM | CM | 4 | 138562 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 4 | MAINTENANCE | SERVICES | 12
2019-03-31 | 13097 | Work Order Description - 13097 - PSPM | PSPM | 1 | 58989 | SCHD | PACK-ISOL | 2018-12-24 | 2019-04-11 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | MECHANICAL | 55
2019-03-31 | 13118 | Work Order Description - 13118 - CM | CM | 4 | 50849 | WSCHD | NORM-OPS | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 3 | INTEGRITY | SERVICES | 12
2019-03-31 | 13123 | Work Order Description - 13123 - CM | CM | 4 | 34006 | WSCHD | NORM-OPS | 2016-07-29 | 2019-09-06 | 2019-05-25 | 2019-05-26 | 4 | MAINTENANCE | CONSTRUCTION | 16
2019-03-31 | 13126 | Work Order Description - 13126 - CM | CM | 4 | 322705 | WSCHD | NORM-OPS | 2016-07-29 | 2019-09-06 | 2019-05-25 | 2019-05-26 | 4 | MAINTENANCE | CONSTRUCTION | 16
2019-03-31 | 13132 | Work Order Description - 13132 - CM | CM | 4 | 494164 | WSCHD | NORM-OPS | 2017-07-21 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | SERVICES | 6
2019-03-31 | 13133 | Work Order Description - 13133 - CM | CM | 4 | 494164 | WSCHD | NORM-OPS | 2016-07-29 | 2019-09-06 | 2019-05-25 | 2019-05-26 | 3 | MAINTENANCE | CONSTRUCTION | 14
2019-03-31 | 13138 | Work Order Description - 13138 - CM | CM | 4 | 247759 | WSCHD | NORM-OPS | 2016-07-25 | 2019-09-06 | 2019-05-25 | 2019-05-26 | 4 | MAINTENANCE | CONSTRUCTION | 14
2019-03-31 | 13142 | Work Order Description - 13142 - CM | CM | 3 | 363175 | WSCHD | NORM-OPS | 2016-07-25 | 2019-04-27 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 13143 | Work Order Description - 13143 - BR | BR | 4 | 70841 | WPLAN | NORM-OPS | 2017-06-05 | 2019-08-28 | 2019-05-25 | 2019-05-25 | 4 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 13144 | Work Order Description - 13144 - CM | CM | 4 | 70841 | WSCHD | NORM-OPS | 2018-08-24 | 2020-08-04 | 2020-01-25 | 2020-01-30 | 4 | INTEGRITY | FABRIC | 120
2019-03-31 | 13145 | Work Order Description - 13145 - CM | CM | 4 | 501158 | WSCHD | NORM-OPS | 2016-07-29 | 2019-09-06 | 2019-05-25 | 2019-05-26 | 4 | MAINTENANCE | CONSTRUCTION | 14
2019-03-31 | 13153 | Work Order Description - 13153 - CM | CM | 4 | 322640 | WSCHD | NORM-OPS | 2016-07-25 | 2019-09-06 | 2019-05-25 | 2019-05-27 | 4 | MAINTENANCE | CONSTRUCTION | 28
2019-03-31 | 13156 | Work Order Description - 13156 - CM | CM | 3 | 321727 | WPLAN | TPS | 2017-07-26 | 2019-09-06 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 13195 | Work Order Description - 13195 - PRJ | PRJ | 3 | 674772 | WSCHD | NORM-OPS | 2016-07-28 | 2019-04-27 | 2019-05-25 | 2019-05-26 | 3 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 13197 | Work Order Description - 13197 - CM | CM | 3 | 322703 | WSCHD | SUBSYS-ISOL | 2018-06-17 | 2020-01-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 13206 | Work Order Description - 13206 - CM | CM | 4 | 326771 | WSCHD | TPS | 2018-06-21 | 2019-09-06 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 13207 | Work Order Description - 13207 - CM | CM | 4 | 326772 | WSCHD | TPS | 2018-06-21 | 2019-09-06 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 13208 | Work Order Description - 13208 - CM | CM | 4 | 248337 | WSCHD | NORM-OPS | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | INTEGRITY | SERVICES | 21
2019-03-31 | 13210 | Work Order Description - 13210 - CM | CM | 4 | 327539 | WSCHD | NORM-OPS | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 4 | MAINTENANCE | SERVICES | 42
2019-03-31 | 13212 | Work Order Description - 13212 - CM | CM | 4 | 327539 | WSCHD | NORM-OPS | 2016-07-29 | 2019-09-06 | 2019-05-25 | 2019-05-26 | 4 | MAINTENANCE | CONSTRUCTION | 14
2019-03-31 | 13239 | Work Order Description - 13239 - CM | CM | 4 | 58391 | SCHD | NORM-OPS | 2018-10-29 | 2019-07-02 | 2019-04-13 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 13244 | Work Order Description - 13244 - CM | CM | 4 | 215022 | WSCHD | NORM-OPS | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | SERVICES | 4
2019-03-31 | 13249 | Work Order Description - 13249 - PSCM | PSCM | 1 | 681203 | WSCHD | NORM-OPS | 2017-07-21 | 2019-04-29 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 13320 | Work Order Description - 13320 - CM | CM | 3 | 671602 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 13326 | Work Order Description - 13326 - CM | CM | 3 | 671603 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 13330 | Work Order Description - 13330 - CM | CM | 2 | 294108 | SCHD | TPS | 2018-05-24 | 2019-03-24 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 13332 | Work Order Description - 13332 - CM | CM | 3 | 323312 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 13334 | Work Order Description - 13334 - CM | CM | 3 | 245656 | WSCHD | SUBSYS-ISOL | 2016-08-05 | 2019-09-06 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | CONSTRUCTION | 28
2019-03-31 | 13337 | Work Order Description - 13337 - CM | CM | 4 | 249449 | WSCHD | NORM-OPS | 2016-08-03 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | SERVICES | 21
2019-03-31 | 13348 | Work Order Description - 13348 - CM | CM | 3 | 531852 | WSCHD | NORM-OPS | 2016-08-05 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | INTEGRITY | SERVICES | 21
2019-03-31 | 13365 | Work Order Description - 13365 - CM | CM | 4 | 501258 | WSCHD | NORM-OPS | 2016-08-05 | 2019-09-06 | 2019-09-28 | 2019-09-29 | 4 | MAINTENANCE | SERVICES | 14
2019-03-31 | 13374 | Work Order Description - 13374 - CM | CM | 3 | 383068 | WPLAN | SYS-ISOL | 2019-01-24 | 2019-11-27 | 2019-07-13 | 2019-07-21 | 3 | MAINTENANCE | CONSTRUCTION | 385
2019-03-31 | 13401 | Work Order Description - 13401 - CM | CM | 3 | 245651 | WSCHD | TPS | 2016-08-07 | 2019-02-11 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 13422 | Work Order Description - 13422 - CM | CM | 4 | 155742 | WSCHD | NORM-OPS | 2018-11-17 | 2020-11-13 | 2019-04-24 | 2019-04-24 | 4 | INTEGRITY | FABRIC | 222
2019-03-31 | 13426 | Work Order Description - 13426 - CM | CM | 4 | 697913 | SCHD | NORM-OPS | 2019-03-20 | 2020-11-13 | 2019-03-30 | 2019-04-07 | 4 | INTEGRITY | FABRIC | 75
2019-03-31 | 13429 | Work Order Description - 13429 - CM | CM | 4 | 204612 | WSCHD | NORM-OPS | 2018-11-17 | 2020-11-13 | 2019-09-07 | 2019-09-07 | 4 | INTEGRITY | FABRIC | 12
2019-03-31 | 13538 | Work Order Description - 13538 - CM | CM | 3 | 580004 | SCHD | NORM-OPS | 2018-10-29 | 2019-06-26 | 2019-04-27 | 2019-04-27 | 2 | WELLS | INSTRUMENTS | 2
2019-03-31 | 13539 | Work Order Description - 13539 - CM | CM | 4 | 661048 | SCHD | PACK-ISOL | 2018-10-29 | 2019-09-26 | 2019-04-27 | 2019-04-27 | 3 | WELLS | INSTRUMENTS | 2
2019-03-31 | 13553 | Work Order Description - 13553 - CM | CM | 2 | 113703 | SCHD | SYS-ISOL | 2018-08-14 | 2019-03-22 | 2019-07-13 | 2019-07-15 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 13569 | Work Order Description - 13569 - CM | CM | 3 | 309056 | SCHD | TPS | 2018-09-06 | 2019-01-06 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 13764 | Work Order Description - 13764 - CM | CM | 1 | 321203 | WSCHD | NORM-OPS | 2017-11-03 | 2020-09-01 | 2019-05-25 | 2019-05-28 | 4 | INTEGRITY | FABRIC | 28
2019-03-31 | 13776 | Work Order Description - 13776 - CM | CM | 3 | 520043 | WSCHD | TPS | 2016-08-18 | 2020-01-17 | 2019-05-25 | 2019-05-26 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 13779 | Work Order Description - 13779 - PSCM | PSCM | 1 | 18982 | WSCHD | NORM-OPS | 2016-12-23 | 2019-12-15 | 2019-08-31 | 2019-08-31 | 4 | INTEGRITY | INSTRUMENTS | 1
2019-03-31 | 13783 | Work Order Description - 13783 - CM | CM | 3 | 361983 | WSCHD | NORM-OPS | 2017-07-21 | 2019-10-16 | 2019-08-31 | 2019-08-31 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 13788 | Work Order Description - 13788 - CM | CM | 3 | 321199 | SCHD | NORM-OPS | 2018-11-14 | 2019-07-01 | 2019-04-27 | 2019-04-29 | 4 | MAINTENANCE | INSTRUMENTS | 32
2019-03-31 | 13795 | Work Order Description - 13795 - CM | CM | 4 | 481746 | SCHD | NORM-OPS | 2019-01-31 | 2020-01-08 | 2019-07-09 | 2019-07-09 | 3 | INTEGRITY | FABRIC | 211.5
2019-03-31 | 13801 | Work Order Description - 13801 - CM | CM | 4 | 481746 | SCHD | NORM-OPS | 2019-02-13 | 2021-02-10 | 2019-06-22 | 2019-06-25 | 4 | INTEGRITY | FABRIC | 48
2019-03-31 | 13806 | Work Order Description - 13806 - CM | CM | 4 | 481746 | SCHD | NORM-OPS | 2018-10-09 | 2019-07-01 | 2019-05-25 | 2019-05-25 | 4 | INTEGRITY | FABRIC | 1
2019-03-31 | 13811 | Work Order Description - 13811 - CM | CM | 4 | 481746 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-01 | 2019-03-30 | 2019-03-30 | 4 | INTEGRITY | FABRIC | 1
2019-03-31 | 13822 | Work Order Description - 13822 - PSCM | PSCM | 1 | 503344 | WSCHD | NORM-OPS | 2016-08-26 | 2019-08-01 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 13823 | Work Order Description - 13823 - CM | CM | 3 | 34020 | WPLAN | TPS | 2017-07-26 | 2019-09-06 | 2019-08-03 | 2019-08-03 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 13826 | Work Order Description - 13826 - PSCM | PSCM | 1 | 328001 | WSCHD | TPS | 2016-08-26 | 2020-08-01 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 31
2019-03-31 | 13827 | Work Order Description - 13827 - PSCM | PSCM | 1 | 298784 | WSCHD | TPS | 2016-08-26 | 2020-08-01 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 27
2019-03-31 | 13840 | Work Order Description - 13840 - PSCM | PSCM | 1 | 501200 | WSCHD | SUBSYS-ISOL | 2016-08-26 | 2020-08-01 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 13841 | Work Order Description - 13841 - PSCM | PSCM | 1 | 322707 | WSCHD | SYS-ISOL | 2016-08-26 | 2019-07-01 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 13849 | Work Order Description - 13849 - PSCM | PSCM | 1 | 327657 | WSCHD | NORM-OPS | 2016-08-26 | 2020-02-01 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 13854 | Work Order Description - 13854 - CM | CM | 3 | 546212 | WSCHD | NORM-OPS | 2017-07-07 | 2019-04-24 | 2019-09-07 | 2019-09-08 | 3 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 13857 | Work Order Description - 13857 - PSCM | PSCM | 1 | 327630 | WSCHD | TPS | 2016-08-26 | 2020-08-01 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 13858 | Work Order Description - 13858 - PSCM | PSCM | 1 | 327628 | WSCHD | SUBSYS-ISOL | 2016-08-26 | 2020-02-01 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 13859 | Work Order Description - 13859 - CM | CM | 3 | 536538 | WSCHD | SUBSYS-ISOL | 2016-08-30 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 13860 | Work Order Description - 13860 - PSCM | PSCM | 1 | 327631 | WSCHD | SUBSYS-ISOL | 2016-08-26 | 2019-06-01 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 13861 | Work Order Description - 13861 - PSCM | PSCM | 1 | 247756 | WSCHD | SUBSYS-ISOL | 2016-08-26 | 2019-11-30 | 2019-09-07 | 2019-09-09 | 4 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 13862 | Work Order Description - 13862 - PSCM | PSCM | 1 | 322818 | WSCHD | SUBSYS-ISOL | 2016-08-26 | 2020-02-01 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 13870 | Work Order Description - 13870 - CM | CM | 3 | 50849 | WSCHD | SUBSYS-ISOL | 2016-08-20 | 2019-09-07 | 2019-04-13 | 2019-04-15 | 3 | INTEGRITY | SERVICES | 42
2019-03-31 | 13871 | Work Order Description - 13871 - CM | CM | 4 | 451348 | WPLAN | NORM-OPS | 2016-11-07 | 2020-01-24 | 2019-07-13 | 2019-07-27 | 3 | INTEGRITY | CONSTRUCTION | 100
2019-03-31 | 13885 | Work Order Description - 13885 - CM | CM | 3 | 495511 | WPLAN | TPS | 2017-07-26 | 2019-08-30 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 13886 | Work Order Description - 13886 - CM | CM | 3 | 215049 | WSCHD | TPS | 2018-05-29 | 2020-01-20 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 13887 | Work Order Description - 13887 - CM | CM | 3 | 327717 | WSCHD | TPS | 2016-08-25 | 2019-09-06 | 2020-05-02 | 2020-05-04 | 4 | MAINTENANCE | MECHANICAL | 52
2019-03-31 | 13888 | Work Order Description - 13888 - CM | CM | 3 | 34051 | WSCHD | TPS | 2016-08-25 | 2019-09-06 | 2020-05-02 | 2020-05-04 | 4 | MAINTENANCE | MECHANICAL | 52
2019-03-31 | 13891 | Work Order Description - 13891 - PSCM | PSCM | 1 | 322681 | WSCHD | SUBSYS-ISOL | 2016-08-25 | 2019-06-01 | 2019-09-07 | 2019-09-08 | 4 | MAINTENANCE | CONSTRUCTION | 27
2019-03-31 | 13893 | Work Order Description - 13893 - CM | CM | 4 | 520842 | WSCHD | SYS-ISOL | 2016-08-23 | 2019-09-06 | 2020-05-02 | 2020-05-05 | 4 | MAINTENANCE | CONSTRUCTION | 23
2019-03-31 | 13900 | Work Order Description - 13900 - CM | CM | 3 | 681388 | WSCHD | NORM-OPS | 2019-02-20 | 2019-10-23 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | CONSTRUCTION | 14
2019-03-31 | 13901 | Work Order Description - 13901 - CM | CM | 3 | 356461 | WSCHD | NORM-OPS | 2019-02-20 | 2019-07-29 | 2019-05-25 | 2019-05-26 | 4 | MAINTENANCE | CONSTRUCTION | 40
2019-03-31 | 13902 | Work Order Description - 13902 - CM | CM | 3 | 671307 | WSCHD | NORM-OPS | 2019-02-20 | 2019-03-29 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | CONSTRUCTION | 18
2019-03-31 | 13903 | Work Order Description - 13903 - CM | CM | 3 | 356464 | WSCHD | NORM-OPS | 2019-02-20 | 2019-07-14 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | CONSTRUCTION | 24
2019-03-31 | 13904 | Work Order Description - 13904 - CM | CM | 3 | 657371 | WSCHD | NORM-OPS | 2019-02-20 | 2019-11-12 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | CONSTRUCTION | 6
2019-03-31 | 13905 | Work Order Description - 13905 - CM | CM | 3 | 356465 | WSCHD | NORM-OPS | 2019-02-20 | 2019-05-08 | 2019-05-25 | 2019-05-26 | 4 | MAINTENANCE | CONSTRUCTION | 40
2019-03-31 | 13906 | Work Order Description - 13906 - CM | CM | 3 | 356466 | WSCHD | NORM-OPS | 2019-02-20 | 2019-03-23 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | CONSTRUCTION | 24
2019-03-31 | 13907 | Work Order Description - 13907 - CM | CM | 3 | 356467 | SCHD | NORM-OPS | 2018-11-15 | 2019-02-04 | 2019-05-25 | 2019-05-26 | 4 | MAINTENANCE | CONSTRUCTION | 40
2019-03-31 | 13908 | Work Order Description - 13908 - BR | BR | 3 | 418143 | WSCHD | NORM-OPS | 2019-02-20 | 2018-12-02 | 2019-05-25 | 2019-05-26 | 4 | MAINTENANCE | MECHANICAL | 47
2019-03-31 | 13909 | Work Order Description - 13909 - BR | BR | 3 | 272152 | WSCHD | NORM-OPS | 2019-02-25 | 2019-01-26 | 2019-04-13 | 2019-04-15 | 4 | MAINTENANCE | MECHANICAL | 47
2019-03-31 | 13910 | Work Order Description - 13910 - BR | BR | 3 | 680843 | WSCHD | NORM-OPS | 2019-02-24 | 2019-07-06 | 2019-04-13 | 2019-04-15 | 4 | MAINTENANCE | MECHANICAL | 47
2019-03-31 | 13911 | Work Order Description - 13911 - CM | CM | 3 | 672872 | WSCHD | NORM-OPS | 2019-02-20 | 2019-02-09 | 2019-05-25 | 2019-05-27 | 4 | MAINTENANCE | MECHANICAL | 47
2019-03-31 | 13912 | Work Order Description - 13912 - CM | CM | 3 | 546995 | WSCHD | NORM-OPS | 2019-02-24 | 2019-01-02 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 13914 | Work Order Description - 13914 - CM | CM | 3 | 546995 | WSCHD | NORM-OPS | 2019-02-24 | 2019-11-15 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 13915 | Work Order Description - 13915 - CM | CM | 3 | 408340 | SCHD | NORM-OPS | 2018-10-29 | 2019-01-25 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | INSTRUMENTS | 38
2019-03-31 | 13917 | Work Order Description - 13917 - PRJ | PRJ | 3 | 479226 | SCHD | NORM-OPS | 2018-09-06 | 2019-08-23 | 2020-05-02 | 2020-05-02 | 3 | ENGINEERING | CONSTRUCTION | 22
2019-03-31 | 13923 | Work Order Description - 13923 - CM | CM | 3 | 138654 | WPLAN | TPS | 2017-07-26 | 2019-09-06 | 2020-05-02 | 2020-05-06 | 4 | MAINTENANCE | MECHANICAL | 45
2019-03-31 | 13969 | Work Order Description - 13969 - CM | CM | 2 | 452029 | WSCHD | NORM-OPS | 2019-03-25 | 2020-01-31 | 2020-03-28 | 2020-03-28 | 3 | INTEGRITY | CONSTRUCTION | 20
2019-03-31 | 14137 | Work Order Description - 14137 - CM | CM | 4 | 400051 | WSCHD | NORM-OPS | 2018-04-12 | 2019-10-14 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 14170 | Work Order Description - 14170 - PM | PM | 3 | 478652 | SCHD | SYS-ISOL | 2018-09-06 | 2019-02-19 | 2019-05-04 | 2019-05-04 | 2 | INTEGRITY | INSPECTION | 6
2019-03-31 | 14206 | Work Order Description - 14206 - CM | CM | 4 | 496734 | WPLAN | TPS | 2017-06-06 | 2019-04-01 | 2020-05-02 | 2020-05-02 | 2 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 14210 | Work Order Description - 14210 - CM | CM | 4 | 352464 | WSCHD | NORM-OPS | 2016-09-14 | 2019-10-11 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 14219 | Work Order Description - 14219 - PSCM | PSCM | 1 | 360702 | WSCHD | NORM-OPS | 2017-09-22 | 2019-08-01 | 2019-05-18 | 2019-05-21 | 3 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 14230 | Work Order Description - 14230 - CM | CM | 4 | 531852 | WSCHD | SUBSYS-ISOL | 2016-08-30 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 4 | INTEGRITY | SERVICES | 21
2019-03-31 | 14237 | Work Order Description - 14237 - CM | CM | 4 | 19009 | WSCHD | NORM-OPS | 2016-09-01 | 2019-09-06 | 2019-09-07 | 2019-09-07 | 4 | INTEGRITY | SERVICES | 18
2019-03-31 | 14239 | Work Order Description - 14239 - CM | CM | 4 | 50849 | WSCHD | NORM-OPS | 2016-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 4 | INTEGRITY | SERVICES | 21
2019-03-31 | 14251 | Work Order Description - 14251 - PSPM | PSPM | 1 | 54110 | WSCHD | PACK-ISOL | 2017-07-21 | 2019-12-29 | 2019-12-07 | 2019-12-07 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 14266 | Work Order Description - 14266 - CM | CM | 3 | 307837 | WSCHD | NORM-OPS | 2016-08-30 | 2019-03-11 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 14342 | Work Order Description - 14342 - CM | CM | 4 | 137614 | WSCHD | NORM-OPS | 2016-09-07 | 2019-09-06 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 14344 | Work Order Description - 14344 - CM | CM | 4 | 404767 | WSCHD | NORM-OPS | 2017-07-21 | 2019-02-22 | 2019-05-25 | 2019-05-25 | 4 | INTEGRITY | SERVICES | 1
2019-03-31 | 14345 | Work Order Description - 14345 - CM | CM | 4 | 321218 | WSCHD | NORM-OPS | 2016-09-15 | 2019-10-01 | 2019-09-28 | 2019-10-21 | 3 | MAINTENANCE | MECHANICAL | 669
2019-03-31 | 14356 | Work Order Description - 14356 - PSCM | PSCM | 1 | 327956 | WSCHD | TPS | 2016-09-07 | 2020-08-01 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 14361 | Work Order Description - 14361 - PSCM | PSCM | 1 | 499514 | WPLAN | NORM-OPS | 2018-12-09 | 2020-08-01 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 43
2019-03-31 | 14362 | Work Order Description - 14362 - CM | CM | 3 | 323081 | WSCHD | TPS | 2018-08-05 | 2019-12-16 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 14375 | Work Order Description - 14375 - PSCM | PSCM | 1 | 501491 | WSCHD | TPS | 2016-09-07 | 2020-08-01 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 14376 | Work Order Description - 14376 - PSCM | PSCM | 1 | 226491 | WSCHD | TPS | 2016-09-07 | 2020-06-01 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 14377 | Work Order Description - 14377 - PSCM | PSCM | 1 | 323257 | WSCHD | TPS | 2016-09-07 | 2020-06-01 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 14383 | Work Order Description - 14383 - BR | BR | 1 | 501726 | WSCHD | TPS | 2018-08-04 | 2020-08-01 | 2020-05-03 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 14385 | Work Order Description - 14385 - BR | BR | 1 | 493013 | WSCHD | TPS | 2018-08-04 | 2020-08-01 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 14394 | Work Order Description - 14394 - PSCM | PSCM | 1 | 489723 | WSCHD | TPS | 2016-09-10 | 2020-08-01 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 14395 | Work Order Description - 14395 - PSCM | PSCM | 1 | 501722 | WSCHD | TPS | 2016-09-10 | 2020-08-01 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 14396 | Work Order Description - 14396 - PSCM | PSCM | 1 | 489724 | WSCHD | TPS | 2016-09-10 | 2020-08-01 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 14397 | Work Order Description - 14397 - CM | CM | 4 | 479577 | SCHD | NORM-OPS | 2018-12-24 | 2019-12-18 | 2019-06-18 | 2019-06-18 | 3 | INTEGRITY | FABRIC | 42
2019-03-31 | 14434 | Work Order Description - 14434 - CM | CM | 4 | 168931 | WSCHD | TPS | 2016-09-14 | 2019-08-01 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 14470 | Work Order Description - 14470 - CM | CM | 4 | 56406 | WSCHD | TPS | 2016-09-14 | 2019-07-17 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 14471 | Work Order Description - 14471 - CM | CM | 4 | 47996 | WSCHD | TPS | 2016-09-14 | 2019-12-30 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 14472 | Work Order Description - 14472 - CM | CM | 4 | 47998 | WSCHD | TPS | 2016-09-14 | 2019-06-12 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 14473 | Work Order Description - 14473 - CM | CM | 4 | 47999 | WSCHD | TPS | 2016-09-14 | 2019-09-01 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 14476 | Work Order Description - 14476 - CM | CM | 3 | 479226 | SCHD | TPS | 2018-09-06 | 2019-04-27 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 14477 | Work Order Description - 14477 - CM | CM | 4 | 360068 | WSCHD | TPS | 2016-09-14 | 2019-09-22 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 14478 | Work Order Description - 14478 - CM | CM | 4 | 48000 | WSCHD | TPS | 2016-09-14 | 2019-10-13 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 14479 | Work Order Description - 14479 - CM | CM | 4 | 261283 | WSCHD | TPS | 2016-09-14 | 2019-08-26 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 14480 | Work Order Description - 14480 - CM | CM | 4 | 360069 | WSCHD | TPS | 2016-09-14 | 2019-12-16 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 14481 | Work Order Description - 14481 - CM | CM | 4 | 261284 | WSCHD | TPS | 2016-09-14 | 2019-03-28 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 15296 | Work Order Description - 15296 - PM | PM | 4 | 535474 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-06-12 | 2019-06-01 | 2019-06-01 | 2 | INTEGRITY | INSTRUMENTS | 2
2019-03-31 | 15394 | Work Order Description - 15394 - CM | CM | 3 | 305417 | WSCHD | NORM-OPS | 2016-09-09 | 2018-12-02 | 2019-09-29 | 2019-09-29 | 3 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 15395 | Work Order Description - 15395 - PSCM | PSCM | 1 | 361858 | WSCHD | NORM-OPS | 2017-07-21 | 2019-12-23 | 2019-09-29 | 2019-09-29 | 3 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 15396 | Work Order Description - 15396 - PSCM | PSCM | 1 | 361859 | WSCHD | NORM-OPS | 2016-09-09 | 2019-12-23 | 2019-09-29 | 2019-09-29 | 3 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 15401 | Work Order Description - 15401 - CM | CM | 3 | 51662 | WSCHD | SYS-ISOL | 2018-06-08 | 2019-02-07 | 2020-05-03 | 2020-05-06 | 3 | MAINTENANCE | CONSTRUCTION | 112
2019-03-31 | 15451 | Work Order Description - 15451 - CM | CM | 4 | 531852 | WSCHD | SUBSYS-ISOL | 2016-09-10 | 2020-01-23 | 2019-09-07 | 2019-09-10 | 4 | INTEGRITY | SERVICES | 84
2019-03-31 | 15453 | Work Order Description - 15453 - CM | CM | 4 | 323312 | WSCHD | SUBSYS-ISOL | 2016-09-15 | 2020-01-01 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | SERVICES | 12
2019-03-31 | 15454 | Work Order Description - 15454 - CM | CM | 3 | 245656 | WSCHD | SUBSYS-ISOL | 2016-09-10 | 2019-07-23 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | SERVICES | 12
2019-03-31 | 15455 | Work Order Description - 15455 - CM | CM | 4 | 249449 | WSCHD | SUBSYS-ISOL | 2016-09-12 | 2019-10-25 | 2019-09-07 | 2019-09-08 | 4 | MAINTENANCE | SERVICES | 24
2019-03-31 | 15472 | Work Order Description - 15472 - PSCM | PSCM | 4 | 48009 | WSCHD | TPS | 2018-06-16 | 2019-09-30 | 2020-05-02 | 2020-05-04 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 15478 | Work Order Description - 15478 - PSCM | PSCM | 1 | 399613 | WSCHD | NORM-OPS | 2016-09-18 | 2019-12-29 | 2019-10-24 | 2019-10-24 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 15484 | Work Order Description - 15484 - CM | CM | 4 | 408320 | WSCHD | NORM-OPS | 2017-07-21 | 2019-09-06 | 2019-06-08 | 2019-06-08 | 4 | MAINTENANCE | SERVICES | 1
2019-03-31 | 15487 | Work Order Description - 15487 - CM | CM | 4 | 659560 | WPLAN | NORM-OPS | 2016-11-07 | 2019-08-24 | 2019-11-29 | 2019-11-30 | 4 | ENGINEERING | CONSTRUCTION | 49
2019-03-31 | 15491 | Work Order Description - 15491 - CM | CM | 2 | 527378 | SCHD | NORM-OPS | 2018-06-21 | 2019-04-06 | 2019-09-08 | 2019-10-10 | 3 | INTEGRITY | CONSTRUCTION | 1200
2019-03-31 | 15531 | Work Order Description - 15531 - CM | CM | 4 | 464262 | SCHD | NORM-OPS | 2019-01-25 | 2019-12-18 | 2020-02-29 | 2020-02-29 | 3 | INTEGRITY | FABRIC | 8
2019-03-31 | 15536 | Work Order Description - 15536 - CM | CM | 3 | 672825 | SCHD | NORM-OPS | 2018-10-29 | 2018-12-05 | 2019-09-07 | 2019-09-10 | 4 | MAINTENANCE | CONSTRUCTION | 42
2019-03-31 | 15542 | Work Order Description - 15542 - CM | CM | 4 | 485479 | WSCHD | NORM-OPS | 2016-09-18 | 2019-06-16 | 2019-09-07 | 2019-09-08 | 4 | INTEGRITY | SERVICES | 10
2019-03-31 | 15568 | Work Order Description - 15568 - PM | PM | 3 | 494978 | SCHD | PACK-ISOL | 2018-09-06 | 2019-05-02 | 2020-02-01 | 2020-02-01 | 2 | INTEGRITY | INSPECTION | 2
2019-03-31 | 15634 | Work Order Description - 15634 - PM | PM | 4 | 243952 | SCHD | EQUIP-ISOL | 2018-09-06 | 2020-11-06 | 2020-11-05 | 2020-11-05 | 1 | INTEGRITY | DRILLING | 4
2019-03-31 | 15635 | Work Order Description - 15635 - PM | PM | 4 | 246202 | WSCHD | EQUIP-ISOL | 2016-09-15 | 2020-01-16 | 2019-12-28 | 2019-12-30 | 2 | INTEGRITY | ELECTRICAL | 19
2019-03-31 | 15641 | Work Order Description - 15641 - CM | CM | 3 | 670209 | WPLAN | TPS | 2018-10-10 | 2019-09-02 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 15652 | Work Order Description - 15652 - PSCM | PSCM | 1 | 361980 | WPLAN | SYS-ISOL | 2018-09-10 | 2020-01-01 | 2019-07-06 | 2021-05-02 | 4 | MAINTENANCE | CONSTRUCTION | 230
2019-03-31 | 15653 | Work Order Description - 15653 - CM | CM | 4 | 408366 | WSCHD | NORM-OPS | 2018-08-30 | 2019-08-10 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 15826 | Work Order Description - 15826 - CM | CM | 4 | 498644 | WSCHD | WELL | 2018-04-16 | 2019-10-09 | 2018-04-16 | 2018-04-16 | 3 | WELLS | WELLS | 7
2019-03-31 | 15827 | Work Order Description - 15827 - CM | CM | 4 | 498643 | SCHD | PACK-ISOL | 2018-10-29 | 2019-09-23 | 2019-04-20 | 2019-04-21 | 3 | WELLS | WELLS | 8
2019-03-31 | 15829 | Work Order Description - 15829 - CM | CM | 4 | 498643 | SCHD | PACK-ISOL | 2018-10-29 | 2019-09-25 | 2019-04-20 | 2019-04-21 | 3 | WELLS | WELLS | 8
2019-03-31 | 15967 | Work Order Description - 15967 - PRJ | PRJ | 4 | 496569 | WSCHD | NORM-OPS | 2017-07-21 | 2019-09-29 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 15987 | Work Order Description - 15987 - CM | CM | 3 | 652246 | WSCHD | NORM-OPS | 2016-10-03 | 2019-12-30 | 2019-04-27 | 2019-05-02 | 3 | MAINTENANCE | MECHANICAL | 83
2019-03-31 | 15989 | Work Order Description - 15989 - CM | CM | 2 | 468114 | WSCHD | SYS-ISOL | 2018-04-12 | 2018-12-04 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 15990 | Work Order Description - 15990 - CM | CM | 4 | 477031 | WSCHD | SYS-ISOL | 2018-06-08 | 2019-01-30 | 2020-05-03 | 2020-05-07 | 4 | MAINTENANCE | CONSTRUCTION | 64
2019-03-31 | 15992 | Work Order Description - 15992 - CM | CM | 3 | 480073 | WSCHD | SUBSYS-ISOL | 2016-10-23 | 2019-09-23 | 2019-12-28 | 2020-01-28 | 3 | OPERATIONS | OPERATIONS | 461.5
2019-03-31 | 15996 | Work Order Description - 15996 - CM | CM | 3 | 408340 | WSCHD | NORM-OPS | 2017-06-22 | 2019-05-25 | 2019-04-13 | 2019-04-25 | 3 | OPERATIONS | OPERATIONS | 147.5
2019-03-31 | 16011 | Work Order Description - 16011 - CM | CM | 1 | 17814 | SCHD | TPS | 2018-08-10 | 2019-11-15 | 2020-05-02 | 2020-05-04 | 3 | INTEGRITY | CONSTRUCTION | 406
2019-03-31 | 16013 | Work Order Description - 16013 - CM | CM | 1 | 17814 | WSCHD | TPS | 2018-10-14 | 2019-05-01 | 2019-05-25 | 2019-05-26 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 16125 | Work Order Description - 16125 - PSCM | PSCM | 1 | 260680 | WSCHD | NORM-OPS | 2016-10-23 | 2020-11-01 | 2020-03-07 | 2020-03-07 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 16147 | Work Order Description - 16147 - PM | PM | 4 | 54314 | WSCHD | PACK-ISOL | 2016-10-04 | 2019-01-15 | 2019-12-28 | 2019-12-28 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 16326 | Work Order Description - 16326 - PSCM | PSCM | 1 | 499769 | WSCHD | TPS | 2016-10-07 | 2020-07-01 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 25
2019-03-31 | 16330 | Work Order Description - 16330 - PSCM | PSCM | 1 | 226412 | WSCHD | TPS | 2018-06-08 | 2019-01-14 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 16331 | Work Order Description - 16331 - PSCM | PSCM | 1 | 493409 | WSCHD | TPS | 2016-10-07 | 2018-12-08 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 25
2019-03-31 | 16345 | Work Order Description - 16345 - PM | PM | 3 | 57183 | WSCHD | EQUIP-ISOL | 2018-11-21 | 2019-10-09 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 16365 | Work Order Description - 16365 - CM | CM | 3 | 314389 | SCHD | NORM-OPS | 2018-10-26 | 2019-06-21 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | INSTRUMENTS | 9
2019-03-31 | 16379 | Work Order Description - 16379 - CM | CM | 3 | 314434 | WSCHD | PACK-ISOL | 2016-10-07 | 2019-02-08 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 16380 | Work Order Description - 16380 - CM | CM | 3 | 541362 | WSCHD | PACK-ISOL | 2016-10-07 | 2019-09-26 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 16381 | Work Order Description - 16381 - CM | CM | 4 | 547545 | WSCHD | NORM-OPS | 2016-10-23 | 2019-06-11 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 16382 | Work Order Description - 16382 - PRJ | PRJ | 2 | 450538 | WPLAN | TPS | 2016-11-06 | 2019-11-24 | 2019-07-13 | 2019-07-13 | 4 | ENGINEERING | CONSTRUCTION | 0
2019-03-31 | 16383 | Work Order Description - 16383 - CM | CM | 4 | 547544 | WSCHD | NORM-OPS | 2016-10-23 | 2019-04-09 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 16384 | Work Order Description - 16384 - CM | CM | 4 | 50472 | WSCHD | NORM-OPS | 2016-10-23 | 2018-12-18 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 16385 | Work Order Description - 16385 - CM | CM | 4 | 547652 | WSCHD | NORM-OPS | 2016-10-23 | 2019-05-28 | 2019-06-29 | 2019-07-03 | 4 | MAINTENANCE | INSTRUMENTS | 52
2019-03-31 | 16408 | Work Order Description - 16408 - PM | PM | 3 | 57187 | WSCHD | EQUIP-ISOL | 2016-10-06 | 2019-01-03 | 2019-08-31 | 2019-08-31 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 16427 | Work Order Description - 16427 - PSPM | PSPM | 1 | 294961 | WSCHD | NORM-OPS | 2018-10-29 | 2019-04-19 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 16428 | Work Order Description - 16428 - PM | PM | 3 | 54625 | WSCHD | EQUIP-ISOL | 2017-11-06 | 2019-10-18 | 2020-12-26 | 2020-12-26 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 16429 | Work Order Description - 16429 - PM | PM | 3 | 54629 | WSCHD | EQUIP-ISOL | 2017-11-06 | 2020-01-24 | 2020-12-26 | 2020-12-26 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 16430 | Work Order Description - 16430 - PM | PM | 3 | 409794 | WSCHD | EQUIP-ISOL | 2016-10-07 | 2019-04-17 | 2019-09-24 | 2019-09-24 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 16435 | Work Order Description - 16435 - PM | PM | 4 | 261980 | WSCHD | PACK-ISOL | 2016-10-07 | 2019-04-07 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 16439 | Work Order Description - 16439 - PM | PM | 3 | 53692 | WSCHD | EQUIP-ISOL | 2017-11-06 | 2019-07-13 | 2019-09-28 | 2019-09-28 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 16443 | Work Order Description - 16443 - PM | PM | 3 | 261847 | WSCHD | EQUIP-ISOL | 2017-11-06 | 2019-02-28 | 2019-09-28 | 2019-09-29 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 16444 | Work Order Description - 16444 - PM | PM | 3 | 54248 | WSCHD | EQUIP-ISOL | 2016-10-07 | 2019-09-19 | 2019-09-28 | 2019-09-29 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 16445 | Work Order Description - 16445 - PM | PM | 3 | 57069 | WSCHD | EQUIP-ISOL | 2016-10-07 | 2019-02-17 | 2019-09-28 | 2019-09-29 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 16498 | Work Order Description - 16498 - CM | CM | 3 | 671276 | WSCHD | NORM-OPS | 2019-02-20 | 2019-06-17 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 16499 | Work Order Description - 16499 - CM | CM | 3 | 356452 | WSCHD | NORM-OPS | 2019-02-24 | 2019-03-13 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 16500 | Work Order Description - 16500 - CM | CM | 3 | 356453 | WSCHD | NORM-OPS | 2019-02-24 | 2020-01-24 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 16640 | Work Order Description - 16640 - CM | CM | 4 | 70841 | WPLAN | NORM-OPS | 2017-02-14 | 2019-04-21 | 2020-03-01 | 2020-03-02 | 4 | INTEGRITY | CONSTRUCTION | 10
2019-03-31 | 16643 | Work Order Description - 16643 - PSCM | PSCM | 1 | 519876 | WSCHD | TPS | 2016-11-18 | 2019-05-01 | 2019-08-31 | 2019-09-02 | 4 | MAINTENANCE | CONSTRUCTION | 28
2019-03-31 | 16644 | Work Order Description - 16644 - PSCM | PSCM | 1 | 495412 | WSCHD | TPS | 2016-11-18 | 2019-06-01 | 2019-08-31 | 2019-09-02 | 4 | MAINTENANCE | CONSTRUCTION | 28
2019-03-31 | 16661 | Work Order Description - 16661 - CM | CM | 4 | 668310 | SCHD | NORM-OPS | 2018-12-18 | 2019-06-10 | 2019-04-20 | 2019-04-21 | 4 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 16855 | Work Order Description - 16855 - CM | CM | 3 | 547706 | WSCHD | SYS-ISOL | 2016-10-26 | 2019-10-21 | 2020-05-02 | 2020-05-04 | 3 | MAINTENANCE | CONSTRUCTION | 21
2019-03-31 | 16897 | Work Order Description - 16897 - CM | CM | 4 | 670468 | WPLAN | NORM-OPS | 2016-10-20 | 2019-10-17 | 2020-07-28 | 2020-07-31 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 16911 | Work Order Description - 16911 - CM | CM | 4 | 375637 | WPLAN | NORM-OPS | 2016-10-20 | 2019-10-17 | 2020-07-28 | 2020-07-31 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 16945 | Work Order Description - 16945 - CM | CM | 1 | 570144 | WSCHD | NORM-OPS | 2018-10-12 | 2019-08-31 | 2019-06-03 | 2019-06-03 | 2 | INTEGRITY | CONSTRUCTION | 4837
2019-03-31 | 16951 | Work Order Description - 16951 - CM | CM | 1 | 570144 | WSCHD | NORM-OPS | 2018-10-12 | 2019-04-01 | 2019-06-03 | 2019-06-04 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 16980 | Work Order Description - 16980 - CM | CM | 4 | 403918 | SCHD | TPS | 2018-11-20 | 2020-01-01 | 2019-06-29 | 2019-06-29 | 4 | INTEGRITY | FABRIC | 200
2019-03-31 | 17017 | Work Order Description - 17017 - CM | CM | 3 | 263344 | SCHD | PACK-ISOL | 2018-09-06 | 2019-02-27 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 17183 | Work Order Description - 17183 - PSPM | PSPM | 1 | 408344 | WSCHD | EQUIP-ISOL | 2017-07-21 | 2019-07-31 | 2020-04-04 | 2020-04-04 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 17224 | Work Order Description - 17224 - PM | PM | 4 | 403492 | SCHD | SYS-ISOL | 2018-05-24 | 2019-12-07 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | ELECTRICAL | 54
2019-03-31 | 17337 | Work Order Description - 17337 - CM | CM | 2 | 313210 | SCHD | TPS | 2018-05-30 | 2020-01-23 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 89
2019-03-31 | 17346 | Work Order Description - 17346 - CM | CM | 4 | 228839 | WPLAN | NORM-OPS | 2019-03-05 | 2020-03-03 | 2019-04-13 | 2019-05-04 | 3 | INTEGRITY | FABRIC | 495
2019-03-31 | 17429 | Work Order Description - 17429 - CM | CM | 3 | 37343 | WPLAN | TPS | 2017-07-26 | 2019-05-16 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | CONSTRUCTION | 16
2019-03-31 | 17430 | Work Order Description - 17430 - CM | CM | 3 | 493293 | WPLAN | TPS | 2017-07-26 | 2019-02-20 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | CONSTRUCTION | 16
2019-03-31 | 17449 | Work Order Description - 17449 - CM | CM | 4 | 451340 | WPLAN | NORM-OPS | 2018-11-01 | 2019-10-01 | 2019-05-04 | 2019-06-04 | 4 | INTEGRITY | FABRIC | 656
2019-03-31 | 17964 | Work Order Description - 17964 - PM | PM | 4 | 96159 | SCHD | NORM-OPS | 2018-06-21 | 2019-12-23 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 17965 | Work Order Description - 17965 - PM | PM | 4 | 96159 | SCHD | NORM-OPS | 2018-06-21 | 2019-09-03 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 17966 | Work Order Description - 17966 - PM | PM | 4 | 96159 | SCHD | NORM-OPS | 2018-06-21 | 2019-11-25 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 17976 | Work Order Description - 17976 - PM | PM | 4 | 96159 | SCHD | NORM-OPS | 2018-06-21 | 2019-07-26 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 17977 | Work Order Description - 17977 - PM | PM | 4 | 96159 | SCHD | NORM-OPS | 2018-06-21 | 2019-05-27 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 18279 | Work Order Description - 18279 - CM | CM | 3 | 534360 | SCHD | TPS | 2018-07-18 | 2019-08-17 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 18333 | Work Order Description - 18333 - CM | CM | 3 | 457370 | WPLAN | TPS | 2017-02-14 | 2020-11-07 | 2020-05-02 | 2020-05-13 | 3 | INTEGRITY | CONSTRUCTION | 224
2019-03-31 | 18376 | Work Order Description - 18376 - CM | CM | 4 | 48268 | SCHD | SYS-ISOL | 2018-10-29 | 2019-06-16 | 2019-07-19 | 2019-07-19 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 18393 | Work Order Description - 18393 - CM | CM | 4 | 652220 | WSCHD | NORM-OPS | 2016-11-12 | 2019-06-24 | 2019-04-06 | 2019-05-12 | 3 | MAINTENANCE | MECHANICAL | 902.5
2019-03-31 | 18498 | Work Order Description - 18498 - CM | CM | 4 | 457377 | WSCHD | NORM-OPS | 2016-11-12 | 2019-07-23 | 2019-10-01 | 2019-10-01 | 4 | MAINTENANCE | INSTRUMENTS | 3.5
2019-03-31 | 18504 | Work Order Description - 18504 - CM | CM | 4 | 481746 | SCHD | NORM-OPS | 2018-10-09 | 2019-07-01 | 2019-04-06 | 2019-04-06 | 4 | INTEGRITY | FABRIC | 0
2019-03-31 | 18505 | Work Order Description - 18505 - CM | CM | 4 | 481746 | SCHD | NORM-OPS | 2018-10-09 | 2019-07-01 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | FABRIC | 0
2019-03-31 | 18506 | Work Order Description - 18506 - CM | CM | 4 | 481746 | SCHD | NORM-OPS | 2018-10-09 | 2019-07-01 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | FABRIC | 0
2019-03-31 | 18509 | Work Order Description - 18509 - CM | CM | 4 | 481746 | SCHD | NORM-OPS | 2018-10-09 | 2019-07-01 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | FABRIC | 0
2019-03-31 | 18510 | Work Order Description - 18510 - CM | CM | 4 | 481746 | SCHD | NORM-OPS | 2018-10-09 | 2019-07-01 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | FABRIC | 0
2019-03-31 | 18511 | Work Order Description - 18511 - CM | CM | 4 | 481746 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-19 | 2020-02-29 | 2020-02-29 | 3 | INTEGRITY | FABRIC | 0
2019-03-31 | 18513 | Work Order Description - 18513 - CM | CM | 4 | 481746 | SCHD | NORM-OPS | 2018-12-24 | 2020-12-16 | 2020-02-29 | 2020-02-29 | 4 | INTEGRITY | FABRIC | 180
2019-03-31 | 18530 | Work Order Description - 18530 - CM | CM | 3 | 249423 | WSCHD | PACK-ISOL | 2016-11-15 | 2019-02-27 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 18624 | Work Order Description - 18624 - CM | CM | 4 | 636281 | WPLAN | NORM-OPS | 2016-12-26 | 2019-09-18 | 2020-02-01 | 2020-02-01 | 3 | INTEGRITY | FABRIC | 0
2019-03-31 | 18678 | Work Order Description - 18678 - CM | CM | 4 | 361980 | WSCHD | SYS-ISOL | 2016-11-12 | 2019-05-21 | 2019-06-01 | 2019-06-14 | 4 | MAINTENANCE | SERVICES | 392
2019-03-31 | 18732 | Work Order Description - 18732 - CM | CM | 3 | 556435 | SCHD | SYS-ISOL | 2018-09-06 | 2019-10-12 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 18738 | Work Order Description - 18738 - CM | CM | 3 | 322638 | WSCHD | TPS | 2018-06-15 | 2019-11-14 | 2020-05-02 | 2020-05-04 | 4 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 18740 | Work Order Description - 18740 - CM | CM | 3 | 33966 | WSCHD | TPS | 2018-06-15 | 2019-09-22 | 2020-05-02 | 2020-05-04 | 4 | MAINTENANCE | CONSTRUCTION | 27
2019-03-31 | 18749 | Work Order Description - 18749 - CM | CM | 4 | 501448 | SCHD | NORM-OPS | 2018-12-24 | 2019-12-18 | 2019-10-05 | 2019-10-05 | 3 | INTEGRITY | FABRIC | 55
2019-03-31 | 18750 | Work Order Description - 18750 - CM | CM | 4 | 501448 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-31 | 2019-06-01 | 2019-06-01 | 4 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 18752 | Work Order Description - 18752 - CM | CM | 4 | 659465 | SCHD | NORM-OPS | 2018-06-21 | 2019-12-19 | 2019-09-29 | 2019-10-03 | 3 | MAINTENANCE | MECHANICAL | 64
2019-03-31 | 18753 | Work Order Description - 18753 - CM | CM | 3 | 555571 | SCHD | SYS-ISOL | 2018-09-06 | 2019-07-14 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 18754 | Work Order Description - 18754 - CM | CM | 3 | 183857 | SCHD | SYS-ISOL | 2018-09-06 | 2019-03-21 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 18755 | Work Order Description - 18755 - CM | CM | 3 | 556434 | SCHD | SYS-ISOL | 2018-09-06 | 2019-05-15 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 18757 | Work Order Description - 18757 - CM | CM | 3 | 183854 | SCHD | SYS-ISOL | 2018-09-06 | 2019-12-26 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 18758 | Work Order Description - 18758 - CM | CM | 3 | 556436 | SCHD | SYS-ISOL | 2018-09-06 | 2019-10-13 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 18759 | Work Order Description - 18759 - CM | CM | 3 | 556437 | SCHD | SYS-ISOL | 2018-09-06 | 2019-04-30 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 18761 | Work Order Description - 18761 - CM | CM | 4 | 472798 | SCHD | NORM-OPS | 2018-12-24 | 2019-12-18 | 2020-02-29 | 2020-02-29 | 3 | INTEGRITY | FABRIC | 144
2019-03-31 | 18762 | Work Order Description - 18762 - CM | CM | 4 | 403920 | SCHD | NORM-OPS | 2018-12-24 | 2019-12-18 | 2019-06-29 | 2019-06-29 | 3 | INTEGRITY | FABRIC | 64
2019-03-31 | 18763 | Work Order Description - 18763 - CM | CM | 4 | 403920 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-19 | 2020-01-25 | 2020-01-25 | 3 | INTEGRITY | FABRIC | 96
2019-03-31 | 18856 | Work Order Description - 18856 - CM | CM | 4 | 361980 | WSCHD | NORM-OPS | 2016-11-14 | 2019-08-26 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | SERVICES | 7
2019-03-31 | 18870 | Work Order Description - 18870 - CM | CM | 3 | 501535 | SCHD | NORM-OPS | 2018-09-06 | 2019-06-10 | 2019-07-13 | 2019-07-13 | 3 | INTEGRITY | INSTRUMENTS | 16
2019-03-31 | 18890 | Work Order Description - 18890 - PSCM | PSCM | 1 | 399431 | WSCHD | NORM-OPS | 2016-11-14 | 2020-01-01 | 2021-03-06 | 2021-03-06 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 18990 | Work Order Description - 18990 - CM | CM | 4 | 481746 | WSCHD | NORM-OPS | 2019-03-25 | 2020-03-02 | 2020-02-29 | 2020-02-29 | 3 | INTEGRITY | CONSTRUCTION | 81
2019-03-31 | 19020 | Work Order Description - 19020 - PSPM | PSPM | 1 | 357578 | WSCHD | PACK-ISOL | 2017-07-21 | 2019-12-02 | 2019-12-28 | 2019-12-28 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 19153 | Work Order Description - 19153 - CM | CM | 3 | 462658 | SCHD | SYS-ISOL | 2018-05-31 | 2019-07-14 | 2019-07-13 | 2019-07-13 | 2 | INTEGRITY | INSTRUMENTS | 28
2019-03-31 | 19171 | Work Order Description - 19171 - CM | CM | 3 | 51802 | WSCHD | TPS | 2017-11-20 | 2019-09-28 | 2019-06-21 | 2019-06-23 | 2 | MAINTENANCE | CONSTRUCTION | 48
2019-03-31 | 19177 | Work Order Description - 19177 - CM | CM | 3 | 441723 | SCHD | SYS-ISOL | 2018-09-14 | 2019-11-11 | 2019-07-13 | 2019-07-29 | 3 | INTEGRITY | CONSTRUCTION | 189
2019-03-31 | 19186 | Work Order Description - 19186 - CM | CM | 3 | 475872 | SCHD | NORM-OPS | 2018-07-18 | 2018-12-19 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | ELECTRICAL | 58
2019-03-31 | 19196 | Work Order Description - 19196 - CM | CM | 3 | 363634 | WSCHD | NORM-OPS | 2018-09-07 | 2020-08-04 | 2019-04-06 | 2019-04-07 | 4 | INTEGRITY | FABRIC | 1
2019-03-31 | 19233 | Work Order Description - 19233 - PSCM | PSCM | 1 | 496963 | WSCHD | NORM-OPS | 2017-09-29 | 2019-04-01 | 2019-04-27 | 2019-04-29 | 3 | MAINTENANCE | INSTRUMENTS | 32
2019-03-31 | 19234 | Work Order Description - 19234 - PSCM | PSCM | 1 | 484907 | WSCHD | NORM-OPS | 2016-11-22 | 2019-07-01 | 2019-06-01 | 2019-06-03 | 3 | MAINTENANCE | INSTRUMENTS | 32
2019-03-31 | 19236 | Work Order Description - 19236 - PSCM | PSCM | 1 | 497291 | WSCHD | NORM-OPS | 2018-01-26 | 2019-09-01 | 2019-04-20 | 2019-04-22 | 3 | MAINTENANCE | INSTRUMENTS | 32
2019-03-31 | 19243 | Work Order Description - 19243 - PSCM | PSCM | 1 | 360939 | WSCHD | NORM-OPS | 2016-11-29 | 2020-04-24 | 2019-09-24 | 2019-09-24 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 19245 | Work Order Description - 19245 - CM | CM | 3 | 249416 | SCHD | TPS | 2019-03-01 | 2019-07-25 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | MECHANICAL | 24.5
2019-03-31 | 19246 | Work Order Description - 19246 - CM | CM | 4 | 245651 | WPLAN | TPS | 2017-07-26 | 2019-03-23 | 2019-04-27 | 2019-04-29 | 4 | MAINTENANCE | MECHANICAL | 23
2019-03-31 | 19247 | Work Order Description - 19247 - CM | CM | 4 | 249423 | WPLAN | TPS | 2017-07-26 | 2019-07-18 | 2019-04-27 | 2019-04-29 | 4 | MAINTENANCE | MECHANICAL | 23
2019-03-31 | 19256 | Work Order Description - 19256 - CM | CM | 4 | 499458 | WSCHD | NORM-OPS | 2018-06-08 | 2019-07-25 | 2020-05-03 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 19264 | Work Order Description - 19264 - CM | CM | 3 | 94406 | WSCHD | TPS | 2018-06-15 | 2019-01-24 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 19336 | Work Order Description - 19336 - PRJ | PRJ | 4 | 185355 | SCHD | NORM-OPS | 2018-07-18 | 2019-01-14 | 2020-03-07 | 2020-03-07 | 4 | MAINTENANCE | MECHANICAL | 0.5
2019-03-31 | 19337 | Work Order Description - 19337 - CM | CM | 4 | 25391 | SCHD | NORM-OPS | 2019-01-25 | 2019-12-18 | 2019-06-18 | 2019-06-18 | 3 | INTEGRITY | FABRIC | 56
2019-03-31 | 19339 | Work Order Description - 19339 - CM | CM | 4 | 215981 | SCHD | NORM-OPS | 2019-02-13 | 2021-02-06 | 2019-06-01 | 2019-06-01 | 4 | INTEGRITY | FABRIC | 124
2019-03-31 | 19348 | Work Order Description - 19348 - PM | PM | 4 | 54308 | SCHD | PACK-ISOL | 2019-03-26 | 2018-12-14 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 19350 | Work Order Description - 19350 - PM | PM | 3 | 360305 | SCHD | PACK-ISOL | 2019-03-26 | 2019-09-11 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 19600 | Work Order Description - 19600 - CM | CM | 1 | 228839 | SCHD | ON LINE | 2018-06-21 | 2019-06-13 | 2019-05-18 | 2019-06-15 | 4 | INTEGRITY | CONSTRUCTION | 609
2019-03-31 | 19671 | Work Order Description - 19671 - CM | CM | 2 | 376190 | SCHD | NORM-OPS | 2018-06-21 | 2019-04-07 | 2019-05-26 | 2019-05-27 | 3 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 19672 | Work Order Description - 19672 - CM | CM | 1 | 267673 | WSCHD | NORM-OPS | 2018-12-19 | 2019-06-01 | 2019-06-01 | 2019-06-01 | 4 | INTEGRITY | CONSTRUCTION | 6
2019-03-31 | 19681 | Work Order Description - 19681 - PRJ | PRJ | 4 | 316144 | WPLAN | NORM-OPS | 2019-03-26 | 2020-01-31 | 2019-12-22 | 2019-12-22 | 2 | ENGINEERING | CONSTRUCTION | 11
2019-03-31 | 19684 | Work Order Description - 19684 - CM | CM | 3 | 666097 | WSCHD | TPS | 2016-12-09 | 2019-01-30 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 19694 | Work Order Description - 19694 - CM | CM | 3 | 326771 | WSCHD | TPS | 2018-06-21 | 2019-03-25 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 19696 | Work Order Description - 19696 - CM | CM | 3 | 326772 | WSCHD | TPS | 2018-06-21 | 2019-12-05 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 19718 | Work Order Description - 19718 - PRJ | PRJ | 4 | 310224 | SCHD | NORM-OPS | 2018-07-06 | 2018-12-18 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | SUBSEA | 4
2019-03-31 | 19744 | Work Order Description - 19744 - PM | PM | 3 | 360355 | WSCHD | PACK-ISOL | 2016-11-28 | 2019-08-02 | 2019-09-30 | 2019-09-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 19829 | Work Order Description - 19829 - CM | CM | 4 | 408340 | WSCHD | NORM-OPS | 2017-06-22 | 2020-01-03 | 2019-05-25 | 2019-05-29 | 4 | OPERATIONS | OPERATIONS | 1
2019-03-31 | 19833 | Work Order Description - 19833 - CM | CM | 3 | 215021 | WSCHD | TPS | 2018-06-20 | 2019-10-06 | 2019-10-05 | 2019-10-05 | 3 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 19850 | Work Order Description - 19850 - CM | CM | 3 | 215038 | WSCHD | TPS | 2018-06-20 | 2019-03-21 | 2019-10-05 | 2019-10-05 | 3 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 19851 | Work Order Description - 19851 - CM | CM | 3 | 183627 | SCHD | NORM-OPS | 2018-03-05 | 2018-12-22 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 19913 | Work Order Description - 19913 - CM | CM | 2 | 218111 | SCHD | PACK-ISOL | 2019-01-09 | 2020-01-01 | 2019-08-03 | 2019-08-06 | 4 | WELLS | WELLS | 768
2019-03-31 | 19936 | Work Order Description - 19936 - CM | CM | 4 | 357103 | WSCHD | SYS-ISOL | 2016-12-05 | 2019-10-29 | 2019-06-24 | 2019-06-25 | 3 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 19975 | Work Order Description - 19975 - CM | CM | 4 | 216916 | SCHD | NORM-OPS | 2018-09-06 | 2019-07-03 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | MECHANICAL | 104
2019-03-31 | 19978 | Work Order Description - 19978 - CM | CM | 3 | 256333 | SCHD | NORM-OPS | 2018-07-06 | 2019-05-01 | 2020-03-07 | 2020-03-07 | 2 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 20377 | Work Order Description - 20377 - CM | CM | 3 | 485479 | WSCHD | NORM-OPS | 2016-12-05 | 2019-05-07 | 2019-05-25 | 2019-05-27 | 3 | MAINTENANCE | CONSTRUCTION | 16
2019-03-31 | 20378 | Work Order Description - 20378 - CM | CM | 3 | 485479 | WSCHD | NORM-OPS | 2016-12-05 | 2019-06-09 | 2019-05-25 | 2019-05-27 | 3 | MAINTENANCE | CONSTRUCTION | 20
2019-03-31 | 20379 | Work Order Description - 20379 - CM | CM | 3 | 485479 | WSCHD | NORM-OPS | 2016-12-05 | 2020-01-12 | 2019-05-25 | 2019-05-27 | 3 | MAINTENANCE | CONSTRUCTION | 20
2019-03-31 | 20380 | Work Order Description - 20380 - CM | CM | 3 | 485479 | WSCHD | NORM-OPS | 2016-12-05 | 2019-10-28 | 2019-05-25 | 2019-05-27 | 3 | MAINTENANCE | CONSTRUCTION | 14
2019-03-31 | 20382 | Work Order Description - 20382 - CM | CM | 3 | 485479 | WSCHD | NORM-OPS | 2016-12-05 | 2019-04-10 | 2019-05-25 | 2019-05-27 | 3 | MAINTENANCE | CONSTRUCTION | 14
2019-03-31 | 20383 | Work Order Description - 20383 - CM | CM | 3 | 485479 | WSCHD | NORM-OPS | 2016-12-05 | 2019-11-04 | 2019-05-25 | 2019-05-27 | 3 | MAINTENANCE | CONSTRUCTION | 16
2019-03-31 | 20404 | Work Order Description - 20404 - CM | CM | 4 | 357419 | WSCHD | NORM-OPS | 2017-07-21 | 2019-04-18 | 2020-05-02 | 2020-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 17
2019-03-31 | 20413 | Work Order Description - 20413 - CM | CM | 3 | 33911 | WSCHD | SYS-ISOL | 2016-12-05 | 2019-05-16 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 20414 | Work Order Description - 20414 - CM | CM | 3 | 33912 | WSCHD | SYS-ISOL | 2016-12-05 | 2019-03-29 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 20415 | Work Order Description - 20415 - CM | CM | 3 | 33913 | WSCHD | SYS-ISOL | 2016-12-05 | 2019-02-15 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 20416 | Work Order Description - 20416 - CM | CM | 3 | 322526 | WSCHD | SYS-ISOL | 2016-12-05 | 2019-09-07 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 20427 | Work Order Description - 20427 - CM | CM | 4 | 403880 | WSCHD | NORM-OPS | 2019-03-25 | 2020-01-31 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | CONSTRUCTION | 82
2019-03-31 | 20452 | Work Order Description - 20452 - PSCM | PSCM | 1 | 520216 | WSCHD | NORM-OPS | 2016-12-23 | 2020-01-06 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 20518 | Work Order Description - 20518 - CM | CM | 3 | 33873 | WPLAN | TPS | 2017-07-26 | 2019-12-24 | 2020-05-02 | 2020-05-04 | 3 | MAINTENANCE | MECHANICAL | 44
2019-03-31 | 20535 | Work Order Description - 20535 - CM | CM | 3 | 33874 | WSCHD | TPS | 2016-12-09 | 2020-01-15 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 20536 | Work Order Description - 20536 - CM | CM | 4 | 322411 | WSCHD | SYS-ISOL | 2016-12-09 | 2019-02-07 | 2020-12-01 | 2020-12-04 | 3 | MAINTENANCE | MECHANICAL | 39
2019-03-31 | 20538 | Work Order Description - 20538 - CM | CM | 3 | 33875 | WSCHD | NORM-OPS | 2016-12-09 | 2019-01-05 | 2020-12-01 | 2020-12-02 | 3 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 20634 | Work Order Description - 20634 - CM | CM | 3 | 481607 | SCHD | TPS | 2018-09-06 | 2019-01-28 | 2020-02-01 | 2020-02-01 | 2 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 20635 | Work Order Description - 20635 - CM | CM | 3 | 535347 | SCHD | NORM-OPS | 2018-09-06 | 2019-11-16 | 2019-09-14 | 2019-09-14 | 3 | MAINTENANCE | MECHANICAL | 56
2019-03-31 | 20638 | Work Order Description - 20638 - CM | CM | 3 | 501025 | WSCHD | TPS | 2018-06-08 | 2019-08-01 | 2020-05-03 | 2020-05-05 | 3 | MAINTENANCE | CONSTRUCTION | 42
2019-03-31 | 20641 | Work Order Description - 20641 - CM | CM | 3 | 327482 | WSCHD | TPS | 2018-06-08 | 2019-11-05 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | CONSTRUCTION | 34
2019-03-31 | 20716 | Work Order Description - 20716 - CM | CM | 4 | 204611 | WPLAN | NORM-OPS | 2016-12-25 | 2020-01-13 | 2019-05-04 | 2019-05-05 | 4 | INTEGRITY | CONSTRUCTION | 4
2019-03-31 | 20717 | Work Order Description - 20717 - PRJ | PRJ | 4 | 368329 | WSCHD | NORM-OPS | 2017-07-21 | 2021-01-01 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 20734 | Work Order Description - 20734 - CM | CM | 3 | 122886 | WSCHD | TPS | 2016-12-28 | 2019-02-09 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 20735 | Work Order Description - 20735 - CM | CM | 3 | 438252 | WSCHD | TPS | 2016-12-28 | 2019-05-04 | 2020-05-02 | 2020-05-04 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 20736 | Work Order Description - 20736 - CM | CM | 3 | 438442 | WSCHD | TPS | 2016-12-28 | 2019-10-16 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 20737 | Work Order Description - 20737 - CM | CM | 3 | 489753 | WSCHD | TPS | 2016-12-28 | 2019-04-02 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | CONSTRUCTION | 22
2019-03-31 | 20745 | Work Order Description - 20745 - CM | CM | 4 | 183628 | SCHD | TPS | 2018-05-30 | 2020-01-23 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 20748 | Work Order Description - 20748 - CM | CM | 3 | 490516 | WSCHD | TPS | 2016-12-28 | 2019-03-08 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 20773 | Work Order Description - 20773 - CM | CM | 4 | 76033 | WPLAN | SUBSYS-ISOL | 2016-12-18 | 2019-02-13 | 2019-07-13 | 2019-07-27 | 4 | INTEGRITY | CONSTRUCTION | 496
2019-03-31 | 20789 | Work Order Description - 20789 - CM | CM | 3 | 534326 | SCHD | NORM-OPS | 2018-09-06 | 2018-12-23 | 2019-09-28 | 2019-09-28 | 2 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 20790 | Work Order Description - 20790 - CM | CM | 3 | 29094 | SCHD | NORM-OPS | 2018-07-06 | 2019-04-06 | 2019-09-28 | 2019-09-28 | 2 | MAINTENANCE | INSTRUMENTS | 39
2019-03-31 | 20795 | Work Order Description - 20795 - CM | CM | 2 | 265766 | SCHD | NORM-OPS | 2018-09-06 | 2019-04-03 | 2019-06-29 | 2019-06-29 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 20956 | Work Order Description - 20956 - PSPM | PSPM | 1 | 360700 | WSCHD | EQUIP-ISOL | 2017-07-21 | 2020-08-01 | 2020-05-02 | 2020-05-02 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 20957 | Work Order Description - 20957 - PSPM | PSPM | 1 | 305225 | WSCHD | EQUIP-ISOL | 2016-12-14 | 2019-09-01 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 20958 | Work Order Description - 20958 - PSPM | PSPM | 1 | 360702 | WSCHD | EQUIP-ISOL | 2018-08-17 | 2019-09-01 | 2019-05-20 | 2019-05-20 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 20976 | Work Order Description - 20976 - PM | PM | 3 | 326116 | SCHD | EQUIP-ISOL | 2019-03-22 | 2019-08-02 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 20977 | Work Order Description - 20977 - PSPM | PSPM | 1 | 326088 | WSCHD | EQUIP-ISOL | 2016-12-14 | 2020-08-01 | 2020-05-02 | 2020-05-02 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 20978 | Work Order Description - 20978 - PSPM | PSPM | 1 | 305204 | WSCHD | EQUIP-ISOL | 2016-12-14 | 2020-08-01 | 2020-03-07 | 2020-03-07 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 21015 | Work Order Description - 21015 - CM | CM | 3 | 484754 | WSCHD | SYS-ISOL | 2016-12-19 | 2019-07-25 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 21224 | Work Order Description - 21224 - PM | PM | 2 | 402622 | SCHD | SYS-ISOL | 2018-07-06 | 2019-05-12 | 2019-05-04 | 2019-05-04 | 2 | INTEGRITY | INSTRUMENTS | 14
2019-03-31 | 21231 | Work Order Description - 21231 - PM | PM | 4 | 315661 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-02-08 | 2020-01-10 | 2020-01-10 | 3 | DRILLING | DRILLING | 60
2019-03-31 | 21334 | Work Order Description - 21334 - CM | CM | 4 | 481746 | SCHD | NORM-OPS | 2018-09-06 | 2019-10-21 | 2019-02-09 | 2019-02-09 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 21360 | Work Order Description - 21360 - CM | CM | 4 | 122680 | SCHD | NORM-OPS | 2018-07-18 | 2019-07-28 | 2019-10-12 | 2019-10-12 | 4 | INTEGRITY | SERVICES | 108
2019-03-31 | 21377 | Work Order Description - 21377 - CM | CM | 3 | 499274 | SCHD | NORM-OPS | 2018-06-21 | 2019-12-20 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 21422 | Work Order Description - 21422 - CM | CM | 3 | 17814 | WSCHD | NORM-OPS | 2018-04-06 | 2020-01-13 | 2019-05-04 | 2019-05-06 | 4 | INTEGRITY | CONSTRUCTION | 16
2019-03-31 | 21501 | Work Order Description - 21501 - CM | CM | 3 | 465048 | SCHD | NORM-OPS | 2018-09-06 | 2019-01-27 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 21502 | Work Order Description - 21502 - CM | CM | 3 | 21464 | SCHD | TPS | 2018-09-06 | 2019-06-21 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 21573 | Work Order Description - 21573 - CM | CM | 3 | 531824 | WSCHD | NORM-OPS | 2016-12-31 | 2019-01-17 | 2019-06-01 | 2019-06-09 | 2 | INTEGRITY | ELECTRICAL | 84
2019-03-31 | 21575 | Work Order Description - 21575 - CM | CM | 3 | 484910 | WSCHD | NORM-OPS | 2016-12-31 | 2019-10-09 | 2019-06-01 | 2019-06-09 | 2 | MAINTENANCE | ELECTRICAL | 84
2019-03-31 | 21576 | Work Order Description - 21576 - CM | CM | 3 | 484909 | WSCHD | NORM-OPS | 2016-12-31 | 2019-11-22 | 2019-06-01 | 2019-06-09 | 2 | MAINTENANCE | ELECTRICAL | 84
2019-03-31 | 21619 | Work Order Description - 21619 - CM | CM | 4 | 399614 | WSCHD | SYS-ISOL | 2016-12-26 | 2018-12-18 | 2020-05-02 | 2020-05-04 | 4 | MAINTENANCE | CONSTRUCTION | 36
2019-03-31 | 21620 | Work Order Description - 21620 - PSCM | PSCM | 1 | 400608 | SCHD | PACK-ISOL | 2018-12-18 | 2019-06-20 | 2019-08-10 | 2019-08-10 | 4 | MAINTENANCE | WELLS | 36
2019-03-31 | 21621 | Work Order Description - 21621 - CM | CM | 4 | 401822 | SCHD | PACK-ISOL | 2018-09-06 | 2019-07-23 | 2019-08-10 | 2019-08-10 | 4 | WELLS | WELLS | 20
2019-03-31 | 21622 | Work Order Description - 21622 - CM | CM | 4 | 579624 | SCHD | PACK-ISOL | 2018-09-06 | 2019-01-14 | 2019-09-07 | 2019-09-07 | 4 | WELLS | WELLS | 18
2019-03-31 | 21629 | Work Order Description - 21629 - CM | CM | 4 | 401865 | SCHD | PACK-ISOL | 2018-09-06 | 2019-10-14 | 2019-10-26 | 2019-10-26 | 4 | WELLS | WELLS | 20
2019-03-31 | 21630 | Work Order Description - 21630 - CM | CM | 4 | 482341 | SCHD | PACK-ISOL | 2018-09-06 | 2020-01-16 | 2019-09-07 | 2019-09-07 | 4 | WELLS | WELLS | 19
2019-03-31 | 21785 | Work Order Description - 21785 - CM | CM | 3 | 309987 | SCHD | NORM-OPS | 2018-07-06 | 2019-12-29 | 2019-10-26 | 2019-10-26 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 21787 | Work Order Description - 21787 - CM | CM | 4 | 569010 | WSCHD | NORM-OPS | 2019-03-25 | 2020-01-30 | 2019-11-30 | 2019-11-30 | 2 | INTEGRITY | CONSTRUCTION | 144
2019-03-31 | 21788 | Work Order Description - 21788 - CM | CM | 4 | 472493 | WSCHD | NORM-OPS | 2019-03-25 | 2020-01-30 | 2019-11-30 | 2019-11-30 | 4 | INTEGRITY | CONSTRUCTION | 144
2019-03-31 | 21794 | Work Order Description - 21794 - CM | CM | 3 | 307837 | WSCHD | NORM-OPS | 2016-12-29 | 2019-07-21 | 2020-05-02 | 2020-05-04 | 4 | MAINTENANCE | MECHANICAL | 35
2019-03-31 | 21798 | Work Order Description - 21798 - CM | CM | 3 | 307838 | WSCHD | NORM-OPS | 2016-12-29 | 2019-12-31 | 2020-05-02 | 2020-05-05 | 4 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 21813 | Work Order Description - 21813 - CM | CM | 3 | 549452 | SCHD | TPS | 2018-07-06 | 2019-08-08 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 21827 | Work Order Description - 21827 - CM | CM | 3 | 418146 | SCHD | NORM-OPS | 2018-11-15 | 2019-03-26 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | CONSTRUCTION | 14
2019-03-31 | 21828 | Work Order Description - 21828 - CM | CM | 3 | 418147 | SCHD | NORM-OPS | 2018-11-15 | 2019-02-15 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | CONSTRUCTION | 14
2019-03-31 | 21850 | Work Order Description - 21850 - CM | CM | 3 | 555285 | SCHD | NORM-OPS | 2018-09-06 | 2019-05-15 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | MECHANICAL | 35
2019-03-31 | 21928 | Work Order Description - 21928 - CM | CM | 4 | 20520 | SCHD | NORM-OPS | 2019-03-13 | 2020-03-10 | 2020-02-29 | 2020-02-29 | 3 | INTEGRITY | FABRIC | 40
2019-03-31 | 21947 | Work Order Description - 21947 - PM | PM | 4 | 547429 | WSCHD | EQUIP-ISOL | 2017-02-10 | 2019-04-21 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | SERVICES | 7
2019-03-31 | 21955 | Work Order Description - 21955 - PM | PM | 4 | 408340 | SCHD | PACK-ISOL | 2019-03-11 | 2019-07-10 | 2019-04-06 | 2019-04-07 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 21960 | Work Order Description - 21960 - PSPM | PSPM | 1 | 248578 | WSCHD | EQUIP-ISOL | 2017-01-04 | 2020-08-01 | 2020-05-02 | 2020-05-02 | 1 | INTEGRITY | CONSTRUCTION | 11
2019-03-31 | 21965 | Work Order Description - 21965 - PSPM | PSPM | 1 | 57930 | WSCHD | EQUIP-ISOL | 2017-01-04 | 2019-09-01 | 2019-04-27 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 47
2019-03-31 | 22102 | Work Order Description - 22102 - CM | CM | 4 | 567118 | SCHD | NORM-OPS | 2019-01-22 | 2020-01-18 | 2020-02-01 | 2020-02-01 | 3 | INTEGRITY | FABRIC | 30
2019-03-31 | 22121 | Work Order Description - 22121 - PSPM | PSPM | 1 | 305202 | WSCHD | EQUIP-ISOL | 2017-01-04 | 2019-08-01 | 2019-07-06 | 2019-07-06 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 22122 | Work Order Description - 22122 - PSPM | PSPM | 1 | 326118 | WSCHD | EQUIP-ISOL | 2017-01-04 | 2019-08-01 | 2019-07-06 | 2019-07-06 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 22124 | Work Order Description - 22124 - PSPM | PSPM | 1 | 305228 | WSCHD | EQUIP-ISOL | 2017-01-04 | 2019-08-01 | 2020-05-02 | 2020-05-02 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 22418 | Work Order Description - 22418 - CM | CM | 4 | 410400 | WSCHD | PACK-ISOL | 2017-07-19 | 2020-01-01 | 2020-05-02 | 2020-05-07 | 3 | MAINTENANCE | MECHANICAL | 44
2019-03-31 | 22427 | Work Order Description - 22427 - CM | CM | 3 | 360946 | WSCHD | PACK-ISOL | 2017-01-21 | 2019-02-28 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 22473 | Work Order Description - 22473 - PM | PM | 4 | 59425 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-02-12 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | INSTRUMENTS | 5
2019-03-31 | 22474 | Work Order Description - 22474 - PM | PM | 2 | 20523 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-12-23 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 22476 | Work Order Description - 22476 - PM | PM | 3 | 258358 | SCHD | EQUIP-ISOL | 2018-05-24 | 2019-08-03 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 22501 | Work Order Description - 22501 - PM | PM | 4 | 262750 | SCHD | NORM-OPS | 2018-09-06 | 2019-02-01 | 2020-01-25 | 2020-01-25 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 22539 | Work Order Description - 22539 - CM | CM | 4 | 312683 | SCHD | NORM-OPS | 2018-07-06 | 2019-05-06 | 2020-02-01 | 2020-02-01 | 3 | MAINTENANCE | MECHANICAL | 86
2019-03-31 | 22552 | Work Order Description - 22552 - CM | CM | 3 | 226420 | WSCHD | NORM-OPS | 2017-01-17 | 2019-06-17 | 2020-04-04 | 2020-04-06 | 4 | MAINTENANCE | MECHANICAL | 31
2019-03-31 | 22594 | Work Order Description - 22594 - PM | PM | 3 | 355624 | WSCHD | EQUIP-ISOL | 2017-01-05 | 2020-04-10 | 2019-06-01 | 2019-06-19 | 3 | MAINTENANCE | ELECTRICAL | 273
2019-03-31 | 22595 | Work Order Description - 22595 - PM | PM | 3 | 666382 | WSCHD | EQUIP-ISOL | 2017-01-05 | 2020-03-17 | 2019-10-06 | 2019-10-06 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 22598 | Work Order Description - 22598 - CM | CM | 2 | 375680 | SCHD | NORM-OPS | 2018-06-21 | 2019-07-03 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 22910 | Work Order Description - 22910 - CM | CM | 4 | 448640 | SCHD | NORM-OPS | 2018-06-21 | 2019-01-03 | 2019-04-20 | 2019-04-21 | 3 | DRILLING | DRILLING | 36
2019-03-31 | 22960 | Work Order Description - 22960 - PSPM | PSPM | 1 | 361201 | WSCHD | EQUIP-ISOL | 2018-06-25 | 2019-09-01 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 22967 | Work Order Description - 22967 - PSPM | PSPM | 1 | 363635 | SCHD | NORM-OPS | 2018-10-29 | 2019-11-10 | 2019-04-27 | 2019-04-28 | 2 | INTEGRITY | INSPECTION | 1
2019-03-31 | 22982 | Work Order Description - 22982 - CM | CM | 3 | 392102 | WMATL | PACK-ISOL | 2017-11-13 | 2019-07-14 | 2019-07-13 | 2019-07-15 | 3 | MAINTENANCE | MECHANICAL | 37
2019-03-31 | 22987 | Work Order Description - 22987 - CM | CM | 3 | 327255 | WSCHD | TPS | 2017-01-09 | 2019-11-17 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | CONSTRUCTION | 22
2019-03-31 | 22988 | Work Order Description - 22988 - CM | CM | 3 | 503347 | WSCHD | TPS | 2017-01-09 | 2020-01-10 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | CONSTRUCTION | 22
2019-03-31 | 22989 | Work Order Description - 22989 - CM | CM | 3 | 33858 | WSCHD | TPS | 2017-01-09 | 2019-10-07 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | CONSTRUCTION | 22
2019-03-31 | 22990 | Work Order Description - 22990 - CM | CM | 3 | 327256 | WSCHD | TPS | 2017-01-09 | 2019-08-07 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | CONSTRUCTION | 22
2019-03-31 | 23008 | Work Order Description - 23008 - CM | CM | 4 | 567119 | SCHD | NORM-OPS | 2019-01-25 | 2020-01-08 | 2019-07-09 | 2019-07-09 | 3 | INTEGRITY | FABRIC | 300
2019-03-31 | 23209 | Work Order Description - 23209 - CM | CM | 4 | 462436 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-08 | 2019-08-31 | 2019-08-31 | 2 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 23247 | Work Order Description - 23247 - PM | PM | 4 | 472269 | SCHD | NORM-OPS | 2018-04-07 | 2019-06-01 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | SERVICES | 105
2019-03-31 | 23288 | Work Order Description - 23288 - CM | CM | 3 | 671275 | WSCHD | NORM-OPS | 2017-01-14 | 2019-10-23 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 23314 | Work Order Description - 23314 - PSPM | PSPM | 1 | 531789 | WSCHD | SUBSYS-ISOL | 2017-10-16 | 2020-08-01 | 2020-05-03 | 2020-05-03 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 23315 | Work Order Description - 23315 - PSPM | PSPM | 1 | 363615 | WSCHD | TPS | 2018-06-13 | 2020-07-31 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 23367 | Work Order Description - 23367 - CM | CM | 4 | 448593 | SCHD | NORM-OPS | 2018-06-21 | 2019-08-07 | 2019-04-06 | 2019-04-21 | 2 | DRILLING | DRILLING | 112
2019-03-31 | 23372 | Work Order Description - 23372 - CM | CM | 3 | 126954 | SCHD | SYS-ISOL | 2018-06-21 | 2019-03-28 | 2019-07-13 | 2019-07-23 | 4 | MAINTENANCE | MECHANICAL | 72
2019-03-31 | 23469 | Work Order Description - 23469 - CM | CM | 3 | 74956 | WPLAN | TPS | 2018-12-17 | 2019-12-07 | 2019-07-13 | 2019-07-13 | 4 | INTEGRITY | CONSTRUCTION | 21
2019-03-31 | 23649 | Work Order Description - 23649 - CM | CM | 2 | 652244 | WSCHD | NORM-OPS | 2017-06-23 | 2019-07-01 | 2019-12-28 | 2019-12-31 | 3 | MAINTENANCE | MECHANICAL | 58
2019-03-31 | 23770 | Work Order Description - 23770 - CM | CM | 4 | 387912 | WPLAN | NORM-OPS | 2017-03-02 | 2019-02-08 | 2019-05-05 | 2019-05-08 | 3 | MAINTENANCE | CONSTRUCTION | 77
2019-03-31 | 23941 | Work Order Description - 23941 - CM | CM | 2 | 671735 | WSCHD | NORM-OPS | 2017-12-01 | 2019-11-19 | 2019-05-18 | 2019-05-25 | 4 | MAINTENANCE | MECHANICAL | 83.5
2019-03-31 | 23958 | Work Order Description - 23958 - CM | CM | 2 | 671736 | WSCHD | NORM-OPS | 2017-09-08 | 2019-09-28 | 2019-05-11 | 2019-05-18 | 4 | MAINTENANCE | MECHANICAL | 83.5
2019-03-31 | 23972 | Work Order Description - 23972 - CM | CM | 2 | 308685 | WSCHD | NORM-OPS | 2017-12-01 | 2019-07-09 | 2019-05-11 | 2019-05-18 | 4 | MAINTENANCE | MECHANICAL | 79
2019-03-31 | 23974 | Work Order Description - 23974 - CM | CM | 2 | 308709 | WSCHD | NORM-OPS | 2017-03-20 | 2018-12-17 | 2019-05-11 | 2019-05-18 | 4 | MAINTENANCE | MECHANICAL | 78
2019-03-31 | 23992 | Work Order Description - 23992 - PRJ | PRJ | 4 | 216022 | SCHD | NORM-OPS | 2018-07-18 | 2019-05-22 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 23996 | Work Order Description - 23996 - CM | CM | 2 | 308710 | WSCHD | NORM-OPS | 2017-12-01 | 2019-10-21 | 2019-05-11 | 2019-06-29 | 4 | MAINTENANCE | MECHANICAL | 79.5
2019-03-31 | 24018 | Work Order Description - 24018 - CM | CM | 2 | 674975 | WSCHD | NORM-OPS | 2017-09-08 | 2019-11-30 | 2019-05-11 | 2019-05-18 | 4 | MAINTENANCE | MECHANICAL | 79.5
2019-03-31 | 24085 | Work Order Description - 24085 - PM | PM | 4 | 25405 | SCHD | NORM-OPS | 2018-09-06 | 2019-09-14 | 2020-04-04 | 2020-04-04 | 2 | INTEGRITY | INSPECTION | 3
2019-03-31 | 24092 | Work Order Description - 24092 - CM | CM | 2 | 652244 | WSCHD | NORM-OPS | 2017-01-24 | 2019-07-01 | 2019-09-28 | 2019-09-30 | 3 | MAINTENANCE | SERVICES | 63
2019-03-31 | 24101 | Work Order Description - 24101 - CM | CM | 3 | 249026 | WSCHD | NORM-OPS | 2017-07-21 | 2019-06-24 | 2019-04-13 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 24109 | Work Order Description - 24109 - CM | CM | 3 | 491978 | SCHD | SYS-ISOL | 2018-07-18 | 2019-03-20 | 2019-06-29 | 2019-06-29 | 2 | MAINTENANCE | MECHANICAL | 34
2019-03-31 | 24110 | Work Order Description - 24110 - CM | CM | 3 | 487529 | SCHD | SYS-ISOL | 2018-07-18 | 2019-08-23 | 2019-06-29 | 2019-06-29 | 2 | MAINTENANCE | MECHANICAL | 34
2019-03-31 | 24115 | Work Order Description - 24115 - CM | CM | 3 | 357132 | WSCHD | PACK-ISOL | 2017-11-20 | 2019-12-02 | 2020-05-02 | 2020-05-04 | 2 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 24146 | Work Order Description - 24146 - CM | CM | 4 | 370154 | WSCHD | NORM-OPS | 2017-01-28 | 2019-12-13 | 2019-04-27 | 2019-04-30 | 4 | INTEGRITY | SERVICES | 70
2019-03-31 | 24263 | Work Order Description - 24263 - CM | CM | 4 | 370154 | WSCHD | NORM-OPS | 2017-01-28 | 2019-04-21 | 2019-04-27 | 2019-04-29 | 4 | INTEGRITY | SERVICES | 54
2019-03-31 | 24509 | Work Order Description - 24509 - CM | CM | 4 | 237406 | SCHD | NORM-OPS | 2019-03-06 | 2020-02-14 | 2019-08-15 | 2019-09-05 | 3 | INTEGRITY | FABRIC | 450
2019-03-31 | 24574 | Work Order Description - 24574 - CM | CM | 3 | 215043 | WSCHD | NORM-OPS | 2017-01-27 | 2019-07-11 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 24575 | Work Order Description - 24575 - CM | CM | 3 | 247863 | WSCHD | NORM-OPS | 2017-01-27 | 2019-11-09 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 24576 | Work Order Description - 24576 - CM | CM | 3 | 494195 | WSCHD | NORM-OPS | 2017-07-21 | 2019-08-07 | 2019-08-31 | 2019-08-31 | 4 | MAINTENANCE | CONSTRUCTION | 14
2019-03-31 | 24600 | Work Order Description - 24600 - CM | CM | 2 | 20523 | SCHD | TPS | 2018-09-06 | 2019-01-19 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 24626 | Work Order Description - 24626 - CM | CM | 3 | 404664 | WSCHD | NORM-OPS | 2017-01-30 | 2019-11-01 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | MECHANICAL | 34
2019-03-31 | 24825 | Work Order Description - 24825 - CM | CM | 3 | 666240 | WSCHD | TPS | 2018-06-07 | 2019-12-28 | 2020-05-03 | 2020-05-05 | 3 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 24832 | Work Order Description - 24832 - CM | CM | 1 | 378847 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-01 | 2019-05-05 | 2019-05-17 | 3 | INTEGRITY | CONSTRUCTION | 237
2019-03-31 | 24847 | Work Order Description - 24847 - PRJ | PRJ | 4 | 650444 | WSCHD | NORM-OPS | 2017-07-21 | 2018-12-14 | 2019-09-15 | 2019-09-16 | 4 | OPERATIONS | OPERATIONS | 8
2019-03-31 | 24898 | Work Order Description - 24898 - CM | CM | 4 | 124571 | WPLAN | ON LINE | 2017-03-03 | 2019-06-02 | 2019-09-08 | 2019-09-08 | 3 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 24902 | Work Order Description - 24902 - CM | CM | 4 | 124570 | WPLAN | ON LINE | 2017-03-03 | 2018-12-30 | 2019-09-08 | 2019-09-08 | 3 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 24903 | Work Order Description - 24903 - CM | CM | 4 | 124572 | WPLAN | ON LINE | 2017-03-03 | 2019-04-07 | 2019-09-08 | 2019-09-08 | 3 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 24909 | Work Order Description - 24909 - BR | BR | 3 | 580004 | WPLAN | TPS | 2017-02-14 | 2020-01-16 | 2020-05-02 | 2020-05-02 | 3 | WELLS | CONSTRUCTION | 0
2019-03-31 | 24910 | Work Order Description - 24910 - CM | CM | 3 | 666233 | WSCHD | TPS | 2018-06-07 | 2019-01-08 | 2020-05-03 | 2020-05-04 | 3 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 24911 | Work Order Description - 24911 - CM | CM | 3 | 245924 | WSCHD | TPS | 2018-06-07 | 2019-10-09 | 2020-05-03 | 2020-05-04 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 24918 | Work Order Description - 24918 - CM | CM | 4 | 80482 | WPLAN | NORM-OPS | 2017-03-03 | 2019-09-19 | 2019-09-08 | 2019-09-08 | 3 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 24934 | Work Order Description - 24934 - BR | BR | 3 | 498644 | WPLAN | TPS | 2017-02-14 | 2019-01-31 | 2020-05-02 | 2020-05-02 | 3 | WELLS | CONSTRUCTION | 0
2019-03-31 | 24943 | Work Order Description - 24943 - CM | CM | 4 | 253213 | SCHD | NORM-OPS | 2018-09-06 | 2019-04-14 | 2020-03-28 | 2020-03-28 | 3 | MAINTENANCE | SERVICES | 2
2019-03-31 | 24966 | Work Order Description - 24966 - CM | CM | 4 | 656284 | WPLAN | PACK-ISOL | 2017-06-06 | 2020-04-09 | 2019-08-31 | 2019-09-02 | 4 | INTEGRITY | CONSTRUCTION | 21
2019-03-31 | 24969 | Work Order Description - 24969 - CM | CM | 4 | 545222 | WSCHD | NORM-OPS | 2017-02-05 | 2019-03-10 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | SERVICES | 27
2019-03-31 | 24970 | Work Order Description - 24970 - CM | CM | 4 | 545222 | WSCHD | NORM-OPS | 2017-02-05 | 2019-11-23 | 2019-10-05 | 2019-10-11 | 4 | MAINTENANCE | OPERATIONS | 16
2019-03-31 | 25128 | Work Order Description - 25128 - CM | CM | 4 | 323649 | SCHD | TPS | 2018-09-06 | 2019-05-31 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 69
2019-03-31 | 25345 | Work Order Description - 25345 - PM | PM | 4 | 666746 | WSCHD | EQUIP-ISOL | 2017-02-10 | 2019-06-20 | 2020-05-02 | 2020-05-02 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 25346 | Work Order Description - 25346 - PM | PM | 4 | 406323 | WSCHD | TPS | 2017-02-10 | 2020-01-07 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | ELECTRICAL | 28
2019-03-31 | 25347 | Work Order Description - 25347 - PM | PM | 4 | 406324 | WSCHD | TPS | 2017-02-10 | 2019-10-15 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | ELECTRICAL | 28
2019-03-31 | 25361 | Work Order Description - 25361 - PM | PM | 4 | 671640 | WSCHD | EQUIP-ISOL | 2017-02-01 | 2019-03-05 | 2019-04-20 | 2019-04-21 | 2 | MAINTENANCE | ELECTRICAL | 23
2019-03-31 | 25407 | Work Order Description - 25407 - PSPM | PSPM | 1 | 360699 | WSCHD | EQUIP-ISOL | 2017-02-01 | 2020-08-01 | 2019-07-06 | 2019-07-06 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 25408 | Work Order Description - 25408 - PSPM | PSPM | 1 | 360701 | WSCHD | EQUIP-ISOL | 2018-10-16 | 2020-06-01 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 25410 | Work Order Description - 25410 - PSPM | PSPM | 1 | 326119 | WSCHD | EQUIP-ISOL | 2017-02-01 | 2020-08-01 | 2020-03-14 | 2020-03-14 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 25411 | Work Order Description - 25411 - PSPM | PSPM | 1 | 326120 | WSCHD | EQUIP-ISOL | 2017-02-01 | 2020-07-01 | 2019-07-06 | 2019-07-06 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 26000 | Work Order Description - 26000 - CM | CM | 4 | 500884 | WSCHD | TPS | 2018-09-23 | 2019-09-16 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | CONSTRUCTION | 26
2019-03-31 | 26046 | Work Order Description - 26046 - CM | CM | 3 | 244135 | WSCHD | NORM-OPS | 2017-02-07 | 2019-03-24 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 26057 | Work Order Description - 26057 - CM | CM | 3 | 527503 | WPLAN | NORM-OPS | 2017-07-14 | 2019-07-30 | 2019-07-13 | 2019-07-15 | 3 | INTEGRITY | CONSTRUCTION | 48
2019-03-31 | 26063 | Work Order Description - 26063 - CM | CM | 2 | 74997 | SCHD | SYS-ISOL | 2018-06-21 | 2019-06-16 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 26208 | Work Order Description - 26208 - PSCM | PSCM | 1 | 547833 | WSCHD | NORM-OPS | 2017-07-21 | 2020-01-04 | 2019-10-26 | 2019-10-26 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 26210 | Work Order Description - 26210 - PSCM | PSCM | 1 | 399654 | WSCHD | NORM-OPS | 2017-07-21 | 2019-05-30 | 2019-10-26 | 2019-10-26 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 26211 | Work Order Description - 26211 - PSCM | PSCM | 1 | 531571 | WSCHD | NORM-OPS | 2017-07-21 | 2020-01-01 | 2019-10-26 | 2019-10-26 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 26212 | Work Order Description - 26212 - PSCM | PSCM | 1 | 531573 | WSCHD | NORM-OPS | 2017-07-21 | 2019-07-10 | 2019-10-26 | 2019-10-26 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 26217 | Work Order Description - 26217 - CM | CM | 2 | 308682 | WSCHD | NORM-OPS | 2017-12-01 | 2019-05-29 | 2019-05-11 | 2019-05-17 | 4 | MAINTENANCE | MECHANICAL | 54.25
2019-03-31 | 26218 | Work Order Description - 26218 - CM | CM | 2 | 671761 | WSCHD | NORM-OPS | 2017-03-20 | 2019-12-20 | 2019-05-11 | 2019-05-17 | 4 | MAINTENANCE | MECHANICAL | 76.5
2019-03-31 | 26362 | Work Order Description - 26362 - CM | CM | 3 | 308532 | WPLAN | SUBSYS-ISOL | 2017-06-06 | 2019-10-20 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | CONSTRUCTION | 14
2019-03-31 | 26363 | Work Order Description - 26363 - CM | CM | 4 | 501146 | SCHD | TPS | 2018-05-24 | 2019-06-27 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 26365 | Work Order Description - 26365 - CM | CM | 3 | 215015 | WSCHD | TPS | 2017-05-09 | 2019-08-10 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 26386 | Work Order Description - 26386 - CM | CM | 3 | 247784 | WSCHD | TPS | 2017-05-09 | 2019-08-10 | 2019-07-06 | 2019-07-06 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 26421 | Work Order Description - 26421 - CM | CM | 4 | 495423 | WSCHD | TPS | 2017-05-09 | 2019-08-10 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 26426 | Work Order Description - 26426 - CM | CM | 3 | 495424 | WSCHD | TPS | 2017-05-09 | 2019-08-10 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 26577 | Work Order Description - 26577 - CM | CM | 4 | 501441 | WSCHD | NORM-OPS | 2019-03-25 | 2019-12-31 | 2020-04-11 | 2020-04-11 | 2 | INTEGRITY | CONSTRUCTION | 21
2019-03-31 | 26598 | Work Order Description - 26598 - CM | CM | 2 | 321115 | WSCHD | NORM-OPS | 2017-02-12 | 2019-05-12 | 2019-06-29 | 2019-06-30 | 3 | MAINTENANCE | MECHANICAL | 46.5
2019-03-31 | 26615 | Work Order Description - 26615 - CM | CM | 4 | 670453 | SCHD | TPS | 2019-01-21 | 2019-07-12 | 2019-07-13 | 2019-07-17 | 3 | MAINTENANCE | MECHANICAL | 43.5
2019-03-31 | 26931 | Work Order Description - 26931 - CM | CM | 4 | 238124 | SCHD | NORM-OPS | 2018-06-21 | 2020-01-07 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 26932 | Work Order Description - 26932 - CM | CM | 4 | 123691 | SCHD | NORM-OPS | 2018-06-21 | 2018-12-30 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 26934 | Work Order Description - 26934 - CM | CM | 4 | 378211 | SCHD | NORM-OPS | 2018-06-21 | 2019-07-01 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 26935 | Work Order Description - 26935 - CM | CM | 4 | 123797 | SCHD | NORM-OPS | 2018-06-21 | 2019-05-30 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 26938 | Work Order Description - 26938 - CM | CM | 3 | 671601 | WSCHD | NORM-OPS | 2017-04-29 | 2019-03-17 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 26939 | Work Order Description - 26939 - CM | CM | 3 | 308530 | WSCHD | NORM-OPS | 2017-06-10 | 2019-05-19 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 27365 | Work Order Description - 27365 - PM | PM | 4 | 321115 | WSCHD | PACK-ISOL | 2017-02-16 | 2019-04-17 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | MECHANICAL | 112
2019-03-31 | 27403 | Work Order Description - 27403 - CM | CM | 4 | 326809 | WSCHD | TPS | 2017-04-08 | 2019-08-12 | 2019-06-15 | 2019-06-18 | 3 | MAINTENANCE | CONSTRUCTION | 65
2019-03-31 | 27528 | Work Order Description - 27528 - CM | CM | 4 | 480103 | WSCHD | TPS | 2017-04-08 | 2019-03-09 | 2019-06-15 | 2019-06-16 | 3 | INTEGRITY | CONSTRUCTION | 14
2019-03-31 | 27539 | Work Order Description - 27539 - CM | CM | 4 | 33404 | WSCHD | NORM-OPS | 2017-04-08 | 2019-08-01 | 2019-06-15 | 2019-06-16 | 3 | INTEGRITY | CONSTRUCTION | 11
2019-03-31 | 27542 | Work Order Description - 27542 - CM | CM | 4 | 357162 | WSCHD | TPS | 2017-04-08 | 2019-03-29 | 2019-06-15 | 2019-06-16 | 3 | MAINTENANCE | CONSTRUCTION | 26
2019-03-31 | 27546 | Work Order Description - 27546 - CM | CM | 3 | 545268 | WSCHD | NORM-OPS | 2017-02-22 | 2019-12-04 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 27547 | Work Order Description - 27547 - CM | CM | 4 | 481607 | SCHD | NORM-OPS | 2018-07-06 | 2020-01-15 | 2019-08-24 | 2019-08-24 | 2 | MAINTENANCE | INSTRUMENTS | 27
2019-03-31 | 27571 | Work Order Description - 27571 - CM | CM | 4 | 496766 | WSCHD | NORM-OPS | 2017-04-08 | 2018-12-02 | 2019-06-15 | 2019-06-16 | 3 | INTEGRITY | CONSTRUCTION | 24
2019-03-31 | 27588 | Work Order Description - 27588 - CM | CM | 4 | 403502 | SCHD | NORM-OPS | 2018-06-21 | 2019-04-08 | 2019-03-16 | 2019-03-16 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 27589 | Work Order Description - 27589 - CM | CM | 4 | 308161 | WSCHD | NORM-OPS | 2019-03-25 | 2021-03-23 | 2020-03-23 | 2020-03-23 | 4 | MAINTENANCE | CONSTRUCTION | 129
2019-03-31 | 27592 | Work Order Description - 27592 - CM | CM | 4 | 410386 | WSCHD | NORM-OPS | 2017-04-08 | 2019-01-11 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | CONSTRUCTION | 9
2019-03-31 | 27595 | Work Order Description - 27595 - CM | CM | 4 | 480103 | WSCHD | NORM-OPS | 2017-04-16 | 2018-12-24 | 2019-06-15 | 2019-06-15 | 3 | INTEGRITY | CONSTRUCTION | 6
2019-03-31 | 27596 | Work Order Description - 27596 - CM | CM | 4 | 33413 | WSCHD | NORM-OPS | 2017-04-16 | 2019-12-17 | 2019-06-15 | 2019-06-15 | 3 | INTEGRITY | CONSTRUCTION | 6
2019-03-31 | 27611 | Work Order Description - 27611 - CM | CM | 3 | 546210 | WSCHD | NORM-OPS | 2017-02-27 | 2019-08-05 | 2019-06-29 | 2019-06-29 | 2 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 27612 | Work Order Description - 27612 - CM | CM | 3 | 19006 | WSCHD | NORM-OPS | 2017-02-27 | 2019-07-10 | 2019-05-04 | 2019-05-04 | 2 | INTEGRITY | ELECTRICAL | 10
2019-03-31 | 27767 | Work Order Description - 27767 - PSCM | PSCM | 1 | 363524 | WSCHD | TPS | 2018-07-10 | 2020-08-01 | 2020-05-02 | 2020-05-07 | 3 | MAINTENANCE | INSTRUMENTS | 68
2019-03-31 | 27781 | Work Order Description - 27781 - CM | CM | 4 | 228839 | WPLAN | NORM-OPS | 2017-03-03 | 2019-02-03 | 2019-05-04 | 2019-05-06 | 4 | INTEGRITY | CONSTRUCTION | 105
2019-03-31 | 27862 | Work Order Description - 27862 - CM | CM | 3 | 556270 | SCHD | NORM-OPS | 2018-12-24 | 2020-01-01 | 2019-06-15 | 2019-06-15 | 3 | INTEGRITY | FABRIC | 201
2019-03-31 | 28034 | Work Order Description - 28034 - CM | CM | 3 | 19008 | WSCHD | NORM-OPS | 2017-10-14 | 2018-12-15 | 2019-04-27 | 2019-04-27 | 2 | INTEGRITY | OPERATIONS | 6
2019-03-31 | 28036 | Work Order Description - 28036 - CM | CM | 4 | 554809 | WPLAN | NORM-OPS | 2017-10-03 | 2019-08-01 | 2020-02-29 | 2020-02-29 | 3 | INTEGRITY | FABRIC | 84
2019-03-31 | 28037 | Work Order Description - 28037 - CM | CM | 3 | 315750 | SCHD | NORM-OPS | 2018-06-21 | 2019-03-22 | 2019-02-16 | 2019-02-16 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 28043 | Work Order Description - 28043 - CM | CM | 4 | 502421 | SCHD | NORM-OPS | 2019-03-15 | 2020-01-01 | 2019-07-02 | 2019-07-02 | 3 | INTEGRITY | FABRIC | 91
2019-03-31 | 28045 | Work Order Description - 28045 - CM | CM | 4 | 216818 | SCHD | NORM-OPS | 2018-11-20 | 2020-01-01 | 2020-02-29 | 2020-02-29 | 3 | INTEGRITY | FABRIC | 91
2019-03-31 | 28047 | Work Order Description - 28047 - PSCM | PSCM | 1 | 671828 | WSCHD | NORM-OPS | 2018-11-15 | 2019-07-01 | 2019-10-19 | 2019-10-19 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 28059 | Work Order Description - 28059 - PSPM | PSPM | 1 | 204613 | WSCHD | NORM-OPS | 2017-08-25 | 2019-11-19 | 2019-10-19 | 2019-12-25 | 2 | INTEGRITY | INSPECTION | 1227
2019-03-31 | 28176 | Work Order Description - 28176 - CM | CM | 3 | 316145 | SCHD | NORM-OPS | 2018-09-06 | 2020-01-11 | 2020-03-07 | 2020-03-07 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 28177 | Work Order Description - 28177 - CM | CM | 4 | 378213 | SCHD | NORM-OPS | 2018-06-21 | 2019-05-11 | 2019-05-05 | 2019-05-05 | 4 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 28179 | Work Order Description - 28179 - BR | BR | 3 | 323130 | WSCHD | TPS | 2018-06-08 | 2019-05-18 | 2020-05-03 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 28181 | Work Order Description - 28181 - BR | BR | 3 | 626577 | WSCHD | TPS | 2018-06-08 | 2019-03-27 | 2020-05-03 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 28182 | Work Order Description - 28182 - CM | CM | 4 | 556357 | SCHD | NORM-OPS | 2018-09-06 | 2018-12-20 | 2020-06-13 | 2020-06-13 | 2 | INTEGRITY | SERVICES | 21
2019-03-31 | 28183 | Work Order Description - 28183 - CM | CM | 4 | 80243 | SCHD | NORM-OPS | 2018-06-21 | 2019-10-27 | 2019-05-05 | 2019-05-05 | 4 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 28184 | Work Order Description - 28184 - BR | BR | 3 | 226423 | WSCHD | TPS | 2018-06-15 | 2018-12-25 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 28200 | Work Order Description - 28200 - CM | CM | 3 | 652302 | WSCHD | NORM-OPS | 2017-07-21 | 2019-07-01 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 28205 | Work Order Description - 28205 - PSCM | PSCM | 1 | 490757 | WSCHD | SUBSYS-ISOL | 2017-03-01 | 2019-07-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 28218 | Work Order Description - 28218 - CM | CM | 4 | 327077 | WSCHD | TPS | 2018-06-08 | 2019-02-09 | 2020-05-03 | 2020-05-03 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 28915 | Work Order Description - 28915 - CM | CM | 4 | 80244 | SCHD | NORM-OPS | 2018-06-21 | 2019-03-17 | 2019-05-05 | 2019-05-05 | 4 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 28917 | Work Order Description - 28917 - CM | CM | 4 | 123803 | SCHD | NORM-OPS | 2018-06-21 | 2019-05-18 | 2019-05-05 | 2019-05-05 | 4 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 28918 | Work Order Description - 28918 - CM | CM | 4 | 123804 | SCHD | NORM-OPS | 2018-06-21 | 2019-11-01 | 2019-05-05 | 2019-05-05 | 4 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 28919 | Work Order Description - 28919 - CM | CM | 4 | 378238 | SCHD | NORM-OPS | 2018-06-21 | 2019-03-21 | 2019-05-05 | 2019-05-05 | 4 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 28920 | Work Order Description - 28920 - CM | CM | 4 | 238290 | SCHD | NORM-OPS | 2018-06-21 | 2019-03-24 | 2019-05-05 | 2019-05-05 | 4 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 28923 | Work Order Description - 28923 - CM | CM | 4 | 378240 | WPLAN | NORM-OPS | 2017-03-02 | 2020-02-13 | 2019-05-05 | 2019-05-05 | 4 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 28924 | Work Order Description - 28924 - CM | CM | 4 | 238291 | WPLAN | NORM-OPS | 2017-03-02 | 2020-02-02 | 2019-05-05 | 2019-05-05 | 4 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 28925 | Work Order Description - 28925 - CM | CM | 4 | 378241 | WPLAN | NORM-OPS | 2017-03-02 | 2020-02-02 | 2019-05-05 | 2019-05-05 | 4 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 28927 | Work Order Description - 28927 - CM | CM | 4 | 238292 | WPLAN | NORM-OPS | 2017-03-02 | 2020-02-02 | 2019-05-05 | 2019-05-05 | 4 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 28941 | Work Order Description - 28941 - CM | CM | 2 | 214948 | WSCHD | SYS-ISOL | 2017-03-14 | 2018-12-23 | 2019-04-13 | 2019-04-14 | 2 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 28952 | Work Order Description - 28952 - CM | CM | 3 | 249416 | SCHD | TPS | 2019-03-01 | 2019-05-10 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 28999 | Work Order Description - 28999 - CM | CM | 2 | 527378 | SCHD | NORM-OPS | 2018-06-21 | 2019-03-20 | 2019-09-09 | 2019-09-10 | 4 | INTEGRITY | CONSTRUCTION | 49
2019-03-31 | 29086 | Work Order Description - 29086 - CM | CM | 3 | 254953 | SCHD | SYS-ISOL | 2018-06-07 | 2019-11-27 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 29148 | Work Order Description - 29148 - CM | CM | 2 | 527378 | INPRG | NORM-OPS | 2019-02-24 | 2019-06-06 | 2019-09-09 | 2019-10-07 | 3 | INTEGRITY | CONSTRUCTION | 241.25
2019-03-31 | 29159 | Work Order Description - 29159 - CM | CM | 2 | 128537 | SCHD | SYS-ISOL | 2019-03-06 | 2019-01-19 | 2019-07-13 | 2019-07-15 | 4 | INTEGRITY | MECHANICAL | 45
2019-03-31 | 29173 | Work Order Description - 29173 - CM | CM | 4 | 528143 | SCHD | NORM-OPS | 2019-03-06 | 2019-11-14 | 2019-03-26 | 2019-04-04 | 4 | INTEGRITY | CONSTRUCTION | 47.5
2019-03-31 | 29174 | Work Order Description - 29174 - CM | CM | 1 | 451342 | SCHD | NORM-OPS | 2019-03-29 | 2019-06-01 | 2019-07-13 | 2019-07-31 | 4 | INTEGRITY | CONSTRUCTION | 340
2019-03-31 | 29176 | Work Order Description - 29176 - CM | CM | 4 | 528143 | SCHD | NORM-OPS | 2019-03-15 | 2019-09-06 | 2019-05-30 | 2019-06-12 | 3 | INTEGRITY | FABRIC | 294
2019-03-31 | 29183 | Work Order Description - 29183 - CM | CM | 2 | 255645 | SCHD | SYS-ISOL | 2018-09-06 | 2019-09-05 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 66
2019-03-31 | 29184 | Work Order Description - 29184 - CM | CM | 2 | 30197 | SCHD | NORM-OPS | 2018-09-06 | 2018-12-22 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 73
2019-03-31 | 29188 | Work Order Description - 29188 - CM | CM | 3 | 361667 | WPLAN | SYS-ISOL | 2019-03-01 | 2019-08-30 | 2019-05-28 | 2019-06-04 | 3 | INTEGRITY | FABRIC | 392
2019-03-31 | 29190 | Work Order Description - 29190 - CM | CM | 1 | 580766 | WSCHD | TPS | 2018-12-19 | 2019-04-04 | 2019-06-01 | 2019-06-04 | 3 | INTEGRITY | CONSTRUCTION | 12
2019-03-31 | 29225 | Work Order Description - 29225 - PM | PM | 4 | 363667 | WSCHD | PACK-ISOL | 2017-03-06 | 2019-07-24 | 2019-06-22 | 2019-06-23 | 1 | INTEGRITY | MECHANICAL | 9
2019-03-31 | 29306 | Work Order Description - 29306 - PSPM | PSPM | 1 | 326089 | WSCHD | EQUIP-ISOL | 2018-10-16 | 2019-11-24 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 29972 | Work Order Description - 29972 - CM | CM | 2 | 392230 | SCHD | NORM-OPS | 2018-06-21 | 2019-05-03 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 29996 | Work Order Description - 29996 - PSPM | PSPM | 1 | 361097 | WSCHD | EQUIP-ISOL | 2017-04-24 | 2020-07-01 | 2019-07-15 | 2019-07-15 | 1 | INTEGRITY | INSTRUMENTS | 5
2019-03-31 | 29997 | Work Order Description - 29997 - PSPM | PSPM | 1 | 361101 | WSCHD | EQUIP-ISOL | 2017-04-24 | 2022-10-30 | 2019-07-15 | 2019-07-15 | 1 | INTEGRITY | INSTRUMENTS | 5
2019-03-31 | 30061 | Work Order Description - 30061 - CM | CM | 3 | 265942 | SCHD | NORM-OPS | 2018-07-06 | 2019-06-17 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 9
2019-03-31 | 30225 | Work Order Description - 30225 - PM | PM | 4 | 96159 | SCHD | NORM-OPS | 2018-06-21 | 2019-09-28 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 31390 | Work Order Description - 31390 - CM | CM | 3 | 214947 | WSCHD | NORM-OPS | 2017-03-17 | 2019-07-08 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 31391 | Work Order Description - 31391 - CM | CM | 3 | 214914 | WSCHD | NORM-OPS | 2017-03-19 | 2020-01-04 | 2019-07-06 | 2019-07-06 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 31392 | Work Order Description - 31392 - CM | CM | 3 | 326722 | WSCHD | NORM-OPS | 2017-03-19 | 2019-09-04 | 2019-07-06 | 2019-07-06 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 31396 | Work Order Description - 31396 - CM | CM | 2 | 262779 | WSCHD | NORM-OPS | 2019-03-25 | 2019-10-31 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | CONSTRUCTION | 32
2019-03-31 | 31426 | Work Order Description - 31426 - CM | CM | 4 | 388234 | SCHD | NORM-OPS | 2019-03-06 | 2020-01-08 | 2019-05-01 | 2019-05-01 | 3 | MAINTENANCE | CONSTRUCTION | 11
2019-03-31 | 31447 | Work Order Description - 31447 - PSCM | PSCM | 4 | 261348 | WSCHD | NORM-OPS | 2018-06-12 | 2019-10-05 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 31589 | Work Order Description - 31589 - CM | CM | 4 | 312718 | SCHD | NORM-OPS | 2018-09-06 | 2019-04-17 | 2019-11-16 | 2019-11-16 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 31609 | Work Order Description - 31609 - CM | CM | 4 | 584465 | SCHD | NORM-OPS | 2018-09-06 | 2019-10-18 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 31704 | Work Order Description - 31704 - CM | CM | 3 | 358160 | WSCHD | NORM-OPS | 2017-06-10 | 2019-05-01 | 2019-05-18 | 2019-05-19 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 31710 | Work Order Description - 31710 - CM | CM | 3 | 214946 | WSCHD | NORM-OPS | 2017-03-23 | 2019-08-26 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 31711 | Work Order Description - 31711 - CM | CM | 3 | 519672 | WSCHD | NORM-OPS | 2017-03-23 | 2018-12-21 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 31718 | Work Order Description - 31718 - CM | CM | 4 | 527428 | WPLAN | NORM-OPS | 2017-06-21 | 2020-01-01 | 2019-06-01 | 2019-06-05 | 4 | INTEGRITY | INSPECTION | 60
2019-03-31 | 31723 | Work Order Description - 31723 - CM | CM | 4 | 479682 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-21 | 2019-11-16 | 2019-11-16 | 4 | MAINTENANCE | MECHANICAL | 17.5
2019-03-31 | 31730 | Work Order Description - 31730 - CM | CM | 4 | 216029 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-31 | 2019-06-01 | 2019-06-01 | 3 | INTEGRITY | CONSTRUCTION | 57.5
2019-03-31 | 31876 | Work Order Description - 31876 - CM | CM | 3 | 21462 | SCHD | TPS | 2018-10-09 | 2019-11-22 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 31887 | Work Order Description - 31887 - CM | CM | 3 | 183627 | SCHD | TPS | 2018-09-06 | 2019-11-15 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 31896 | Work Order Description - 31896 - CM | CM | 3 | 247586 | WSCHD | NORM-OPS | 2017-03-23 | 2019-03-30 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 31897 | Work Order Description - 31897 - CM | CM | 3 | 214912 | WSCHD | NORM-OPS | 2017-03-23 | 2019-08-06 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 31898 | Work Order Description - 31898 - CM | CM | 3 | 214913 | WSCHD | NORM-OPS | 2017-03-23 | 2019-08-30 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 32570 | Work Order Description - 32570 - CM | CM | 1 | 481325 | WPLAN | TPS | 2017-06-06 | 2019-04-19 | 2019-07-06 | 2019-07-06 | 4 | INTEGRITY | CONSTRUCTION | 11
2019-03-31 | 32589 | Work Order Description - 32589 - CM | CM | 4 | 501014 | SCHD | NORM-OPS | 2018-09-06 | 2019-03-21 | 2019-05-18 | 2019-05-18 | 4 | MAINTENANCE | SAFETY | 17
2019-03-31 | 32591 | Work Order Description - 32591 - CM | CM | 4 | 481595 | SCHD | NORM-OPS | 2018-09-06 | 2019-03-21 | 2019-05-18 | 2019-05-18 | 4 | MAINTENANCE | SAFETY | 17
2019-03-31 | 32593 | Work Order Description - 32593 - CM | CM | 4 | 481596 | SCHD | NORM-OPS | 2018-09-06 | 2019-03-21 | 2019-05-18 | 2019-05-18 | 4 | MAINTENANCE | SAFETY | 30
2019-03-31 | 32598 | Work Order Description - 32598 - CM | CM | 4 | 97470 | SCHD | NORM-OPS | 2019-02-13 | 2019-03-21 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 32988 | Work Order Description - 32988 - CM | CM | 4 | 320026 | WSCHD | NORM-OPS | 2019-03-25 | 2019-09-10 | 2020-03-07 | 2020-03-07 | 3 | INTEGRITY | CONSTRUCTION | 35
2019-03-31 | 32990 | Work Order Description - 32990 - CM | CM | 4 | 392761 | SCHD | NORM-OPS | 2019-02-13 | 2019-10-01 | 2019-04-01 | 2019-04-02 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 33138 | Work Order Description - 33138 - CM | CM | 4 | 479573 | SCHD | NORM-OPS | 2018-07-18 | 2019-06-05 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 35
2019-03-31 | 33160 | Work Order Description - 33160 - PRJ | PRJ | 3 | 463382 | SCHD | NORM-OPS | 2018-07-06 | 2019-04-14 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | SERVICES | 14
2019-03-31 | 33163 | Work Order Description - 33163 - PM | PM | 4 | 547429 | WSCHD | NORM-OPS | 2017-03-28 | 2019-06-27 | 2019-05-04 | 2019-05-05 | 1 | MAINTENANCE | SERVICES | 14
2019-03-31 | 33191 | Work Order Description - 33191 - CM | CM | 4 | 247628 | WSCHD | NORM-OPS | 2017-04-08 | 2019-04-23 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 33242 | Work Order Description - 33242 - PM | PM | 4 | 246173 | WSCHD | NORM-OPS | 2017-03-29 | 2019-10-08 | 2019-05-04 | 2019-05-05 | 1 | MAINTENANCE | SERVICES | 14
2019-03-31 | 33421 | Work Order Description - 33421 - CM | CM | 3 | 254610 | SCHD | NORM-OPS | 2018-09-06 | 2019-03-20 | 2019-05-18 | 2019-05-18 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 33446 | Work Order Description - 33446 - CM | CM | 2 | 495409 | WSCHD | TPS | 2017-07-06 | 2019-03-30 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 33502 | Work Order Description - 33502 - CM | CM | 3 | 35657 | SCHD | NORM-OPS | 2018-07-18 | 2019-09-20 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 33503 | Work Order Description - 33503 - CM | CM | 3 | 537911 | SCHD | NORM-OPS | 2018-09-06 | 2019-03-28 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 33530 | Work Order Description - 33530 - CM | CM | 3 | 226531 | WSCHD | TPS | 2017-04-18 | 2019-03-31 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 33535 | Work Order Description - 33535 - CM | CM | 2 | 490536 | SCHD | SYS-ISOL | 2018-06-21 | 2019-10-09 | 2019-05-04 | 2019-05-04 | 3 | INTEGRITY | MECHANICAL | 24
2019-03-31 | 33549 | Work Order Description - 33549 - CM | CM | 4 | 500773 | WSCHD | TPS | 2017-04-23 | 2019-03-31 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 33553 | Work Order Description - 33553 - CM | CM | 4 | 323342 | WSCHD | NORM-OPS | 2017-04-08 | 2020-04-01 | 2019-11-01 | 2019-11-03 | 3 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 33560 | Work Order Description - 33560 - CM | CM | 4 | 323342 | WSCHD | NORM-OPS | 2017-04-09 | 2019-06-08 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | CONSTRUCTION | 2
2019-03-31 | 33658 | Work Order Description - 33658 - PM | PM | 3 | 33394 | WSCHD | TPS | 2017-04-03 | 2019-09-20 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 33677 | Work Order Description - 33677 - PSPM | PSPM | 1 | 305203 | WSCHD | EQUIP-ISOL | 2017-04-03 | 2020-08-01 | 2020-05-02 | 2020-05-02 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 34610 | Work Order Description - 34610 - CM | CM | 1 | 481325 | SCHD | NORM-OPS | 2019-01-31 | 2019-04-02 | 2019-07-17 | 2019-07-22 | 4 | INTEGRITY | FABRIC | 673
2019-03-31 | 34829 | Work Order Description - 34829 - CM | CM | 4 | 480103 | WSCHD | NORM-OPS | 2017-04-08 | 2020-04-01 | 2019-10-26 | 2019-10-27 | 3 | INTEGRITY | SERVICES | 27
2019-03-31 | 34833 | Work Order Description - 34833 - CM | CM | 4 | 480103 | WSCHD | NORM-OPS | 2017-04-08 | 2019-04-03 | 2019-10-26 | 2019-10-26 | 4 | INTEGRITY | SERVICES | 13.5
2019-03-31 | 34841 | Work Order Description - 34841 - CM | CM | 4 | 210976 | WSCHD | NORM-OPS | 2017-07-21 | 2019-04-03 | 2020-05-02 | 2020-05-02 | 4 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 34844 | Work Order Description - 34844 - CM | CM | 4 | 403817 | SCHD | NORM-OPS | 2018-09-06 | 2019-05-15 | 2019-06-15 | 2019-06-15 | 3 | INTEGRITY | FABRIC | 131
2019-03-31 | 34846 | Work Order Description - 34846 - CM | CM | 4 | 357163 | WSCHD | NORM-OPS | 2017-04-08 | 2019-04-03 | 2019-10-26 | 2019-10-26 | 4 | MAINTENANCE | SERVICES | 12
2019-03-31 | 34847 | Work Order Description - 34847 - CM | CM | 3 | 308162 | WSCHD | NORM-OPS | 2017-04-08 | 2019-04-03 | 2019-10-26 | 2019-10-26 | 4 | MAINTENANCE | SERVICES | 12
2019-03-31 | 34858 | Work Order Description - 34858 - CM | CM | 4 | 497845 | WSCHD | NORM-OPS | 2017-04-08 | 2020-04-01 | 2019-08-18 | 2019-08-18 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 34914 | Work Order Description - 34914 - CM | CM | 4 | 327293 | WSCHD | TPS | 2017-05-03 | 2019-04-02 | 2020-05-02 | 2020-05-04 | 2 | MAINTENANCE | MECHANICAL | 27
2019-03-31 | 34916 | Work Order Description - 34916 - CM | CM | 3 | 322542 | WSCHD | SYS-ISOL | 2017-05-15 | 2019-03-21 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 13
2019-03-31 | 34932 | Work Order Description - 34932 - PM | PM | 4 | 33432 | WSCHD | PACK-ISOL | 2017-04-06 | 2018-12-01 | 2019-04-13 | 2019-04-14 | 2 | INTEGRITY | MECHANICAL | 116
2019-03-31 | 34938 | Work Order Description - 34938 - PSPM | PSPM | 1 | 294961 | WSCHD | NORM-OPS | 2018-10-29 | 2019-04-19 | 2019-04-06 | 2019-04-07 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 35033 | Work Order Description - 35033 - CM | CM | 4 | 323342 | WSCHD | NORM-OPS | 2017-04-08 | 2020-04-01 | 2019-12-28 | 2020-01-01 | 3 | MAINTENANCE | SERVICES | 105
2019-03-31 | 35060 | Work Order Description - 35060 - CM | CM | 3 | 53520 | SCHD | NORM-OPS | 2019-03-01 | 2019-09-08 | 2019-04-13 | 2019-04-14 | 3 | INTEGRITY | MECHANICAL | 1
2019-03-31 | 35061 | Work Order Description - 35061 - CM | CM | 4 | 249497 | WSCHD | NORM-OPS | 2017-04-08 | 2019-07-14 | 2019-05-04 | 2019-05-07 | 3 | MAINTENANCE | CONSTRUCTION | 101
2019-03-31 | 35125 | Work Order Description - 35125 - CM | CM | 4 | 245671 | WSCHD | NORM-OPS | 2017-04-08 | 2019-02-05 | 2019-10-05 | 2019-10-08 | 3 | MAINTENANCE | CONSTRUCTION | 101
2019-03-31 | 35127 | Work Order Description - 35127 - CM | CM | 4 | 323343 | WSCHD | NORM-OPS | 2017-04-08 | 2019-02-27 | 2019-10-05 | 2019-10-08 | 3 | MAINTENANCE | CONSTRUCTION | 101
2019-03-31 | 35138 | Work Order Description - 35138 - CM | CM | 4 | 249517 | WSCHD | NORM-OPS | 2017-04-08 | 2019-03-24 | 2019-10-05 | 2019-10-08 | 3 | MAINTENANCE | CONSTRUCTION | 100
2019-03-31 | 35146 | Work Order Description - 35146 - CM | CM | 4 | 501441 | SCHD | NORM-OPS | 2018-09-06 | 2019-05-14 | 2019-08-10 | 2019-08-10 | 3 | INTEGRITY | FABRIC | 248
2019-03-31 | 35161 | Work Order Description - 35161 - CM | CM | 4 | 491732 | SCHD | SYS-ISOL | 2019-01-17 | 2019-04-07 | 2019-05-18 | 2019-05-18 | 4 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 35166 | Work Order Description - 35166 - CM | CM | 4 | 546068 | WSCHD | NORM-OPS | 2017-04-10 | 2019-04-07 | 2019-08-31 | 2019-09-03 | 4 | MAINTENANCE | ELECTRICAL | 64
2019-03-31 | 35192 | Work Order Description - 35192 - PSCM | PSCM | 1 | 34085 | WSCHD | TPS | 2018-06-08 | 2020-08-01 | 2020-05-03 | 2020-05-06 | 2 | MAINTENANCE | MECHANICAL | 39
2019-03-31 | 35301 | Work Order Description - 35301 - CM | CM | 4 | 551329 | SCHD | NORM-OPS | 2018-10-05 | 2019-04-01 | 2020-02-29 | 2020-02-29 | 3 | MAINTENANCE | FABRIC | 100
2019-03-31 | 35363 | Work Order Description - 35363 - CM | CM | 4 | 678020 | WRISKREV | NORM-OPS | 2019-03-11 | 2019-09-10 |  |  | 3 | INTEGRITY | FABRIC | 54
2019-03-31 | 35367 | Work Order Description - 35367 - CM | CM | 4 | 490170 | WSCHD | SUBSYS-ISOL | 2018-06-02 | 2019-05-28 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 35391 | Work Order Description - 35391 - CM | CM | 3 | 479579 | WSCHD | NORM-OPS | 2019-03-25 | 2019-07-31 | 2019-06-01 | 2019-06-01 | 2 | INTEGRITY | CONSTRUCTION | 147
2019-03-31 | 35482 | Work Order Description - 35482 - PSCM | PSCM | 1 | 546068 | WSCHD | NORM-OPS | 2018-11-14 | 2019-03-31 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | SERVICES | 60
2019-03-31 | 35516 | Work Order Description - 35516 - PSPM | PSPM | 1 | 248364 | WSCHD | EQUIP-ISOL | 2018-10-17 | 2019-10-01 | 2019-08-17 | 2019-08-17 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 35650 | Work Order Description - 35650 - CM | CM | 4 | 450925 | SCHD | NORM-OPS | 2019-03-06 | 2019-06-11 | 2019-09-01 | 2019-09-24 | 2 | INTEGRITY | ELECTRICAL | 148.5
2019-03-31 | 35658 | Work Order Description - 35658 - CM | CM | 4 | 450925 | SCHD | NORM-OPS | 2019-03-06 | 2019-05-12 | 2019-05-11 | 2019-09-13 | 2 | INTEGRITY | ELECTRICAL | 953
2019-03-31 | 35659 | Work Order Description - 35659 - CM | CM | 4 | 450925 | SCHD | NORM-OPS | 2019-01-11 | 2019-02-19 | 2019-08-31 | 2019-09-18 | 3 | INTEGRITY | ELECTRICAL | 266
2019-03-31 | 35660 | Work Order Description - 35660 - CM | CM | 4 | 450925 | SCHD | NORM-OPS | 2019-01-11 | 2019-05-20 | 2019-08-31 | 2019-11-06 | 3 | INTEGRITY | ELECTRICAL | 908
2019-03-31 | 35661 | Work Order Description - 35661 - CM | CM | 4 | 450925 | SCHD | NORM-OPS | 2019-01-24 | 2019-07-04 | 2019-08-31 | 2019-11-15 | 3 | INTEGRITY | ELECTRICAL | 1078
2019-03-31 | 35662 | Work Order Description - 35662 - CM | CM | 4 | 450925 | SCHD | NORM-OPS | 2019-01-11 | 2019-04-12 | 2019-08-31 | 2019-09-04 | 4 | INTEGRITY | ELECTRICAL | 70
2019-03-31 | 35663 | Work Order Description - 35663 - CM | CM | 4 | 450925 | SCHD | NORM-OPS | 2019-01-11 | 2019-04-12 | 2019-08-31 | 2019-09-07 | 4 | INTEGRITY | ELECTRICAL | 1
2019-03-31 | 35664 | Work Order Description - 35664 - CM | CM | 4 | 450925 | SCHD | NORM-OPS | 2019-01-24 | 2019-05-12 | 2019-08-31 | 2019-09-11 | 2 | INTEGRITY | ELECTRICAL | 160
2019-03-31 | 35665 | Work Order Description - 35665 - CM | CM | 4 | 450925 | SCHD | NORM-OPS | 2019-01-11 | 2019-04-12 | 2019-08-31 | 2019-09-01 | 4 | INTEGRITY | ELECTRICAL | 1
2019-03-31 | 35683 | Work Order Description - 35683 - PSCM | PSCM | 1 | 447441 | WPLAN | NORM-OPS | 2019-03-03 | 2019-06-01 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | MECHANICAL | 128
2019-03-31 | 35685 | Work Order Description - 35685 - CM | CM | 4 | 450925 | SCHD | NORM-OPS | 2019-01-11 | 2019-04-12 | 2019-08-31 | 2019-09-07 | 4 | INTEGRITY | ELECTRICAL | 112
2019-03-31 | 35686 | Work Order Description - 35686 - CM | CM | 4 | 450925 | SCHD | NORM-OPS | 2019-01-11 | 2019-04-12 | 2019-08-31 | 2019-09-02 | 4 | INTEGRITY | ELECTRICAL | 42
2019-03-31 | 35688 | Work Order Description - 35688 - CM | CM | 4 | 450925 | SCHD | NORM-OPS | 2019-01-11 | 2019-04-12 | 2019-08-31 | 2019-09-03 | 4 | INTEGRITY | ELECTRICAL | 48
2019-03-31 | 35689 | Work Order Description - 35689 - CM | CM | 4 | 450925 | SCHD | NORM-OPS | 2019-01-11 | 2019-04-12 | 2019-08-31 | 2019-09-01 | 4 | INTEGRITY | ELECTRICAL | 9
2019-03-31 | 35779 | Work Order Description - 35779 - CM | CM | 3 | 308834 | WSCHD | TPS | 2018-06-07 | 2020-01-16 | 2020-05-03 | 2020-05-05 | 3 | MAINTENANCE | MECHANICAL | 19
2019-03-31 | 35783 | Work Order Description - 35783 - CM | CM | 1 | 17814 | WPLAN | TPS | 2017-06-09 | 2020-09-01 | 2020-05-02 | 2020-05-04 | 4 | INTEGRITY | CONSTRUCTION | 126
2019-03-31 | 35857 | Work Order Description - 35857 - BR | BR | 3 | 398778 | WMATL | NORM-OPS | 2018-10-10 | 2020-01-22 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 35858 | Work Order Description - 35858 - CM | CM | 4 | 503361 | WSCHD | NORM-OPS | 2019-03-25 | 2019-07-24 | 2020-02-29 | 2020-02-29 | 3 | OPERATIONS | MECHANICAL | 20
2019-03-31 | 36017 | Work Order Description - 36017 - CM | CM | 4 | 35546 | SCHD | NORM-OPS | 2018-07-06 | 2019-10-19 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 19
2019-03-31 | 36034 | Work Order Description - 36034 - CM | CM | 4 | 73378 | WPLAN | NORM-OPS | 2017-06-16 | 2019-06-15 | 2019-05-05 | 2019-05-05 | 4 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 36463 | Work Order Description - 36463 - PM | PM | 2 | 554790 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-01-05 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 36753 | Work Order Description - 36753 - CM | CM | 4 | 419551 | INPRG | NORM-OPS | 2019-02-20 | 2019-03-26 | 2019-03-30 | 2019-05-04 | 3 | DRILLING | DRILLING | 36.5
2019-03-31 | 36758 | Work Order Description - 36758 - PSCM | PSCM | 2 | 498644 | WSCHD | TPS | 2019-02-28 | 2019-04-01 | 2019-04-27 | 2019-04-27 | 3 | WELLS | INSTRUMENTS | 5.5
2019-03-31 | 36855 | Work Order Description - 36855 - PSCM | PSCM | 1 | 357099 | WSCHD | PACK-ISOL | 2017-04-24 | 2020-07-01 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 36858 | Work Order Description - 36858 - CM | CM | 4 | 419350 | WSCHD | NORM-OPS | 2017-04-26 | 2019-06-11 | 2019-04-27 | 2019-04-27 | 3 | DRILLING | DRILLING | 8
2019-03-31 | 37170 | Work Order Description - 37170 - PSCM | PSCM | 1 | 260432 | WSCHD | SYS-ISOL | 2017-04-27 | 2019-04-22 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | CONSTRUCTION | 4
2019-03-31 | 37186 | Work Order Description - 37186 - CM | CM | 3 | 357143 | WSCHD | TPS | 2017-05-04 | 2019-03-15 | 2020-05-02 | 2020-05-04 | 2 | MAINTENANCE | MECHANICAL | 38
2019-03-31 | 37194 | Work Order Description - 37194 - CM | CM | 4 | 663305 | SCHD | NORM-OPS | 2019-02-13 | 2019-11-29 | 2019-04-04 | 2019-04-15 | 4 | MAINTENANCE | INSTRUMENTS | 46
2019-03-31 | 37208 | Work Order Description - 37208 - PSPM | PSPM | 1 | 399599 | WSCHD | EQUIP-ISOL | 2017-04-24 | 2019-08-01 | 2019-05-31 | 2019-05-31 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 37468 | Work Order Description - 37468 - CM | CM | 3 | 411434 | WSCHD | PACK-ISOL | 2017-07-19 | 2020-01-04 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 37605 | Work Order Description - 37605 - CM | CM | 4 | 501361 | SCHD | NORM-OPS | 2018-07-18 | 2019-04-24 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | SERVICES | 8
2019-03-31 | 37708 | Work Order Description - 37708 - CM | CM | 2 | 556288 | WSCHD | TPS | 2019-03-25 | 2020-07-30 | 2019-07-13 | 2019-07-13 | 3 | INTEGRITY | CONSTRUCTION | 120
2019-03-31 | 37715 | Work Order Description - 37715 - CM | CM | 3 | 409922 | WSCHD | PACK-ISOL | 2017-06-26 | 2019-05-13 | 2019-10-26 | 2019-10-26 | 3 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 37768 | Work Order Description - 37768 - CM | CM | 3 | 33902 | WSCHD | NORM-OPS | 2018-05-13 | 2019-04-15 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | CONSTRUCTION | 4
2019-03-31 | 37769 | Work Order Description - 37769 - CM | CM | 4 | 214871 | WSCHD | TPS | 2018-05-01 | 2019-03-20 | 2020-05-02 | 2020-05-04 | 3 | MAINTENANCE | CONSTRUCTION | 28
2019-03-31 | 37770 | Work Order Description - 37770 - CM | CM | 3 | 495139 | WSCHD | NORM-OPS | 2018-05-13 | 2019-11-03 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 37772 | Work Order Description - 37772 - CM | CM | 1 | 326617 | WSCHD | TPS | 2018-04-17 | 2019-04-01 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | CONSTRUCTION | 4
2019-03-31 | 37773 | Work Order Description - 37773 - CM | CM | 4 | 451342 | WPLAN | NORM-OPS | 2017-06-21 | 2019-08-01 | 2019-03-23 | 2019-03-26 | 4 | INTEGRITY | FABRIC | 120
2019-03-31 | 37800 | Work Order Description - 37800 - PM | PM | 4 | 551618 | SCHD | NORM-OPS | 2018-07-06 | 2019-09-22 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 37801 | Work Order Description - 37801 - PM | PM | 4 | 35256 | SCHD | NORM-OPS | 2018-07-06 | 2019-02-05 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 37806 | Work Order Description - 37806 - PM | PM | 3 | 303994 | SCHD | NORM-OPS | 2018-05-18 | 2019-02-04 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 37908 | Work Order Description - 37908 - PM | PM | 3 | 408679 | SCHD | PACK-ISOL | 2018-09-06 | 2019-05-01 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 37929 | Work Order Description - 37929 - PM | PM | 4 | 499419 | WSCHD | EQUIP-ISOL | 2017-06-28 | 2020-01-16 | 2019-10-22 | 2019-10-23 | 2 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 37989 | Work Order Description - 37989 - CM | CM | 2 | 315355 | WSCHD | NORM-OPS | 2017-05-02 | 2019-02-20 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 37991 | Work Order Description - 37991 - CM | CM | 2 | 545260 | WSCHD | PACK-ISOL | 2017-05-09 | 2019-04-11 | 2019-04-22 | 2019-04-22 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 38010 | Work Order Description - 38010 - CM | CM | 4 | 368215 | WSCHD | NORM-OPS | 2017-12-01 | 2018-12-25 | 2019-08-31 | 2019-09-30 | 2 | MAINTENANCE | ELECTRICAL | 625
2019-03-31 | 38011 | Work Order Description - 38011 - CM | CM | 3 | 554762 | SCHD | SYS-ISOL | 2018-06-04 | 2019-07-09 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 38091 | Work Order Description - 38091 - CM | CM | 4 | 368215 | WSCHD | NORM-OPS | 2017-05-03 | 2018-12-08 | 2019-08-31 | 2019-09-01 | 3 | MAINTENANCE | ELECTRICAL | 89
2019-03-31 | 38095 | Work Order Description - 38095 - CM | CM | 2 | 674738 | WSCHD | NORM-OPS | 2019-01-15 | 2019-02-27 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 38113 | Work Order Description - 38113 - CM | CM | 4 | 497446 | WSCHD | NORM-OPS | 2017-05-05 | 2019-11-18 | 2019-04-20 | 2019-04-21 | 3 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 38128 | Work Order Description - 38128 - CM | CM | 3 | 259466 | SCHD | SYS-ISOL | 2018-08-18 | 2019-02-28 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 38139 | Work Order Description - 38139 - CM | CM | 2 | 595905 | WSCHD | TPS | 2018-06-08 | 2019-07-02 | 2019-08-31 | 2019-09-02 | 3 | MAINTENANCE | INSTRUMENTS | 33
2019-03-31 | 38729 | Work Order Description - 38729 - PM | PM | 4 | 310034 | SCHD | PACK-ISOL | 2018-09-06 | 2019-08-03 | 2019-08-24 | 2019-08-24 | 1 | INTEGRITY | MECHANICAL | 18
2019-03-31 | 38741 | Work Order Description - 38741 - PM | PM | 4 | 310192 | SCHD | EQUIP-ISOL | 2018-09-06 | 2020-01-25 | 2019-06-15 | 2019-06-15 | 2 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 39011 | Work Order Description - 39011 - PM | PM | 3 | 25159 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-10-21 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 39117 | Work Order Description - 39117 - CM | CM | 3 | 33918 | WSCHD | SYS-ISOL | 2017-05-15 | 2019-03-19 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 39119 | Work Order Description - 39119 - CM | CM | 3 | 500961 | WSCHD | SYS-ISOL | 2017-05-15 | 2020-01-16 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 39125 | Work Order Description - 39125 - CM | CM | 3 | 327402 | WSCHD | SYS-ISOL | 2017-05-15 | 2020-01-20 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 39465 | Work Order Description - 39465 - PSPM | PSPM | 1 | 326081 | WSCHD | EQUIP-ISOL | 2017-11-07 | 2021-01-01 | 2019-12-27 | 2019-12-27 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 39466 | Work Order Description - 39466 - PSPM | PSPM | 1 | 360698 | WSCHD | EQUIP-ISOL | 2017-11-07 | 2021-01-01 | 2019-12-27 | 2019-12-27 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 40316 | Work Order Description - 40316 - CM | CM | 4 | 353433 | WSCHD | NORM-OPS | 2017-08-25 | 2019-05-03 | 2019-05-04 | 2019-05-05 | 4 | MAINTENANCE | INSTRUMENTS | 187
2019-03-31 | 40345 | Work Order Description - 40345 - CM | CM | 4 | 666270 | WSCHD | TPS | 2017-05-08 | 2019-05-04 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 40461 | Work Order Description - 40461 - PSCM | PSCM | 1 | 33833 | WSCHD | NORM-OPS | 2018-06-20 | 2019-06-08 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 40502 | Work Order Description - 40502 - CM | CM | 4 | 217594 | SCHD | NORM-OPS | 2018-09-06 | 2019-04-10 | 2020-02-29 | 2020-02-29 | 3 | MAINTENANCE | FABRIC | 64
2019-03-31 | 41014 | Work Order Description - 41014 - CM | CM | 4 | 671611 | WPLAN | TPS | 2017-08-03 | 2019-02-20 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | CONSTRUCTION | 0
2019-03-31 | 41677 | Work Order Description - 41677 - CM | CM | 4 | 540544 | WSCHD | NORM-OPS | 2017-05-13 | 2019-09-06 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 41709 | Work Order Description - 41709 - CM | CM | 3 | 546660 | WSCHD | TPS | 2017-06-02 | 2019-02-28 | 2020-05-02 | 2020-05-05 | 3 | MAINTENANCE | MECHANICAL | 44
2019-03-31 | 41710 | Work Order Description - 41710 - CM | CM | 1 | 467918 | WPLAN | TPS | 2017-07-04 | 2019-06-01 | 2020-05-02 | 2020-05-05 | 4 | INTEGRITY | CONSTRUCTION | 28
2019-03-31 | 41714 | Work Order Description - 41714 - CM | CM | 4 | 547540 | WPLAN | NORM-OPS | 2018-11-29 | 2020-05-25 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | SERVICES | 34
2019-03-31 | 41728 | Work Order Description - 41728 - CM | CM | 4 | 674780 | WSCHD | TPS | 2017-08-18 | 2019-05-13 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | CONSTRUCTION | 76
2019-03-31 | 42037 | Work Order Description - 42037 - CM | CM | 3 | 309889 | SCHD | TPS | 2018-09-06 | 2019-05-14 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 42048 | Work Order Description - 42048 - PSCM | PSCM | 1 | 547511 | WSCHD | NORM-OPS | 2017-05-28 | 2019-05-06 | 2019-12-27 | 2019-12-27 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 42060 | Work Order Description - 42060 - PSCM | PSCM | 1 | 361948 | SCHD | NORM-OPS | 2019-02-16 | 2019-08-17 | 2019-05-25 | 2019-05-28 | 3 | MAINTENANCE | INSTRUMENTS | 52
2019-03-31 | 42114 | Work Order Description - 42114 - PM | PM | 4 | 183627 | SCHD | EQUIP-ISOL | 2018-07-06 | 2019-07-04 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 42148 | Work Order Description - 42148 - PSCM | PSCM | 1 | 547734 | WSCHD | NORM-OPS | 2017-05-21 | 2019-05-15 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | INSTRUMENTS | 32
2019-03-31 | 42286 | Work Order Description - 42286 - CM | CM | 3 | 249017 | WSCHD | NORM-OPS | 2017-05-24 | 2019-06-18 | 2019-09-07 | 2019-09-09 | 2 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 42331 | Work Order Description - 42331 - PSPM | PSPM | 1 | 361127 | WSCHD | EQUIP-ISOL | 2017-05-18 | 2024-01-01 | 2021-03-18 | 2021-03-18 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 42789 | Work Order Description - 42789 - CM | CM | 4 | 137908 | WSCHD | NORM-OPS | 2018-02-09 | 2019-01-21 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 42805 | Work Order Description - 42805 - PSPM | PSPM | 1 | 399726 | WSCHD | EQUIP-ISOL | 2017-05-19 | 2020-10-01 | 2020-08-01 | 2020-08-01 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 42910 | Work Order Description - 42910 - CM | CM | 4 | 172651 | WPLAN | NORM-OPS | 2017-06-09 | 2018-12-28 | 2019-04-27 | 2019-05-02 | 3 | INTEGRITY | CONSTRUCTION | 56
2019-03-31 | 42911 | Work Order Description - 42911 - CM | CM | 4 | 172651 | WPLAN | NORM-OPS | 2017-06-09 | 2019-08-22 | 2019-04-27 | 2019-05-02 | 4 | INTEGRITY | CONSTRUCTION | 56
2019-03-31 | 42913 | Work Order Description - 42913 - CM | CM | 4 | 172651 | WPLAN | NORM-OPS | 2017-06-09 | 2019-02-08 | 2019-06-01 | 2019-06-06 | 4 | INTEGRITY | CONSTRUCTION | 56
2019-03-31 | 42916 | Work Order Description - 42916 - CM | CM | 4 | 172651 | WSCHD | NORM-OPS | 2019-03-25 | 2020-03-06 | 2019-05-25 | 2019-06-05 | 3 | INTEGRITY | FABRIC | 240
2019-03-31 | 42927 | Work Order Description - 42927 - CM | CM | 4 | 303827 | SCHD | NORM-OPS | 2019-01-27 | 2020-01-08 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | FABRIC | 441
2019-03-31 | 42945 | Work Order Description - 42945 - CM | CM | 3 | 457370 | WPLAN | SYS-ISOL | 2017-06-09 | 2019-05-19 | 2020-05-02 | 2020-05-04 | 4 | INTEGRITY | CONSTRUCTION | 42
2019-03-31 | 42946 | Work Order Description - 42946 - CM | CM | 3 | 457370 | WSCHD | NORM-OPS | 2018-02-22 | 2019-05-19 | 2019-05-11 | 2019-05-12 | 4 | INTEGRITY | CONSTRUCTION | 21
2019-03-31 | 42972 | Work Order Description - 42972 - CM | CM | 3 | 501061 | WSCHD | SYS-ISOL | 2018-06-15 | 2020-01-06 | 2019-05-04 | 2019-05-06 | 3 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 42996 | Work Order Description - 42996 - CM | CM | 4 | 33413 | WSCHD | NORM-OPS | 2017-05-29 | 2019-05-21 | 2019-04-13 | 2019-04-29 | 3 | OPERATIONS | OPERATIONS | 112
2019-03-31 | 43010 | Work Order Description - 43010 - PM | PM | 4 | 327351 | WSCHD | EQUIP-ISOL | 2017-05-22 | 2019-07-23 | 2019-09-28 | 2019-09-28 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 43036 | Work Order Description - 43036 - PM | PM | 4 | 18985 | WSCHD | EQUIP-ISOL | 2017-05-22 | 2020-01-13 | 2022-03-31 | 2022-04-02 | 2 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 43471 | Work Order Description - 43471 - CM | CM | 4 | 501457 | SCHD | NORM-OPS | 2018-12-24 | 2019-11-01 | 2019-04-13 | 2019-04-13 | 3 | INTEGRITY | FABRIC | 34
2019-03-31 | 43476 | Work Order Description - 43476 - CM | CM | 3 | 327719 | WSCHD | TPS | 2017-05-24 | 2019-07-20 | 2019-05-05 | 2019-05-07 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 43499 | Work Order Description - 43499 - CM | CM | 3 | 370154 | WPLAN | NORM-OPS | 2017-06-09 | 2019-08-06 | 2019-05-11 | 2019-05-11 | 4 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 43502 | Work Order Description - 43502 - CM | CM | 3 | 26799 | SCHD | SYS-ISOL | 2018-09-05 | 2019-06-05 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 43506 | Work Order Description - 43506 - PSCM | PSCM | 1 | 578829 | SCHD | PACK-ISOL | 2018-09-06 | 2019-05-23 | 2019-05-04 | 2019-05-04 | 4 | WELLS | WELLS | 12
2019-03-31 | 43513 | Work Order Description - 43513 - PSCM | PSCM | 1 | 578790 | SCHD | PACK-ISOL | 2018-07-18 | 2019-05-23 | 2019-05-04 | 2019-05-04 | 4 | WELLS | WELLS | 12
2019-03-31 | 43532 | Work Order Description - 43532 - CM | CM | 3 | 463402 | SCHD | TPS | 2018-09-06 | 2019-04-11 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 43905 | Work Order Description - 43905 - CM | CM | 1 | 531854 | SCHD | NORM-OPS | 2019-03-11 | 2019-05-24 | 2019-03-30 | 2019-04-07 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 43922 | Work Order Description - 43922 - CM | CM | 3 | 470089 | SCHD | SYS-ISOL | 2018-09-05 | 2019-08-12 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 43962 | Work Order Description - 43962 - CM | CM | 2 | 322888 | WSCHD | NORM-OPS | 2017-06-30 | 2019-10-24 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 43963 | Work Order Description - 43963 - CM | CM | 2 | 471732 | WSCHD | NORM-OPS | 2018-01-05 | 2019-05-03 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 43968 | Work Order Description - 43968 - CM | CM | 2 | 520589 | WSCHD | NORM-OPS | 2018-02-09 | 2019-01-24 | 2019-06-01 | 2019-06-04 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 44427 | Work Order Description - 44427 - CM | CM | 3 | 272734 | WSCHD | SYS-ISOL | 2017-07-10 | 2019-06-14 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 61
2019-03-31 | 44429 | Work Order Description - 44429 - CM | CM | 3 | 308208 | WSCHD | NORM-OPS | 2017-06-05 | 2019-03-21 | 2019-09-07 | 2019-09-09 | 3 | MAINTENANCE | INSTRUMENTS | 38
2019-03-31 | 44460 | Work Order Description - 44460 - CM | CM | 1 | 697913 | WPLAN | NORM-OPS | 2018-06-08 | 2019-09-01 | 2019-05-18 | 2019-05-18 | 3 | INTEGRITY | CONSTRUCTION | 4
2019-03-31 | 44461 | Work Order Description - 44461 - CM | CM | 1 | 697913 | WPLAN | NORM-OPS | 2018-06-08 | 2019-09-01 | 2019-05-18 | 2019-05-18 | 3 | INTEGRITY | CONSTRUCTION | 4
2019-03-31 | 44462 | Work Order Description - 44462 - CM | CM | 1 | 697913 | WPLAN | NORM-OPS | 2017-06-06 | 2019-04-19 | 2019-04-13 | 2019-04-14 | 3 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 44594 | Work Order Description - 44594 - PSPM | PSPM | 1 | 465443 | SCHD | PACK-ISOL | 2018-10-09 | 2019-09-02 | 2019-06-08 | 2019-06-08 | 3 | WELLS | WELLS | 6
2019-03-31 | 44658 | Work Order Description - 44658 - CM | CM | 4 | 671209 | WSCHD | NORM-OPS | 2017-07-22 | 2018-12-07 | 2019-04-06 | 2019-04-07 | 3 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 44864 | Work Order Description - 44864 - CM | CM | 4 | 496734 | WSCHD | SYS-ISOL | 2017-09-08 | 2019-06-21 | 2019-07-06 | 2019-07-07 | 3 | INTEGRITY | CONSTRUCTION | 31
2019-03-31 | 44878 | Work Order Description - 44878 - CM | CM | 3 | 312718 | WPLAN | SYS-ISOL | 2017-08-29 | 2018-12-21 | 2020-06-13 | 2020-06-13 | 3 | MAINTENANCE | CONSTRUCTION | 4
2019-03-31 | 44930 | Work Order Description - 44930 - CM | CM | 3 | 26511 | SCHD | TPS | 2018-07-18 | 2019-03-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 47207 | Work Order Description - 47207 - BR | BR | 1 | 227941 | SCHD | NORM-OPS | 2018-06-21 | 2019-10-31 | 2019-04-21 | 2019-04-21 | 4 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 47246 | Work Order Description - 47246 - BR | BR | 4 | 500959 | SCHD | SYS-ISOL | 2018-09-06 | 2019-10-31 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 34
2019-03-31 | 47261 | Work Order Description - 47261 - CM | CM | 4 | 243594 | SCHD | NORM-OPS | 2018-09-06 | 2019-10-31 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | DRILLING | 24
2019-03-31 | 47267 | Work Order Description - 47267 - PM | PM | 4 | 356944 | WSCHD | EQUIP-ISOL | 2017-11-02 | 2019-08-04 | 2019-05-25 | 2019-05-27 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 47268 | Work Order Description - 47268 - PM | PM | 4 | 308563 | WSCHD | EQUIP-ISOL | 2017-11-02 | 2019-07-25 | 2019-04-20 | 2019-04-21 | 2 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 47271 | Work Order Description - 47271 - PM | PM | 4 | 357285 | WSCHD | EQUIP-ISOL | 2017-11-02 | 2019-05-15 | 2019-10-26 | 2019-10-28 | 2 | MAINTENANCE | ELECTRICAL | 30
2019-03-31 | 47300 | Work Order Description - 47300 - PM | PM | 4 | 436705 | SCHD | NORM-OPS | 2018-04-07 | 2019-11-07 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | INSPECTION | 1
2019-03-31 | 47301 | Work Order Description - 47301 - PM | PM | 4 | 185409 | SCHD | NORM-OPS | 2018-04-07 | 2019-03-20 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | INSPECTION | 1
2019-03-31 | 47349 | Work Order Description - 47349 - PSCM | PSCM | 1 | 321834 | WSCHD | TPS | 2018-09-26 | 2019-11-01 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 57
2019-03-31 | 47350 | Work Order Description - 47350 - PSCM | PSCM | 1 | 321833 | WSCHD | TPS | 2018-09-26 | 2019-11-01 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 62
2019-03-31 | 47354 | Work Order Description - 47354 - CM | CM | 4 | 449176 | INPRG | SYS-ISOL | 2018-07-07 | 2019-03-31 | 2018-06-01 | 2018-06-01 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 47391 | Work Order Description - 47391 - PSCM | PSCM | 1 | 502738 | WSCHD | TPS | 2018-09-26 | 2019-11-01 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 37
2019-03-31 | 47547 | Work Order Description - 47547 - CM | CM | 4 | 245879 | WSCHD | TPS | 2017-11-19 | 2019-07-06 | 2020-01-01 | 2020-01-01 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 47582 | Work Order Description - 47582 - PM | PM | 4 | 656290 | WSCHD | PACK-ISOL | 2017-11-04 | 2019-07-14 | 2019-04-13 | 2019-04-16 | 2 | INTEGRITY | MECHANICAL | 65
2019-03-31 | 47585 | Work Order Description - 47585 - PM | PM | 4 | 676326 | SCHD | NORM-OPS | 2018-10-29 | 2019-07-04 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 47709 | Work Order Description - 47709 - CM | CM | 4 | 419551 | WSCHD | NORM-OPS | 2017-12-21 | 2019-11-03 | 2019-06-01 | 2019-06-01 | 4 | DRILLING | DRILLING | 183
2019-03-31 | 47717 | Work Order Description - 47717 - CM | CM | 4 | 465033 | WPLAN | NORM-OPS | 2017-11-22 | 2019-11-03 | 2020-02-29 | 2020-02-29 | 4 | INTEGRITY | CONSTRUCTION | 14
2019-03-31 | 47738 | Work Order Description - 47738 - BR | BR | 3 | 392511 | SCHD | NORM-OPS | 2019-02-13 | 2019-11-04 | 2019-04-28 | 2019-04-28 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 47763 | Work Order Description - 47763 - PM | PM | 4 | 309717 | SCHD | PACK-ISOL | 2018-07-06 | 2019-11-11 | 2019-08-24 | 2019-08-24 | 1 | INTEGRITY | MECHANICAL | 18
2019-03-31 | 47856 | Work Order Description - 47856 - PSPM | PSPM | 1 | 487831 | SCHD | EQUIP-ISOL | 2018-09-06 | 2020-01-01 | 2019-10-05 | 2019-10-05 | 1 | INTEGRITY | MECHANICAL | 6
2019-03-31 | 47882 | Work Order Description - 47882 - BR | BR | 2 | 33804 | WSCHD | ON LINE | 2017-11-27 | 2019-11-05 | 2019-07-06 | 2019-07-08 | 4 | MAINTENANCE | CONSTRUCTION | 44
2019-03-31 | 48229 | Work Order Description - 48229 - BR | BR | 3 | 490625 | SCHD | SYS-ISOL | 2018-07-18 | 2019-11-07 | 2024-06-01 | 2024-06-01 | 4 | INTEGRITY | MECHANICAL | 64
2019-03-31 | 48233 | Work Order Description - 48233 - BR | BR | 4 | 403537 | SCHD | TPS | 2018-11-05 | 2018-12-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 48349 | Work Order Description - 48349 - CM | CM | 3 | 254102 | SCHD | PACK-ISOL | 2018-09-06 | 2019-11-08 | 2019-08-03 | 2019-08-06 | 4 | MAINTENANCE | MECHANICAL | 144
2019-03-31 | 48450 | Work Order Description - 48450 - PM | PM | 4 | 262750 | SCHD | NORM-OPS | 2018-06-21 | 2019-08-24 | 2020-04-11 | 2020-04-11 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 48454 | Work Order Description - 48454 - PM | PM | 4 | 464225 | SCHD | NORM-OPS | 2018-06-21 | 2019-07-05 | 2019-05-18 | 2019-05-18 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 48524 | Work Order Description - 48524 - BR | BR | 2 | 51243 | WSCHD | EQUIP-ISOL | 2018-06-08 | 2019-04-15 | 2020-05-03 | 2020-05-08 | 2 | MAINTENANCE | INSTRUMENTS | 78
2019-03-31 | 48527 | Work Order Description - 48527 - PRJ | PRJ | 2 | 306714 | SCHD | SYS-ISOL | 2018-01-12 | 2019-01-04 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 48599 | Work Order Description - 48599 - CM | CM | 2 | 172651 | WSCHD | NORM-OPS | 2017-11-11 | 2019-11-10 | 2019-09-28 | 2019-09-29 | 4 | INTEGRITY | FABRIC | 14
2019-03-31 | 48611 | Work Order Description - 48611 - CM | CM | 4 | 464583 | SCHD | NORM-OPS | 2018-09-06 | 2019-11-10 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | DRILLING | 37
2019-03-31 | 48709 | Work Order Description - 48709 - BR | BR | 3 | 449077 | WMATL | NORM-OPS | 2017-12-01 | 2019-11-11 | 2019-05-04 | 2019-05-04 | 4 | INTEGRITY | MECHANICAL | 7
2019-03-31 | 48718 | Work Order Description - 48718 - PSCM | PSCM | 1 | 551696 | SCHD | NORM-OPS | 2018-09-06 | 2019-11-11 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 48777 | Work Order Description - 48777 - BR | BR | 3 | 666130 | WSCHD | SYS-ISOL | 2017-11-23 | 2019-10-21 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 48799 | Work Order Description - 48799 - CM | CM | 4 | 479578 | WPLAN | NORM-OPS | 2017-11-22 | 2020-02-01 | 2019-06-01 | 2019-06-01 | 3 | INTEGRITY | FABRIC | 250
2019-03-31 | 48823 | Work Order Description - 48823 - CM | CM | 1 | 403817 | SCHD | NORM-OPS | 2019-01-25 | 2019-04-26 | 2019-04-20 | 2019-05-01 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 48828 | Work Order Description - 48828 - CM | CM | 1 | 403817 | WPLAN | NORM-OPS | 2017-11-22 | 2019-08-01 | 2019-07-13 | 2019-07-13 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 48959 | Work Order Description - 48959 - BR | BR | 3 | 545222 | WSCHD | SYS-ISOL | 2018-05-26 | 2019-11-14 | 2019-04-27 | 2019-05-28 | 4 | MAINTENANCE | MECHANICAL | 292.5
2019-03-31 | 48965 | Work Order Description - 48965 - BR | BR | 1 | 368216 | WPLAN | NORM-OPS | 2018-02-14 | 2019-11-13 | 2019-08-31 | 2019-09-08 | 4 | MAINTENANCE | ELECTRICAL | 94
2019-03-31 | 49251 | Work Order Description - 49251 - CM | CM | 2 | 314370 | SCHD | ON LINE | 2019-03-22 | 2019-12-04 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | FABRIC | 108
2019-03-31 | 49255 | Work Order Description - 49255 - CM | CM | 2 | 408344 | WSCHD | TPS | 2018-11-17 | 2019-11-14 | 2019-08-03 | 2019-08-04 | 4 | INTEGRITY | CONSTRUCTION | 120
2019-03-31 | 49409 | Work Order Description - 49409 - PM | PM | 4 | 314161 | WSCHD | EQUIP-ISOL | 2017-11-16 | 2019-10-04 | 2019-05-04 | 2019-05-06 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 49410 | Work Order Description - 49410 - PM | PM | 4 | 308465 | WSCHD | EQUIP-ISOL | 2017-11-16 | 2019-04-02 | 2019-04-27 | 2019-05-01 | 2 | MAINTENANCE | INSTRUMENTS | 29
2019-03-31 | 49517 | Work Order Description - 49517 - CM | CM | 2 | 18465 | WSCHD | NORM-OPS | 2017-12-01 | 2019-11-15 | 2019-06-01 | 2019-06-03 | 4 | MAINTENANCE | DRILLING | 30
2019-03-31 | 49526 | Work Order Description - 49526 - CM | CM | 4 | 458749 | SCHD | NORM-OPS | 2018-09-06 | 2019-11-15 | 2019-09-07 | 2019-09-08 | 4 | MAINTENANCE | INSTRUMENTS | 39
2019-03-31 | 49528 | Work Order Description - 49528 - CM | CM | 4 | 25682 | SCHD | NORM-OPS | 2018-09-06 | 2019-11-15 | 2019-03-16 | 2019-03-17 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 49530 | Work Order Description - 49530 - CM | CM | 3 | 105753 | WMATL | SYS-ISOL | 2019-02-13 | 2019-08-05 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 49531 | Work Order Description - 49531 - CM | CM | 3 | 504052 | SCHD | SYS-ISOL | 2018-09-06 | 2018-12-13 | 2019-09-21 | 2019-09-21 | 2 | MAINTENANCE | MECHANICAL | 51
2019-03-31 | 49538 | Work Order Description - 49538 - PM | PM | 4 | 666277 | WSCHD | NORM-OPS | 2018-08-05 | 2019-08-13 | 2019-05-04 | 2019-05-05 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 49649 | Work Order Description - 49649 - CM | CM | 3 | 520388 | SCHD | PACK-ISOL | 2018-10-29 | 2019-10-22 | 2019-04-20 | 2019-04-21 | 3 | WELLS | MECHANICAL | 8
2019-03-31 | 49650 | Work Order Description - 49650 - CM | CM | 2 | 50241 | WSCHD | NORM-OPS | 2017-12-01 | 2019-11-16 | 2019-04-20 | 2019-04-21 | 4 | MAINTENANCE | DRILLING | 13
2019-03-31 | 49656 | Work Order Description - 49656 - CM | CM | 3 | 520389 | SCHD | PACK-ISOL | 2018-10-29 | 2019-01-17 | 2019-04-20 | 2019-04-21 | 3 | WELLS | MECHANICAL | 8
2019-03-31 | 49661 | Work Order Description - 49661 - CM | CM | 2 | 481607 | SCHD | SYS-ISOL | 2018-09-06 | 2019-11-16 | 2019-08-24 | 2019-08-24 | 4 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 49684 | Work Order Description - 49684 - CM | CM | 1 | 260432 | WSCHD | SYS-ISOL | 2018-06-19 | 2019-11-16 | 2020-05-03 | 2020-05-03 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 49689 | Work Order Description - 49689 - PSCM | PSCM | 4 | 185355 | SCHD | NORM-OPS | 2018-09-06 | 2019-07-02 | 2019-02-16 | 2019-02-16 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 49784 | Work Order Description - 49784 - PSPM | PSPM | 4 | 326081 | WSCHD | EQUIP-ISOL | 2017-11-19 | 2019-08-17 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 49785 | Work Order Description - 49785 - PM | PM | 4 | 489638 | SCHD | PACK-ISOL | 2018-12-05 | 2019-01-12 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 15
2019-03-31 | 49786 | Work Order Description - 49786 - PM | PM | 4 | 489638 | SCHD | PACK-ISOL | 2018-12-05 | 2019-09-22 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 15
2019-03-31 | 49800 | Work Order Description - 49800 - PM | PM | 4 | 308896 | WSCHD | NORM-OPS | 2017-11-19 | 2019-07-11 | 2020-12-12 | 2020-12-12 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 49814 | Work Order Description - 49814 - PM | PM | 4 | 305553 | WSCHD | EQUIP-ISOL | 2017-11-19 | 2019-07-31 | 2020-03-07 | 2020-03-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 49827 | Work Order Description - 49827 - PM | PM | 3 | 360342 | WSCHD | EQUIP-ISOL | 2017-11-19 | 2019-05-30 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 49910 | Work Order Description - 49910 - BR | BR | 3 | 324360 | WSCHD | NORM-OPS | 2017-11-28 | 2019-12-15 | 2019-08-03 | 2019-08-05 | 2 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 50047 | Work Order Description - 50047 - CM | CM | 4 | 186054 | WMATL | PACK-ISOL | 2017-11-24 | 2019-07-05 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 50150 | Work Order Description - 50150 - BR | BR | 3 | 308482 | WSCHD | ON LINE | 2017-11-24 | 2019-11-23 | 2019-04-20 | 2019-04-24 | 4 | MAINTENANCE | MECHANICAL | 64
2019-03-31 | 50163 | Work Order Description - 50163 - BR | BR | 4 | 471235 | SCHD | SYS-ISOL | 2018-09-06 | 2019-11-20 | 2019-08-01 | 2019-08-01 | 4 | INTEGRITY | DRILLING | 30
2019-03-31 | 50271 | Work Order Description - 50271 - CM | CM | 4 | 106036 | SCHD | NORM-OPS | 2019-02-13 | 2019-11-21 | 2019-09-21 | 2019-09-21 | 4 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 50274 | Work Order Description - 50274 - BR | BR | 3 | 325453 | WMATL | SYS-ISOL | 2017-12-27 | 2019-11-21 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 50275 | Work Order Description - 50275 - BR | BR | 3 | 671601 | WSCHD | PACK-ISOL | 2018-08-03 | 2019-11-21 | 2019-09-07 | 2019-09-13 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 50300 | Work Order Description - 50300 - BR | BR | 3 | 321218 | WSCHD | PACK-ISOL | 2017-11-23 | 2019-02-18 | 2019-04-20 | 2019-04-21 | 2 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 50312 | Work Order Description - 50312 - PM | PM | 2 | 321115 | WSCHD | NORM-OPS | 2017-11-23 | 2018-12-27 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 50364 | Work Order Description - 50364 - CM | CM | 4 | 323096 | WSCHD | PACK-ISOL | 2017-11-23 | 2019-09-10 | 2019-04-26 | 2019-04-26 | 3 | MAINTENANCE | SERVICES | 7
2019-03-31 | 50381 | Work Order Description - 50381 - CM | CM | 4 | 19009 | WSCHD | NORM-OPS | 2017-12-07 | 2019-03-28 | 2019-09-07 | 2019-09-09 | 3 | INTEGRITY | INSTRUMENTS | 79
2019-03-31 | 50411 | Work Order Description - 50411 - CM | CM | 1 | 489300 | WSCHD | NORM-OPS | 2019-03-01 | 2019-07-01 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 50429 | Work Order Description - 50429 - BR | BR | 1 | 489326 | SCHD | NORM-OPS | 2018-11-26 | 2019-11-22 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 50558 | Work Order Description - 50558 - PRJ | PRJ | 4 | 652220 | SCHD | PACK-ISOL | 2019-03-28 | 2019-07-14 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | SERVICES | 140
2019-03-31 | 50563 | Work Order Description - 50563 - CM | CM | 4 | 499459 | WSCHD | NORM-OPS | 2017-11-30 | 2019-04-05 | 2019-09-07 | 2019-09-09 | 3 | MAINTENANCE | INSTRUMENTS | 31
2019-03-31 | 50567 | Work Order Description - 50567 - CM | CM | 4 | 53511 | WSCHD | NORM-OPS | 2017-12-07 | 2019-08-31 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | INSTRUMENTS | 5
2019-03-31 | 50574 | Work Order Description - 50574 - CM | CM | 4 | 527272 | SCHD | NORM-OPS | 2018-06-21 | 2019-11-23 | 2019-05-04 | 2019-05-06 | 4 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 52099 | Work Order Description - 52099 - PSPM | PSPM | 1 | 677353 | WSCHD | PACK-ISOL | 2017-11-27 | 2019-06-01 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 52109 | Work Order Description - 52109 - PM | PM | 4 | 25391 | SCHD | NORM-OPS | 2018-09-06 | 2019-01-18 | 2020-03-07 | 2020-03-07 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 52167 | Work Order Description - 52167 - BR | BR | 3 | 469774 | SCHD | SYS-ISOL | 2018-09-06 | 2019-11-27 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | MECHANICAL | 50
2019-03-31 | 52171 | Work Order Description - 52171 - BR | BR | 3 | 503636 | SCHD | SYS-ISOL | 2018-09-06 | 2019-01-16 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 50
2019-03-31 | 52175 | Work Order Description - 52175 - CM | CM | 1 | 484754 | WSCHD | TPS | 2018-07-16 | 2019-11-26 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 52188 | Work Order Description - 52188 - CM | CM | 4 | 656202 | SCHD | NORM-OPS | 2018-09-07 | 2019-04-13 | 2019-04-06 | 2019-04-07 | 3 | INTEGRITY | INSTRUMENTS | 17
2019-03-31 | 52201 | Work Order Description - 52201 - CM | CM | 4 | 408309 | WSCHD | SYS-ISOL | 2017-11-29 | 2019-06-14 | 2019-07-06 | 2019-07-07 | 3 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 52203 | Work Order Description - 52203 - CM | CM | 1 | 17814 | WSCHD | NORM-OPS | 2018-07-16 | 2019-11-26 | 2019-05-11 | 2019-05-12 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 52209 | Work Order Description - 52209 - CM | CM | 4 | 74832 | SCHD | NORM-OPS | 2018-06-21 | 2020-01-01 | 2019-04-16 | 2019-04-21 | 4 | DRILLING | DRILLING | 1
2019-03-31 | 52217 | Work Order Description - 52217 - CM | CM | 4 | 237407 | WPLAN | NORM-OPS | 2018-02-26 | 2019-11-06 | 2019-04-21 | 2019-04-27 | 4 | INTEGRITY | FABRIC | 147
2019-03-31 | 52245 | Work Order Description - 52245 - BR | BR | 1 | 450910 | SCHD | PACK-ISOL | 2018-11-20 | 2019-07-01 | 2019-07-13 | 2019-07-13 | 3 | OPERATIONS | MECHANICAL | 1
2019-03-31 | 52287 | Work Order Description - 52287 - PM | PM | 4 | 25391 | SCHD | NORM-OPS | 2018-07-18 | 2019-09-07 | 2020-03-07 | 2020-03-07 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 52288 | Work Order Description - 52288 - PM | PM | 4 | 25391 | SCHD | NORM-OPS | 2018-07-18 | 2019-03-13 | 2020-03-07 | 2020-03-07 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 52409 | Work Order Description - 52409 - CM | CM | 1 | 527137 | WPLAN | NORM-OPS | 2018-08-03 | 2020-07-27 | 2019-09-21 | 2019-09-21 | 4 | OPERATIONS | MECHANICAL | 7
2019-03-31 | 52411 | Work Order Description - 52411 - CM | CM | 4 | 252063 | WSCHD | NORM-OPS | 2017-12-02 | 2019-01-07 | 2019-06-01 | 2019-06-01 | 3 | DRILLING | DRILLING | 50
2019-03-31 | 52461 | Work Order Description - 52461 - CM | CM | 4 | 675122 | WSCHD | NORM-OPS | 2017-11-29 | 2019-08-24 | 2019-07-27 | 2019-07-29 | 3 | MAINTENANCE | INSTRUMENTS | 31
2019-03-31 | 52464 | Work Order Description - 52464 - CM | CM | 4 | 485513 | WSCHD | NORM-OPS | 2017-11-29 | 2019-03-24 | 2019-07-27 | 2019-07-27 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 52587 | Work Order Description - 52587 - PM | PM | 4 | 669989 | SCHD | NORM-OPS | 2018-03-30 | 2019-09-18 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | INSPECTION | 1
2019-03-31 | 52588 | Work Order Description - 52588 - PM | PM | 4 | 127844 | SCHD | NORM-OPS | 2018-03-30 | 2020-01-09 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | INSPECTION | 1
2019-03-31 | 52589 | Work Order Description - 52589 - PM | PM | 4 | 74889 | SCHD | NORM-OPS | 2018-03-30 | 2019-04-16 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | INSPECTION | 1
2019-03-31 | 52645 | Work Order Description - 52645 - CM | CM | 4 | 137521 | WSCHD | NORM-OPS | 2017-12-06 | 2019-04-01 | 2019-09-07 | 2019-09-10 | 3 | MAINTENANCE | INSTRUMENTS | 37
2019-03-31 | 52666 | Work Order Description - 52666 - CM | CM | 4 | 674307 | WSCHD | NORM-OPS | 2017-12-13 | 2019-11-28 | 2019-07-20 | 2019-07-21 | 4 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 52789 | Work Order Description - 52789 - PM | PM | 4 | 680977 | WSCHD | EQUIP-ISOL | 2017-11-30 | 2018-12-11 | 2019-04-13 | 2019-04-15 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 52797 | Work Order Description - 52797 - PM | PM | 4 | 399630 | WSCHD | EQUIP-ISOL | 2017-11-30 | 2019-08-25 | 2019-08-31 | 2019-08-31 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 52861 | Work Order Description - 52861 - CM | CM | 4 | 295961 | WSCHD | NORM-OPS | 2018-01-04 | 2019-02-18 | 2019-05-18 | 2019-05-19 | 3 | MAINTENANCE | INSTRUMENTS | 31
2019-03-31 | 52868 | Work Order Description - 52868 - BR | BR | 3 | 502591 | SCHD | PACK-ISOL | 2018-09-06 | 2019-12-07 | 2019-05-25 | 2019-05-26 | 4 | MAINTENANCE | INSTRUMENTS | 26
2019-03-31 | 52871 | Work Order Description - 52871 - CM | CM | 3 | 254785 | WMATL | TPS | 2018-01-10 | 2019-11-29 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 52885 | Work Order Description - 52885 - BR | BR | 3 | 399524 | WSCHD | SYS-ISOL | 2018-09-15 | 2019-11-29 | 2019-05-24 | 2019-05-24 | 4 | MAINTENANCE | MECHANICAL | 50
2019-03-31 | 52896 | Work Order Description - 52896 - BR | BR | 3 | 666130 | WSCHD | SYS-ISOL | 2018-09-15 | 2019-01-24 | 2019-12-01 | 2019-12-01 | 3 | MAINTENANCE | MECHANICAL | 56
2019-03-31 | 52921 | Work Order Description - 52921 - BR | BR | 3 | 138432 | WSCHD | SYS-ISOL | 2018-05-16 | 2019-11-29 | 2019-09-07 | 2019-09-09 | 4 | MAINTENANCE | MECHANICAL | 23
2019-03-31 | 52929 | Work Order Description - 52929 - CM | CM | 3 | 481324 | WSCHD | NORM-OPS | 2018-11-17 | 2019-11-29 | 2019-07-12 | 2019-07-13 | 4 | INTEGRITY | FABRIC | 73
2019-03-31 | 52962 | Work Order Description - 52962 - PM | PM | 4 | 309157 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-04-13 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | DRILLING | 6
2019-03-31 | 53056 | Work Order Description - 53056 - BR | BR | 4 | 361950 | WSCHD | SYS-ISOL | 2017-12-07 | 2019-09-07 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 53064 | Work Order Description - 53064 - BR | BR | 4 | 399585 | WPLAN | SYS-ISOL | 2017-12-06 | 2019-06-03 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 53066 | Work Order Description - 53066 - BR | BR | 4 | 361951 | WSCHD | SYS-ISOL | 2017-12-07 | 2019-08-23 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 53068 | Work Order Description - 53068 - BR | BR | 4 | 399586 | WSCHD | SYS-ISOL | 2017-12-07 | 2019-10-07 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 53091 | Work Order Description - 53091 - BR | BR | 3 | 323293 | SCHD | NORM-OPS | 2018-10-29 | 2018-12-29 | 2019-04-20 | 2019-04-21 | 3 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 53140 | Work Order Description - 53140 - PM | PM | 4 | 308468 | WSCHD | EQUIP-ISOL | 2017-12-02 | 2019-11-07 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 53141 | Work Order Description - 53141 - PM | PM | 4 | 19020 | WSCHD | EQUIP-ISOL | 2017-12-02 | 2019-04-08 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | INSTRUMENTS | 3
2019-03-31 | 53189 | Work Order Description - 53189 - PM | PM | 4 | 401613 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-03-14 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 53190 | Work Order Description - 53190 - PM | PM | 4 | 409192 | SCHD | NORM-OPS | 2018-09-06 | 2019-01-14 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 53191 | Work Order Description - 53191 - PM | PM | 4 | 30523 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-05-07 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 53193 | Work Order Description - 53193 - PM | PM | 4 | 401609 | SCHD | EQUIP-ISOL | 2018-04-20 | 2019-07-29 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 53195 | Work Order Description - 53195 - PM | PM | 4 | 409190 | SCHD | EQUIP-ISOL | 2018-09-06 | 2020-01-22 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 53196 | Work Order Description - 53196 - PM | PM | 4 | 303990 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-12-31 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 54603 | Work Order Description - 54603 - BR | BR | 4 | 273535 | WSCHD | NORM-OPS | 2018-04-05 | 2019-12-01 | 2019-06-24 | 2019-06-24 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 54607 | Work Order Description - 54607 - CM | CM | 1 | 484917 | WPLAN | SYS-ISOL | 2018-02-18 | 2019-12-01 | 2019-09-07 | 2019-09-10 | 4 | INTEGRITY | CONSTRUCTION | 24
2019-03-31 | 54611 | Work Order Description - 54611 - CM | CM | 3 | 467877 | WPLAN | SYS-ISOL | 2018-02-16 | 2019-12-01 | 2020-05-02 | 2020-05-05 | 4 | INTEGRITY | CONSTRUCTION | 16
2019-03-31 | 54624 | Work Order Description - 54624 - BR | BR | 1 | 553243 | WSCHD | NORM-OPS | 2018-03-02 | 2019-12-01 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 54636 | Work Order Description - 54636 - BR | BR | 2 | 325482 | SCHD | NORM-OPS | 2018-07-06 | 2019-12-01 | 2019-05-18 | 2019-05-18 | 4 | MAINTENANCE | MECHANICAL | 45
2019-03-31 | 54650 | Work Order Description - 54650 - PM | PM | 4 | 546656 | WSCHD | NORM-OPS | 2017-12-03 | 2019-12-24 | 2020-02-09 | 2020-02-09 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 54652 | Work Order Description - 54652 - PM | PM | 4 | 308893 | WSCHD | NORM-OPS | 2017-12-03 | 2019-04-16 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 54653 | Work Order Description - 54653 - PM | PM | 4 | 137564 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-11-11 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 54657 | Work Order Description - 54657 - PM | PM | 4 | 308893 | WSCHD | NORM-OPS | 2017-12-03 | 2019-11-07 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 54768 | Work Order Description - 54768 - BR | BR | 2 | 312718 | SCHD | SYS-ISOL | 2018-07-18 | 2019-12-07 | 2019-11-16 | 2019-11-17 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 54780 | Work Order Description - 54780 - CM | CM | 4 | 496734 | SCHD | SYS-ISOL | 2018-11-15 | 2020-01-01 | 2019-04-27 | 2019-04-30 | 4 | INTEGRITY | MECHANICAL | 41
2019-03-31 | 54792 | Work Order Description - 54792 - BR | BR | 4 | 520042 | WPLAN | PACK-ISOL | 2017-12-07 | 2019-05-04 | 2019-06-01 | 2019-06-04 | 3 | MAINTENANCE | MECHANICAL | 49
2019-03-31 | 54815 | Work Order Description - 54815 - CM | CM | 3 | 503968 | WMATL | TPS | 2018-12-05 | 2019-12-09 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 56
2019-03-31 | 54838 | Work Order Description - 54838 - CM | CM | 3 | 310166 | SCHD | NORM-OPS | 2019-02-13 | 2021-02-10 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | FABRIC | 0
2019-03-31 | 54928 | Work Order Description - 54928 - CM | CM | 4 | 188422 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-05 | 2019-08-24 | 2019-08-24 | 4 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 54952 | Work Order Description - 54952 - CM | CM | 4 | 307843 | WSCHD | NORM-OPS | 2018-09-21 | 2019-12-05 | 2019-04-27 | 2019-05-01 | 4 | MAINTENANCE | MECHANICAL | 60
2019-03-31 | 54968 | Work Order Description - 54968 - BR | BR | 2 | 126924 | SCHD | NORM-OPS | 2018-06-21 | 2019-06-15 | 2019-06-15 | 2019-06-20 | 2 | INTEGRITY | CONSTRUCTION | 67
2019-03-31 | 55016 | Work Order Description - 55016 - CM | CM | 4 | 527273 | SCHD | ON LINE | 2018-06-21 | 2019-12-06 | 2019-05-18 | 2019-05-23 | 4 | MAINTENANCE | MECHANICAL | 56
2019-03-31 | 55040 | Work Order Description - 55040 - BR | BR | 3 | 465450 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-07 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 55042 | Work Order Description - 55042 - CM | CM | 4 | 185355 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-07 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 69
2019-03-31 | 55072 | Work Order Description - 55072 - CM | CM | 4 | 476491 | WSCHD | NORM-OPS | 2018-03-06 | 2020-01-04 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 55149 | Work Order Description - 55149 - CM | CM | 4 | 322633 | WPLAN | TPS | 2017-12-09 | 2019-12-08 | 2020-12-01 | 2020-12-02 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 55248 | Work Order Description - 55248 - CM | CM | 4 | 479375 | SCHD | NORM-OPS | 2018-06-21 | 2019-04-28 | 2019-03-23 | 2019-03-23 | 3 | MAINTENANCE | DRILLING | 57
2019-03-31 | 55256 | Work Order Description - 55256 - BR | BR | 4 | 472258 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-10 | 2019-09-14 | 2019-09-14 | 4 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 55261 | Work Order Description - 55261 - BR | BR | 4 | 479551 | WPLAN | NORM-OPS | 2018-12-21 | 2019-12-10 | 2019-11-02 | 2019-11-02 | 4 | INTEGRITY | SERVICES | 48
2019-03-31 | 55303 | Work Order Description - 55303 - BR | BR | 3 | 50864 | WSCHD | SYS-ISOL | 2017-12-29 | 2019-12-10 | 2019-09-28 | 2019-09-28 | 4 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 55326 | Work Order Description - 55326 - CM | CM | 1 | 403817 | WPLAN | NORM-OPS | 2018-01-03 | 2019-08-29 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | CONSTRUCTION | 80
2019-03-31 | 55327 | Work Order Description - 55327 - CM | CM | 4 | 262744 | WSCHD | NORM-OPS | 2019-03-25 | 2019-10-31 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | CONSTRUCTION | 217
2019-03-31 | 55349 | Work Order Description - 55349 - BR | BR | 3 | 74978 | SCHD | NORM-OPS | 2018-08-30 | 2019-01-07 | 2019-09-07 | 2019-09-10 | 2 | ENGINEERING | CONSTRUCTION | 42
2019-03-31 | 55353 | Work Order Description - 55353 - BR | BR | 3 | 43398 | SCHD | PACK-ISOL | 2019-02-13 | 2020-01-16 | 2019-04-24 | 2019-04-25 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 55407 | Work Order Description - 55407 - PM | PM | 4 | 541035 | WSCHD | NORM-OPS | 2017-12-13 | 2018-12-08 | 2020-12-05 | 2020-12-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 55440 | Work Order Description - 55440 - PM | PM | 4 | 314530 | WSCHD | EQUIP-ISOL | 2018-08-24 | 2019-03-28 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 55441 | Work Order Description - 55441 - PM | PM | 4 | 674224 | WSCHD | EQUIP-ISOL | 2018-08-24 | 2019-02-10 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 55444 | Work Order Description - 55444 - PM | PM | 4 | 400439 | WSCHD | EQUIP-ISOL | 2018-08-24 | 2019-10-22 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 55469 | Work Order Description - 55469 - PM | PM | 4 | 58419 | WSCHD | SUBSYS-ISOL | 2017-12-13 | 2019-07-19 | 2019-09-21 | 2019-09-21 | 1 | MAINTENANCE | OPERATIONS | 4
2019-03-31 | 55474 | Work Order Description - 55474 - PM | PM | 4 | 399940 | WSCHD | EQUIP-ISOL | 2017-12-13 | 2019-01-09 | 2020-05-02 | 2020-05-02 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 55482 | Work Order Description - 55482 - PM | PM | 4 | 19020 | WSCHD | EQUIP-ISOL | 2017-12-13 | 2019-05-11 | 2019-06-22 | 2019-06-22 | 2 | INTEGRITY | ELECTRICAL | 4
2019-03-31 | 55484 | Work Order Description - 55484 - PM | PM | 4 | 546030 | SCHD | NORM-OPS | 2018-10-29 | 2019-12-12 | 2019-05-04 | 2019-05-05 | 1 | MAINTENANCE | SERVICES | 14
2019-03-31 | 55505 | Work Order Description - 55505 - PSPM | PSPM | 1 | 361094 | WSCHD | EQUIP-ISOL | 2018-07-09 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 55617 | Work Order Description - 55617 - PM | PM | 4 | 478652 | WSCHD | SYS-ISOL | 2019-03-25 | 2019-07-17 | 2019-05-01 | 2019-05-01 | 2 | INTEGRITY | MECHANICAL | 32
2019-03-31 | 55622 | Work Order Description - 55622 - PM | PM | 4 | 479825 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-04-01 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | DRILLING | 8
2019-03-31 | 55787 | Work Order Description - 55787 - BR | BR | 1 | 651077 | SCHD | NORM-OPS | 2019-02-22 | 2019-12-12 | 2019-06-22 | 2019-06-23 | 4 | MAINTENANCE | MECHANICAL | 58
2019-03-31 | 56297 | Work Order Description - 56297 - BR | BR | 4 | 362951 | WSCHD | NORM-OPS | 2018-08-08 | 2019-12-28 | 2019-06-08 | 2019-06-10 | 4 | MAINTENANCE | MECHANICAL | 63
2019-03-31 | 56299 | Work Order Description - 56299 - BR | BR | 1 | 531923 | WSCHD | NORM-OPS | 2018-09-14 | 2019-12-12 | 2019-05-04 | 2019-05-05 | 4 | MAINTENANCE | MECHANICAL | 91.5
2019-03-31 | 56330 | Work Order Description - 56330 - PSPM | PSPM | 1 | 399830 | WSCHD | TPS | 2019-01-30 | 2019-05-20 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | CONSTRUCTION | 34
2019-03-31 | 56403 | Work Order Description - 56403 - BR | BR | 4 | 652220 | WSCHD | NORM-OPS | 2017-12-14 | 2019-12-13 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | SERVICES | 1
2019-03-31 | 56409 | Work Order Description - 56409 - CM | CM | 4 | 493747 | SCHD | NORM-OPS | 2018-09-04 | 2019-12-07 | 2019-03-09 | 2019-03-10 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 56421 | Work Order Description - 56421 - CM | CM | 3 | 482154 | WPLAN | SYS-ISOL | 2017-12-23 | 2019-01-27 | 2020-03-07 | 2020-03-07 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 56621 | Work Order Description - 56621 - BR | BR | 4 | 226882 | WSCHD | SYS-ISOL | 2018-09-15 | 2021-01-01 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | MECHANICAL | 44
2019-03-31 | 56622 | Work Order Description - 56622 - CM | CM | 3 | 36116 | WPLAN | PACK-ISOL | 2017-12-26 | 2019-12-14 | 2019-04-20 | 2019-05-02 | 4 | WELLS | WELLS | 5244
2019-03-31 | 56635 | Work Order Description - 56635 - BR | BR | 3 | 58372 | WSCHD | PACK-ISOL | 2018-01-07 | 2020-01-06 | 2019-04-20 | 2019-04-21 | 4 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 56637 | Work Order Description - 56637 - PSCM | PSCM | 1 | 679719 | WSCHD | SUBSYS-ISOL | 2018-08-05 | 2019-06-01 | 2019-09-07 | 2019-09-20 | 3 | MAINTENANCE | INSTRUMENTS | 95
2019-03-31 | 56638 | Work Order Description - 56638 - PSCM | PSCM | 1 | 58335 | WSCHD | PACK-ISOL | 2018-01-31 | 2019-05-01 | 2019-09-07 | 2019-09-09 | 3 | MAINTENANCE | INSTRUMENTS | 37
2019-03-31 | 56660 | Work Order Description - 56660 - PM | PM | 3 | 261979 | WSCHD | PACK-ISOL | 2017-12-16 | 2019-02-09 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 56661 | Work Order Description - 56661 - PM | PM | 3 | 57142 | WSCHD | PACK-ISOL | 2017-12-16 | 2019-10-21 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 56662 | Work Order Description - 56662 - PM | PM | 3 | 360508 | WSCHD | PACK-ISOL | 2017-12-16 | 2019-01-01 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 56663 | Work Order Description - 56663 - PM | PM | 3 | 53170 | WSCHD | PACK-ISOL | 2017-12-16 | 2020-01-19 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 56664 | Work Order Description - 56664 - PM | PM | 3 | 53174 | WSCHD | PACK-ISOL | 2017-12-16 | 2019-12-21 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 56665 | Work Order Description - 56665 - PM | PM | 3 | 54465 | WSCHD | PACK-ISOL | 2017-12-16 | 2019-04-03 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 56666 | Work Order Description - 56666 - PM | PM | 3 | 53175 | WSCHD | PACK-ISOL | 2017-12-16 | 2019-03-09 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 56667 | Work Order Description - 56667 - PM | PM | 3 | 409626 | WSCHD | PACK-ISOL | 2017-12-16 | 2019-09-05 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 56670 | Work Order Description - 56670 - PM | PM | 3 | 360513 | WSCHD | PACK-ISOL | 2017-12-16 | 2019-08-20 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 56671 | Work Order Description - 56671 - PM | PM | 3 | 53176 | WSCHD | PACK-ISOL | 2017-12-16 | 2020-01-08 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 56672 | Work Order Description - 56672 - PM | PM | 3 | 360514 | WSCHD | PACK-ISOL | 2017-12-16 | 2019-12-19 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 56673 | Work Order Description - 56673 - PM | PM | 3 | 53566 | WSCHD | PACK-ISOL | 2017-12-16 | 2019-03-17 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 56674 | Work Order Description - 56674 - PM | PM | 3 | 410053 | WSCHD | PACK-ISOL | 2017-12-16 | 2019-01-09 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 56677 | Work Order Description - 56677 - PM | PM | 4 | 531885 | SCHD | EQUIP-ISOL | 2018-09-03 | 2019-10-23 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | INSTRUMENTS | 3
2019-03-31 | 56680 | Work Order Description - 56680 - PSPM | PSPM | 1 | 357608 | WSCHD | PACK-ISOL | 2018-10-29 | 2020-01-01 | 2019-10-26 | 2019-10-26 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 56685 | Work Order Description - 56685 - PSPM | PSPM | 1 | 54069 | WSCHD | PACK-ISOL | 2017-12-16 | 2019-05-01 | 2019-10-26 | 2019-10-26 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 56686 | Work Order Description - 56686 - PSPM | PSPM | 1 | 399508 | WSCHD | PACK-ISOL | 2017-12-16 | 2019-05-01 | 2019-10-26 | 2019-10-26 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 56721 | Work Order Description - 56721 - PM | PM | 2 | 188988 | SCHD | SYS-ISOL | 2018-09-06 | 2018-12-16 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 56722 | Work Order Description - 56722 - PM | PM | 2 | 310082 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-06-27 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 57039 | Work Order Description - 57039 - CM | CM | 4 | 25221 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-15 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 57040 | Work Order Description - 57040 - CM | CM | 3 | 310208 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-15 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 57041 | Work Order Description - 57041 - CM | CM | 4 | 309889 | SCHD | NORM-OPS | 2018-09-04 | 2019-07-25 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 57170 | Work Order Description - 57170 - BR | BR | 4 | 127403 | WPLAN | NORM-OPS | 2017-12-26 | 2019-12-16 | 2019-10-31 | 2019-11-03 | 4 | INTEGRITY | INSPECTION | 21
2019-03-31 | 57172 | Work Order Description - 57172 - PRJ | PRJ | 4 | 216388 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-16 | 2019-11-02 | 2019-11-03 | 4 | DRILLING | ELECTRICAL | 1
2019-03-31 | 57178 | Work Order Description - 57178 - BR | BR | 4 | 451510 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-25 | 2019-09-08 | 2019-09-09 | 4 | INTEGRITY | CONSTRUCTION | 21
2019-03-31 | 57385 | Work Order Description - 57385 - BR | BR | 3 | 656290 | WSCHD | SYS-ISOL | 2018-02-09 | 2019-11-09 | 2019-04-13 | 2019-04-14 | 3 | INTEGRITY | MECHANICAL | 1
2019-03-31 | 57559 | Work Order Description - 57559 - BR | BR | 1 | 465450 | WPLAN | PACK-ISOL | 2018-01-05 | 2019-12-18 | 2019-10-12 | 2019-10-12 | 4 | WELLS | WELLS | 1
2019-03-31 | 57647 | Work Order Description - 57647 - PSPM | PSPM | 1 | 399727 | WSCHD | EQUIP-ISOL | 2018-06-20 | 2020-08-01 | 2020-01-04 | 2020-01-04 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 57670 | Work Order Description - 57670 - PSPM | PSPM | 1 | 107669 | WSCHD | PACK-ISOL | 2018-07-06 | 2019-09-02 | 2019-07-20 | 2019-07-20 | 3 | WELLS | WELLS | 6
2019-03-31 | 57751 | Work Order Description - 57751 - CM | CM | 1 | 228839 | SCHD | NORM-OPS | 2018-12-24 | 2019-07-01 | 2019-06-06 | 2019-06-06 | 3 | INTEGRITY | CONSTRUCTION | 98.5
2019-03-31 | 57956 | Work Order Description - 57956 - CM | CM | 4 | 403404 | SCHD | PACK-ISOL | 2018-07-06 | 2019-06-10 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 57958 | Work Order Description - 57958 - CM | CM | 4 | 464229 | WPLAN | NORM-OPS | 2019-01-27 | 2020-01-08 | 2019-09-21 | 2019-09-24 | 3 | INTEGRITY | FABRIC | 216
2019-03-31 | 57960 | Work Order Description - 57960 - CM | CM | 2 | 499045 | SCHD | NORM-OPS | 2019-03-29 | 2019-09-25 | 2019-08-10 | 2019-08-11 | 3 | MAINTENANCE | FABRIC | 84
2019-03-31 | 57962 | Work Order Description - 57962 - CM | CM | 3 | 320153 | WPLAN | NORM-OPS | 2017-12-27 | 2019-10-09 | 2020-03-28 | 2020-03-29 | 3 | INTEGRITY | SERVICES | 72
2019-03-31 | 57985 | Work Order Description - 57985 - CM | CM | 4 | 478275 | SCHD | ON LINE | 2018-03-09 | 2019-12-20 | 2020-02-29 | 2020-02-29 | 4 | INTEGRITY | FABRIC | 1
2019-03-31 | 57990 | Work Order Description - 57990 - CM | CM | 4 | 402290 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-20 | 2019-07-20 | 2019-07-20 | 4 | INTEGRITY | FABRIC | 6
2019-03-31 | 57993 | Work Order Description - 57993 - CM | CM | 4 | 316146 | SCHD | NORM-OPS | 2018-09-06 | 2019-05-11 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | SERVICES | 42
2019-03-31 | 58032 | Work Order Description - 58032 - CM | CM | 4 | 320396 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-20 | 2019-08-10 | 2019-08-10 | 4 | INTEGRITY | FABRIC | 60
2019-03-31 | 58035 | Work Order Description - 58035 - CM | CM | 3 | 320396 | SCHD | NORM-OPS | 2019-02-13 | 2021-02-06 | 2019-06-08 | 2019-06-08 | 4 | INTEGRITY | FABRIC | 160
2019-03-31 | 58059 | Work Order Description - 58059 - BR | BR | 3 | 666257 | WSCHD | TPS | 2018-06-12 | 2019-12-20 | 2020-05-02 | 2020-05-10 | 4 | MAINTENANCE | MECHANICAL | 35
2019-03-31 | 58240 | Work Order Description - 58240 - BR | BR | 3 | 322415 | WSCHD | SYS-ISOL | 2018-09-15 | 2018-12-05 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 58
2019-03-31 | 58242 | Work Order Description - 58242 - BR | BR | 3 | 327297 | WSCHD | SYS-ISOL | 2018-09-15 | 2019-11-11 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 58252 | Work Order Description - 58252 - PSCM | PSCM | 4 | 57928 | WSCHD | NORM-OPS | 2018-02-11 | 2019-12-21 | 2019-08-03 | 2019-08-12 | 4 | MAINTENANCE | INSTRUMENTS | 70
2019-03-31 | 58359 | Work Order Description - 58359 - CM | CM | 4 | 177242 | SCHD | NORM-OPS | 2018-07-06 | 2019-10-19 | 2019-06-08 | 2019-06-08 | 2 | MAINTENANCE | ELECTRICAL | 63
2019-03-31 | 58471 | Work Order Description - 58471 - BR | BR | 3 | 57128 | WSCHD | PACK-ISOL | 2017-12-24 | 2019-06-02 | 2019-04-13 | 2019-04-16 | 3 | MAINTENANCE | INSTRUMENTS | 42
2019-03-31 | 58491 | Work Order Description - 58491 - BR | BR | 4 | 678028 | WSCHD | NORM-OPS | 2018-01-10 | 2019-07-07 | 2019-06-01 | 2019-06-04 | 3 | MAINTENANCE | DRILLING | 24
2019-03-31 | 58714 | Work Order Description - 58714 - PM | PM | 4 | 399485 | WSCHD | EQUIP-ISOL | 2017-12-27 | 2019-01-27 | 2019-06-01 | 2019-06-01 | 2 | INTEGRITY | DRILLING | 4
2019-03-31 | 58797 | Work Order Description - 58797 - CM | CM | 4 | 58163 | SCHD | SYS-ISOL | 2018-12-05 | 2019-12-28 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 58815 | Work Order Description - 58815 - PM | PM | 4 | 137550 | WSCHD | EQUIP-ISOL | 2017-12-28 | 2019-09-22 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 58816 | Work Order Description - 58816 - PM | PM | 4 | 471679 | SCHD | EQUIP-ISOL | 2018-09-07 | 2019-04-13 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 58832 | Work Order Description - 58832 - PM | PM | 2 | 480203 | WSCHD | PACK-ISOL | 2017-12-28 | 2020-01-08 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 58840 | Work Order Description - 58840 - PM | PM | 4 | 490496 | SCHD | PACK-ISOL | 2018-05-30 | 2019-12-16 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 58841 | Work Order Description - 58841 - PM | PM | 3 | 409531 | SCHD | PACK-ISOL | 2018-05-30 | 2019-12-08 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 58844 | Work Order Description - 58844 - PM | PM | 4 | 408873 | SCHD | PACK-ISOL | 2018-05-30 | 2019-10-23 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 58928 | Work Order Description - 58928 - CM | CM | 4 | 95502 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-27 | 2019-10-12 | 2019-10-12 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 58929 | Work Order Description - 58929 - BR | BR | 2 | 501036 | WPLAN | SYS-ISOL | 2018-05-06 | 2019-12-27 | 2019-10-12 | 2019-10-12 | 4 | INTEGRITY | SERVICES | 161
2019-03-31 | 59125 | Work Order Description - 59125 - PM | PM | 4 | 399632 | WSCHD | EQUIP-ISOL | 2017-12-30 | 2019-12-23 | 2019-08-31 | 2019-08-31 | 1 | INTEGRITY | CONSTRUCTION | 7
2019-03-31 | 59217 | Work Order Description - 59217 - PM | PM | 4 | 308894 | WSCHD | NORM-OPS | 2017-12-31 | 2019-07-07 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 59259 | Work Order Description - 59259 - PSPM | PSPM | 1 | 547543 | WSCHD | NORM-OPS | 2017-12-31 | 2020-09-01 | 2020-03-06 | 2020-03-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 59401 | Work Order Description - 59401 - PM | PM | 4 | 318813 | SCHD | PACK-ISOL | 2018-10-29 | 2020-01-25 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 59466 | Work Order Description - 59466 - PM | PM | 4 | 438720 | SCHD | PACK-ISOL | 2018-06-07 | 2019-04-18 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 59467 | Work Order Description - 59467 - PM | PM | 4 | 176856 | SCHD | EQUIP-ISOL | 2018-06-07 | 2019-01-27 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 59474 | Work Order Description - 59474 - PM | PM | 3 | 478664 | SCHD | EQUIP-ISOL | 2018-05-24 | 2019-02-14 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 59478 | Work Order Description - 59478 - PM | PM | 4 | 554809 | SCHD | NORM-OPS | 2018-07-06 | 2019-07-04 | 2019-05-04 | 2019-05-04 | 1 | INTEGRITY | MEDIC | 4
2019-03-31 | 59518 | Work Order Description - 59518 - PM | PM | 4 | 375476 | SCHD | NORM-OPS | 2018-05-11 | 2019-12-17 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | INSPECTION | 1
2019-03-31 | 59519 | Work Order Description - 59519 - PM | PM | 3 | 127842 | SCHD | NORM-OPS | 2018-05-11 | 2019-08-09 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | INSPECTION | 1
2019-03-31 | 59520 | Work Order Description - 59520 - PM | PM | 4 | 74890 | SCHD | NORM-OPS | 2018-05-11 | 2020-01-23 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | INSPECTION | 1
2019-03-31 | 59521 | Work Order Description - 59521 - PM | PM | 4 | 448768 | SCHD | NORM-OPS | 2018-05-11 | 2018-12-16 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | INSPECTION | 1
2019-03-31 | 59522 | Work Order Description - 59522 - PM | PM | 4 | 127843 | SCHD | NORM-OPS | 2018-05-11 | 2020-01-15 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | INSPECTION | 1
2019-03-31 | 59523 | Work Order Description - 59523 - PM | PM | 4 | 375477 | SCHD | NORM-OPS | 2018-05-11 | 2019-08-09 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | INSPECTION | 1
2019-03-31 | 61525 | Work Order Description - 61525 - PSPM | PSPM | 1 | 595630 | WSCHD | EQUIP-ISOL | 2018-01-03 | 2020-01-01 | 2019-05-18 | 2019-05-19 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 61526 | Work Order Description - 61526 - PM | PM | 4 | 248463 | WSCHD | EQUIP-ISOL | 2018-01-03 | 2019-11-04 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 61529 | Work Order Description - 61529 - PSPM | PSPM | 1 | 361921 | WSCHD | NORM-OPS | 2018-05-29 | 2021-09-01 | 2019-04-30 | 2019-04-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 61616 | Work Order Description - 61616 - BR | BR | 4 | 25473 | SCHD | NORM-OPS | 2018-09-06 | 2020-01-02 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | DRILLING | 8
2019-03-31 | 61622 | Work Order Description - 61622 - CM | CM | 1 | 356355 | SCHD | NORM-OPS | 2018-12-10 | 2020-01-02 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 61624 | Work Order Description - 61624 - BR | BR | 1 | 546779 | SCHD | NORM-OPS | 2018-12-10 | 2020-01-02 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 61646 | Work Order Description - 61646 - BR | BR | 3 | 478661 | WMATL | TPS | 2018-02-06 | 2019-10-24 | 2019-07-13 | 2019-07-13 | 2 | INTEGRITY | MECHANICAL | 3
2019-03-31 | 61885 | Work Order Description - 61885 - BR | BR | 1 | 361898 | WPLAN | PACK-ISOL | 2018-01-06 | 2020-01-04 | 2019-06-01 | 2019-06-06 | 4 | MAINTENANCE | MECHANICAL | 102
2019-03-31 | 61924 | Work Order Description - 61924 - CM | CM | 1 | 356355 | SCHD | NORM-OPS | 2018-12-03 | 2020-01-04 | 2019-04-13 | 2019-04-15 | 4 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 61951 | Work Order Description - 61951 - PM | PM | 3 | 363614 | WSCHD | EQUIP-ISOL | 2018-01-06 | 2020-01-17 | 2019-04-27 | 2019-04-28 | 1 | INTEGRITY | INSTRUMENTS | 12
2019-03-31 | 62053 | Work Order Description - 62053 - BR | BR | 1 | 670511 | WPLAN | TPS | 2018-12-17 | 2020-01-05 | 2019-07-18 | 2019-07-18 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 62055 | Work Order Description - 62055 - CM | CM | 3 | 316077 | WSCHD | TPS | 2019-03-25 | 2020-07-30 | 2019-07-13 | 2019-07-13 | 3 | INTEGRITY | CONSTRUCTION | 3
2019-03-31 | 62329 | Work Order Description - 62329 - BR | BR | 4 | 368215 | WSCHD | NORM-OPS | 2018-03-02 | 2020-01-07 | 2019-05-04 | 2019-05-08 | 4 | INTEGRITY | CONSTRUCTION | 17
2019-03-31 | 62391 | Work Order Description - 62391 - BR | BR | 4 | 545298 | WSCHD | NORM-OPS | 2018-02-23 | 2020-01-07 | 2019-04-20 | 2019-04-21 | 4 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 62537 | Work Order Description - 62537 - CM | CM | 4 | 327967 | WPLAN | TPS | 2018-09-26 | 2020-01-08 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 57
2019-03-31 | 62538 | Work Order Description - 62538 - CM | CM | 4 | 323091 | WSCHD | TPS | 2018-09-26 | 2020-01-08 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 58
2019-03-31 | 62540 | Work Order Description - 62540 - CM | CM | 4 | 323092 | WPLAN | TPS | 2018-09-26 | 2020-01-08 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 68
2019-03-31 | 62550 | Work Order Description - 62550 - PM | PM | 4 | 314873 | SCHD | EQUIP-ISOL | 2018-09-25 | 2019-11-11 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 62553 | Work Order Description - 62553 - PM | PM | 4 | 272729 | SCHD | EQUIP-ISOL | 2018-09-25 | 2019-02-26 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 62556 | Work Order Description - 62556 - PM | PM | 4 | 399771 | WSCHD | EQUIP-ISOL | 2018-01-09 | 2019-06-15 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 11
2019-03-31 | 62557 | Work Order Description - 62557 - PM | PM | 4 | 653434 | WSCHD | EQUIP-ISOL | 2018-01-09 | 2019-03-10 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 62558 | Work Order Description - 62558 - PM | PM | 4 | 656245 | WSCHD | EQUIP-ISOL | 2018-01-09 | 2019-09-12 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 62559 | Work Order Description - 62559 - PM | PM | 4 | 359198 | WSCHD | EQUIP-ISOL | 2018-01-09 | 2019-04-06 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 62564 | Work Order Description - 62564 - PM | PM | 4 | 272734 | SCHD | EQUIP-ISOL | 2018-09-25 | 2019-01-26 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 62751 | Work Order Description - 62751 - PM | PM | 4 | 671828 | WSCHD | PACK-ISOL | 2018-07-18 | 2019-08-26 | 2019-04-27 | 2019-04-28 | 1 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 62754 | Work Order Description - 62754 - PM | PM | 4 | 363674 | SCHD | PACK-ISOL | 2018-10-23 | 2019-09-16 | 2019-04-20 | 2019-04-21 | 1 | INTEGRITY | INSTRUMENTS | 15
2019-03-31 | 62755 | Work Order Description - 62755 - PM | PM | 4 | 56429 | WSCHD | EQUIP-ISOL | 2018-01-10 | 2018-12-18 | 2019-04-27 | 2019-04-28 | 1 | INTEGRITY | INSTRUMENTS | 15
2019-03-31 | 62756 | Work Order Description - 62756 - PM | PM | 4 | 363675 | SCHD | PACK-ISOL | 2018-10-29 | 2019-03-19 | 2019-05-04 | 2019-05-05 | 1 | INTEGRITY | MECHANICAL | 15
2019-03-31 | 62877 | Work Order Description - 62877 - CM | CM | 3 | 383836 | WPLAN | NORM-OPS | 2018-03-10 | 2020-01-10 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 62907 | Work Order Description - 62907 - CM | CM | 3 | 312683 | WRISKREV | PACK-ISOL | 2019-03-19 | 2018-12-26 | 2020-02-01 | 2020-03-07 | 3 | MAINTENANCE | MECHANICAL | 2456
2019-03-31 | 62969 | Work Order Description - 62969 - BR | BR | 3 | 403201 | SCHD | PACK-ISOL | 2018-07-08 | 2020-01-07 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 62978 | Work Order Description - 62978 - PM | PM | 4 | 25392 | SCHD | NORM-OPS | 2018-07-06 | 2020-01-06 | 2019-04-13 | 2019-04-13 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 63070 | Work Order Description - 63070 - CM | CM | 1 | 320396 | WPLAN | NORM-OPS | 2018-03-24 | 2020-01-11 | 2019-06-29 | 2019-06-29 | 4 | INTEGRITY | FABRIC | 60
2019-03-31 | 63073 | Work Order Description - 63073 - CM | CM | 4 | 320396 | WPLAN | NORM-OPS | 2018-02-07 | 2019-08-01 | 2019-06-22 | 2019-06-22 | 3 | INTEGRITY | FABRIC | 60
2019-03-31 | 63092 | Work Order Description - 63092 - BR | BR | 4 | 320396 | WPLAN | NORM-OPS | 2018-05-08 | 2019-10-20 | 2019-06-15 | 2019-06-15 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 63095 | Work Order Description - 63095 - CM | CM | 4 | 320396 | WPLAN | NORM-OPS | 2018-02-07 | 2020-01-11 | 2019-06-15 | 2019-06-15 | 4 | INTEGRITY | FABRIC | 60
2019-03-31 | 63096 | Work Order Description - 63096 - BR | BR | 4 | 320396 | WPLAN | NORM-OPS | 2018-05-08 | 2020-01-11 | 2019-12-07 | 2019-12-07 | 4 | MAINTENANCE | INSPECTION | 1
2019-03-31 | 63244 | Work Order Description - 63244 - BR | BR | 4 | 481473 | WSCHD | NORM-OPS | 2018-01-14 | 2020-01-12 | 2019-05-04 | 2019-05-04 | 4 | OPERATIONS | DRILLING | 80
2019-03-31 | 63401 | Work Order Description - 63401 - PSPM | PSPM | 1 | 57148 | WSCHD | PACK-ISOL | 2018-01-15 | 2020-01-01 | 2019-07-27 | 2019-07-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 63428 | Work Order Description - 63428 - PSPM | PSPM | 1 | 357620 | WSCHD | PACK-ISOL | 2018-01-15 | 2020-01-01 | 2019-10-05 | 2019-10-05 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 63429 | Work Order Description - 63429 - PSPM | PSPM | 1 | 656066 | WSCHD | PACK-ISOL | 2018-01-15 | 2020-01-01 | 2019-10-05 | 2019-10-05 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 63430 | Work Order Description - 63430 - PSPM | PSPM | 1 | 653325 | WSCHD | PACK-ISOL | 2018-01-15 | 2020-01-01 | 2019-10-05 | 2019-10-05 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 63917 | Work Order Description - 63917 - PM | PM | 4 | 399591 | WSCHD | PACK-ISOL | 2018-01-16 | 2019-10-02 | 2019-10-05 | 2019-10-05 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 63918 | Work Order Description - 63918 - PM | PM | 4 | 653329 | WSCHD | PACK-ISOL | 2018-01-16 | 2019-06-15 | 2019-10-05 | 2019-10-05 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 63974 | Work Order Description - 63974 - CM | CM | 2 | 266420 | SCHD | NORM-OPS | 2018-06-21 | 2020-01-15 | 2019-04-30 | 2019-05-01 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 64039 | Work Order Description - 64039 - CM | CM | 4 | 368279 | WSCHD | NORM-OPS | 2018-11-22 | 2020-01-15 | 2019-05-18 | 2019-05-19 | 4 | INTEGRITY | FABRIC | 127.8
2019-03-31 | 64045 | Work Order Description - 64045 - CM | CM | 3 | 375725 | SCHD | NORM-OPS | 2018-06-21 | 2020-01-15 | 2019-08-18 | 2019-08-19 | 4 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 64157 | Work Order Description - 64157 - CM | CM | 3 | 487505 | SCHD | SYS-ISOL | 2019-03-18 | 2019-01-31 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | INSTRUMENTS | 104
2019-03-31 | 64171 | Work Order Description - 64171 - CM | CM | 4 | 403817 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-31 | 2019-06-01 | 2019-06-08 | 3 | INTEGRITY | CONSTRUCTION | 292
2019-03-31 | 64173 | Work Order Description - 64173 - PRJ | PRJ | 4 | 403817 | WPLAN | NORM-OPS | 2018-04-28 | 2020-01-09 | 2019-04-27 | 2019-04-27 | 4 | DRILLING | DRILLING | 1
2019-03-31 | 64189 | Work Order Description - 64189 - PRJ | PRJ | 4 | 321115 | WSCHD | PACK-ISOL | 2018-01-19 | 2019-05-01 | 2019-06-01 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 850
2019-03-31 | 64193 | Work Order Description - 64193 - PRJ | PRJ | 4 | 480203 | WSCHD | PACK-ISOL | 2019-03-28 | 2019-06-03 | 2019-04-20 | 2019-04-22 | 4 | MAINTENANCE | MECHANICAL | 954
2019-03-31 | 64217 | Work Order Description - 64217 - BR | BR | 4 | 138089 | SCHD | NORM-OPS | 2018-12-03 | 2020-01-16 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 64237 | Work Order Description - 64237 - PSPM | PSPM | 1 | 361183 | WSCHD | EQUIP-ISOL | 2018-01-18 | 2020-01-01 | 2019-09-07 | 2019-09-07 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 64459 | Work Order Description - 64459 - PSCM | PSCM | 4 | 294959 | SCHD | NORM-OPS | 2018-08-31 | 2019-12-10 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 64489 | Work Order Description - 64489 - PRJ | PRJ | 4 | 555933 | SCHD | SYS-ISOL | 2018-09-06 | 2020-01-17 | 2019-03-30 | 2019-03-30 | 4 | DRILLING | DRILLING | 1
2019-03-31 | 64493 | Work Order Description - 64493 - BR | BR | 1 | 552640 | SCHD | NORM-OPS | 2018-09-06 | 2020-05-05 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | DRILLING | 821.5
2019-03-31 | 64504 | Work Order Description - 64504 - PSPM | PSPM | 1 | 261082 | WSCHD | SYS-ISOL | 2018-11-14 | 2020-09-01 | 2019-08-31 | 2019-08-31 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 64510 | Work Order Description - 64510 - PSPM | PSPM | 4 | 73393 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-05-15 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | ELECTRICAL | 31
2019-03-31 | 64634 | Work Order Description - 64634 - CM | CM | 3 | 535962 | SCHD | SYS-ISOL | 2019-03-20 | 2020-01-18 | 2019-03-30 | 2019-04-14 | 4 | MAINTENANCE | OPERATIONS | 1
2019-03-31 | 64712 | Work Order Description - 64712 - PM | PM | 4 | 183627 | SCHD | EQUIP-ISOL | 2018-07-06 | 2019-01-15 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 64847 | Work Order Description - 64847 - CM | CM | 1 | 567229 | WMATL | NORM-OPS | 2018-01-26 | 2020-01-19 | 2019-07-27 | 2019-07-27 | 4 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 64851 | Work Order Description - 64851 - BR | BR | 4 | 448711 | WPLAN | NORM-OPS | 2018-06-04 | 2019-08-01 | 2019-05-25 | 2019-05-31 | 4 | INTEGRITY | INSPECTION | 140
2019-03-31 | 64868 | Work Order Description - 64868 - BR | BR | 4 | 403817 | SCHD | NORM-OPS | 2019-01-20 | 2020-01-19 | 2019-06-15 | 2019-06-15 | 4 | INTEGRITY | FABRIC | 180
2019-03-31 | 64878 | Work Order Description - 64878 - BR | BR | 3 | 36463 | SCHD | NORM-OPS | 2018-06-21 | 2018-12-15 | 2019-04-06 | 2019-04-07 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 64910 | Work Order Description - 64910 - PM | PM | 2 | 33427 | SCHD | NORM-OPS | 2018-10-29 | 2019-01-21 | 2019-04-20 | 2019-04-21 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 64916 | Work Order Description - 64916 - PSPM | PSPM | 1 | 399755 | WSCHD | EQUIP-ISOL | 2018-01-21 | 2020-01-01 | 2019-07-06 | 2019-07-06 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 65061 | Work Order Description - 65061 - CM | CM | 4 | 294916 | WSCHD | NORM-OPS | 2018-01-22 | 2019-05-23 | 2019-04-27 | 2019-05-01 | 2 | MAINTENANCE | ELECTRICAL | 30
2019-03-31 | 65077 | Work Order Description - 65077 - BR | BR | 3 | 465446 | SCHD | NORM-OPS | 2018-07-18 | 2019-02-09 | 2019-05-25 | 2019-05-25 | 3 | WELLS | MECHANICAL | 42
2019-03-31 | 65083 | Work Order Description - 65083 - CM | CM | 3 | 318619 | WSCHD | PACK-ISOL | 2018-01-28 | 2019-03-13 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 65183 | Work Order Description - 65183 - CM | CM | 4 | 498804 | WPLAN | NORM-OPS | 2018-02-07 | 2020-01-21 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | CONSTRUCTION | 176
2019-03-31 | 65184 | Work Order Description - 65184 - CM | CM | 4 | 419556 | WSCHD | NORM-OPS | 2018-02-15 | 2020-01-21 | 2019-06-01 | 2019-06-03 | 4 | DRILLING | DRILLING | 32
2019-03-31 | 65234 | Work Order Description - 65234 - BR | BR | 4 | 355461 | WPLAN | NORM-OPS | 2018-04-01 | 2019-07-24 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | CONSTRUCTION | 48
2019-03-31 | 65364 | Work Order Description - 65364 - PSCM | PSCM | 1 | 491591 | SCHD | NORM-OPS | 2018-07-18 | 2020-01-24 | 2019-10-05 | 2019-10-05 | 4 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 65371 | Work Order Description - 65371 - BR | BR | 4 | 311813 | SCHD | SYS-ISOL | 2018-09-06 | 2020-01-22 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | MECHANICAL | 19
2019-03-31 | 65386 | Work Order Description - 65386 - BR | BR | 3 | 663606 | SCHD | SYS-ISOL | 2018-07-09 | 2019-02-12 | 2019-07-13 | 2019-07-15 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 65428 | Work Order Description - 65428 - CM | CM | 3 | 553103 | SCHD | SYS-ISOL | 2018-11-20 | 2019-08-22 | 2019-05-04 | 2019-05-06 | 3 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 65429 | Work Order Description - 65429 - CM | CM | 4 | 546035 | WPLAN | NORM-OPS | 2018-06-16 | 2020-01-22 | 2019-04-27 | 2019-04-27 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 65442 | Work Order Description - 65442 - CM | CM | 3 | 308461 | WSCHD | NORM-OPS | 2018-03-16 | 2020-01-22 | 2019-07-06 | 2019-07-09 | 4 | MAINTENANCE | MECHANICAL | 22.5
2019-03-31 | 65443 | Work Order Description - 65443 - CM | CM | 3 | 308460 | WSCHD | NORM-OPS | 2018-01-26 | 2020-01-22 | 2019-07-06 | 2019-07-09 | 4 | MAINTENANCE | MECHANICAL | 55
2019-03-31 | 65449 | Work Order Description - 65449 - CM | CM | 4 | 653421 | WSCHD | NORM-OPS | 2018-01-24 | 2020-01-22 | 2019-04-06 | 2019-04-22 | 4 | MAINTENANCE | DRILLING | 114
2019-03-31 | 65470 | Work Order Description - 65470 - PM | PM | 4 | 303769 | SCHD | PACK-ISOL | 2018-05-30 | 2019-10-07 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 65471 | Work Order Description - 65471 - PM | PM | 4 | 476739 | SCHD | PACK-ISOL | 2018-06-21 | 2019-03-10 | 2019-08-17 | 2019-08-17 | 2 | DRILLING | DRILLING | 1
2019-03-31 | 65472 | Work Order Description - 65472 - PM | PM | 4 | 320715 | SCHD | PACK-ISOL | 2018-06-21 | 2019-08-12 | 2019-08-17 | 2019-08-17 | 2 | DRILLING | DRILLING | 1
2019-03-31 | 65473 | Work Order Description - 65473 - PM | PM | 4 | 552599 | SCHD | PACK-ISOL | 2018-06-21 | 2019-04-01 | 2019-08-17 | 2019-08-17 | 2 | DRILLING | DRILLING | 1
2019-03-31 | 65474 | Work Order Description - 65474 - PM | PM | 4 | 216594 | SCHD | PACK-ISOL | 2018-06-21 | 2019-01-18 | 2019-08-17 | 2019-08-17 | 2 | INTEGRITY | DRILLING | 14
2019-03-31 | 65475 | Work Order Description - 65475 - PM | PM | 4 | 502362 | SCHD | PACK-ISOL | 2018-06-21 | 2019-12-18 | 2019-07-06 | 2019-07-06 | 2 | INTEGRITY | DRILLING | 14
2019-03-31 | 65617 | Work Order Description - 65617 - CM | CM | 2 | 450548 | SCHD | NORM-OPS | 2018-06-21 | 2019-08-04 | 2019-04-28 | 2019-04-28 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 65697 | Work Order Description - 65697 - PRJ | PRJ | 4 | 479374 | SCHD | NORM-OPS | 2019-01-25 | 2020-01-24 | 2019-04-27 | 2019-04-27 | 4 | DRILLING | ELECTRICAL | 0
2019-03-31 | 65750 | Work Order Description - 65750 - BR | BR | 3 | 183855 | SCHD | SYS-ISOL | 2018-09-06 | 2020-01-24 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 65753 | Work Order Description - 65753 - BR | BR | 4 | 74229 | SCHD | NORM-OPS | 2018-08-24 | 2020-02-02 | 2019-10-05 | 2019-10-05 | 4 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 65784 | Work Order Description - 65784 - BR | BR | 4 | 375928 | SCHD | NORM-OPS | 2018-09-06 | 2019-03-23 | 2019-07-07 | 2019-07-11 | 3 | ENGINEERING | CONSTRUCTION | 58
2019-03-31 | 65857 | Work Order Description - 65857 - CM | CM | 4 | 460745 | WPLAN | PACK-ISOL | 2018-08-06 | 2019-04-23 | 2019-05-18 | 2019-05-19 | 3 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 65875 | Work Order Description - 65875 - PM | PM | 4 | 357113 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-04-25 | 2019-04-06 | 2019-04-07 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 65877 | Work Order Description - 65877 - PSPM | PSPM | 1 | 248423 | WSCHD | EQUIP-ISOL | 2018-01-26 | 2019-06-23 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 66013 | Work Order Description - 66013 - BR | BR | 1 | 670509 | SCHD | NORM-OPS | 2018-06-21 | 2020-01-25 | 2019-04-24 | 2019-04-24 | 4 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 66147 | Work Order Description - 66147 - CM | CM | 1 | 671829 | WSCHD | NORM-OPS | 2018-01-30 | 2019-07-01 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 66172 | Work Order Description - 66172 - PM | PM | 2 | 51220 | WSCHD | EQUIP-ISOL | 2018-01-28 | 2020-01-01 | 2020-07-26 | 2020-07-29 | 2 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 66194 | Work Order Description - 66194 - PM | PM | 4 | 401446 | SCHD | PACK-ISOL | 2018-05-30 | 2018-12-23 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 66336 | Work Order Description - 66336 - BR | BR | 4 | 492764 | WPLAN | NORM-OPS | 2019-01-20 | 2020-01-27 | 2020-02-29 | 2020-02-29 | 4 | MAINTENANCE | FABRIC | 584
2019-03-31 | 66338 | Work Order Description - 66338 - BR | BR | 1 | 492764 | WPLAN | NORM-OPS | 2018-02-18 | 2020-01-27 | 2019-11-09 | 2019-11-09 | 4 | MAINTENANCE | INSPECTION | 2
2019-03-31 | 66340 | Work Order Description - 66340 - BR | BR | 1 | 492764 | WPLAN | NORM-OPS | 2018-02-18 | 2020-01-27 | 2019-11-09 | 2019-11-09 | 4 | MAINTENANCE | INSPECTION | 1
2019-03-31 | 66381 | Work Order Description - 66381 - BR | BR | 2 | 555201 | SCHD | NORM-OPS | 2018-09-06 | 2019-04-07 | 2019-05-04 | 2019-05-04 | 3 | INTEGRITY | SERVICES | 48
2019-03-31 | 66382 | Work Order Description - 66382 - CM | CM | 4 | 659561 | WPLAN | NORM-OPS | 2019-01-09 | 2020-01-27 | 2019-09-01 | 2019-09-04 | 4 | INTEGRITY | CONSTRUCTION | 56
2019-03-31 | 66465 | Work Order Description - 66465 - BR | BR | 3 | 674225 | WSCHD | SYS-ISOL | 2018-03-29 | 2020-01-28 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 66526 | Work Order Description - 66526 - BR | BR | 4 | 403817 | SCHD | NORM-OPS | 2018-10-09 | 2020-02-02 | 2019-09-07 | 2019-09-07 | 4 | INTEGRITY | CONSTRUCTION | 42
2019-03-31 | 66611 | Work Order Description - 66611 - CM | CM | 3 | 259939 | SCHD | SYS-ISOL | 2018-09-06 | 2019-10-24 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 66617 | Work Order Description - 66617 - CM | CM | 1 | 484754 | WSCHD | NORM-OPS | 2018-03-30 | 2020-01-29 | 2019-04-13 | 2019-04-29 | 4 | INTEGRITY | FABRIC | 167.8
2019-03-31 | 66765 | Work Order Description - 66765 - PSPM | PSPM | 1 | 399541 | WSCHD | EQUIP-ISOL | 2018-01-31 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 66775 | Work Order Description - 66775 - CM | CM | 4 | 472798 | WPLAN | NORM-OPS | 2018-05-01 | 2019-05-01 | 2019-06-15 | 2019-06-20 | 3 | INTEGRITY | FABRIC | 84
2019-03-31 | 66782 | Work Order Description - 66782 - CM | CM | 4 | 567119 | WPLAN | NORM-OPS | 2018-05-01 | 2019-10-01 | 2019-06-29 | 2019-06-29 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 66929 | Work Order Description - 66929 - PM | PM | 4 | 308482 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-03-07 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 66930 | Work Order Description - 66930 - PM | PM | 4 | 671792 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-01-18 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 68610 | Work Order Description - 68610 - CM | CM | 4 | 17254 | WSCHD | NORM-OPS | 2019-02-22 | 2019-07-01 | 2019-04-13 | 2019-04-28 | 3 | INTEGRITY | INSPECTION | 1
2019-03-31 | 68662 | Work Order Description - 68662 - PM | PM | 3 | 409424 | SCHD | PACK-ISOL | 2018-05-24 | 2019-11-24 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 68666 | Work Order Description - 68666 - PM | PM | 4 | 396317 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-12-18 | 2019-05-25 | 2019-05-25 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 68764 | Work Order Description - 68764 - PSCM | PSCM | 1 | 671828 | WMATL | PACK-ISOL | 2018-04-02 | 2020-01-19 | 2019-04-13 | 2019-04-16 | 3 | MAINTENANCE | MECHANICAL | 37
2019-03-31 | 68775 | Work Order Description - 68775 - CM | CM | 3 | 671537 | WSCHD | SYS-ISOL | 2018-03-31 | 2020-02-01 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | MECHANICAL | 46
2019-03-31 | 68779 | Work Order Description - 68779 - PSCM | PSCM | 1 | 356357 | WSCHD | NORM-OPS | 2019-02-20 | 2020-05-18 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 68895 | Work Order Description - 68895 - PSCM | PSCM | 4 | 653823 | SCHD | NORM-OPS | 2019-03-22 | 2020-02-02 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 68898 | Work Order Description - 68898 - CM | CM | 4 | 402031 | INPRG | NORM-OPS | 2019-03-17 | 2020-02-02 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | MECHANICAL | 71
2019-03-31 | 68907 | Work Order Description - 68907 - PSCM | PSCM | 1 | 500414 | WSCHD | NORM-OPS | 2018-04-12 | 2020-02-02 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 69154 | Work Order Description - 69154 - CM | CM | 3 | 671828 | WPLAN | NORM-OPS | 2018-02-18 | 2019-02-26 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 69157 | Work Order Description - 69157 - CM | CM | 3 | 675036 | WPLAN | NORM-OPS | 2018-02-18 | 2020-01-05 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 69266 | Work Order Description - 69266 - CM | CM | 4 | 306078 | SCHD | NORM-OPS | 2018-09-06 | 2020-02-04 | 2020-01-04 | 2020-01-04 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 69277 | Work Order Description - 69277 - BR | BR | 3 | 481330 | SCHD | NORM-OPS | 2018-10-29 | 2019-01-24 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 69308 | Work Order Description - 69308 - BR | BR | 2 | 459860 | SCHD | NORM-OPS | 2018-09-06 | 2020-02-04 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 69317 | Work Order Description - 69317 - BR | BR | 3 | 357332 | WSCHD | EQUIP-ISOL | 2018-02-12 | 2019-11-08 | 2019-04-13 | 2019-04-14 | 2 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 69379 | Work Order Description - 69379 - PM | PM | 4 | 665119 | SCHD | EQUIP-ISOL | 2018-06-21 | 2020-01-23 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 69463 | Work Order Description - 69463 - CM | CM | 4 | 399727 | WSCHD | NORM-OPS | 2018-02-06 | 2019-02-14 | 2019-04-20 | 2019-04-21 | 3 | INTEGRITY | OPERATIONS | 8
2019-03-31 | 69465 | Work Order Description - 69465 - CM | CM | 4 | 399485 | WSCHD | NORM-OPS | 2018-02-06 | 2018-12-27 | 2019-05-25 | 2019-05-25 | 3 | INTEGRITY | OPERATIONS | 8
2019-03-31 | 69495 | Work Order Description - 69495 - CM | CM | 1 | 457402 | WSCHD | NORM-OPS | 2018-02-18 | 2020-02-05 | 2019-11-02 | 2019-11-03 | 4 | MAINTENANCE | ELECTRICAL | 63
2019-03-31 | 69522 | Work Order Description - 69522 - CM | CM | 4 | 477388 | WPLAN | PACK-ISOL | 2018-04-26 | 2019-07-07 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 69684 | Work Order Description - 69684 - PM | PM | 3 | 531859 | SCHD | PACK-ISOL | 2018-10-29 | 2018-12-08 | 2019-04-27 | 2019-04-28 | 1 | INTEGRITY | MECHANICAL | 2
2019-03-31 | 69685 | Work Order Description - 69685 - PM | PM | 3 | 56321 | SCHD | PACK-ISOL | 2018-10-29 | 2019-03-08 | 2019-04-27 | 2019-04-28 | 1 | INTEGRITY | MECHANICAL | 2
2019-03-31 | 69686 | Work Order Description - 69686 - PM | PM | 3 | 363639 | WSCHD | PACK-ISOL | 2018-06-27 | 2019-01-29 | 2019-05-25 | 2019-05-25 | 1 | INTEGRITY | MECHANICAL | 2
2019-03-31 | 69687 | Work Order Description - 69687 - PM | PM | 3 | 531879 | SCHD | PACK-ISOL | 2018-08-03 | 2019-10-25 | 2019-05-25 | 2019-05-27 | 1 | INTEGRITY | MECHANICAL | 2
2019-03-31 | 69726 | Work Order Description - 69726 - PM | PM | 4 | 485706 | WSCHD | EQUIP-ISOL | 2018-02-08 | 2019-05-27 | 2020-06-13 | 2020-06-14 | 2 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 69826 | Work Order Description - 69826 - CM | CM | 4 | 136684 | WPLAN | NORM-OPS | 2018-02-22 | 2020-02-07 | 2019-04-20 | 2019-04-28 | 4 | MAINTENANCE | DRILLING | 60
2019-03-31 | 69854 | Work Order Description - 69854 - CM | CM | 4 | 661010 | WPLAN | NORM-OPS | 2018-02-22 | 2020-02-07 | 2019-06-01 | 2019-06-03 | 4 | DRILLING | DRILLING | 20
2019-03-31 | 69856 | Work Order Description - 69856 - CM | CM | 4 | 579775 | WSCHD | NORM-OPS | 2018-02-22 | 2020-02-07 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | DRILLING | 9
2019-03-31 | 69859 | Work Order Description - 69859 - CM | CM | 4 | 579776 | WSCHD | NORM-OPS | 2018-02-22 | 2020-02-07 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | DRILLING | 9
2019-03-31 | 69860 | Work Order Description - 69860 - BR | BR | 3 | 404911 | WSCHD | NORM-OPS | 2018-03-21 | 2018-12-13 | 2019-04-20 | 2019-04-21 | 3 | MAINTENANCE | INSTRUMENTS | 23
2019-03-31 | 69862 | Work Order Description - 69862 - BR | BR | 3 | 404912 | WSCHD | SYS-ISOL | 2018-03-21 | 2019-03-01 | 2019-04-20 | 2019-04-22 | 3 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 69900 | Work Order Description - 69900 - PM | PM | 4 | 383308 | SCHD | EQUIP-ISOL | 2018-09-12 | 2019-10-22 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 69967 | Work Order Description - 69967 - CM | CM | 2 | 262409 | SCHD | NORM-OPS | 2019-01-31 | 2019-02-28 | 2019-05-18 | 2019-05-18 | 3 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 69991 | Work Order Description - 69991 - CM | CM | 4 | 666778 | WPLAN | NORM-OPS | 2018-02-22 | 2020-02-08 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | DRILLING | 12
2019-03-31 | 69998 | Work Order Description - 69998 - CM | CM | 4 | 307448 | WPLAN | NORM-OPS | 2018-02-22 | 2019-03-04 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | DRILLING | 12
2019-03-31 | 69999 | Work Order Description - 69999 - CM | CM | 4 | 666781 | WPLAN | NORM-OPS | 2018-02-22 | 2020-02-08 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | DRILLING | 12
2019-03-31 | 70051 | Work Order Description - 70051 - PM | PM | 4 | 403998 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-06-06 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 70056 | Work Order Description - 70056 - PM | PM | 3 | 403998 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-06-06 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 70074 | Work Order Description - 70074 - PM | PM | 4 | 100403 | SCHD | EQUIP-ISOL | 2018-09-12 | 2019-04-27 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 70131 | Work Order Description - 70131 - CM | CM | 2 | 451448 | SCHD | NORM-OPS | 2018-06-21 | 2020-02-09 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 70146 | Work Order Description - 70146 - CM | CM | 4 | 652220 | WSCHD | NORM-OPS | 2018-03-06 | 2020-02-09 | 2019-07-12 | 2019-07-21 | 4 | MAINTENANCE | FABRIC | 157.5
2019-03-31 | 70148 | Work Order Description - 70148 - CM | CM | 4 | 546068 | WSCHD | NORM-OPS | 2018-03-06 | 2020-02-09 | 2019-07-12 | 2019-07-21 | 4 | MAINTENANCE | FABRIC | 157.5
2019-03-31 | 70160 | Work Order Description - 70160 - CM | CM | 3 | 465924 | SCHD | PACK-ISOL | 2018-07-06 | 2019-03-02 | 2019-04-14 | 2019-04-14 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 70173 | Work Order Description - 70173 - PM | PM | 4 | 18946 | WSCHD | EQUIP-ISOL | 2018-02-11 | 2019-11-22 | 2019-06-08 | 2019-06-08 | 2 | INTEGRITY | INSTRUMENTS | 10
2019-03-31 | 70179 | Work Order Description - 70179 - PM | PM | 3 | 361207 | WSCHD | EQUIP-ISOL | 2018-02-11 | 2019-12-06 | 2020-05-30 | 2020-05-30 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 70294 | Work Order Description - 70294 - BR | BR | 3 | 315982 | SCHD | NORM-OPS | 2018-07-06 | 2020-02-10 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 70317 | Work Order Description - 70317 - CM | CM | 3 | 189046 | WMATL | PACK-ISOL | 2018-03-07 | 2019-12-04 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 70318 | Work Order Description - 70318 - CM | CM | 3 | 262382 | WMATL | PACK-ISOL | 2018-02-16 | 2018-12-19 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 70330 | Work Order Description - 70330 - PSPM | PSPM | 1 | 399758 | WSCHD | TPS | 2018-12-09 | 2019-10-01 | 2019-05-25 | 2019-05-25 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 70399 | Work Order Description - 70399 - PSCM | PSCM | 1 | 325633 | SCHD | PACK-ISOL | 2019-03-15 | 2019-08-01 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 35
2019-03-31 | 70423 | Work Order Description - 70423 - PSCM | PSCM | 1 | 681797 | WSCHD | NORM-OPS | 2018-06-28 | 2020-06-25 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 70558 | Work Order Description - 70558 - CM | CM | 4 | 383707 | SCHD | NORM-OPS | 2018-06-21 | 2020-02-12 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 70576 | Work Order Description - 70576 - CM | CM | 4 | 670511 | WPLAN | NORM-OPS | 2018-02-20 | 2019-10-28 | 2019-09-01 | 2019-09-01 | 3 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 70598 | Work Order Description - 70598 - CM | CM | 3 | 295923 | SCHD | NORM-OPS | 2019-02-06 | 2020-09-13 | 2019-03-30 | 2019-04-12 | 4 | INTEGRITY | FABRIC | 213.5
2019-03-31 | 70600 | Work Order Description - 70600 - CM | CM | 1 | 295960 | SCHD | NORM-OPS | 2019-02-06 | 2019-09-24 | 2019-04-13 | 2019-05-03 | 2 | INTEGRITY | FABRIC | 1100
2019-03-31 | 70762 | Work Order Description - 70762 - BR | BR | 2 | 361589 | WSCHD | TPS | 2018-06-01 | 2019-02-23 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 70767 | Work Order Description - 70767 - PM | PM | 4 | 671641 | WSCHD | EQUIP-ISOL | 2018-02-15 | 2019-06-10 | 2019-04-13 | 2019-04-15 | 2 | MAINTENANCE | ELECTRICAL | 44
2019-03-31 | 70800 | Work Order Description - 70800 - PM | PM | 4 | 216084 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-03-24 | 2019-08-24 | 2019-08-24 | 2 | MAINTENANCE | DRILLING | 5
2019-03-31 | 71249 | Work Order Description - 71249 - PSPM | PSPM | 1 | 399804 | WSCHD | EQUIP-ISOL | 2018-02-16 | 2019-07-01 | 2019-08-03 | 2019-08-03 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 71305 | Work Order Description - 71305 - PSCM | PSCM | 1 | 136833 | WMATL | NORM-OPS | 2018-03-12 | 2020-02-15 | 2019-04-20 | 2019-04-24 | 4 | MAINTENANCE | ELECTRICAL | 60
2019-03-31 | 71371 | Work Order Description - 71371 - CM | CM | 1 | 528137 | SCHD | NORM-OPS | 2019-03-08 | 2020-01-01 | 2019-05-11 | 2019-05-11 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 71388 | Work Order Description - 71388 - CM | CM | 1 | 451323 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-02 | 2019-03-31 | 2019-04-08 | 3 | INTEGRITY | CONSTRUCTION | 146.5
2019-03-31 | 71494 | Work Order Description - 71494 - BR | BR | 4 | 580016 | WPLAN | NORM-OPS | 2018-02-18 | 2020-04-03 | 2019-07-20 | 2019-07-23 | 4 | INTEGRITY | CONSTRUCTION | 139
2019-03-31 | 71507 | Work Order Description - 71507 - BR | BR | 3 | 33633 | WSCHD | TPS | 2018-02-18 | 2019-07-13 | 2020-12-01 | 2020-12-05 | 3 | MAINTENANCE | MECHANICAL | 56
2019-03-31 | 71543 | Work Order Description - 71543 - PSPM | PSPM | 1 | 309251 | SCHD | PACK-ISOL | 2019-03-16 | 2019-04-02 | 2019-11-02 | 2019-11-02 | 1 | INTEGRITY | MECHANICAL | 48
2019-03-31 | 71682 | Work Order Description - 71682 - CM | CM | 3 | 361590 | WSCHD | SUBSYS-ISOL | 2018-04-01 | 2019-03-08 | 2019-07-27 | 2019-07-28 | 3 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 71686 | Work Order Description - 71686 - BR | BR | 2 | 256492 | SCHD | NORM-OPS | 2018-09-06 | 2019-10-30 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 71687 | Work Order Description - 71687 - BR | BR | 3 | 256492 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-25 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 71831 | Work Order Description - 71831 - PRJ | PRJ | 4 | 320059 | SCHD | NORM-OPS | 2018-03-05 | 2020-02-18 | 2020-01-04 | 2020-01-04 | 4 | DRILLING | DRILLING | 1
2019-03-31 | 71889 | Work Order Description - 71889 - PM | PM | 4 | 448769 | SCHD | SUBSYS-ISOL | 2018-06-01 | 2019-09-27 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 71994 | Work Order Description - 71994 - CM | CM | 4 | 66680 | WPLAN | NORM-OPS | 2018-02-22 | 2020-02-19 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | DRILLING | 16
2019-03-31 | 71997 | Work Order Description - 71997 - CM | CM | 4 | 419569 | WPLAN | NORM-OPS | 2018-02-22 | 2020-02-19 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | DRILLING | 16
2019-03-31 | 71999 | Work Order Description - 71999 - CM | CM | 4 | 484583 | WPLAN | NORM-OPS | 2018-02-22 | 2020-02-19 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | DRILLING | 16
2019-03-31 | 72000 | Work Order Description - 72000 - CM | CM | 4 | 66680 | WPLAN | NORM-OPS | 2018-02-22 | 2020-02-19 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | DRILLING | 12
2019-03-31 | 72003 | Work Order Description - 72003 - CM | CM | 4 | 419569 | WSCHD | NORM-OPS | 2018-03-10 | 2019-11-04 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | DRILLING | 12
2019-03-31 | 72005 | Work Order Description - 72005 - CM | CM | 4 | 484583 | WPLAN | NORM-OPS | 2018-02-22 | 2020-02-19 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | DRILLING | 12
2019-03-31 | 72081 | Work Order Description - 72081 - PM | PM | 4 | 482470 | SCHD | EQUIP-ISOL | 2018-07-06 | 2018-12-08 | 2019-08-31 | 2019-08-31 | 3 | INTEGRITY | SERVICES | 30
2019-03-31 | 72193 | Work Order Description - 72193 - CM | CM | 4 | 357335 | WPLAN | NORM-OPS | 2018-08-29 | 2019-05-24 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | MECHANICAL | 40
2019-03-31 | 72195 | Work Order Description - 72195 - CM | CM | 4 | 357335 | WPLAN | NORM-OPS | 2018-05-17 | 2019-01-18 | 2019-05-25 | 2019-05-29 | 3 | MAINTENANCE | MECHANICAL | 60
2019-03-31 | 72198 | Work Order Description - 72198 - CM | CM | 1 | 697913 | WSCHD | NORM-OPS | 2019-02-11 | 2019-04-13 | 2019-04-06 | 2019-04-06 | 3 | INTEGRITY | CONSTRUCTION | 331
2019-03-31 | 72209 | Work Order Description - 72209 - CM | CM | 1 | 481746 | WPLAN | NORM-OPS | 2018-05-02 | 2019-07-01 | 2019-05-04 | 2019-05-14 | 3 | INTEGRITY | CONSTRUCTION | 216
2019-03-31 | 72240 | Work Order Description - 72240 - BR | BR | 3 | 478636 | WPLAN | NORM-OPS | 2018-03-24 | 2020-02-20 | 2019-08-24 | 2019-08-24 | 4 | INTEGRITY | CONSTRUCTION | 4
2019-03-31 | 72242 | Work Order Description - 72242 - BR | BR | 3 | 253779 | SCHD | NORM-OPS | 2018-07-06 | 2019-08-04 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 72243 | Work Order Description - 72243 - BR | BR | 3 | 625950 | SCHD | NORM-OPS | 2018-09-06 | 2019-08-24 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 72335 | Work Order Description - 72335 - PRJ | PRJ | 3 | 496569 | WSCHD | TPS | 2018-06-01 | 2019-06-01 | 2019-07-06 | 2019-07-12 | 4 | ENGINEERING | CONSTRUCTION | 128
2019-03-31 | 72359 | Work Order Description - 72359 - BR | BR | 2 | 324413 | WPLAN | SYS-ISOL | 2018-03-27 | 2020-03-25 | 2019-06-01 | 2019-06-04 | 4 | MAINTENANCE | SUBSEA | 24
2019-03-31 | 72360 | Work Order Description - 72360 - BR | BR | 2 | 324414 | WPLAN | SYS-ISOL | 2018-03-27 | 2020-03-25 | 2019-06-01 | 2019-06-04 | 4 | MAINTENANCE | SUBSEA | 24
2019-03-31 | 72488 | Work Order Description - 72488 - BR | BR | 1 | 670511 | WPLAN | NORM-OPS | 2018-09-25 | 2020-09-19 | 2019-04-13 | 2019-04-17 | 4 | MAINTENANCE | MECHANICAL | 95
2019-03-31 | 72573 | Work Order Description - 72573 - CM | CM | 1 | 138560 | WSCHD | PACK-ISOL | 2018-03-06 | 2019-09-01 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 72576 | Work Order Description - 72576 - CM | CM | 4 | 544350 | SCHD | NORM-OPS | 2018-09-06 | 2019-10-14 | 2019-02-02 | 2019-02-02 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 74023 | Work Order Description - 74023 - BR | BR | 4 | 499126 | WPLAN | PACK-ISOL | 2018-04-12 | 2020-02-25 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | INSPECTION | 1
2019-03-31 | 74031 | Work Order Description - 74031 - CM | CM | 3 | 378719 | WPLAN | SUBSYS-ISOL | 2018-03-27 | 2019-01-21 | 2019-07-13 | 2019-07-16 | 3 | MAINTENANCE | MECHANICAL | 25
2019-03-31 | 74039 | Work Order Description - 74039 - CM | CM | 1 | 697913 | WSCHD | NORM-OPS | 2019-02-11 | 2019-06-01 | 2019-04-06 | 2019-04-07 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 74358 | Work Order Description - 74358 - CM | CM | 1 | 697913 | WPLAN | NORM-OPS | 2018-03-01 | 2019-04-08 | 2019-04-13 | 2019-04-13 | 3 | INTEGRITY | CONSTRUCTION | 104
2019-03-31 | 74364 | Work Order Description - 74364 - CM | CM | 1 | 697913 | WPLAN | NORM-OPS | 2018-03-01 | 2019-06-01 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 74367 | Work Order Description - 74367 - BR | BR | 3 | 137779 | WSCHD | PACK-ISOL | 2018-02-27 | 2019-08-01 | 2019-05-04 | 2019-05-22 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 74368 | Work Order Description - 74368 - BR | BR | 3 | 11530 | WMATL | SYS-ISOL | 2019-02-22 | 2019-09-26 | 2019-02-21 | 2019-02-23 | 1 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 74375 | Work Order Description - 74375 - CM | CM | 1 | 697913 | SCHD | NORM-OPS | 2019-03-05 | 2019-04-13 | 2019-04-06 | 2019-04-06 | 3 | INTEGRITY | CONSTRUCTION | 76.5
2019-03-31 | 74412 | Work Order Description - 74412 - PM | PM | 4 | 51530 | WSCHD | NORM-OPS | 2018-02-26 | 2019-11-19 | 2020-12-26 | 2020-12-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 74428 | Work Order Description - 74428 - PM | PM | 4 | 305582 | WSCHD | EQUIP-ISOL | 2018-02-26 | 2019-06-02 | 2020-03-07 | 2020-03-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 74746 | Work Order Description - 74746 - PM | PM | 4 | 668433 | SCHD | PACK-ISOL | 2018-06-13 | 2019-09-02 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 74812 | Work Order Description - 74812 - CM | CM | 1 | 185355 | SCHD | NORM-OPS | 2018-09-06 | 2020-02-26 | 2019-08-03 | 2019-08-04 | 4 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 74817 | Work Order Description - 74817 - BR | BR | 4 | 128955 | SCHD | NORM-OPS | 2018-07-18 | 2020-02-26 | 2019-10-05 | 2019-10-09 | 4 | MAINTENANCE | CONSTRUCTION | 150
2019-03-31 | 74837 | Work Order Description - 74837 - CM | CM | 3 | 308460 | WSCHD | SYS-ISOL | 2018-03-02 | 2018-12-10 | 2019-07-06 | 2019-07-19 | 2 | MAINTENANCE | MECHANICAL | 187
2019-03-31 | 74848 | Work Order Description - 74848 - CM | CM | 1 | 403562 | WPLAN | NORM-OPS | 2018-05-01 | 2019-11-01 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | FABRIC | 1
2019-03-31 | 74850 | Work Order Description - 74850 - CM | CM | 1 | 403562 | WPLAN | NORM-OPS | 2018-05-01 | 2019-11-01 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | FABRIC | 1
2019-03-31 | 74858 | Work Order Description - 74858 - BR | BR | 3 | 13545 | SCHD | PACK-ISOL | 2018-08-27 | 2019-09-26 | 2019-07-01 | 2019-07-02 | 3 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 74870 | Work Order Description - 74870 - CM | CM | 3 | 308585 | SCHD | NORM-OPS | 2018-11-22 | 2019-05-27 | 2019-04-20 | 2019-04-21 | 3 | MAINTENANCE | MECHANICAL | 5.5
2019-03-31 | 74903 | Work Order Description - 74903 - PM | PM | 4 | 24955 | SCHD | EQUIP-ISOL | 2018-09-06 | 2020-04-08 | 2020-02-29 | 2020-02-29 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 74905 | Work Order Description - 74905 - PM | PM | 4 | 309503 | INPRG | EQUIP-ISOL | 2018-06-11 | 2020-04-08 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 74910 | Work Order Description - 74910 - PM | PM | 4 | 309681 | SCHD | EQUIP-ISOL | 2018-09-06 | 2020-04-08 | 2020-01-04 | 2020-01-04 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 74911 | Work Order Description - 74911 - PM | PM | 4 | 310003 | SCHD | EQUIP-ISOL | 2018-09-06 | 2020-04-08 | 2020-01-04 | 2020-01-04 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 74912 | Work Order Description - 74912 - PM | PM | 4 | 309682 | SCHD | EQUIP-ISOL | 2018-09-06 | 2020-04-08 | 2020-01-04 | 2020-01-04 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 74913 | Work Order Description - 74913 - PM | PM | 4 | 25085 | SCHD | EQUIP-ISOL | 2018-09-06 | 2020-04-08 | 2020-01-04 | 2020-01-04 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 75048 | Work Order Description - 75048 - PSCM | PSCM | 1 | 316311 | SCHD | NORM-OPS | 2019-02-06 | 2020-02-27 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 75059 | Work Order Description - 75059 - BR | BR | 2 | 451453 | WPLAN | PACK-ISOL | 2018-03-06 | 2020-02-27 | 2019-08-04 | 2019-08-07 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 75067 | Work Order Description - 75067 - BR | BR | 4 | 481715 | SCHD | NORM-OPS | 2018-09-06 | 2020-02-27 | 2019-11-16 | 2019-12-19 | 4 | ENGINEERING | CONSTRUCTION | 30
2019-03-31 | 75100 | Work Order Description - 75100 - CM | CM | 4 | 113266 | WPLAN | NORM-OPS | 2018-09-01 | 2020-02-27 | 2019-09-29 | 2019-10-05 | 4 | INTEGRITY | CONSTRUCTION | 96
2019-03-31 | 75106 | Work Order Description - 75106 - CM | CM | 1 | 403817 | WPLAN | NORM-OPS | 2018-05-01 | 2019-07-01 | 2019-09-28 | 2019-09-28 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 75109 | Work Order Description - 75109 - CM | CM | 1 | 403817 | WPLAN | NORM-OPS | 2018-05-01 | 2019-07-01 | 2019-06-01 | 2019-06-01 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 75110 | Work Order Description - 75110 - CM | CM | 4 | 551401 | SCHD | NORM-OPS | 2019-01-25 | 2019-11-25 | 2019-03-16 | 2019-03-16 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 75120 | Work Order Description - 75120 - CM | CM | 3 | 378814 | WPLAN | TPS | 2018-06-04 | 2019-07-02 | 2019-07-18 | 2019-07-18 | 4 | INTEGRITY | CONSTRUCTION | 40
2019-03-31 | 75123 | Work Order Description - 75123 - CM | CM | 4 | 444925 | SCHD | NORM-OPS | 2018-07-03 | 2020-05-22 | 2019-10-05 | 2019-10-05 | 4 | MAINTENANCE | FABRIC | 7
2019-03-31 | 75126 | Work Order Description - 75126 - CM | CM | 1 | 378847 | SCHD | NORM-OPS | 2019-03-15 | 2020-08-01 | 2019-04-28 | 2019-04-28 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 75134 | Work Order Description - 75134 - PM | PM | 4 | 674850 | WSCHD | EQUIP-ISOL | 2018-03-01 | 2020-01-04 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 75135 | Work Order Description - 75135 - PM | PM | 4 | 671669 | WSCHD | EQUIP-ISOL | 2018-03-01 | 2019-11-15 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 75208 | Work Order Description - 75208 - CM | CM | 1 | 403817 | WPLAN | NORM-OPS | 2018-05-06 | 2019-08-31 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 75287 | Work Order Description - 75287 - PM | PM | 4 | 262784 | SCHD | NORM-OPS | 2018-07-06 | 2019-09-24 | 2020-02-15 | 2020-02-15 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 75289 | Work Order Description - 75289 - PM | PM | 4 | 380955 | SCHD | NORM-OPS | 2018-08-27 | 2019-06-23 | 2019-04-20 | 2019-04-20 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 75292 | Work Order Description - 75292 - PM | PM | 4 | 262785 | SCHD | NORM-OPS | 2018-09-06 | 2019-08-10 | 2019-04-20 | 2019-04-20 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 75293 | Work Order Description - 75293 - PM | PM | 4 | 262785 | SCHD | NORM-OPS | 2018-09-06 | 2019-07-13 | 2019-04-20 | 2019-04-20 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 75296 | Work Order Description - 75296 - PSPM | PSPM | 4 | 262786 | SCHD | NORM-OPS | 2018-08-27 | 2019-11-12 | 2019-07-06 | 2019-07-06 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 75297 | Work Order Description - 75297 - PM | PM | 4 | 262786 | SCHD | NORM-OPS | 2018-08-27 | 2019-11-29 | 2019-07-06 | 2019-07-06 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 75298 | Work Order Description - 75298 - PSPM | PSPM | 4 | 262786 | SCHD | NORM-OPS | 2018-09-06 | 2019-07-30 | 2022-03-05 | 2022-03-05 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 75308 | Work Order Description - 75308 - PM | PM | 3 | 479870 | SCHD | NORM-OPS | 2018-09-06 | 2019-08-31 | 2019-11-23 | 2019-11-23 | 3 | INTEGRITY | INSPECTION | 30
2019-03-31 | 75309 | Work Order Description - 75309 - PSPM | PSPM | 1 | 25401 | SCHD | NORM-OPS | 2018-09-06 | 2020-06-03 | 2020-05-16 | 2020-05-16 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 75310 | Work Order Description - 75310 - PSPM | PSPM | 1 | 262805 | SCHD | NORM-OPS | 2018-09-06 | 2020-06-03 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 75311 | Work Order Description - 75311 - PSPM | PSPM | 1 | 262805 | SCHD | NORM-OPS | 2018-09-06 | 2020-06-03 | 2020-05-16 | 2020-05-16 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 75313 | Work Order Description - 75313 - PM | PM | 1 | 262786 | SCHD | NORM-OPS | 2018-09-06 | 2020-06-03 | 2020-02-01 | 2020-02-01 | 3 | INTEGRITY | INSPECTION | 4
2019-03-31 | 75314 | Work Order Description - 75314 - PSPM | PSPM | 1 | 25401 | SCHD | NORM-OPS | 2018-09-06 | 2020-06-03 | 2018-04-14 | 2018-04-14 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 75323 | Work Order Description - 75323 - PSPM | PSPM | 1 | 464255 | SCHD | NORM-OPS | 2018-09-06 | 2020-06-03 | 2020-05-02 | 2020-05-02 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 75329 | Work Order Description - 75329 - PSPM | PSPM | 1 | 25401 | SCHD | NORM-OPS | 2018-09-06 | 2020-06-03 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 75451 | Work Order Description - 75451 - BR | BR | 4 | 574575 | WSCHD | NORM-OPS | 2018-08-10 | 2020-02-29 | 2019-04-27 | 2019-04-28 | 4 | OPERATIONS | CONSTRUCTION | 93
2019-03-31 | 75465 | Work Order Description - 75465 - BR | BR | 1 | 481746 | WPLAN | NORM-OPS | 2018-03-18 | 2019-09-01 | 2019-05-25 | 2019-05-27 | 3 | INTEGRITY | CONSTRUCTION | 36
2019-03-31 | 75475 | Work Order Description - 75475 - BR | BR | 4 | 268048 | WSCHD | NORM-OPS | 2018-08-10 | 2020-02-29 | 2019-04-27 | 2019-04-28 | 4 | OPERATIONS | CONSTRUCTION | 85.5
2019-03-31 | 75482 | Work Order Description - 75482 - CM | CM | 1 | 697913 | WPLAN | NORM-OPS | 2018-03-05 | 2019-10-14 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 75529 | Work Order Description - 75529 - BR | BR | 4 | 472772 | SCHD | PACK-ISOL | 2018-07-18 | 2019-07-15 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 75530 | Work Order Description - 75530 - CM | CM | 3 | 308461 | WSCHD | PACK-ISOL | 2018-04-20 | 2019-08-19 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 75580 | Work Order Description - 75580 - PSPM | PSPM | 1 | 247357 | SCHD | EQUIP-ISOL | 2019-02-01 | 2019-07-01 | 2019-04-20 | 2019-04-21 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 75591 | Work Order Description - 75591 - PM | PM | 2 | 487445 | SCHD | SUBSYS-ISOL | 2019-03-19 | 2019-05-09 | 2019-06-15 | 2019-06-15 | 2 | MAINTENANCE | INSTRUMENTS | 114
2019-03-31 | 76780 | Work Order Description - 76780 - CM | CM | 2 | 176568 | SCHD | PACK-ISOL | 2018-07-18 | 2019-12-12 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 76791 | Work Order Description - 76791 - CM | CM | 3 | 544411 | WMATL | SYS-ISOL | 2018-03-13 | 2019-04-15 | 2019-05-18 | 2019-05-19 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 76811 | Work Order Description - 76811 - CM | CM | 4 | 124364 | WPLAN | NORM-OPS | 2018-08-04 | 2019-11-25 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | CONSTRUCTION | 0
2019-03-31 | 76860 | Work Order Description - 76860 - CM | CM | 1 | 481472 | SCHD | NORM-OPS | 2018-07-26 | 2020-03-02 | 2019-04-13 | 2019-04-15 | 4 | OPERATIONS | CONSTRUCTION | 1
2019-03-31 | 76861 | Work Order Description - 76861 - BR | BR | 4 | 481645 | SCHD | NORM-OPS | 2018-03-13 | 2020-03-02 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 76908 | Work Order Description - 76908 - BR | BR | 4 | 361497 | SCHD | NORM-OPS | 2018-03-30 | 2020-03-02 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 76973 | Work Order Description - 76973 - PM | PM | 2 | 51243 | WSCHD | EQUIP-ISOL | 2018-03-04 | 2019-11-29 | 2020-03-14 | 2020-03-17 | 2 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 76984 | Work Order Description - 76984 - PM | PM | 4 | 406361 | SCHD | EQUIP-ISOL | 2018-07-26 | 2019-06-28 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 76994 | Work Order Description - 76994 - PM | PM | 4 | 136833 | WSCHD | NORM-OPS | 2018-03-04 | 2019-11-05 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | DRILLING | 4
2019-03-31 | 76995 | Work Order Description - 76995 - PM | PM | 4 | 408048 | WSCHD | NORM-OPS | 2018-03-04 | 2019-04-04 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | DRILLING | 3.5
2019-03-31 | 76996 | Work Order Description - 76996 - PM | PM | 4 | 408048 | WSCHD | NORM-OPS | 2018-03-04 | 2019-02-24 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | DRILLING | 4
2019-03-31 | 76997 | Work Order Description - 76997 - PM | PM | 4 | 408048 | WSCHD | NORM-OPS | 2018-03-04 | 2019-07-16 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | DRILLING | 4
2019-03-31 | 76998 | Work Order Description - 76998 - PM | PM | 4 | 408048 | WSCHD | NORM-OPS | 2018-03-04 | 2019-07-09 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | DRILLING | 4
2019-03-31 | 76999 | Work Order Description - 76999 - PM | PM | 4 | 408048 | WSCHD | NORM-OPS | 2018-03-04 | 2018-12-31 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | DRILLING | 4
2019-03-31 | 77000 | Work Order Description - 77000 - PM | PM | 4 | 408048 | WSCHD | NORM-OPS | 2018-03-04 | 2020-01-15 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | DRILLING | 4
2019-03-31 | 77001 | Work Order Description - 77001 - PM | PM | 4 | 408048 | WSCHD | NORM-OPS | 2018-03-04 | 2019-07-10 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | DRILLING | 4
2019-03-31 | 77002 | Work Order Description - 77002 - PM | PM | 4 | 136833 | WSCHD | NORM-OPS | 2018-03-04 | 2019-03-18 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | DRILLING | 4
2019-03-31 | 77003 | Work Order Description - 77003 - PM | PM | 4 | 408048 | WSCHD | NORM-OPS | 2018-03-04 | 2020-01-03 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | DRILLING | 4
2019-03-31 | 77025 | Work Order Description - 77025 - PM | PM | 4 | 262707 | SCHD | NORM-OPS | 2018-09-06 | 2019-08-23 | 2019-04-20 | 2019-04-20 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 77102 | Work Order Description - 77102 - BR | BR | 2 | 316039 | WMATL | PACK-ISOL | 2018-08-28 | 2019-06-25 | 2019-08-03 | 2019-08-03 | 3 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 77121 | Work Order Description - 77121 - CM | CM | 3 | 83929 | SCHD | ON LINE | 2018-07-03 | 2020-03-03 | 2019-03-30 | 2019-04-01 | 4 | INTEGRITY | FABRIC | 23
2019-03-31 | 77191 | Work Order Description - 77191 - PSPM | PSPM | 1 | 248270 | WSCHD | EQUIP-ISOL | 2018-11-29 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | CONSTRUCTION | 4
2019-03-31 | 77440 | Work Order Description - 77440 - CM | CM | 4 | 478664 | WPLAN | NORM-OPS | 2018-05-11 | 2020-03-05 | 2020-02-29 | 2020-02-29 | 4 | MAINTENANCE | FABRIC | 1
2019-03-31 | 77442 | Work Order Description - 77442 - BR | BR | 4 | 481746 | WPLAN | NORM-OPS | 2018-03-11 | 2020-03-05 | 2019-07-20 | 2019-07-21 | 4 | INTEGRITY | INSPECTION | 42
2019-03-31 | 77450 | Work Order Description - 77450 - CM | CM | 2 | 383355 | WPLAN | NORM-OPS | 2018-09-01 | 2020-03-05 | 2019-06-08 | 2019-06-08 | 4 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 77516 | Work Order Description - 77516 - PM | PM | 4 | 308595 | WSCHD | EQUIP-ISOL | 2018-03-08 | 2019-12-04 | 2019-04-27 | 2019-04-28 | 2 | MAINTENANCE | ELECTRICAL | 23
2019-03-31 | 77603 | Work Order Description - 77603 - CM | CM | 3 | 417522 | WRISKQ | NORM-OPS | 2019-03-01 | 2021-02-26 |  |  | 4 | MAINTENANCE | FABRIC | 36
2019-03-31 | 77607 | Work Order Description - 77607 - CM | CM | 3 | 76033 | WPLAN | ON LINE | 2018-09-13 | 2020-03-06 | 2019-08-17 | 2019-08-25 | 4 | INTEGRITY | FABRIC | 60
2019-03-31 | 77828 | Work Order Description - 77828 - BR | BR | 4 | 481633 | SCHD | TPS | 2018-09-06 | 2020-03-07 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 40
2019-03-31 | 77863 | Work Order Description - 77863 - BR | BR | 2 | 489486 | WPLAN | NORM-OPS | 2018-03-18 | 2019-09-06 | 2019-06-29 | 2019-06-29 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 77869 | Work Order Description - 77869 - PSPM | PSPM | 1 | 665073 | SCHD | NORM-OPS | 2018-10-05 | 2019-07-29 | 2019-03-16 | 2019-03-16 | 1 | INTEGRITY | MECHANICAL | 1
2019-03-31 | 77873 | Work Order Description - 77873 - PSPM | PSPM | 1 | 665051 | SCHD | EQUIP-ISOL | 2018-10-05 | 2019-11-22 | 2019-10-22 | 2019-10-22 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 77922 | Work Order Description - 77922 - PM | PM | 4 | 353518 | WSCHD | NORM-OPS | 2018-03-10 | 2019-12-01 | 2020-03-07 | 2020-03-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 78014 | Work Order Description - 78014 - BR | BR | 3 | 214822 | WPLAN | NORM-OPS | 2018-03-16 | 2019-03-30 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 78159 | Work Order Description - 78159 - BR | BR | 4 | 361858 | WSCHD | NORM-OPS | 2018-06-21 | 2019-07-05 | 2019-09-28 | 2019-09-28 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 78166 | Work Order Description - 78166 - BR | BR | 4 | 499125 | SCHD | ON LINE | 2018-09-06 | 2020-03-09 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 78173 | Work Order Description - 78173 - BR | BR | 3 | 25206 | SCHD | TPS | 2018-09-24 | 2019-06-30 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 40
2019-03-31 | 78184 | Work Order Description - 78184 - PSCM | PSCM | 2 | 574514 | WPLAN | NORM-OPS | 2018-10-26 | 2019-09-20 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | MECHANICAL | 0
2019-03-31 | 78224 | Work Order Description - 78224 - PSPM | PSPM | 1 | 368321 | WSCHD | NORM-OPS | 2018-08-31 | 2019-09-01 | 2019-04-20 | 2019-04-21 | 1 | INTEGRITY | INSPECTION | 340
2019-03-31 | 78229 | Work Order Description - 78229 - PM | PM | 4 | 547298 | WSCHD | PACK-ISOL | 2018-03-12 | 2019-07-05 | 2019-04-27 | 2019-04-28 | 1 | OPERATIONS | MECHANICAL | 58
2019-03-31 | 78230 | Work Order Description - 78230 - PM | PM | 4 | 410324 | WSCHD | PACK-ISOL | 2019-02-24 | 2019-10-21 | 2019-04-27 | 2019-04-28 | 1 | OPERATIONS | MECHANICAL | 58
2019-03-31 | 78231 | Work Order Description - 78231 - PM | PM | 4 | 361798 | WSCHD | PACK-ISOL | 2019-02-24 | 2019-07-21 | 2019-04-27 | 2019-04-28 | 1 | OPERATIONS | MECHANICAL | 58
2019-03-31 | 78233 | Work Order Description - 78233 - PM | PM | 4 | 361803 | WSCHD | PACK-ISOL | 2019-02-24 | 2019-02-18 | 2019-04-27 | 2019-04-28 | 1 | OPERATIONS | MECHANICAL | 118
2019-03-31 | 78330 | Work Order Description - 78330 - CM | CM | 4 | 653284 | WSCHD | NORM-OPS | 2018-03-21 | 2020-09-23 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 78369 | Work Order Description - 78369 - CM | CM | 4 | 96159 | SCHD | NORM-OPS | 2018-07-03 | 2020-03-10 | 2019-09-07 | 2019-09-21 | 4 | MAINTENANCE | FABRIC | 100
2019-03-31 | 78457 | Work Order Description - 78457 - BR | BR | 4 | 484754 | SCHD | NORM-OPS | 2018-10-29 | 2019-01-24 | 2019-04-13 | 2019-04-14 | 3 | OPERATIONS | OPERATIONS | 72
2019-03-31 | 78465 | Work Order Description - 78465 - BR | BR | 4 | 481648 | WSCHD | PACK-ISOL | 2019-03-25 | 2019-10-31 | 2020-02-29 | 2020-02-29 | 2 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 78475 | Work Order Description - 78475 - CM | CM | 3 | 215576 | WSCHD | TPS | 2018-06-08 | 2018-12-25 | 2020-05-03 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 78476 | Work Order Description - 78476 - CM | CM | 3 | 215577 | WSCHD | TPS | 2018-06-08 | 2019-06-23 | 2020-05-02 | 2020-05-02 | 2 | MAINTENANCE | MECHANICAL | 35
2019-03-31 | 78486 | Work Order Description - 78486 - CM | CM | 3 | 76033 | SCHD | TPS | 2019-01-07 | 2019-07-11 | 2019-07-13 | 2019-07-16 | 2 | INTEGRITY | CONSTRUCTION | 40
2019-03-31 | 78513 | Work Order Description - 78513 - BR | BR | 2 | 383836 | WMATL | SYS-ISOL | 2019-03-26 | 2018-12-17 | 2019-07-13 | 2019-07-15 | 3 | MAINTENANCE | MECHANICAL | 47
2019-03-31 | 78514 | Work Order Description - 78514 - PM | PM | 4 | 546035 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-10-09 | 2019-04-13 | 2019-04-14 | 2 | INTEGRITY | INSTRUMENTS | 10
2019-03-31 | 78608 | Work Order Description - 78608 - PM | PM | 4 | 670511 | SCHD | PACK-ISOL | 2018-06-21 | 2019-04-07 | 2019-05-25 | 2019-05-28 | 3 | MAINTENANCE | MECHANICAL | 72
2019-03-31 | 78615 | Work Order Description - 78615 - PM | PM | 4 | 272733 | SCHD | EQUIP-ISOL | 2018-09-25 | 2020-01-05 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 78705 | Work Order Description - 78705 - BR | BR | 4 | 355360 | WPLAN | NORM-OPS | 2018-03-18 | 2019-05-11 | 2019-06-01 | 2019-06-09 | 3 | INTEGRITY | CONSTRUCTION | 107
2019-03-31 | 78777 | Work Order Description - 78777 - PM | PM | 4 | 54830 | WSCHD | EQUIP-ISOL | 2018-03-16 | 2019-08-02 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 78778 | Work Order Description - 78778 - PM | PM | 4 | 262300 | WSCHD | EQUIP-ISOL | 2018-03-16 | 2019-12-11 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 78870 | Work Order Description - 78870 - BR | BR | 3 | 549159 | SCHD | SYS-ISOL | 2018-09-06 | 2018-12-14 | 2019-07-06 | 2019-07-07 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 78930 | Work Order Description - 78930 - CM | CM | 4 | 447441 | SCHD | NORM-OPS | 2018-09-03 | 2019-03-05 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 79006 | Work Order Description - 79006 - PM | PM | 4 | 216158 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-05-24 | 2019-03-30 | 2019-03-30 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 79534 | Work Order Description - 79534 - PM | PM | 4 | 357283 | WSCHD | EQUIP-ISOL | 2018-03-19 | 2019-06-20 | 2019-10-26 | 2019-10-26 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 79547 | Work Order Description - 79547 - PM | PM | 4 | 262707 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-15 | 2019-04-20 | 2019-04-20 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 79616 | Work Order Description - 79616 - BR | BR | 4 | 248558 | WSCHD | TPS | 2018-06-15 | 2020-03-17 | 2020-05-03 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 79619 | Work Order Description - 79619 - BR | BR | 4 | 248559 | WSCHD | TPS | 2018-06-15 | 2020-03-17 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | CONSTRUCTION | 2
2019-03-31 | 79621 | Work Order Description - 79621 - BR | BR | 4 | 37252 | WSCHD | TPS | 2018-06-15 | 2020-03-17 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | CONSTRUCTION | 2
2019-03-31 | 79623 | Work Order Description - 79623 - BR | BR | 4 | 520524 | WSCHD | TPS | 2018-06-15 | 2020-03-17 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | CONSTRUCTION | 2
2019-03-31 | 79644 | Work Order Description - 79644 - BR | BR | 4 | 655468 | SCHD | NORM-OPS | 2018-09-06 | 2019-07-25 | 2019-04-20 | 2019-04-23 | 3 | INTEGRITY | INSTRUMENTS | 28
2019-03-31 | 79646 | Work Order Description - 79646 - BR | BR | 4 | 72762 | SCHD | NORM-OPS | 2018-10-05 | 2019-11-26 | 2019-04-13 | 2019-04-15 | 3 | INTEGRITY | MECHANICAL | 16.5
2019-03-31 | 79652 | Work Order Description - 79652 - CM | CM | 4 | 555818 | SCHD | NORM-OPS | 2018-09-06 | 2019-03-13 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | CONSTRUCTION | 10
2019-03-31 | 79807 | Work Order Description - 79807 - CM | CM | 2 | 680870 | WSCHD | TPS | 2018-04-09 | 2019-10-06 | 2020-05-02 | 2020-05-05 | 3 | MAINTENANCE | INSTRUMENTS | 31
2019-03-31 | 79810 | Work Order Description - 79810 - CM | CM | 2 | 272171 | WSCHD | TPS | 2018-04-10 | 2019-03-22 | 2020-05-02 | 2020-05-05 | 3 | MAINTENANCE | INSTRUMENTS | 31
2019-03-31 | 80003 | Work Order Description - 80003 - CM | CM | 1 | 457402 | WSCHD | NORM-OPS | 2018-05-16 | 2020-03-19 | 2019-11-02 | 2019-11-03 | 4 | MAINTENANCE | ELECTRICAL | 56
2019-03-31 | 80028 | Work Order Description - 80028 - CM | CM | 4 | 556180 | SCHD | NORM-OPS | 2018-09-06 | 2020-03-19 | 2020-01-04 | 2020-01-04 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 80032 | Work Order Description - 80032 - CM | CM | 4 | 555793 | SCHD | NORM-OPS | 2018-11-05 | 2020-05-07 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 80196 | Work Order Description - 80196 - CM | CM | 4 | 368215 | WPLAN | NORM-OPS | 2018-03-25 | 2020-03-20 | 2019-08-04 | 2019-08-15 | 4 | INTEGRITY | FABRIC | 154
2019-03-31 | 80198 | Work Order Description - 80198 - CM | CM | 3 | 462543 | INPRG | PACK-ISOL | 2019-01-29 | 2018-12-26 | 2019-05-04 | 2019-05-04 | 3 | OPERATIONS | OPERATIONS | 1
2019-03-31 | 80284 | Work Order Description - 80284 - PSPM | PSPM | 1 | 659395 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-08-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 80383 | Work Order Description - 80383 - CM | CM | 4 | 316255 | SCHD | NORM-OPS | 2018-09-06 | 2020-03-21 | 2019-05-04 | 2019-05-05 | 4 | MAINTENANCE | DRILLING | 8
2019-03-31 | 80389 | Work Order Description - 80389 - CM | CM | 4 | 312872 | WMATL | NORM-OPS | 2018-10-26 | 2020-03-21 | 2019-06-15 | 2019-06-15 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 80390 | Work Order Description - 80390 - BR | BR | 4 | 502955 | SCHD | PACK-ISOL | 2018-07-09 | 2019-05-05 | 2019-04-20 | 2019-04-20 | 3 | DRILLING | DRILLING | 0
2019-03-31 | 80399 | Work Order Description - 80399 - CM | CM | 3 | 21421 | SCHD | SYS-ISOL | 2018-09-06 | 2020-03-21 | 2019-10-12 | 2019-10-12 | 4 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 80406 | Work Order Description - 80406 - PRJ | PRJ | 4 | 320027 | SCHD | PACK-ISOL | 2018-07-09 | 2019-05-05 | 2019-04-06 | 2019-04-06 | 3 | DRILLING | DRILLING | 1
2019-03-31 | 80407 | Work Order Description - 80407 - PRJ | PRJ | 4 | 320027 | SCHD | PACK-ISOL | 2018-07-09 | 2019-03-23 | 2019-03-30 | 2019-03-30 | 3 | DRILLING | DRILLING | 30
2019-03-31 | 80412 | Work Order Description - 80412 - PRJ | PRJ | 4 | 320026 | SCHD | PACK-ISOL | 2018-07-18 | 2020-05-03 | 2019-08-31 | 2019-08-31 | 4 | DRILLING | DRILLING | 10
2019-03-31 | 80432 | Work Order Description - 80432 - PRJ | PRJ | 4 | 204615 | WSCHD | NORM-OPS | 2018-03-23 | 2019-07-02 | 2019-05-04 | 2019-05-17 | 4 | INTEGRITY | INSPECTION | 245
2019-03-31 | 80590 | Work Order Description - 80590 - BR | BR | 3 | 308894 | WSCHD | TPS | 2018-06-08 | 2019-03-24 | 2020-05-03 | 2020-05-09 | 3 | MAINTENANCE | MECHANICAL | 41
2019-03-31 | 80731 | Work Order Description - 80731 - PM | PM | 4 | 361144 | WSCHD | EQUIP-ISOL | 2018-03-26 | 2019-07-25 | 2020-06-06 | 2020-06-06 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 80809 | Work Order Description - 80809 - BR | BR | 4 | 554963 | SCHD | PACK-ISOL | 2018-09-06 | 2020-05-03 | 2019-05-11 | 2019-05-11 | 4 | INTEGRITY | DRILLING | 10
2019-03-31 | 80810 | Work Order Description - 80810 - PRJ | PRJ | 4 | 320026 | SCHD | PACK-ISOL | 2018-09-06 | 2020-05-03 | 2019-05-11 | 2019-05-11 | 4 | DRILLING | DRILLING | 10
2019-03-31 | 80812 | Work Order Description - 80812 - CM | CM | 3 | 308592 | SCHD | ON LINE | 2018-09-01 | 2019-09-26 | 2019-05-18 | 2019-05-18 | 3 | MAINTENANCE | MECHANICAL | 64
2019-03-31 | 80816 | Work Order Description - 80816 - CM | CM | 4 | 403426 | SCHD | NORM-OPS | 2018-09-06 | 2020-03-24 | 2019-09-21 | 2019-09-21 | 4 | OPERATIONS | FABRIC | 24
2019-03-31 | 80826 | Work Order Description - 80826 - PRJ | PRJ | 4 | 320026 | SCHD | NORM-OPS | 2018-09-06 | 2020-05-03 | 2019-03-30 | 2019-03-30 | 4 | DRILLING | DRILLING | 20
2019-03-31 | 80828 | Work Order Description - 80828 - PRJ | PRJ | 4 | 320026 | SCHD | PACK-ISOL | 2018-07-06 | 2019-03-26 | 2019-04-06 | 2019-04-06 | 3 | DRILLING | DRILLING | 1
2019-03-31 | 80830 | Work Order Description - 80830 - PRJ | PRJ | 4 | 215887 | SCHD | PACK-ISOL | 2018-07-18 | 2019-03-26 | 2019-04-06 | 2019-04-06 | 3 | DRILLING | DRILLING | 70
2019-03-31 | 80869 | Work Order Description - 80869 - PM | PM | 4 | 387912 | SCHD | EQUIP-ISOL | 2018-06-21 | 2020-01-20 | 2019-08-04 | 2019-08-05 | 2 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 80870 | Work Order Description - 80870 - PM | PM | 4 | 668417 | SCHD | EQUIP-ISOL | 2018-06-21 | 2018-12-21 | 2019-08-04 | 2019-08-04 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 80957 | Work Order Description - 80957 - BR | BR | 2 | 320026 | SCHD | NORM-OPS | 2018-07-18 | 2019-03-27 | 2019-04-27 | 2019-04-27 | 3 | DRILLING | DRILLING | 30
2019-03-31 | 80958 | Work Order Description - 80958 - PRJ | PRJ | 4 | 320026 | SCHD | PACK-ISOL | 2018-07-06 | 2019-05-05 | 2019-05-04 | 2019-05-04 | 3 | DRILLING | DRILLING | 183
2019-03-31 | 80977 | Work Order Description - 80977 - CM | CM | 4 | 553779 | WSCHD | NORM-OPS | 2018-06-02 | 2019-03-27 | 2019-06-01 | 2019-06-02 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 80994 | Work Order Description - 80994 - BR | BR | 4 | 520837 | WPLAN | NORM-OPS | 2018-05-03 | 2019-03-27 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 80995 | Work Order Description - 80995 - CM | CM | 4 | 215390 | WPLAN | PACK-ISOL | 2018-04-03 | 2019-03-09 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 81112 | Work Order Description - 81112 - CM | CM | 4 | 360753 | WPLAN | NORM-OPS | 2018-03-29 | 2020-03-26 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | CONSTRUCTION | 12
2019-03-31 | 81132 | Work Order Description - 81132 - PM | PM | 4 | 128061 | SCHD | PACK-ISOL | 2018-06-21 | 2019-09-27 | 2019-05-18 | 2019-05-18 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 81375 | Work Order Description - 81375 - BR | BR | 4 | 74831 | INPRG | NORM-OPS | 2018-04-05 | 2020-03-28 | 2019-10-06 | 2019-11-03 | 4 | DRILLING | DRILLING | 1
2019-03-31 | 81386 | Work Order Description - 81386 - CM | CM | 4 | 512772 | WSCHD | NORM-OPS | 2018-04-01 | 2020-03-28 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 81411 | Work Order Description - 81411 - CM | CM | 4 | 255843 | SCHD | NORM-OPS | 2018-09-06 | 2020-03-28 | 2019-05-18 | 2019-05-18 | 4 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 81415 | Work Order Description - 81415 - CM | CM | 3 | 308730 | WPLAN | NORM-OPS | 2018-04-01 | 2019-03-30 | 2019-05-18 | 2019-05-18 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 81500 | Work Order Description - 81500 - BR | BR | 4 | 677187 | WSCHD | NORM-OPS | 2018-05-03 | 2020-03-29 | 2019-09-07 | 2019-10-08 | 4 | MAINTENANCE | ELECTRICAL | 662
2019-03-31 | 81507 | Work Order Description - 81507 - BR | BR | 4 | 447441 | SCHD | NORM-OPS | 2018-07-06 | 2020-03-29 | 2019-05-04 | 2019-05-07 | 4 | MAINTENANCE | ELECTRICAL | 16
2019-03-31 | 81510 | Work Order Description - 81510 - PRJ | PRJ | 4 | 632455 | SCHD | NORM-OPS | 2018-11-16 | 2020-03-29 | 2020-04-18 | 2020-04-24 | 4 | ENGINEERING | CONSTRUCTION | 28
2019-03-31 | 81519 | Work Order Description - 81519 - PM | PM | 4 | 261950 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-09-26 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 81523 | Work Order Description - 81523 - PM | PM | 4 | 546657 | WSCHD | NORM-OPS | 2018-04-01 | 2019-08-19 | 2021-09-25 | 2021-09-25 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 81529 | Work Order Description - 81529 - PM | PM | 4 | 308894 | SCHD | NORM-OPS | 2018-10-29 | 2019-01-14 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 81555 | Work Order Description - 81555 - PM | PM | 4 | 261039 | WSCHD | EQUIP-ISOL | 2018-04-01 | 2018-12-26 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 81695 | Work Order Description - 81695 - PM | PM | 4 | 323504 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-07-20 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 81764 | Work Order Description - 81764 - CM | CM | 4 | 402086 | SCHD | NORM-OPS | 2018-07-18 | 2020-03-31 | 2020-02-01 | 2020-02-01 | 4 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 81797 | Work Order Description - 81797 - CM | CM | 3 | 262439 | SCHD | TPS | 2018-09-24 | 2018-12-29 | 2019-07-13 | 2019-07-14 | 3 | MAINTENANCE | ELECTRICAL | 126
2019-03-31 | 81798 | Work Order Description - 81798 - PSCM | PSCM | 1 | 652220 | WSCHD | NORM-OPS | 2018-05-24 | 2019-05-22 | 2019-04-20 | 2019-04-21 | 3 | MAINTENANCE | ELECTRICAL | 96
2019-03-31 | 81814 | Work Order Description - 81814 - PSPM | PSPM | 1 | 531479 | WSCHD | SUBSYS-ISOL | 2018-04-03 | 2020-08-01 | 2020-06-06 | 2020-06-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 81821 | Work Order Description - 81821 - PSPM | PSPM | 1 | 18946 | WSCHD | SUBSYS-ISOL | 2018-04-03 | 2020-08-01 | 2020-06-06 | 2020-06-06 | 1 | INTEGRITY | INSTRUMENTS | 6
2019-03-31 | 81822 | Work Order Description - 81822 - PSPM | PSPM | 1 | 399409 | WSCHD | SUBSYS-ISOL | 2018-04-03 | 2020-08-01 | 2020-06-06 | 2020-06-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 81849 | Work Order Description - 81849 - PM | PM | 4 | 354614 | SCHD | PACK-ISOL | 2018-10-29 | 2019-08-22 | 2019-03-30 | 2019-03-31 | 2 | MAINTENANCE | MECHANICAL | 110
2019-03-31 | 81988 | Work Order Description - 81988 - PM | PM | 2 | 670211 | SCHD | PACK-ISOL | 2018-06-21 | 2019-11-17 | 2019-03-17 | 2019-03-26 | 2 | MAINTENANCE | ELECTRICAL | 45
2019-03-31 | 83026 | Work Order Description - 83026 - PSCM | PSCM | 1 | 407926 | WSCHD | NORM-OPS | 2018-05-27 | 2020-04-01 | 2019-04-20 | 2019-04-23 | 4 | MAINTENANCE | INSTRUMENTS | 32
2019-03-31 | 83081 | Work Order Description - 83081 - PM | PM | 4 | 544405 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-09-01 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 83169 | Work Order Description - 83169 - CM | CM | 3 | 670209 | SCHD | NORM-OPS | 2019-03-29 | 2019-04-04 | 2019-11-30 | 2019-12-12 | 3 | MAINTENANCE | ELECTRICAL | 68
2019-03-31 | 83179 | Work Order Description - 83179 - PSCM | PSCM | 2 | 527308 | SCHD | NORM-OPS | 2018-06-21 | 2020-04-02 | 2019-04-27 | 2019-05-30 | 4 | MAINTENANCE | MECHANICAL | 53.5
2019-03-31 | 83203 | Work Order Description - 83203 - BR | BR | 4 | 500196 | WSCHD | PACK-ISOL | 2018-05-31 | 2020-04-02 | 2019-05-04 | 2019-05-05 | 4 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 83355 | Work Order Description - 83355 - PRJ | PRJ | 3 | 681872 | WPLAN | TPS | 2018-05-03 | 2019-07-11 | 2020-05-02 | 2020-05-25 | 4 | ENGINEERING | CONSTRUCTION | 533
2019-03-31 | 83461 | Work Order Description - 83461 - BR | BR | 4 | 651607 | WPLAN | NORM-OPS | 2018-05-03 | 2020-04-04 | 2019-04-06 | 2019-04-10 | 4 | MAINTENANCE | ELECTRICAL | 60
2019-03-31 | 83475 | Work Order Description - 83475 - PM | PM | 4 | 272732 | SCHD | EQUIP-ISOL | 2018-09-25 | 2019-12-07 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 84481 | Work Order Description - 84481 - BR | BR | 4 | 479510 | WPLAN | NORM-OPS | 2018-04-21 | 2020-04-07 | 2020-03-07 | 2020-03-09 | 4 | INTEGRITY | CONSTRUCTION | 15
2019-03-31 | 84483 | Work Order Description - 84483 - CM | CM | 1 | 668310 | WPLAN | NORM-OPS | 2018-04-10 | 2020-04-07 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | ELECTRICAL | 16
2019-03-31 | 84661 | Work Order Description - 84661 - BR | BR | 4 | 555057 | SCHD | NORM-OPS | 2018-09-06 | 2020-04-08 | 2020-03-07 | 2020-03-09 | 4 | INTEGRITY | CONSTRUCTION | 63
2019-03-31 | 84662 | Work Order Description - 84662 - PSCM | PSCM | 3 | 74970 | SCHD | PACK-ISOL | 2018-09-10 | 2019-01-04 | 2019-06-09 | 2019-09-09 | 4 | MAINTENANCE | MECHANICAL | 174
2019-03-31 | 84688 | Work Order Description - 84688 - CM | CM | 3 | 368329 | WSCHD | TPS | 2018-06-12 | 2019-04-10 | 2019-06-08 | 2019-06-18 | 3 | INTEGRITY | CONSTRUCTION | 210
2019-03-31 | 84713 | Work Order Description - 84713 - CM | CM | 3 | 357139 | WSCHD | SYS-ISOL | 2018-04-15 | 2019-06-19 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 84719 | Work Order Description - 84719 - CM | CM | 4 | 546035 | WSCHD | NORM-OPS | 2018-04-13 | 2020-04-08 | 2019-05-04 | 2019-05-07 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 84867 | Work Order Description - 84867 - BR | BR | 4 | 263140 | SCHD | NORM-OPS | 2018-06-21 | 2020-04-09 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 84870 | Work Order Description - 84870 - CM | CM | 4 | 479267 | WPLAN | NORM-OPS | 2018-04-21 | 2020-04-09 | 2020-02-29 | 2020-03-05 | 4 | INTEGRITY | CONSTRUCTION | 108
2019-03-31 | 84876 | Work Order Description - 84876 - BR | BR | 3 | 494600 | WPLAN | TPS | 2018-05-13 | 2019-05-13 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 84878 | Work Order Description - 84878 - BR | BR | 3 | 248430 | WPLAN | TPS | 2018-05-13 | 2019-05-13 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 84881 | Work Order Description - 84881 - CM | CM | 4 | 33653 | WSCHD | PACK-ISOL | 2018-05-13 | 2019-04-10 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 84896 | Work Order Description - 84896 - BR | BR | 3 | 493012 | WPLAN | PACK-ISOL | 2018-05-13 | 2019-05-13 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 84898 | Work Order Description - 84898 - CM | CM | 3 | 467877 | WSCHD | NORM-OPS | 2019-03-24 | 2019-09-19 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | FABRIC | 52
2019-03-31 | 84932 | Work Order Description - 84932 - PM | PM | 4 | 396308 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-10-12 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 6
2019-03-31 | 85052 | Work Order Description - 85052 - CM | CM | 1 | 467877 | WPLAN | TPS | 2018-05-03 | 2020-04-10 | 2020-05-02 | 2020-05-09 | 4 | INTEGRITY | CONSTRUCTION | 80
2019-03-31 | 85057 | Work Order Description - 85057 - BR | BR | 3 | 308426 | WSCHD | PACK-ISOL | 2018-06-27 | 2020-04-10 | 2019-04-13 | 2019-04-16 | 4 | MAINTENANCE | MECHANICAL | 35
2019-03-31 | 85087 | Work Order Description - 85087 - PM | PM | 2 | 480203 | WSCHD | PACK-ISOL | 2018-04-13 | 2019-02-25 | 2019-04-13 | 2019-04-17 | 2 | MAINTENANCE | MECHANICAL | 70
2019-03-31 | 85089 | Work Order Description - 85089 - PM | PM | 4 | 411395 | WPLAN | NORM-OPS | 2018-04-13 | 2019-05-01 | 2019-04-09 | 2019-04-16 | 2 | INTEGRITY | INSPECTION | 104
2019-03-31 | 85104 | Work Order Description - 85104 - PSPM | PSPM | 1 | 487751 | SCHD | EQUIP-ISOL | 2018-10-04 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 1 | INTEGRITY | MECHANICAL | 46
2019-03-31 | 85181 | Work Order Description - 85181 - CM | CM | 3 | 51130 | WPLAN | SYS-ISOL | 2018-05-13 | 2020-04-11 | 2019-09-07 | 2019-09-08 | 4 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 85191 | Work Order Description - 85191 - BR | BR | 1 | 520184 | WRISKQ | TPS | 2019-03-03 | 2021-03-01 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 85215 | Work Order Description - 85215 - BR | BR | 3 | 50959 | WSCHD | NORM-OPS | 2018-04-19 | 2019-04-13 | 2019-06-08 | 2019-06-09 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 85374 | Work Order Description - 85374 - CM | CM | 3 | 295923 | WSCHD | NORM-OPS | 2018-04-15 | 2020-04-12 | 2019-04-27 | 2019-04-28 | 4 | INTEGRITY | FABRIC | 48
2019-03-31 | 85376 | Work Order Description - 85376 - CM | CM | 1 | 403880 | WPLAN | NORM-OPS | 2019-01-19 | 2019-04-17 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 85377 | Work Order Description - 85377 - CM | CM | 4 | 556357 | WPLAN | NORM-OPS | 2018-06-10 | 2020-06-11 | 2020-02-29 | 2020-02-29 | 4 | INTEGRITY | FABRIC | 1
2019-03-31 | 85389 | Work Order Description - 85389 - BR | BR | 3 | 249448 | WSCHD | PACK-ISOL | 2018-04-15 | 2019-04-14 | 2019-08-31 | 2019-09-06 | 3 | MAINTENANCE | MECHANICAL | 58
2019-03-31 | 85416 | Work Order Description - 85416 - BR | BR | 3 | 533183 | SCHD | TPS | 2018-08-13 | 2019-04-15 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | OPERATIONS | 12
2019-03-31 | 85431 | Work Order Description - 85431 - PM | PM | 2 | 540776 | SCHD | EQUIP-ISOL | 2019-02-01 | 2019-05-06 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 75
2019-03-31 | 85513 | Work Order Description - 85513 - BR | BR | 3 | 215166 | WPLAN | NORM-OPS | 2018-06-01 | 2019-04-15 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 40
2019-03-31 | 85514 | Work Order Description - 85514 - BR | BR | 3 | 327930 | WPLAN | NORM-OPS | 2018-05-31 | 2019-04-15 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 92
2019-03-31 | 85516 | Work Order Description - 85516 - CM | CM | 3 | 258822 | WMATL | NORM-OPS | 2018-10-08 | 2019-08-22 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 85520 | Work Order Description - 85520 - BR | BR | 4 | 501090 | WPLAN | NORM-OPS | 2018-04-21 | 2020-04-13 | 2020-02-29 | 2020-03-01 | 4 | INTEGRITY | CONSTRUCTION | 27
2019-03-31 | 85547 | Work Order Description - 85547 - CM | CM | 3 | 530323 | WSCHD | NORM-OPS | 2018-04-22 | 2020-04-13 | 2019-04-27 | 2019-04-28 | 4 | INTEGRITY | FABRIC | 90
2019-03-31 | 85553 | Work Order Description - 85553 - BR | BR | 3 | 327910 | WPLAN | NORM-OPS | 2018-05-29 | 2019-04-15 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 108
2019-03-31 | 85635 | Work Order Description - 85635 - PSPM | PSPM | 1 | 19006 | WSCHD | SYS-ISOL | 2018-04-16 | 2020-07-01 | 2020-05-02 | 2020-05-02 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 85637 | Work Order Description - 85637 - CM | CM | 4 | 237443 | WPLAN | NORM-OPS | 2018-08-04 | 2020-04-14 | 2019-04-13 | 2019-04-16 | 4 | INTEGRITY | FABRIC | 224
2019-03-31 | 85643 | Work Order Description - 85643 - BR | BR | 3 | 51155 | SCHD | NORM-OPS | 2019-01-13 | 2019-08-10 | 2019-04-24 | 2019-04-24 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 85650 | Work Order Description - 85650 - PM | PM | 4 | 403492 | SCHD | EQUIP-ISOL | 2018-05-24 | 2020-04-09 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | ELECTRICAL | 72
2019-03-31 | 85652 | Work Order Description - 85652 - PSPM | PSPM | 1 | 403492 | SCHD | EQUIP-ISOL | 2018-09-06 | 2020-02-25 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 85670 | Work Order Description - 85670 - CM | CM | 2 | 215897 | SCHD | SYS-ISOL | 2019-02-13 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 85683 | Work Order Description - 85683 - CM | CM | 4 | 316145 | SCHD | NORM-OPS | 2019-03-15 | 2020-03-07 | 2019-03-02 | 2019-03-02 | 3 | INTEGRITY | FABRIC | 20
2019-03-31 | 85684 | Work Order Description - 85684 - CM | CM | 1 | 215897 | SCHD | NORM-OPS | 2019-03-15 | 2020-03-07 | 2019-06-29 | 2019-06-30 | 3 | INTEGRITY | FABRIC | 70
2019-03-31 | 85713 | Work Order Description - 85713 - PM | PM | 4 | 248465 | WSCHD | EQUIP-ISOL | 2018-04-17 | 2019-02-06 | 2019-05-04 | 2019-05-05 | 1 | INTEGRITY | CONSTRUCTION | 7
2019-03-31 | 85730 | Work Order Description - 85730 - PM | PM | 3 | 487798 | SCHD | PACK-ISOL | 2018-07-06 | 2019-10-14 | 2019-08-03 | 2019-08-03 | 1 | INTEGRITY | MECHANICAL | 18
2019-03-31 | 85777 | Work Order Description - 85777 - PM | PM | 4 | 127909 | SCHD | EQUIP-ISOL | 2018-06-21 | 2020-01-01 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 85786 | Work Order Description - 85786 - PM | PM | 4 | 127908 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-11-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 85787 | Work Order Description - 85787 - PM | PM | 4 | 74912 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-05-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 86071 | Work Order Description - 86071 - CM | CM | 4 | 484754 | SCHD | NORM-OPS | 2018-10-29 | 2020-04-15 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | CONSTRUCTION | 16
2019-03-31 | 86074 | Work Order Description - 86074 - PSPM | PSPM | 1 | 531755 | WSCHD | SUBSYS-ISOL | 2018-04-17 | 2019-05-01 | 2019-10-26 | 2019-10-26 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 86079 | Work Order Description - 86079 - BR | BR | 4 | 481715 | SCHD | NORM-OPS | 2018-04-18 | 2020-04-15 | 2019-08-03 | 2019-08-03 | 4 | INTEGRITY | SERVICES | 2714.5
2019-03-31 | 86080 | Work Order Description - 86080 - BR | BR | 3 | 110847 | SCHD | ON LINE | 2019-03-06 | 2020-04-15 | 2019-07-28 | 2019-07-28 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 86136 | Work Order Description - 86136 - BR | BR | 4 | 398904 | SCHD | ON LINE | 2019-02-13 | 2020-04-15 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 86144 | Work Order Description - 86144 - PSCM | PSCM | 1 | 679153 | SCHD | NORM-OPS | 2018-10-29 | 2019-04-17 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 86241 | Work Order Description - 86241 - CM | CM | 3 | 554786 | SCHD | TPS | 2018-10-09 | 2019-01-17 | 2019-07-13 | 2019-07-23 | 3 | MAINTENANCE | INSTRUMENTS | 72
2019-03-31 | 86266 | Work Order Description - 86266 - BR | BR | 4 | 464098 | SCHD | NORM-OPS | 2018-07-17 | 2020-07-14 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 86278 | Work Order Description - 86278 - BR | BR | 3 | 503752 | SCHD | TPS | 2018-09-06 | 2018-12-19 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 86282 | Work Order Description - 86282 - BR | BR | 1 | 481746 | SCHD | NORM-OPS | 2018-08-24 | 2020-04-16 | 2019-03-30 | 2019-04-22 | 4 | INTEGRITY | FABRIC | 1
2019-03-31 | 86285 | Work Order Description - 86285 - BR | BR | 3 | 470263 | SCHD | PACK-ISOL | 2018-07-06 | 2019-10-30 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 86288 | Work Order Description - 86288 - BR | BR | 3 | 470264 | SCHD | PACK-ISOL | 2018-07-08 | 2019-04-18 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 86301 | Work Order Description - 86301 - CM | CM | 1 | 228839 | WPLAN | NORM-OPS | 2018-08-07 | 2019-04-18 | 2019-05-05 | 2019-05-11 | 3 | INTEGRITY | CONSTRUCTION | 120
2019-03-31 | 86334 | Work Order Description - 86334 - PM | PM | 4 | 357284 | WSCHD | EQUIP-ISOL | 2018-04-19 | 2019-10-21 | 2019-09-21 | 2019-09-22 | 2 | MAINTENANCE | ELECTRICAL | 9
2019-03-31 | 86428 | Work Order Description - 86428 - CM | CM | 4 | 57460 | WPLAN | NORM-OPS | 2018-05-11 | 2019-05-09 | 2020-02-29 | 2020-02-29 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 86431 | Work Order Description - 86431 - CM | CM | 4 | 501444 | WPLAN | NORM-OPS | 2018-05-16 | 2020-04-17 | 2020-03-07 | 2020-03-07 | 4 | INTEGRITY | FABRIC | 1
2019-03-31 | 86434 | Work Order Description - 86434 - CM | CM | 1 | 57460 | WPLAN | NORM-OPS | 2018-05-16 | 2019-07-01 | 2019-05-04 | 2019-05-15 | 3 | INTEGRITY | CONSTRUCTION | 252
2019-03-31 | 86457 | Work Order Description - 86457 - CM | CM | 1 | 57460 | WPLAN | NORM-OPS | 2018-05-11 | 2019-06-08 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 86458 | Work Order Description - 86458 - CM | CM | 4 | 57460 | WPLAN | NORM-OPS | 2018-05-11 | 2019-05-09 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 86626 | Work Order Description - 86626 - PSCM | PSCM | 1 | 584564 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-01 | 2019-04-20 | 2019-05-07 | 3 | INTEGRITY | CONSTRUCTION | 384
2019-03-31 | 86628 | Work Order Description - 86628 - CM | CM | 4 | 481600 | SCHD | NORM-OPS | 2018-09-06 | 2020-04-18 | 2020-03-28 | 2020-04-08 | 4 | OPERATIONS | SERVICES | 168
2019-03-31 | 86629 | Work Order Description - 86629 - BR | BR | 4 | 237408 | WPLAN | NORM-OPS | 2018-04-20 | 2019-04-20 | 2019-05-05 | 2019-05-05 | 3 | INTEGRITY | CONSTRUCTION | 150
2019-03-31 | 86630 | Work Order Description - 86630 - CM | CM | 3 | 325575 | SCHD | SYS-ISOL | 2018-09-06 | 2019-04-20 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 86631 | Work Order Description - 86631 - CM | CM | 3 | 499274 | SCHD | SYS-ISOL | 2018-09-06 | 2019-04-20 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 86661 | Work Order Description - 86661 - PSCM | PSCM | 1 | 546068 | WSCHD | NORM-OPS | 2018-05-24 | 2019-05-22 | 2019-04-20 | 2019-04-21 | 3 | MAINTENANCE | ELECTRICAL | 96
2019-03-31 | 86662 | Work Order Description - 86662 - PSCM | PSCM | 1 | 679153 | WSCHD | NORM-OPS | 2018-05-13 | 2019-04-20 | 2019-04-06 | 2019-04-07 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 86687 | Work Order Description - 86687 - PM | PM | 4 | 675037 | SCHD | PACK-ISOL | 2019-03-11 | 2019-09-03 | 2019-04-06 | 2019-04-07 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 86853 | Work Order Description - 86853 - BR | BR | 3 | 469096 | WPLAN | SYS-ISOL | 2018-06-13 | 2018-12-05 | 2019-04-24 | 2019-04-24 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 86930 | Work Order Description - 86930 - PM | PM | 2 | 500981 | SCHD | EQUIP-ISOL | 2018-07-06 | 2019-03-13 | 2019-05-04 | 2019-05-04 | 1 | INTEGRITY | INSTRUMENTS | 10
2019-03-31 | 87107 | Work Order Description - 87107 - BR | BR | 2 | 363262 | WSCHD | NORM-OPS | 2018-04-23 | 2020-04-20 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 87112 | Work Order Description - 87112 - BR | BR | 3 | 272735 | SCHD | SYS-ISOL | 2018-11-13 | 2019-11-13 | 2019-04-20 | 2019-04-21 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 87113 | Work Order Description - 87113 - BR | BR | 3 | 531479 | WSCHD | NORM-OPS | 2018-04-22 | 2019-04-22 | 2019-10-26 | 2019-10-30 | 3 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 87114 | Work Order Description - 87114 - CM | CM | 1 | 567116 | WPLAN | NORM-OPS | 2018-07-21 | 2019-04-22 | 2019-04-20 | 2019-04-20 | 3 | ENGINEERING | CONSTRUCTION | 1
2019-03-31 | 87115 | Work Order Description - 87115 - BR | BR | 2 | 536466 | WSCHD | NORM-OPS | 2018-04-23 | 2019-07-25 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 87116 | Work Order Description - 87116 - BR | BR | 2 | 536467 | WSCHD | NORM-OPS | 2018-04-23 | 2020-04-20 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 87117 | Work Order Description - 87117 - BR | BR | 2 | 363263 | WSCHD | NORM-OPS | 2018-04-23 | 2020-04-20 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 87118 | Work Order Description - 87118 - BR | BR | 2 | 469325 | WSCHD | NORM-OPS | 2018-04-23 | 2020-04-20 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 87119 | Work Order Description - 87119 - BR | BR | 2 | 469327 | WSCHD | NORM-OPS | 2018-04-23 | 2020-04-20 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 87121 | Work Order Description - 87121 - BR | BR | 2 | 530952 | WSCHD | NORM-OPS | 2018-04-23 | 2020-04-20 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 87122 | Work Order Description - 87122 - BR | BR | 2 | 363264 | WSCHD | NORM-OPS | 2018-04-23 | 2020-04-20 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 87123 | Work Order Description - 87123 - BR | BR | 2 | 363265 | WSCHD | NORM-OPS | 2018-04-23 | 2020-04-20 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 87124 | Work Order Description - 87124 - BR | BR | 2 | 469330 | WSCHD | NORM-OPS | 2018-04-23 | 2020-04-20 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 87125 | Work Order Description - 87125 - BR | BR | 2 | 363270 | WSCHD | NORM-OPS | 2018-04-23 | 2020-04-20 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 87126 | Work Order Description - 87126 - CM | CM | 1 | 502745 | SCHD | NORM-OPS | 2018-09-06 | 2020-04-20 | 2019-08-31 | 2019-08-31 | 4 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 87268 | Work Order Description - 87268 - BR | BR | 3 | 312387 | SCHD | ON LINE | 2018-09-06 | 2020-04-21 | 2020-01-04 | 2020-01-04 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 87286 | Work Order Description - 87286 - CM | CM | 2 | 546552 | WSCHD | SYS-ISOL | 2018-09-27 | 2019-04-23 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 19
2019-03-31 | 87302 | Work Order Description - 87302 - CM | CM | 3 | 110790 | WPLAN | PACK-ISOL | 2018-05-10 | 2019-04-23 | 2019-04-28 | 2019-05-22 | 3 | MAINTENANCE | MECHANICAL | 60
2019-03-31 | 87310 | Work Order Description - 87310 - BR | BR | 1 | 669486 | WPLAN | NORM-OPS | 2018-05-01 | 2019-04-24 | 2019-05-18 | 2019-06-01 | 2 | INTEGRITY | CONSTRUCTION | 200
2019-03-31 | 87322 | Work Order Description - 87322 - CM | CM | 4 | 407972 | SCHD | NORM-OPS | 2018-10-29 | 2020-04-21 | 2019-09-21 | 2019-09-21 | 4 | MAINTENANCE | ELECTRICAL | 40
2019-03-31 | 87324 | Work Order Description - 87324 - PSCM | PSCM | 1 | 361923 | WSCHD | SYS-ISOL | 2018-07-08 | 2020-04-21 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 87412 | Work Order Description - 87412 - BR | BR | 3 | 546279 | WPLAN | NORM-OPS | 2018-05-13 | 2020-04-22 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 87419 | Work Order Description - 87419 - CM | CM | 4 | 567116 | SCHD | NORM-OPS | 2019-03-29 | 2020-03-07 | 2020-02-29 | 2020-03-01 | 3 | INTEGRITY | FABRIC | 180
2019-03-31 | 87420 | Work Order Description - 87420 - CM | CM | 1 | 567116 | WPLAN | NORM-OPS | 2018-05-11 | 2019-05-09 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 87426 | Work Order Description - 87426 - CM | CM | 3 | 128801 | WPLAN | TPS | 2018-07-22 | 2019-04-04 | 2019-07-13 | 2019-07-15 | 3 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 87480 | Work Order Description - 87480 - PSPM | PSPM | 1 | 399835 | WSCHD | EQUIP-ISOL | 2018-04-25 | 2020-01-01 | 2019-04-27 | 2019-04-28 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 87488 | Work Order Description - 87488 - PM | PM | 3 | 668862 | SCHD | PACK-ISOL | 2018-06-21 | 2019-12-15 | 2019-08-31 | 2019-08-31 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 87578 | Work Order Description - 87578 - CM | CM | 4 | 263129 | SCHD | NORM-OPS | 2018-09-06 | 2020-04-23 | 2020-02-22 | 2020-02-22 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 87591 | Work Order Description - 87591 - CM | CM | 3 | 402622 | WPLAN | NORM-OPS | 2018-05-01 | 2018-12-30 | 2019-06-15 | 2019-06-20 | 2 | INTEGRITY | MECHANICAL | 36
2019-03-31 | 87697 | Work Order Description - 87697 - PSCM | PSCM | 1 | 402290 | WMATL | NORM-OPS | 2018-05-14 | 2020-04-24 | 2019-06-15 | 2019-06-15 | 4 | INTEGRITY | MECHANICAL | 2
2019-03-31 | 87698 | Work Order Description - 87698 - CM | CM | 4 | 460839 | WPLAN | SYS-ISOL | 2018-05-11 | 2020-04-24 | 2019-06-15 | 2019-06-22 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 87703 | Work Order Description - 87703 - PRJ | PRJ | 4 | 499092 | SCHD | TPS | 2018-06-12 | 2020-01-19 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | CONSTRUCTION | 18
2019-03-31 | 87743 | Work Order Description - 87743 - CM | CM | 4 | 680607 | WPLAN | NORM-OPS | 2018-05-13 | 2020-04-24 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 87752 | Work Order Description - 87752 - CM | CM | 3 | 295923 | WSCHD | NORM-OPS | 2019-03-24 | 2020-03-20 | 2019-04-22 | 2019-04-23 | 3 | INTEGRITY | FABRIC | 54
2019-03-31 | 87753 | Work Order Description - 87753 - CM | CM | 3 | 272052 | WPLAN | NORM-OPS | 2018-05-13 | 2020-04-24 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 87763 | Work Order Description - 87763 - PM | PM | 2 | 33427 | WSCHD | PACK-ISOL | 2018-04-27 | 2019-08-19 | 2019-04-27 | 2019-05-01 | 2 | MAINTENANCE | INSTRUMENTS | 35
2019-03-31 | 87908 | Work Order Description - 87908 - CM | CM | 1 | 465838 | SCHD | NORM-OPS | 2018-09-06 | 2020-04-25 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 87979 | Work Order Description - 87979 - PM | PM | 4 | 25391 | SCHD | NORM-OPS | 2018-07-18 | 2019-04-12 | 2019-08-03 | 2019-08-03 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 87983 | Work Order Description - 87983 - PM | PM | 3 | 98448 | SCHD | PACK-ISOL | 2018-06-21 | 2019-04-17 | 2019-08-31 | 2019-08-31 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 88041 | Work Order Description - 88041 - BR | BR | 3 | 554615 | SCHD | ON LINE | 2018-07-06 | 2019-07-11 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 88053 | Work Order Description - 88053 - CM | CM | 3 | 321199 | WSCHD | SYS-ISOL | 2018-05-04 | 2020-04-26 | 2019-05-25 | 2019-05-26 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 88213 | Work Order Description - 88213 - CM | CM | 2 | 408340 | SCHD | NORM-OPS | 2018-10-29 | 2019-04-29 | 2019-05-25 | 2019-05-26 | 3 | OPERATIONS | OPERATIONS | 8
2019-03-31 | 88216 | Work Order Description - 88216 - CM | CM | 4 | 527253 | SCHD | TPS | 2019-02-13 | 2020-02-04 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 88263 | Work Order Description - 88263 - PM | PM | 4 | 533322 | SCHD | EQUIP-ISOL | 2018-07-18 | 2019-02-01 | 2019-02-23 | 2019-02-23 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 88284 | Work Order Description - 88284 - PM | PM | 3 | 395990 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-02-20 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 88289 | Work Order Description - 88289 - PM | PM | 4 | 375615 | SCHD | PACK-ISOL | 2018-06-21 | 2019-09-16 | 2019-05-26 | 2019-05-26 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 88459 | Work Order Description - 88459 - CM | CM | 3 | 418118 | WSCHD | NORM-OPS | 2018-08-01 | 2020-04-28 | 2019-04-13 | 2019-04-15 | 4 | MAINTENANCE | MECHANICAL | 21.5
2019-03-31 | 88473 | Work Order Description - 88473 - CM | CM | 4 | 113092 | INPRG | ON LINE | 2018-11-30 | 2020-04-28 | 2019-04-27 | 2019-11-29 | 4 | MAINTENANCE | MECHANICAL | 81.5
2019-03-31 | 88474 | Work Order Description - 88474 - BR | BR | 4 | 652220 | WSCHD | NORM-OPS | 2018-05-01 | 2020-04-29 | 2019-04-27 | 2019-04-29 | 4 | MAINTENANCE | SERVICES | 10
2019-03-31 | 88487 | Work Order Description - 88487 - PSPM | PSPM | 1 | 487752 | SCHD | EQUIP-ISOL | 2018-10-18 | 2020-05-21 | 2020-04-18 | 2020-04-18 | 1 | INTEGRITY | MECHANICAL | 46
2019-03-31 | 88541 | Work Order Description - 88541 - CM | CM | 1 | 459600 | SCHD | NORM-OPS | 2018-09-06 | 2020-04-29 | 2019-11-02 | 2019-11-02 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 88546 | Work Order Description - 88546 - BR | BR | 1 | 546306 | WSCHD | PACK-ISOL | 2018-07-08 | 2019-07-08 | 2019-05-11 | 2019-05-15 | 3 | MAINTENANCE | CONSTRUCTION | 49
2019-03-31 | 88552 | Work Order Description - 88552 - BR | BR | 1 | 671297 | SCHD | PACK-ISOL | 2018-10-19 | 2019-07-08 | 2019-05-04 | 2019-05-07 | 3 | MAINTENANCE | CONSTRUCTION | 49
2019-03-31 | 88553 | Work Order Description - 88553 - BR | BR | 1 | 359385 | SCHD | PACK-ISOL | 2018-10-19 | 2019-07-08 | 2019-05-04 | 2019-05-07 | 3 | MAINTENANCE | CONSTRUCTION | 43
2019-03-31 | 88554 | Work Order Description - 88554 - BR | BR | 1 | 308153 | WSCHD | PACK-ISOL | 2018-10-23 | 2019-07-08 | 2019-05-04 | 2019-05-07 | 3 | MAINTENANCE | CONSTRUCTION | 43
2019-03-31 | 88559 | Work Order Description - 88559 - BR | BR | 1 | 308154 | WSCHD | PACK-ISOL | 2018-10-23 | 2019-07-08 | 2019-05-04 | 2019-05-07 | 3 | MAINTENANCE | CONSTRUCTION | 43
2019-03-31 | 88560 | Work Order Description - 88560 - PSCM | PSCM | 1 | 308155 | WSCHD | PACK-ISOL | 2018-10-23 | 2019-07-08 | 2019-05-04 | 2019-05-07 | 3 | MAINTENANCE | CONSTRUCTION | 43
2019-03-31 | 88561 | Work Order Description - 88561 - BR | BR | 1 | 247125 | WSCHD | PACK-ISOL | 2018-10-23 | 2019-07-08 | 2019-05-04 | 2019-05-07 | 3 | MAINTENANCE | CONSTRUCTION | 43
2019-03-31 | 88568 | Work Order Description - 88568 - BR | BR | 1 | 411132 | WSCHD | PACK-ISOL | 2018-10-23 | 2019-07-08 | 2019-05-04 | 2019-05-07 | 3 | MAINTENANCE | CONSTRUCTION | 43
2019-03-31 | 88569 | Work Order Description - 88569 - BR | BR | 1 | 247103 | SCHD | PACK-ISOL | 2018-10-19 | 2019-07-08 | 2019-05-04 | 2019-05-07 | 3 | MAINTENANCE | CONSTRUCTION | 43
2019-03-31 | 88570 | Work Order Description - 88570 - BR | BR | 1 | 357154 | SCHD | PACK-ISOL | 2018-10-19 | 2019-07-10 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | CONSTRUCTION | 17
2019-03-31 | 88576 | Work Order Description - 88576 - BR | BR | 1 | 357156 | WSCHD | PACK-ISOL | 2018-10-19 | 2019-07-08 | 2019-05-04 | 2019-05-07 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 88580 | Work Order Description - 88580 - BR | BR | 1 | 308158 | WSCHD | PACK-ISOL | 2018-10-19 | 2019-07-08 | 2019-05-04 | 2019-05-07 | 3 | MAINTENANCE | CONSTRUCTION | 51
2019-03-31 | 88584 | Work Order Description - 88584 - BR | BR | 1 | 356290 | SCHD | PACK-ISOL | 2018-10-19 | 2019-07-08 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | CONSTRUCTION | 40
2019-03-31 | 88588 | Work Order Description - 88588 - BR | BR | 1 | 308156 | SCHD | PACK-ISOL | 2018-10-19 | 2019-07-08 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | CONSTRUCTION | 43
2019-03-31 | 88589 | Work Order Description - 88589 - BR | BR | 1 | 247109 | WSCHD | PACK-ISOL | 2018-10-25 | 2019-07-08 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | CONSTRUCTION | 43
2019-03-31 | 88590 | Work Order Description - 88590 - BR | BR | 1 | 247108 | WSCHD | TPS | 2018-10-21 | 2019-07-08 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | CONSTRUCTION | 43
2019-03-31 | 88612 | Work Order Description - 88612 - PSPM | PSPM | 1 | 261206 | WSCHD | EQUIP-ISOL | 2018-05-02 | 2019-09-22 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 88697 | Work Order Description - 88697 - CM | CM | 2 | 45196 | WSCHD | NORM-OPS | 2018-09-15 | 2019-10-14 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 88714 | Work Order Description - 88714 - CM | CM | 1 | 460192 | WMATL | TPS | 2018-09-06 | 2020-04-30 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 45
2019-03-31 | 88716 | Work Order Description - 88716 - BR | BR | 2 | 520731 | WPLAN | PACK-ISOL | 2018-05-17 | 2020-04-30 | 2020-05-02 | 2020-05-04 | 4 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 88717 | Work Order Description - 88717 - CM | CM | 3 | 540396 | SCHD | TPS | 2018-08-31 | 2020-04-30 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 88732 | Work Order Description - 88732 - CM | CM | 4 | 215921 | SCHD | NORM-OPS | 2018-09-06 | 2020-04-30 | 2020-03-28 | 2020-03-28 | 4 | INTEGRITY | FABRIC | 2
2019-03-31 | 88739 | Work Order Description - 88739 - PM | PM | 2 | 249700 | SCHD | EQUIP-ISOL | 2018-12-10 | 2019-05-04 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 88741 | Work Order Description - 88741 - PM | PM | 4 | 674851 | WSCHD | EQUIP-ISOL | 2018-05-03 | 2019-08-15 | 2019-04-13 | 2019-04-15 | 2 | MAINTENANCE | ELECTRICAL | 29
2019-03-31 | 88822 | Work Order Description - 88822 - BR | BR | 3 | 357304 | WSCHD | SYS-ISOL | 2018-06-01 | 2020-05-01 | 2019-05-11 | 2019-05-14 | 4 | MAINTENANCE | MECHANICAL | 35
2019-03-31 | 88880 | Work Order Description - 88880 - PM | PM | 2 | 305395 | WSCHD | NORM-OPS | 2018-05-04 | 2019-10-22 | 2019-08-31 | 2019-08-31 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 88883 | Work Order Description - 88883 - PSPM | PSPM | 1 | 249449 | SCHD | SUBSYS-ISOL | 2018-09-21 | 2019-07-01 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSPECTION | 12
2019-03-31 | 88889 | Work Order Description - 88889 - PM | PM | 3 | 360482 | WSCHD | EQUIP-ISOL | 2018-05-04 | 2019-03-27 | 2020-03-28 | 2020-03-28 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 88890 | Work Order Description - 88890 - PM | PM | 3 | 54473 | WSCHD | PACK-ISOL | 2018-05-04 | 2020-01-15 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 88891 | Work Order Description - 88891 - PM | PM | 3 | 360522 | WSCHD | PACK-ISOL | 2018-05-04 | 2019-12-31 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 88893 | Work Order Description - 88893 - PM | PM | 3 | 54474 | WSCHD | PACK-ISOL | 2018-05-04 | 2019-07-10 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 88894 | Work Order Description - 88894 - PM | PM | 3 | 360523 | SCHD | PACK-ISOL | 2019-03-29 | 2019-06-29 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 88904 | Work Order Description - 88904 - PM | PM | 4 | 368177 | SCHD | EQUIP-ISOL | 2018-10-19 | 2019-03-06 | 2019-04-06 | 2019-04-07 | 2 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 88905 | Work Order Description - 88905 - PM | PM | 4 | 368177 | SCHD | EQUIP-ISOL | 2018-10-19 | 2019-03-04 | 2019-04-06 | 2019-04-07 | 2 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 88943 | Work Order Description - 88943 - PM | PM | 4 | 653434 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-04-25 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 88945 | Work Order Description - 88945 - PM | PM | 4 | 671828 | WSCHD | PACK-ISOL | 2018-05-04 | 2020-01-11 | 2019-04-27 | 2019-04-28 | 1 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 88971 | Work Order Description - 88971 - PM | PM | 4 | 262785 | SCHD | NORM-OPS | 2018-08-27 | 2019-12-17 | 2019-04-20 | 2019-04-20 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 88972 | Work Order Description - 88972 - PSPM | PSPM | 4 | 464259 | SCHD | NORM-OPS | 2018-08-27 | 2019-06-21 | 2019-09-07 | 2019-09-07 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 88973 | Work Order Description - 88973 - PM | PM | 4 | 464259 | SCHD | NORM-OPS | 2018-07-18 | 2019-08-11 | 2019-09-07 | 2019-09-07 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 89025 | Work Order Description - 89025 - PM | PM | 3 | 99543 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-04-13 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 89033 | Work Order Description - 89033 - PM | PM | 3 | 186604 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-07-24 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 89034 | Work Order Description - 89034 - PM | PM | 3 | 178888 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-11-30 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 89040 | Work Order Description - 89040 - PM | PM | 3 | 396150 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-06-11 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 89045 | Work Order Description - 89045 - PM | PM | 3 | 179087 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-10-12 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 89046 | Work Order Description - 89046 - PM | PM | 3 | 78354 | SCHD | EQUIP-ISOL | 2019-03-06 | 2018-12-24 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 89062 | Work Order Description - 89062 - PM | PM | 3 | 395992 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-09-01 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 89980 | Work Order Description - 89980 - CM | CM | 3 | 363765 | INPRG | TPS | 2018-07-04 | 2020-05-02 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | INSPECTION | 41
2019-03-31 | 89994 | Work Order Description - 89994 - BR | BR | 3 | 51480 | WSCHD | TPS | 2018-06-07 | 2020-05-02 | 2020-05-02 | 2020-05-05 | 4 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 89996 | Work Order Description - 89996 - CM | CM | 1 | 450973 | SCHD | NORM-OPS | 2019-02-13 | 2020-05-02 | 2019-04-14 | 2019-04-14 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 90001 | Work Order Description - 90001 - BR | BR | 3 | 308838 | WSCHD | NORM-OPS | 2018-06-08 | 2020-05-02 | 2020-05-03 | 2020-05-03 | 4 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 90047 | Work Order Description - 90047 - PM | PM | 4 | 310033 | SCHD | PACK-ISOL | 2018-07-18 | 2018-12-11 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | MECHANICAL | 18
2019-03-31 | 90161 | Work Order Description - 90161 - CM | CM | 3 | 256339 | WSCHD | TPS | 2019-03-25 | 2019-08-31 | 2019-07-13 | 2019-07-13 | 2 | INTEGRITY | CONSTRUCTION | 2
2019-03-31 | 90175 | Work Order Description - 90175 - CM | CM | 1 | 544715 | WPLAN | TPS | 2018-05-06 | 2019-08-01 | 2019-06-01 | 2019-06-02 | 3 | MAINTENANCE | ELECTRICAL | 16
2019-03-31 | 90210 | Work Order Description - 90210 - PM | PM | 4 | 314186 | SCHD | NORM-OPS | 2018-10-29 | 2019-07-08 | 2020-12-05 | 2020-12-05 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 90349 | Work Order Description - 90349 - CM | CM | 4 | 183648 | SCHD | ON LINE | 2018-09-06 | 2019-10-08 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 90360 | Work Order Description - 90360 - CM | CM | 1 | 155742 | WSCHD | NORM-OPS | 2018-11-17 | 2020-05-04 | 2019-05-04 | 2019-05-08 | 4 | INTEGRITY | FABRIC | 60
2019-03-31 | 90363 | Work Order Description - 90363 - CM | CM | 4 | 579234 | SCHD | NORM-OPS | 2018-09-06 | 2019-11-05 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 90367 | Work Order Description - 90367 - CM | CM | 4 | 462436 | WPLAN | NORM-OPS | 2018-05-11 | 2019-05-06 | 2020-02-01 | 2020-02-01 | 3 | MAINTENANCE | FABRIC | 1
2019-03-31 | 90519 | Work Order Description - 90519 - BR | BR | 3 | 461046 | WMATL | SYS-ISOL | 2018-06-04 | 2020-05-05 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 90535 | Work Order Description - 90535 - BR | BR | 3 | 480102 | WSCHD | SYS-ISOL | 2018-06-01 | 2019-05-06 | 2019-04-20 | 2019-04-22 | 3 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 90536 | Work Order Description - 90536 - PSPM | PSPM | 1 | 261029 | WSCHD | EQUIP-ISOL | 2018-05-07 | 2021-08-31 | 2021-07-31 | 2021-07-31 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 90537 | Work Order Description - 90537 - CM | CM | 1 | 57460 | WPLAN | NORM-OPS | 2018-06-07 | 2019-05-07 | 2019-05-25 | 2019-05-25 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 90539 | Work Order Description - 90539 - CM | CM | 1 | 57460 | WPLAN | NORM-OPS | 2018-06-10 | 2020-05-05 | 2019-05-25 | 2019-05-25 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 90543 | Work Order Description - 90543 - CM | CM | 1 | 57460 | WPLAN | NORM-OPS | 2018-06-07 | 2019-05-07 | 2019-05-04 | 2019-05-04 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 90550 | Work Order Description - 90550 - CM | CM | 1 | 57460 | WPLAN | NORM-OPS | 2018-06-07 | 2019-05-01 | 2019-05-25 | 2019-06-01 | 3 | INTEGRITY | CONSTRUCTION | 504
2019-03-31 | 90552 | Work Order Description - 90552 - CM | CM | 1 | 501444 | WPLAN | NORM-OPS | 2018-06-07 | 2019-05-07 | 2019-06-01 | 2019-06-01 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 90589 | Work Order Description - 90589 - PM | PM | 4 | 126192 | SCHD | EQUIP-ISOL | 2018-06-21 | 2018-12-31 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 90592 | Work Order Description - 90592 - PM | PM | 4 | 78534 | SCHD | PACK-ISOL | 2018-06-21 | 2019-03-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 90707 | Work Order Description - 90707 - PM | PM | 3 | 124177 | SCHD | PACK-ISOL | 2018-06-21 | 2019-05-04 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 90708 | Work Order Description - 90708 - PM | PM | 3 | 266276 | SCHD | PACK-ISOL | 2018-06-21 | 2019-05-04 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 90709 | Work Order Description - 90709 - PM | PM | 3 | 125963 | SCHD | PACK-ISOL | 2018-06-21 | 2019-05-04 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 90817 | Work Order Description - 90817 - BR | BR | 2 | 478026 | WMATL | NORM-OPS | 2018-05-21 | 2020-05-07 | 2019-09-07 | 2019-09-07 | 4 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 91056 | Work Order Description - 91056 - CM | CM | 3 | 670458 | WMATL | PACK-ISOL | 2018-07-05 | 2019-05-10 | 2019-06-02 | 2019-06-13 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 91060 | Work Order Description - 91060 - CM | CM | 3 | 216011 | SCHD | SYS-ISOL | 2018-11-10 | 2019-07-21 | 2019-05-11 | 2019-05-11 | 3 | INTEGRITY | INSTRUMENTS | 2
2019-03-31 | 91069 | Work Order Description - 91069 - CM | CM | 4 | 491255 | SCHD | NORM-OPS | 2018-10-04 | 2019-07-01 | 2019-05-18 | 2019-05-18 | 3 | INTEGRITY | FABRIC | 280
2019-03-31 | 91080 | Work Order Description - 91080 - CM | CM | 4 | 555228 | SCHD | NORM-OPS | 2018-09-06 | 2019-01-02 | 2020-05-30 | 2020-05-30 | 4 | OPERATIONS | OPERATIONS | 1
2019-03-31 | 91177 | Work Order Description - 91177 - BR | BR | 3 | 462620 | SCHD | NORM-OPS | 2018-09-06 | 2020-05-09 | 2019-06-22 | 2019-06-22 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 91181 | Work Order Description - 91181 - CM | CM | 4 | 547275 | WMATL | NORM-OPS | 2018-05-17 | 2020-05-09 | 2019-04-27 | 2019-04-28 | 4 | OPERATIONS | MECHANICAL | 28
2019-03-31 | 91250 | Work Order Description - 91250 - CM | CM | 3 | 555572 | WMATL | SYS-ISOL | 2018-05-17 | 2018-12-04 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 91290 | Work Order Description - 91290 - PSPM | PSPM | 1 | 388215 | SCHD | TPS | 2018-12-27 | 2019-06-02 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 91349 | Work Order Description - 91349 - CM | CM | 3 | 383838 | SCHD | ON LINE | 2018-07-03 | 2020-05-10 | 2019-04-06 | 2019-04-07 | 4 | MAINTENANCE | FABRIC | 24
2019-03-31 | 91378 | Work Order Description - 91378 - BR | BR | 4 | 265465 | SCHD | NORM-OPS | 2018-11-05 | 2020-05-10 | 2019-04-13 | 2019-04-13 | 4 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 91384 | Work Order Description - 91384 - CM | CM | 4 | 81279 | SCHD | PACK-ISOL | 2018-09-06 | 2020-05-11 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 91523 | Work Order Description - 91523 - CM | CM | 4 | 568174 | SCHD | PACK-ISOL | 2018-09-06 | 2020-05-11 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 91525 | Work Order Description - 91525 - CM | CM | 4 | 445967 | SCHD | PACK-ISOL | 2018-09-06 | 2020-05-11 | 2019-05-18 | 2019-05-18 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 91528 | Work Order Description - 91528 - CM | CM | 3 | 583997 | SCHD | PACK-ISOL | 2019-01-25 | 2020-05-11 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 91625 | Work Order Description - 91625 - CM | CM | 4 | 482737 | WSCHD | NORM-OPS | 2019-03-25 | 2019-07-31 | 2019-06-01 | 2019-06-02 | 3 | INTEGRITY | CONSTRUCTION | 24
2019-03-31 | 91632 | Work Order Description - 91632 - CM | CM | 4 | 484935 | WPLAN | NORM-OPS | 2018-05-17 | 2019-12-01 | 2019-05-11 | 2019-05-11 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 91634 | Work Order Description - 91634 - PSCM | PSCM | 1 | 531789 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-03-30 | 2019-04-04 | 4 | INTEGRITY | INSPECTION | 775.5
2019-03-31 | 91636 | Work Order Description - 91636 - BR | BR | 3 | 545266 | WPLAN | PACK-ISOL | 2018-05-14 | 2020-05-12 | 2019-09-07 | 2019-10-04 | 4 | MAINTENANCE | MECHANICAL | 456
2019-03-31 | 91648 | Work Order Description - 91648 - CM | CM | 1 | 467877 | WSCHD | NORM-OPS | 2018-11-17 | 2020-05-12 | 2019-05-04 | 2019-05-08 | 4 | INTEGRITY | FABRIC | 219
2019-03-31 | 91649 | Work Order Description - 91649 - CM | CM | 1 | 467877 | WSCHD | NORM-OPS | 2018-11-16 | 2020-05-12 | 2019-05-04 | 2019-05-08 | 4 | INTEGRITY | FABRIC | 227.5
2019-03-31 | 91679 | Work Order Description - 91679 - PSPM | PSPM | 1 | 309198 | SCHD | TPS | 2018-12-05 | 2019-06-01 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 8
2019-03-31 | 91692 | Work Order Description - 91692 - PM | PM | 3 | 383839 | SCHD | PACK-ISOL | 2018-06-21 | 2019-04-09 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 91693 | Work Order Description - 91693 - PM | PM | 3 | 375679 | SCHD | PACK-ISOL | 2018-06-21 | 2019-05-28 | 2019-07-06 | 2019-07-06 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 91767 | Work Order Description - 91767 - CM | CM | 4 | 361639 | WPLAN | NORM-OPS | 2018-05-17 | 2020-05-13 | 2020-05-09 | 2020-05-09 | 4 | INTEGRITY | INSPECTION | 1
2019-03-31 | 91791 | Work Order Description - 91791 - PSCM | PSCM | 1 | 465450 | SCHD | PACK-ISOL | 2018-09-06 | 2020-05-13 | 2020-02-01 | 2020-02-01 | 4 | WELLS | WELLS | 42
2019-03-31 | 91792 | Work Order Description - 91792 - CM | CM | 1 | 57460 | WPLAN | NORM-OPS | 2018-05-16 | 2020-05-13 | 2019-11-30 | 2019-11-30 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 91797 | Work Order Description - 91797 - PSCM | PSCM | 1 | 465450 | SCHD | PACK-ISOL | 2018-09-06 | 2020-05-13 | 2019-10-26 | 2019-10-26 | 4 | WELLS | WELLS | 42
2019-03-31 | 91801 | Work Order Description - 91801 - PSCM | PSCM | 1 | 465450 | SCHD | PACK-ISOL | 2018-09-06 | 2020-05-13 | 2019-10-12 | 2019-10-12 | 4 | WELLS | WELLS | 42
2019-03-31 | 91803 | Work Order Description - 91803 - PSCM | PSCM | 1 | 465450 | SCHD | PACK-ISOL | 2018-09-06 | 2020-05-13 | 2019-10-12 | 2019-10-12 | 4 | WELLS | WELLS | 42
2019-03-31 | 91804 | Work Order Description - 91804 - PSCM | PSCM | 1 | 465450 | SCHD | PACK-ISOL | 2018-09-06 | 2020-05-13 | 2019-10-12 | 2019-10-12 | 4 | WELLS | WELLS | 30
2019-03-31 | 91806 | Work Order Description - 91806 - BR | BR | 1 | 465450 | WPLAN | PACK-ISOL | 2018-06-29 | 2020-05-13 | 2019-08-03 | 2019-08-03 | 4 | WELLS | WELLS | 1
2019-03-31 | 91808 | Work Order Description - 91808 - CM | CM | 2 | 95306 | SCHD | PACK-ISOL | 2018-09-06 | 2020-05-13 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | MECHANICAL | 6.5
2019-03-31 | 91934 | Work Order Description - 91934 - PM | PM | 4 | 469066 | SCHD | EQUIP-ISOL | 2018-09-25 | 2019-06-22 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 91940 | Work Order Description - 91940 - PM | PM | 4 | 664951 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-07-18 | 2019-04-28 | 2019-04-28 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 92031 | Work Order Description - 92031 - BR | BR | 3 | 308838 | WSCHD | TPS | 2018-05-18 | 2020-05-15 | 2020-05-02 | 2020-05-04 | 4 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 92034 | Work Order Description - 92034 - BR | BR | 4 | 355393 | WSCHD | NORM-OPS | 2018-06-08 | 2019-12-12 | 2019-04-27 | 2019-04-28 | 2 | INTEGRITY | MECHANICAL | 62
2019-03-31 | 92036 | Work Order Description - 92036 - BR | BR | 3 | 215611 | WSCHD | TPS | 2018-05-18 | 2020-05-15 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 25
2019-03-31 | 92038 | Work Order Description - 92038 - BR | BR | 3 | 245960 | WSCHD | TPS | 2018-05-18 | 2020-05-15 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | CONSTRUCTION | 25
2019-03-31 | 92053 | Work Order Description - 92053 - CM | CM | 4 | 484754 | SCHD | NORM-OPS | 2018-10-29 | 2020-05-15 | 2019-05-04 | 2019-05-05 | 4 | INTEGRITY | FABRIC | 150
2019-03-31 | 92061 | Work Order Description - 92061 - CM | CM | 3 | 484754 | WSCHD | NORM-OPS | 2018-05-27 | 2020-05-15 | 2019-04-13 | 2019-04-20 | 4 | INTEGRITY | FABRIC | 124
2019-03-31 | 92107 | Work Order Description - 92107 - PM | PM | 4 | 450692 | SCHD | NORM-OPS | 2018-06-21 | 2019-05-08 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | SAFETY | 29
2019-03-31 | 92405 | Work Order Description - 92405 - CM | CM | 1 | 80458 | SCHD | NORM-OPS | 2018-06-01 | 2020-05-16 | 2019-04-27 | 2019-04-29 | 4 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 92586 | Work Order Description - 92586 - CM | CM | 1 | 481714 | WPLAN | NORM-OPS | 2018-06-07 | 2020-06-04 | 2019-05-25 | 2019-06-29 | 4 | INTEGRITY | CONSTRUCTION | 834
2019-03-31 | 92619 | Work Order Description - 92619 - PM | PM | 4 | 546702 | WSCHD | NORM-OPS | 2018-05-20 | 2019-08-19 | 2020-05-02 | 2020-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 92641 | Work Order Description - 92641 - PM | PM | 4 | 355548 | WSCHD | EQUIP-ISOL | 2018-05-20 | 2019-03-02 | 2022-12-31 | 2023-01-02 | 2 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 92666 | Work Order Description - 92666 - PSPM | PSPM | 1 | 388109 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-07-01 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 92736 | Work Order Description - 92736 - CM | CM | 4 | 18683 | SCHD | NORM-OPS | 2018-09-06 | 2020-05-18 | 2019-08-31 | 2019-08-31 | 4 | MAINTENANCE | INSTRUMENTS | 70
2019-03-31 | 92762 | Work Order Description - 92762 - CM | CM | 4 | 626120 | SCHD | NORM-OPS | 2019-03-29 | 2021-02-06 | 2019-08-24 | 2019-08-24 | 4 | INTEGRITY | FABRIC | 3
2019-03-31 | 92779 | Work Order Description - 92779 - PM | PM | 4 | 666777 | WSCHD | NORM-OPS | 2018-05-21 | 2019-08-29 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | DRILLING | 8
2019-03-31 | 92790 | Work Order Description - 92790 - PSPM | PSPM | 1 | 399723 | WSCHD | EQUIP-ISOL | 2018-10-29 | 2019-11-29 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 92907 | Work Order Description - 92907 - BR | BR | 1 | 48006 | WSCHD | SYS-ISOL | 2018-06-01 | 2019-05-21 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 92913 | Work Order Description - 92913 - BR | BR | 1 | 307401 | WMATL | SYS-ISOL | 2018-05-31 | 2019-05-21 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 93014 | Work Order Description - 93014 - PM | PM | 4 | 80369 | SCHD | PACK-ISOL | 2018-06-21 | 2018-12-30 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 93015 | Work Order Description - 93015 - PM | PM | 3 | 110773 | SCHD | PACK-ISOL | 2018-06-21 | 2018-12-24 | 2019-05-18 | 2019-05-18 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 93087 | Work Order Description - 93087 - CM | CM | 3 | 361654 | WSCHD | NORM-OPS | 2019-02-25 | 2020-05-20 | 2019-05-25 | 2019-05-26 | 4 | INTEGRITY | FABRIC | 49
2019-03-31 | 93120 | Work Order Description - 93120 - CM | CM | 3 | 496963 | SCHD | NORM-OPS | 2018-06-15 | 2020-05-20 | 2019-06-03 | 2019-06-04 | 4 | INTEGRITY | FABRIC | 180
2019-03-31 | 93175 | Work Order Description - 93175 - CM | CM | 4 | 452109 | SCHD | NORM-OPS | 2018-09-06 | 2019-06-05 | 2020-04-18 | 2020-04-18 | 4 | MAINTENANCE | CONSTRUCTION | 22
2019-03-31 | 93421 | Work Order Description - 93421 - PSCM | PSCM | 1 | 674395 | WSCHD | PACK-ISOL | 2018-08-25 | 2020-08-01 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 93422 | Work Order Description - 93422 - PSCM | PSCM | 1 | 671266 | WSCHD | TPS | 2017-06-10 | 2020-08-01 | 2020-05-02 | 2020-05-04 | 3 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 93427 | Work Order Description - 93427 - CM | CM | 4 | 658773 | SCHD | NORM-OPS | 2018-09-06 | 2019-06-05 | 2019-04-20 | 2019-04-20 | 4 | INTEGRITY | FABRIC | 6
2019-03-31 | 93508 | Work Order Description - 93508 - PM | PM | 4 | 81493 | SCHD | PACK-ISOL | 2018-06-21 | 2019-09-23 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 93543 | Work Order Description - 93543 - CM | CM | 3 | 549377 | SCHD | NORM-OPS | 2018-07-18 | 2019-01-10 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | FABRIC | 12
2019-03-31 | 93556 | Work Order Description - 93556 - CM | CM | 2 | 479579 | SCHD | NORM-OPS | 2018-11-08 | 2019-07-01 | 2019-02-16 | 2019-02-17 | 3 | INTEGRITY | FABRIC | 140
2019-03-31 | 93557 | Work Order Description - 93557 - CM | CM | 4 | 226532 | WSCHD | NORM-OPS | 2017-06-16 | 2018-12-08 | 2019-12-28 | 2019-12-29 | 2 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 93583 | Work Order Description - 93583 - PM | PM | 3 | 262305 | WSCHD | EQUIP-ISOL | 2017-06-08 | 2019-08-11 | 2019-12-28 | 2019-12-28 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 93846 | Work Order Description - 93846 - CM | CM | 3 | 487378 | SCHD | TPS | 2018-05-24 | 2019-06-15 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 93874 | Work Order Description - 93874 - CM | CM | 4 | 491740 | WSCHD | NORM-OPS | 2018-06-08 | 2019-08-25 | 2020-05-03 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 93875 | Work Order Description - 93875 - CM | CM | 4 | 491771 | WSCHD | TPS | 2017-06-15 | 2019-10-14 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 94117 | Work Order Description - 94117 - PSCM | PSCM | 1 | 243625 | SCHD | NORM-OPS | 2018-09-06 | 2019-06-07 | 2019-05-18 | 2019-05-18 | 4 | MAINTENANCE | DRILLING | 14
2019-03-31 | 94128 | Work Order Description - 94128 - PM | PM | 4 | 247296 | WSCHD | NORM-OPS | 2018-03-18 | 2019-10-01 | 2019-09-01 | 2019-09-05 | 1 | INTEGRITY | INSPECTION | 30
2019-03-31 | 94129 | Work Order Description - 94129 - PM | PM | 4 | 247296 | WSCHD | NORM-OPS | 2018-03-18 | 2019-10-01 | 2019-09-01 | 2019-09-05 | 1 | INTEGRITY | INSPECTION | 30
2019-03-31 | 94130 | Work Order Description - 94130 - PM | PM | 4 | 247296 | WSCHD | NORM-OPS | 2018-03-18 | 2019-10-01 | 2019-09-01 | 2019-09-05 | 1 | INTEGRITY | INSPECTION | 30
2019-03-31 | 94131 | Work Order Description - 94131 - PM | PM | 4 | 247296 | WSCHD | NORM-OPS | 2018-03-18 | 2019-10-01 | 2019-09-01 | 2019-09-05 | 1 | INTEGRITY | INSPECTION | 30
2019-03-31 | 94146 | Work Order Description - 94146 - CM | CM | 1 | 403537 | SCHD | NORM-OPS | 2018-09-06 | 2020-01-01 | 2020-02-29 | 2020-02-29 | 3 | INTEGRITY | FABRIC | 12
2019-03-31 | 94164 | Work Order Description - 94164 - CM | CM | 4 | 258106 | SCHD | NORM-OPS | 2018-09-06 | 2019-06-12 | 2020-03-14 | 2020-03-14 | 4 | MAINTENANCE | CONSTRUCTION | 16
2019-03-31 | 94170 | Work Order Description - 94170 - CM | CM | 4 | 215916 | SCHD | NORM-OPS | 2018-09-06 | 2019-11-17 | 2019-09-07 | 2019-09-07 | 4 | INTEGRITY | FABRIC | 32
2019-03-31 | 94380 | Work Order Description - 94380 - PSCM | PSCM | 1 | 481746 | SCHD | NORM-OPS | 2018-06-21 | 2019-06-14 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | FABRIC | 1
2019-03-31 | 94461 | Work Order Description - 94461 - CM | CM | 4 | 261243 | WSCHD | TPS | 2017-06-18 | 2019-06-16 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | MECHANICAL | 8
2019-03-31 | 94470 | Work Order Description - 94470 - CM | CM | 4 | 215410 | WPLAN | TPS | 2017-06-18 | 2019-01-31 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | CONSTRUCTION | 18
2019-03-31 | 94477 | Work Order Description - 94477 - CM | CM | 1 | 17814 | WSCHD | TPS | 2018-06-07 | 2020-07-02 | 2020-05-02 | 2020-05-06 | 3 | INTEGRITY | CONSTRUCTION | 24.5
2019-03-31 | 94534 | Work Order Description - 94534 - PRJ | PRJ | 4 | 478640 | SCHD | NORM-OPS | 2018-09-06 | 2019-09-20 | 2019-05-18 | 2019-05-18 | 4 | INTEGRITY | MECHANICAL | 1
2019-03-31 | 94546 | Work Order Description - 94546 - CM | CM | 4 | 652160 | WSCHD | NORM-OPS | 2017-06-20 | 2019-06-18 | 2019-07-06 | 2019-08-01 | 4 | MAINTENANCE | MECHANICAL | 368
2019-03-31 | 94579 | Work Order Description - 94579 - CM | CM | 2 | 57976 | WSCHD | TPS | 2017-06-20 | 2019-03-03 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | INSTRUMENTS | 18.5
2019-03-31 | 94591 | Work Order Description - 94591 - CM | CM | 4 | 545261 | WSCHD | NORM-OPS | 2017-06-24 | 2019-06-19 | 2019-07-27 | 2019-07-28 | 4 | MAINTENANCE | SERVICES | 42
2019-03-31 | 94592 | Work Order Description - 94592 - CM | CM | 4 | 545261 | WSCHD | NORM-OPS | 2017-06-24 | 2019-06-19 | 2019-12-28 | 2019-12-28 | 4 | MAINTENANCE | SERVICES | 12
2019-03-31 | 94609 | Work Order Description - 94609 - PM | PM | 2 | 408274 | WSCHD | EQUIP-ISOL | 2017-07-22 | 2019-05-27 | 2019-04-26 | 2019-04-30 | 1 | INTEGRITY | MECHANICAL | 64
2019-03-31 | 95443 | Work Order Description - 95443 - CM | CM | 3 | 33953 | WSCHD | SYS-ISOL | 2018-06-15 | 2019-11-15 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 95647 | Work Order Description - 95647 - CM | CM | 4 | 531038 | WSCHD | NORM-OPS | 2017-06-27 | 2019-11-30 | 2019-08-31 | 2019-08-31 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 95663 | Work Order Description - 95663 - PSCM | PSCM | 1 | 360506 | WSCHD | NORM-OPS | 2017-06-27 | 2019-12-29 | 2019-05-18 | 2019-05-18 | 3 | MAINTENANCE | CONSTRUCTION | 6
2019-03-31 | 95696 | Work Order Description - 95696 - CM | CM | 2 | 652482 | WSCHD | NORM-OPS | 2017-06-27 | 2019-08-03 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | SERVICES | 37
2019-03-31 | 95735 | Work Order Description - 95735 - CM | CM | 4 | 19074 | WSCHD | NORM-OPS | 2017-06-27 | 2019-06-25 | 2019-06-29 | 2019-06-30 | 3 | INTEGRITY | SERVICES | 30
2019-03-31 | 95736 | Work Order Description - 95736 - CM | CM | 3 | 19074 | WSCHD | NORM-OPS | 2017-06-27 | 2019-06-25 | 2019-06-29 | 2019-06-29 | 3 | INTEGRITY | SERVICES | 21
2019-03-31 | 96186 | Work Order Description - 96186 - PSPM | PSPM | 1 | 464965 | SCHD | PACK-ISOL | 2018-09-06 | 2019-10-01 | 2019-09-07 | 2019-09-07 | 3 | WELLS | WELLS | 6
2019-03-31 | 96188 | Work Order Description - 96188 - PSPM | PSPM | 1 | 465444 | SCHD | PACK-ISOL | 2018-09-24 | 2019-09-02 | 2019-06-08 | 2019-06-08 | 3 | WELLS | WELLS | 6
2019-03-31 | 96204 | Work Order Description - 96204 - CM | CM | 4 | 215905 | SCHD | SYS-ISOL | 2018-09-06 | 2019-06-26 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | MECHANICAL | 38
2019-03-31 | 96572 | Work Order Description - 96572 - CM | CM | 3 | 20522 | WSCHD | NORM-OPS | 2019-03-25 | 2020-01-30 | 2019-04-13 | 2019-04-13 | 2 | INTEGRITY | CONSTRUCTION | 23
2019-03-31 | 96864 | Work Order Description - 96864 - CM | CM | 1 | 462586 | SCHD | NORM-OPS | 2018-12-05 | 2019-10-01 | 2020-03-07 | 2020-03-07 | 3 | MAINTENANCE | CONSTRUCTION | 15
2019-03-31 | 96868 | Work Order Description - 96868 - CM | CM | 4 | 137978 | WSCHD | NORM-OPS | 2017-07-03 | 2019-06-29 | 2019-06-29 | 2019-07-01 | 4 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 96870 | Work Order Description - 96870 - PSCM | PSCM | 1 | 138432 | WSCHD | PACK-ISOL | 2017-07-08 | 2020-08-01 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | INSTRUMENTS | 9
2019-03-31 | 96873 | Work Order Description - 96873 - CM | CM | 3 | 308099 | WSCHD | TPS | 2017-07-06 | 2019-07-01 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 96874 | Work Order Description - 96874 - CM | CM | 4 | 138062 | WSCHD | NORM-OPS | 2017-07-03 | 2019-06-29 | 2019-04-20 | 2019-04-22 | 4 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 96878 | Work Order Description - 96878 - PSCM | PSCM | 4 | 259498 | SCHD | SYS-ISOL | 2018-09-06 | 2019-10-28 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | MECHANICAL | 59
2019-03-31 | 96889 | Work Order Description - 96889 - CM | CM | 4 | 556287 | SCHD | TPS | 2019-03-15 | 2019-09-29 | 2019-07-13 | 2019-07-13 | 3 | INTEGRITY | INSPECTION | 40
2019-03-31 | 96897 | Work Order Description - 96897 - CM | CM | 3 | 313087 | SCHD | SYS-ISOL | 2018-09-06 | 2020-01-08 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 59
2019-03-31 | 96959 | Work Order Description - 96959 - CM | CM | 3 | 354680 | WSCHD | TPS | 2017-07-13 | 2019-09-09 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 13
2019-03-31 | 96967 | Work Order Description - 96967 - CM | CM | 3 | 578792 | SCHD | PACK-ISOL | 2018-09-06 | 2019-07-03 | 2019-06-01 | 2019-06-01 | 2 | WELLS | MECHANICAL | 22
2019-03-31 | 97077 | Work Order Description - 97077 - CM | CM | 4 | 316077 | SCHD | NORM-OPS | 2018-05-31 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 97274 | Work Order Description - 97274 - CM | CM | 4 | 463456 | SCHD | NORM-OPS | 2018-07-06 | 2019-05-17 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 73
2019-03-31 | 97275 | Work Order Description - 97275 - PSCM | PSCM | 4 | 477536 | SCHD | SYS-ISOL | 2018-09-06 | 2020-01-10 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | MECHANICAL | 65
2019-03-31 | 97276 | Work Order Description - 97276 - PSCM | PSCM | 3 | 492103 | SCHD | SYS-ISOL | 2018-09-06 | 2019-02-19 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | MECHANICAL | 59
2019-03-31 | 97278 | Work Order Description - 97278 - PSCM | PSCM | 1 | 33968 | WSCHD | TPS | 2018-06-16 | 2020-08-01 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | CONSTRUCTION | 28
2019-03-31 | 98599 | Work Order Description - 98599 - CM | CM | 3 | 310148 | SCHD | TPS | 2018-09-06 | 2019-07-05 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 98601 | Work Order Description - 98601 - PRJ | PRJ | 4 | 320026 | SCHD | NORM-OPS | 2018-09-06 | 2019-01-21 | 2019-06-15 | 2019-06-15 | 4 | DRILLING | DRILLING | 1
2019-03-31 | 98610 | Work Order Description - 98610 - CM | CM | 3 | 578828 | SCHD | PACK-ISOL | 2018-07-18 | 2019-01-31 | 2019-03-23 | 2019-03-23 | 2 | WELLS | INSTRUMENTS | 4
2019-03-31 | 98764 | Work Order Description - 98764 - CM | CM | 3 | 312827 | SCHD | SYS-ISOL | 2018-09-06 | 2019-02-17 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 98925 | Work Order Description - 98925 - CM | CM | 3 | 265732 | SCHD | NORM-OPS | 2018-07-06 | 2019-08-11 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 99397 | Work Order Description - 99397 - PM | PM | 4 | 487555 | SCHD | SUBSYS-ISOL | 2018-09-06 | 2019-08-21 | 2020-01-04 | 2020-01-04 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 99398 | Work Order Description - 99398 - PM | PM | 4 | 309984 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-15 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 99446 | Work Order Description - 99446 - PRJ | PRJ | 3 | 403528 | SCHD | TPS | 2018-06-13 | 2019-05-27 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 99504 | Work Order Description - 99504 - PRJ | PRJ | 3 | 403528 | SCHD | NORM-OPS | 2018-07-06 | 2019-04-14 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 99511 | Work Order Description - 99511 - PRJ | PRJ | 3 | 403528 | SCHD | NORM-OPS | 2018-07-06 | 2019-05-09 | 2019-03-30 | 2019-03-30 | 3 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 99517 | Work Order Description - 99517 - PRJ | PRJ | 3 | 403528 | SCHD | NORM-OPS | 2018-07-06 | 2019-02-08 | 2019-03-30 | 2019-03-30 | 3 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 99518 | Work Order Description - 99518 - PRJ | PRJ | 3 | 403528 | SCHD | NORM-OPS | 2018-07-06 | 2019-07-18 | 2019-03-30 | 2019-03-30 | 3 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 99519 | Work Order Description - 99519 - PRJ | PRJ | 3 | 403528 | SCHD | NORM-OPS | 2018-07-06 | 2019-09-29 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 99522 | Work Order Description - 99522 - PRJ | PRJ | 3 | 403528 | SCHD | NORM-OPS | 2018-07-06 | 2020-01-14 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 99527 | Work Order Description - 99527 - PRJ | PRJ | 3 | 403528 | SCHD | NORM-OPS | 2018-12-05 | 2018-12-24 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 99528 | Work Order Description - 99528 - PRJ | PRJ | 3 | 403528 | SCHD | NORM-OPS | 2018-07-06 | 2020-01-14 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | ELECTRICAL | 42
2019-03-31 | 99566 | Work Order Description - 99566 - CM | CM | 3 | 313584 | WSCHD | TPS | 2017-07-14 | 2019-07-12 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 99696 | Work Order Description - 99696 - CM | CM | 3 | 318305 | WSCHD | TPS | 2017-07-16 | 2019-07-12 | 2020-05-02 | 2020-05-06 | 4 | MAINTENANCE | MECHANICAL | 51
2019-03-31 | 99958 | Work Order Description - 99958 - CM | CM | 3 | 463251 | SCHD | NORM-OPS | 2018-07-18 | 2020-01-14 | 2019-08-03 | 2019-08-03 | 2 | MAINTENANCE | MECHANICAL | 65
2019-03-31 | 100057 | Work Order Description - 100057 - CM | CM | 4 | 305851 | SCHD | NORM-OPS | 2018-07-06 | 2019-05-14 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | ELECTRICAL | 38
2019-03-31 | 100077 | Work Order Description - 100077 - CM | CM | 2 | 499187 | WMATL | NORM-OPS | 2018-12-10 | 2019-11-24 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | MECHANICAL | 86
2019-03-31 | 100113 | Work Order Description - 100113 - CM | CM | 3 | 401353 | SCHD | NORM-OPS | 2018-07-18 | 2019-07-15 | 2019-05-18 | 2019-05-18 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 100137 | Work Order Description - 100137 - PSCM | PSCM | 1 | 554222 | WSCHD | NORM-OPS | 2017-07-26 | 2020-01-01 | 2019-05-25 | 2019-05-26 | 3 | MAINTENANCE | INSTRUMENTS | 9
2019-03-31 | 100139 | Work Order Description - 100139 - CM | CM | 4 | 259477 | SCHD | NORM-OPS | 2018-09-06 | 2019-07-15 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 100149 | Work Order Description - 100149 - BR | BR | 1 | 519828 | WSCHD | SUBSYS-ISOL | 2018-07-27 | 2020-08-01 | 2019-09-07 | 2019-09-08 | 3 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 100159 | Work Order Description - 100159 - CM | CM | 2 | 316077 | WSCHD | TPS | 2019-03-25 | 2020-07-30 | 2019-07-13 | 2019-07-13 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 100170 | Work Order Description - 100170 - CM | CM | 3 | 215925 | SCHD | NORM-OPS | 2018-06-21 | 2019-04-08 | 2019-07-06 | 2019-07-06 | 2 | INTEGRITY | SUBSEA | 36
2019-03-31 | 100171 | Work Order Description - 100171 - PRJ | PRJ | 3 | 215925 | SCHD | NORM-OPS | 2018-09-06 | 2019-07-12 | 2019-05-25 | 2019-05-25 | 2 | INTEGRITY | SUBSEA | 96
2019-03-31 | 100276 | Work Order Description - 100276 - CM | CM | 4 | 370293 | WSCHD | PACK-ISOL | 2017-07-19 | 2019-04-28 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 100404 | Work Order Description - 100404 - CM | CM | 2 | 502677 | SCHD | SYS-ISOL | 2018-09-06 | 2019-07-18 | 2019-06-08 | 2019-06-08 | 4 | MAINTENANCE | INSTRUMENTS | 39
2019-03-31 | 100450 | Work Order Description - 100450 - CM | CM | 4 | 361587 | SCHD | NORM-OPS | 2018-11-13 | 2019-07-03 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 100453 | Work Order Description - 100453 - CM | CM | 4 | 409892 | WSCHD | NORM-OPS | 2017-08-01 | 2019-09-26 | 2019-09-24 | 2019-09-25 | 3 | MAINTENANCE | INSTRUMENTS | 11
2019-03-31 | 100457 | Work Order Description - 100457 - CM | CM | 4 | 361459 | WSCHD | NORM-OPS | 2017-08-01 | 2019-10-08 | 2019-09-28 | 2019-09-29 | 3 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 100468 | Work Order Description - 100468 - CM | CM | 4 | 404905 | WSCHD | NORM-OPS | 2017-08-01 | 2019-07-18 | 2019-09-28 | 2019-09-29 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 100479 | Work Order Description - 100479 - CM | CM | 3 | 138442 | WSCHD | NORM-OPS | 2018-06-05 | 2019-05-27 | 2019-09-07 | 2019-09-08 | 3 | MAINTENANCE | INSTRUMENTS | 11
2019-03-31 | 100525 | Work Order Description - 100525 - CM | CM | 4 | 51659 | WSCHD | NORM-OPS | 2017-07-21 | 2019-12-18 | 2019-04-13 | 2019-04-16 | 2 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 100527 | Work Order Description - 100527 - CM | CM | 4 | 545222 | WSCHD | NORM-OPS | 2017-07-21 | 2019-06-26 | 2019-04-13 | 2019-04-16 | 2 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 100545 | Work Order Description - 100545 - CM | CM | 4 | 493015 | WPLAN | SYS-ISOL | 2017-07-23 | 2019-07-01 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 100621 | Work Order Description - 100621 - PSCM | PSCM | 1 | 323957 | SCHD | NORM-OPS | 2018-09-06 | 2019-07-20 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 44
2019-03-31 | 100665 | Work Order Description - 100665 - CM | CM | 3 | 29669 | SCHD | SYS-ISOL | 2018-09-06 | 2019-02-25 | 2019-07-20 | 2019-07-20 | 1 | MAINTENANCE | MECHANICAL | 82
2019-03-31 | 100695 | Work Order Description - 100695 - CM | CM | 3 | 262409 | SCHD | PACK-ISOL | 2018-07-06 | 2019-09-16 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 100713 | Work Order Description - 100713 - CM | CM | 3 | 293649 | WPLAN | TPS | 2017-08-01 | 2019-10-13 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 100714 | Work Order Description - 100714 - CM | CM | 3 | 247681 | WPLAN | TPS | 2017-08-01 | 2019-08-11 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 100716 | Work Order Description - 100716 - CM | CM | 3 | 499568 | WPLAN | TPS | 2017-08-01 | 2019-05-26 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 100718 | Work Order Description - 100718 - CM | CM | 4 | 491627 | WPLAN | TPS | 2017-08-01 | 2019-07-10 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 100720 | Work Order Description - 100720 - PRJ | PRJ | 4 | 481606 | SCHD | NORM-OPS | 2018-09-06 | 2019-07-23 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | ELECTRICAL | 28
2019-03-31 | 100742 | Work Order Description - 100742 - CM | CM | 2 | 411109 | WPLAN | TPS | 2017-08-01 | 2019-07-02 | 2020-05-03 | 2020-05-05 | 2 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 100801 | Work Order Description - 100801 - CM | CM | 3 | 361952 | WSCHD | NORM-OPS | 2018-09-21 | 2019-07-24 | 2019-08-03 | 2019-08-05 | 3 | MAINTENANCE | INSTRUMENTS | 25
2019-03-31 | 100863 | Work Order Description - 100863 - CM | CM | 3 | 409745 | WSCHD | TPS | 2017-08-01 | 2019-07-25 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 100864 | Work Order Description - 100864 - CM | CM | 3 | 137414 | WSCHD | TPS | 2017-08-01 | 2019-07-25 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 100907 | Work Order Description - 100907 - CM | CM | 4 | 327995 | WPLAN | TPS | 2017-07-28 | 2019-11-08 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | CONSTRUCTION | 0
2019-03-31 | 100959 | Work Order Description - 100959 - CM | CM | 1 | 403817 | SCHD | NORM-OPS | 2019-01-25 | 2019-07-01 | 2019-06-08 | 2019-06-08 | 3 | INTEGRITY | FABRIC | 690
2019-03-31 | 101027 | Work Order Description - 101027 - PSCM | PSCM | 3 | 320317 | WPLAN | TPS | 2019-01-24 | 2019-04-19 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 105
2019-03-31 | 101317 | Work Order Description - 101317 - PRJ | PRJ | 4 | 320026 | SCHD | SYS-ISOL | 2018-03-09 | 2019-07-31 | 2019-05-25 | 2019-05-25 | 4 | DRILLING | DRILLING | 1
2019-03-31 | 101359 | Work Order Description - 101359 - CM | CM | 4 | 215920 | SCHD | SYS-ISOL | 2018-06-21 | 2019-01-25 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSTRUMENTS | 11
2019-03-31 | 101361 | Work Order Description - 101361 - CM | CM | 4 | 556052 | SCHD | SYS-ISOL | 2018-06-21 | 2018-12-16 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 35
2019-03-31 | 101363 | Work Order Description - 101363 - CM | CM | 4 | 215919 | SCHD | SYS-ISOL | 2018-10-10 | 2019-09-16 | 2019-08-03 | 2019-08-03 | 3 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 101364 | Work Order Description - 101364 - CM | CM | 4 | 499057 | SCHD | NORM-OPS | 2018-07-06 | 2019-01-26 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 101365 | Work Order Description - 101365 - CM | CM | 4 | 310193 | SCHD | NORM-OPS | 2018-07-06 | 2019-11-24 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 101368 | Work Order Description - 101368 - CM | CM | 4 | 325359 | SCHD | NORM-OPS | 2018-07-06 | 2018-12-18 | 2019-08-03 | 2019-08-03 | 3 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 101419 | Work Order Description - 101419 - CM | CM | 4 | 479226 | SCHD | NORM-OPS | 2018-07-06 | 2019-04-09 | 2020-01-04 | 2020-01-04 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 101477 | Work Order Description - 101477 - CM | CM | 1 | 481714 | SCHD | NORM-OPS | 2018-09-10 | 2020-01-01 | 2019-04-13 | 2019-04-13 | 3 | INTEGRITY | FABRIC | 120
2019-03-31 | 102372 | Work Order Description - 102372 - PM | PM | 2 | 188988 | SCHD | SYS-ISOL | 2019-03-19 | 2019-06-05 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 64
2019-03-31 | 102410 | Work Order Description - 102410 - PM | PM | 3 | 555321 | SCHD | EQUIP-ISOL | 2018-07-06 | 2019-09-21 | 2019-08-10 | 2019-08-10 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 102698 | Work Order Description - 102698 - CM | CM | 3 | 259471 | SCHD | TPS | 2018-09-06 | 2019-06-16 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 102699 | Work Order Description - 102699 - CM | CM | 3 | 312683 | SCHD | NORM-OPS | 2018-07-18 | 2019-04-18 | 2019-10-12 | 2019-10-12 | 3 | MAINTENANCE | MECHANICAL | 140
2019-03-31 | 102858 | Work Order Description - 102858 - CM | CM | 4 | 312683 | SCHD | NORM-OPS | 2018-06-21 | 2019-12-14 | 2020-01-04 | 2020-01-04 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 102882 | Work Order Description - 102882 - CM | CM | 3 | 309124 | SCHD | TPS | 2018-05-30 | 2019-11-23 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 102883 | Work Order Description - 102883 - CM | CM | 4 | 216915 | SCHD | TPS | 2018-09-24 | 2019-08-17 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 39
2019-03-31 | 102916 | Work Order Description - 102916 - PSCM | PSCM | 1 | 502675 | SCHD | TPS | 2018-09-06 | 2019-09-10 | 2019-07-13 | 2019-07-13 | 3 | INTEGRITY | MECHANICAL | 19
2019-03-31 | 102925 | Work Order Description - 102925 - CM | CM | 4 | 216916 | SCHD | NORM-OPS | 2018-06-21 | 2019-08-31 | 2019-05-25 | 2019-05-25 | 3 | INTEGRITY | MECHANICAL | 8
2019-03-31 | 102941 | Work Order Description - 102941 - CM | CM | 3 | 29082 | SCHD | NORM-OPS | 2018-08-25 | 2019-08-27 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | INSTRUMENTS | 60
2019-03-31 | 102992 | Work Order Description - 102992 - CM | CM | 3 | 312683 | SCHD | NORM-OPS | 2018-07-06 | 2019-11-19 | 2019-08-24 | 2019-08-24 | 2 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 103007 | Work Order Description - 103007 - CM | CM | 4 | 325633 | SCHD | NORM-OPS | 2018-07-18 | 2018-12-22 | 2019-12-07 | 2019-12-07 | 2 | MAINTENANCE | ELECTRICAL | 11
2019-03-31 | 103168 | Work Order Description - 103168 - PM | PM | 2 | 312683 | SCHD | PACK-ISOL | 2018-07-06 | 2019-12-12 | 2019-08-24 | 2019-08-24 | 2 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 103258 | Work Order Description - 103258 - CM | CM | 4 | 216030 | SCHD | NORM-OPS | 2019-02-13 | 2021-02-06 | 2019-07-06 | 2019-07-06 | 4 | INTEGRITY | FABRIC | 20
2019-03-31 | 103373 | Work Order Description - 103373 - CM | CM | 4 | 29673 | SCHD | TPS | 2018-09-06 | 2019-06-07 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 60
2019-03-31 | 103535 | Work Order Description - 103535 - CM | CM | 4 | 28343 | SCHD | NORM-OPS | 2018-07-18 | 2019-07-11 | 2019-06-29 | 2019-06-29 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 103724 | Work Order Description - 103724 - CM | CM | 3 | 555793 | SCHD | TPS | 2018-05-18 | 2019-11-25 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 15
2019-03-31 | 103725 | Work Order Description - 103725 - CM | CM | 4 | 555793 | SCHD | NORM-OPS | 2018-09-06 | 2019-08-24 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 103781 | Work Order Description - 103781 - CM | CM | 4 | 555933 | SCHD | SYS-ISOL | 2018-06-19 | 2019-08-24 | 2019-08-03 | 2019-08-03 | 4 | DRILLING | DRILLING | 1
2019-03-31 | 103831 | Work Order Description - 103831 - CM | CM | 3 | 479683 | SCHD | NORM-OPS | 2018-06-21 | 2019-01-14 | 2019-05-04 | 2019-05-04 | 3 | INTEGRITY | SUBSEA | 18
2019-03-31 | 103832 | Work Order Description - 103832 - CM | CM | 3 | 215925 | SCHD | NORM-OPS | 2018-07-18 | 2019-12-31 | 2019-06-01 | 2019-06-01 | 2 | INTEGRITY | SUBSEA | 18
2019-03-31 | 103909 | Work Order Description - 103909 - CM | CM | 3 | 262750 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-28 | 2019-08-03 | 2019-08-03 | 3 | INTEGRITY | FABRIC | 44
2019-03-31 | 104086 | Work Order Description - 104086 - CM | CM | 3 | 555284 | SCHD | SYS-ISOL | 2018-09-06 | 2019-08-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 104105 | Work Order Description - 104105 - CM | CM | 2 | 552011 | WPLAN | NORM-OPS | 2017-08-31 | 2018-12-23 | 2020-03-07 | 2020-03-07 | 3 | MAINTENANCE | CONSTRUCTION | 0
2019-03-31 | 104157 | Work Order Description - 104157 - CM | CM | 3 | 490562 | SCHD | SYS-ISOL | 2018-09-06 | 2018-12-09 | 2019-05-04 | 2019-05-04 | 2 | INTEGRITY | MECHANICAL | 47
2019-03-31 | 104192 | Work Order Description - 104192 - CM | CM | 4 | 258535 | SCHD | NORM-OPS | 2018-05-24 | 2019-07-08 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 59
2019-03-31 | 104196 | Work Order Description - 104196 - CM | CM | 3 | 262409 | SCHD | NORM-OPS | 2018-07-06 | 2019-04-21 | 2019-05-18 | 2019-05-18 | 3 | MAINTENANCE | CONSTRUCTION | 8
2019-03-31 | 104220 | Work Order Description - 104220 - CM | CM | 3 | 555973 | SCHD | NORM-OPS | 2018-07-18 | 2019-08-27 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 104249 | Work Order Description - 104249 - CM | CM | 4 | 481599 | SCHD | NORM-OPS | 2018-09-06 | 2019-09-05 | 2019-08-10 | 2019-08-10 | 4 | OPERATIONS | MECHANICAL | 21
2019-03-31 | 104279 | Work Order Description - 104279 - CM | CM | 4 | 21232 | SCHD | SYS-ISOL | 2018-09-06 | 2019-03-14 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 104282 | Work Order Description - 104282 - CM | CM | 4 | 462436 | SCHD | NORM-OPS | 2018-09-06 | 2019-09-06 | 2019-08-31 | 2019-08-31 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 104951 | Work Order Description - 104951 - CM | CM | 4 | 481746 | SCHD | NORM-OPS | 2019-01-25 | 2019-12-18 | 2020-02-29 | 2020-02-29 | 3 | INTEGRITY | FABRIC | 32
2019-03-31 | 105066 | Work Order Description - 105066 - CM | CM | 4 | 481808 | WSCHD | NORM-OPS | 2019-03-25 | 2019-02-27 | 2020-04-11 | 2020-04-11 | 3 | MAINTENANCE | MECHANICAL | 54
2019-03-31 | 105140 | Work Order Description - 105140 - CM | CM | 4 | 216927 | SCHD | NORM-OPS | 2018-06-21 | 2018-12-24 | 2019-08-03 | 2019-08-03 | 4 | OPERATIONS | SAFETY | 10
2019-03-31 | 105155 | Work Order Description - 105155 - CM | CM | 3 | 262750 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-19 | 2019-05-18 | 2019-05-18 | 3 | INTEGRITY | FABRIC | 21
2019-03-31 | 105577 | Work Order Description - 105577 - CM | CM | 3 | 495033 | SCHD | SYS-ISOL | 2018-07-06 | 2019-09-20 | 2019-06-15 | 2019-06-15 | 4 | INTEGRITY | INSTRUMENTS | 1
2019-03-31 | 105746 | Work Order Description - 105746 - CM | CM | 4 | 556288 | WPLAN | NORM-OPS | 2017-10-03 | 2019-10-01 | 2019-08-03 | 2019-08-03 | 3 | INTEGRITY | FABRIC | 95
2019-03-31 | 105755 | Work Order Description - 105755 - CM | CM | 3 | 309428 | WPLAN | NORM-OPS | 2018-11-22 | 2020-01-01 | 2019-08-10 | 2019-08-10 | 3 | INTEGRITY | FABRIC | 52
2019-03-31 | 105759 | Work Order Description - 105759 - CM | CM | 4 | 556288 | SCHD | NORM-OPS | 2019-03-15 | 2020-01-01 | 2019-12-21 | 2019-12-21 | 3 | INTEGRITY | FABRIC | 480
2019-03-31 | 105825 | Work Order Description - 105825 - CM | CM | 4 | 501448 | WPLAN | NORM-OPS | 2018-12-24 | 2020-12-16 | 2020-02-22 | 2020-02-22 | 4 | INTEGRITY | FABRIC | 1
2019-03-31 | 105850 | Work Order Description - 105850 - CM | CM | 4 | 479514 | SCHD | NORM-OPS | 2019-02-13 | 2020-02-12 | 2019-08-13 | 2019-08-13 | 3 | MAINTENANCE | FABRIC | 90
2019-03-31 | 105863 | Work Order Description - 105863 - PSCM | PSCM | 1 | 396058 | SCHD | NORM-OPS | 2018-06-21 | 2019-09-27 | 2019-07-13 | 2019-07-13 | 4 | INTEGRITY | WELLS | 201
2019-03-31 | 105872 | Work Order Description - 105872 - PSCM | PSCM | 1 | 665693 | SCHD | NORM-OPS | 2018-06-21 | 2019-09-27 | 2019-07-13 | 2019-07-13 | 4 | INTEGRITY | WELLS | 201
2019-03-31 | 105942 | Work Order Description - 105942 - CM | CM | 1 | 472798 | WPLAN | NORM-OPS | 2018-05-01 | 2019-07-01 | 2019-05-18 | 2019-05-18 | 3 | INTEGRITY | FABRIC | 272
2019-03-31 | 105972 | Work Order Description - 105972 - CM | CM | 3 | 402290 | SCHD | NORM-OPS | 2018-12-20 | 2019-12-18 | 2019-06-18 | 2019-06-18 | 3 | INTEGRITY | FABRIC | 18
2019-03-31 | 105986 | Work Order Description - 105986 - CM | CM | 2 | 20514 | SCHD | TPS | 2018-09-06 | 2020-02-15 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | SERVICES | 700
2019-03-31 | 105988 | Work Order Description - 105988 - CM | CM | 2 | 183629 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-10 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 105995 | Work Order Description - 105995 - CM | CM | 4 | 470454 | SCHD | NORM-OPS | 2018-09-06 | 2019-10-01 | 2019-06-15 | 2019-06-15 | 4 | MAINTENANCE | MECHANICAL | 17
2019-03-31 | 106052 | Work Order Description - 106052 - CM | CM | 4 | 477468 | SCHD | NORM-OPS | 2018-09-06 | 2019-07-01 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 106063 | Work Order Description - 106063 - CM | CM | 3 | 464183 | SCHD | SYS-ISOL | 2018-01-12 | 2019-03-17 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 106065 | Work Order Description - 106065 - CM | CM | 4 | 320718 | SCHD | SYS-ISOL | 2018-06-21 | 2019-10-04 | 2019-04-27 | 2019-04-27 | 4 | DRILLING | DRILLING | 5
2019-03-31 | 106073 | Work Order Description - 106073 - CM | CM | 4 | 479219 | WSCHD | NORM-OPS | 2019-03-25 | 2019-01-29 | 2020-05-11 | 2020-05-11 | 2 | MAINTENANCE | DRILLING | 14
2019-03-31 | 106081 | Work Order Description - 106081 - CM | CM | 4 | 320718 | SCHD | SYS-ISOL | 2018-07-18 | 2019-10-04 | 2019-03-23 | 2019-03-23 | 4 | DRILLING | DRILLING | 1
2019-03-31 | 106099 | Work Order Description - 106099 - CM | CM | 4 | 35377 | SCHD | TPS | 2018-09-06 | 2019-10-04 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 106139 | Work Order Description - 106139 - CM | CM | 1 | 472493 | WPLAN | NORM-OPS | 2018-04-27 | 2020-01-01 | 2019-06-01 | 2019-06-01 | 3 | INTEGRITY | CONSTRUCTION | 224
2019-03-31 | 106176 | Work Order Description - 106176 - PSCM | PSCM | 1 | 29686 | SCHD | PACK-ISOL | 2018-07-06 | 2019-09-11 | 2019-08-31 | 2019-08-31 | 4 | MAINTENANCE | WELLS | 104
2019-03-31 | 106193 | Work Order Description - 106193 - PSCM | PSCM | 1 | 402153 | SCHD | NORM-OPS | 2018-09-06 | 2019-10-08 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | SAFETY | 6
2019-03-31 | 106207 | Work Order Description - 106207 - PRJ | PRJ | 4 | 476345 | SCHD | TPS | 2018-09-06 | 2019-05-23 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | ELECTRICAL | 16
2019-03-31 | 106903 | Work Order Description - 106903 - PRJ | PRJ | 4 | 490534 | SCHD | SYS-ISOL | 2018-09-06 | 2019-10-11 | 2019-05-04 | 2019-05-04 | 4 | INTEGRITY | MECHANICAL | 11
2019-03-31 | 106932 | Work Order Description - 106932 - CM | CM | 3 | 499108 | SCHD | PACK-ISOL | 2018-09-06 | 2019-09-14 | 2019-08-03 | 2019-08-03 | 4 | MAINTENANCE | WELLS | 114
2019-03-31 | 106933 | Work Order Description - 106933 - PSCM | PSCM | 1 | 464998 | SCHD | PACK-ISOL | 2018-10-09 | 2019-06-15 | 2019-05-11 | 2019-05-11 | 3 | WELLS | WELLS | 18
2019-03-31 | 106957 | Work Order Description - 106957 - CM | CM | 4 | 402153 | SCHD | NORM-OPS | 2018-09-06 | 2019-10-12 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | SAFETY | 4
2019-03-31 | 106969 | Work Order Description - 106969 - CM | CM | 1 | 403825 | SCHD | NORM-OPS | 2018-09-06 | 2019-10-13 | 2020-02-29 | 2020-02-29 | 4 | INTEGRITY | FABRIC | 40
2019-03-31 | 106975 | Work Order Description - 106975 - PSCM | PSCM | 1 | 490491 | SCHD | NORM-OPS | 2018-05-24 | 2019-10-13 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | MECHANICAL | 23
2019-03-31 | 107139 | Work Order Description - 107139 - PSCM | PSCM | 1 | 500827 | SCHD | TPS | 2019-01-25 | 2019-05-01 | 2019-04-20 | 2019-04-20 | 4 | OPERATIONS | MECHANICAL | 1
2019-03-31 | 107143 | Work Order Description - 107143 - PSCM | PSCM | 1 | 479070 | WMATL | TPS | 2017-12-18 | 2019-05-01 | 2019-04-20 | 2019-04-20 | 4 | OPERATIONS | MECHANICAL | 12
2019-03-31 | 107144 | Work Order Description - 107144 - PSCM | PSCM | 1 | 481542 | WMATL | TPS | 2017-12-22 | 2019-05-01 | 2019-04-20 | 2019-04-20 | 4 | OPERATIONS | MECHANICAL | 25
2019-03-31 | 107147 | Work Order Description - 107147 - PSCM | PSCM | 1 | 479046 | WMATL | TPS | 2017-12-22 | 2019-05-01 | 2019-04-20 | 2019-04-20 | 4 | OPERATIONS | MECHANICAL | 25
2019-03-31 | 107148 | Work Order Description - 107148 - PSCM | PSCM | 1 | 403251 | WMATL | TPS | 2017-12-22 | 2019-05-01 | 2019-04-20 | 2019-04-20 | 4 | OPERATIONS | MECHANICAL | 25
2019-03-31 | 107150 | Work Order Description - 107150 - PSCM | PSCM | 1 | 481543 | WMATL | TPS | 2019-01-25 | 2019-05-01 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | MECHANICAL | 27
2019-03-31 | 107151 | Work Order Description - 107151 - PSCM | PSCM | 1 | 403252 | SCHD | TPS | 2019-01-25 | 2019-05-01 | 2019-04-20 | 2019-04-20 | 4 | OPERATIONS | MECHANICAL | 48
2019-03-31 | 107152 | Work Order Description - 107152 - PSCM | PSCM | 1 | 403253 | WMATL | TPS | 2017-12-27 | 2019-05-01 | 2019-07-13 | 2019-07-13 | 4 | OPERATIONS | MECHANICAL | 24
2019-03-31 | 107153 | Work Order Description - 107153 - CM | CM | 4 | 32589 | SCHD | SYS-ISOL | 2018-06-21 | 2019-12-09 | 2019-05-04 | 2019-05-04 | 3 | DRILLING | DRILLING | 1
2019-03-31 | 107154 | Work Order Description - 107154 - CM | CM | 4 | 32589 | SCHD | SYS-ISOL | 2018-09-06 | 2019-03-11 | 2019-06-22 | 2019-06-22 | 3 | DRILLING | DRILLING | 2
2019-03-31 | 107155 | Work Order Description - 107155 - CM | CM | 4 | 32589 | SCHD | SYS-ISOL | 2018-09-06 | 2019-09-14 | 2019-05-18 | 2019-05-18 | 3 | DRILLING | DRILLING | 1
2019-03-31 | 107156 | Work Order Description - 107156 - CM | CM | 4 | 32589 | SCHD | SYS-ISOL | 2018-09-06 | 2019-12-24 | 2019-05-04 | 2019-05-04 | 3 | DRILLING | DRILLING | 1
2019-03-31 | 107191 | Work Order Description - 107191 - CM | CM | 4 | 243379 | SCHD | NORM-OPS | 2018-08-10 | 2019-10-18 | 2019-03-23 | 2019-03-23 | 4 | MAINTENANCE | DRILLING | 1
2019-03-31 | 107342 | Work Order Description - 107342 - CM | CM | 3 | 262863 | SCHD | NORM-OPS | 2019-03-13 | 2019-12-18 | 2019-08-03 | 2019-08-03 | 3 | INTEGRITY | FABRIC | 135
2019-03-31 | 110857 | Work Order Description - 110857 - PM | PM | 4 | 677488 | WSCHD | EQUIP-ISOL | 2017-08-10 | 2019-01-13 | 2019-05-04 | 2019-05-10 | 2 | INTEGRITY | MECHANICAL | 20
2019-03-31 | 110862 | Work Order Description - 110862 - CM | CM | 4 | 321696 | WSCHD | TPS | 2011-07-12 | 2019-10-05 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 110864 | Work Order Description - 110864 - CM | CM | 4 | 215340 | WPLAN | TPS | 2017-07-26 | 2019-11-04 | 2020-05-02 | 2020-05-02 | 2 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 110865 | Work Order Description - 110865 - CM | CM | 4 | 226617 | WSCHD | TPS | 2018-06-15 | 2019-05-10 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 110871 | Work Order Description - 110871 - CM | CM | 4 | 653275 | WSCHD | NORM-OPS | 2017-07-11 | 2019-03-08 | 2019-08-31 | 2019-09-01 | 2 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 110901 | Work Order Description - 110901 - CM | CM | 4 | 33744 | WSCHD | TPS | 2018-06-08 | 2018-12-14 | 2020-05-03 | 2020-05-04 | 3 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 110902 | Work Order Description - 110902 - CM | CM | 4 | 308922 | WSCHD | NORM-OPS | 2011-11-28 | 2019-07-20 | 2020-01-04 | 2020-01-04 | 2 | MAINTENANCE | MECHANICAL | 4.7
2019-03-31 | 110914 | Work Order Description - 110914 - CM | CM | 4 | 501564 | WSCHD | TPS | 2015-08-28 | 2019-02-09 | 2020-05-02 | 2020-05-03 | 2 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 110924 | Work Order Description - 110924 - CM | CM | 4 | 261281 | WSCHD | TPS | 2017-07-07 | 2020-01-01 | 2020-05-02 | 2020-05-06 | 2 | MAINTENANCE | MECHANICAL | 70
2019-03-31 | 110934 | Work Order Description - 110934 - CM | CM | 4 | 676357 | WPLAN | NORM-OPS | 2018-02-14 | 2019-07-01 | 2019-06-29 | 2019-07-01 | 3 | INTEGRITY | DRILLING | 42
2019-03-31 | 110944 | Work Order Description - 110944 - CM | CM | 4 | 501328 | WSCHD | TPS | 2015-06-10 | 2019-07-30 | 2020-05-02 | 2020-05-06 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 110946 | Work Order Description - 110946 - CM | CM | 3 | 547761 | WSCHD | TPS | 2011-11-28 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 2 | MAINTENANCE | CONSTRUCTION | 29
2019-03-31 | 122273 | Work Order Description - 122273 - BR | BR | 4 | 527984 | SCHD | NORM-OPS | 2019-03-22 | 2019-05-08 | 2019-03-23 | 2019-03-24 | 4 | INTEGRITY | FABRIC | 8
2019-03-31 | 122288 | Work Order Description - 122288 - PSCM | PSCM | 2 | 266820 | WMATL | TPS | 2019-03-06 | 2019-05-11 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 122295 | Work Order Description - 122295 - CM | CM | 2 | 453360 | WPLAN | TPS | 2018-12-17 | 2019-05-12 | 2019-07-13 | 2019-07-20 | 4 | MAINTENANCE | MECHANICAL | 111
2019-03-31 | 122319 | Work Order Description - 122319 - BR | BR | 3 | 128075 | WPLAN | TPS | 2017-06-21 | 2019-06-01 | 2019-07-13 | 2019-07-15 | 4 | INTEGRITY | CONSTRUCTION | 119
2019-03-31 | 122344 | Work Order Description - 122344 - PM | PM | 4 | 396364 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-11-26 | 2019-04-30 | 2019-04-30 | 1 | INTEGRITY | MECHANICAL | 0
2019-03-31 | 122767 | Work Order Description - 122767 - PM | PM | 3 | 453770 | SCHD | EQUIP-ISOL | 2018-06-01 | 2018-12-04 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 123271 | Work Order Description - 123271 - BR | BR | 3 | 668557 | SCHD | SYS-ISOL | 2018-06-21 | 2020-01-05 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 123272 | Work Order Description - 123272 - BR | BR | 2 | 450556 | WPLAN | TPS | 2018-12-17 | 2019-05-22 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 123292 | Work Order Description - 123292 - CM | CM | 4 | 453381 | WPLAN | SUBSYS-ISOL | 2017-06-02 | 2019-05-23 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 123311 | Work Order Description - 123311 - CM | CM | 4 | 450961 | WPLAN | TPS | 2018-12-17 | 2019-05-24 | 2019-07-13 | 2019-07-18 | 4 | MAINTENANCE | MECHANICAL | 84
2019-03-31 | 123323 | Work Order Description - 123323 - BR | BR | 3 | 124363 | WPLAN | NORM-OPS | 2017-08-15 | 2019-06-26 | 2019-05-03 | 2019-05-11 | 4 | MAINTENANCE | CONSTRUCTION | 200
2019-03-31 | 123598 | Work Order Description - 123598 - PM | PM | 4 | 665730 | SCHD | NORM-OPS | 2018-12-17 | 2019-10-11 | 2019-08-03 | 2019-08-03 | 1 | INTEGRITY | SUBSEA | 1
2019-03-31 | 123603 | Work Order Description - 123603 - CM | CM | 4 | 228280 | SCHD | NORM-OPS | 2018-06-21 | 2019-06-30 | 2020-02-01 | 2020-02-01 | 3 | INTEGRITY | MECHANICAL | 6
2019-03-31 | 123663 | Work Order Description - 123663 - BR | BR | 3 | 110705 | SCHD | NORM-OPS | 2018-06-21 | 2019-06-09 | 2019-04-20 | 2019-04-22 | 4 | MAINTENANCE | MECHANICAL | 34
2019-03-31 | 123664 | Work Order Description - 123664 - BR | BR | 3 | 383738 | SCHD | NORM-OPS | 2018-06-21 | 2019-07-10 | 2019-07-14 | 2019-07-16 | 4 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 123673 | Work Order Description - 123673 - CM | CM | 4 | 669486 | WPLAN | NORM-OPS | 2019-03-16 | 2019-11-01 | 2019-04-30 | 2019-05-11 | 3 | INTEGRITY | FABRIC | 240
2019-03-31 | 123680 | Work Order Description - 123680 - CM | CM | 4 | 127459 | SCHD | NORM-OPS | 2018-06-21 | 2019-06-11 | 2019-05-26 | 2019-05-27 | 4 | INTEGRITY | FABRIC | 14
2019-03-31 | 123955 | Work Order Description - 123955 - BR | BR | 2 | 127817 | WPLAN | NORM-OPS | 2018-10-08 | 2019-06-24 | 2019-05-12 | 2019-05-13 | 4 | INTEGRITY | MECHANICAL | 24
2019-03-31 | 123958 | Work Order Description - 123958 - CM | CM | 4 | 376217 | SCHD | NORM-OPS | 2018-09-12 | 2019-04-01 | 2019-09-01 | 2019-09-05 | 4 | INTEGRITY | CONSTRUCTION | 70
2019-03-31 | 123959 | Work Order Description - 123959 - CM | CM | 4 | 74958 | WPLAN | NORM-OPS | 2017-07-07 | 2019-05-04 | 2019-03-23 | 2019-03-25 | 4 | INTEGRITY | CONSTRUCTION | 70
2019-03-31 | 123961 | Work Order Description - 123961 - CM | CM | 4 | 75039 | WPLAN | NORM-OPS | 2017-07-07 | 2019-05-02 | 2019-03-23 | 2019-03-27 | 4 | INTEGRITY | CONSTRUCTION | 84
2019-03-31 | 124074 | Work Order Description - 124074 - CM | CM | 3 | 128731 | WMATL | SYS-ISOL | 2017-11-13 | 2020-01-25 | 2019-07-13 | 2019-07-15 | 3 | MAINTENANCE | MECHANICAL | 31
2019-03-31 | 124077 | Work Order Description - 124077 - CM | CM | 1 | 127594 | WPLAN | NORM-OPS | 2017-07-07 | 2019-07-02 | 2019-05-17 | 2019-05-17 | 4 | INTEGRITY | CONSTRUCTION | 537
2019-03-31 | 124090 | Work Order Description - 124090 - CM | CM | 4 | 78797 | WPLAN | TPS | 2017-08-12 | 2019-07-05 | 2019-07-13 | 2019-07-15 | 4 | MAINTENANCE | MECHANICAL | 80
2019-03-31 | 124097 | Work Order Description - 124097 - CM | CM | 4 | 228839 | SCHD | NORM-OPS | 2019-03-12 | 2019-09-10 | 2019-04-13 | 2019-06-28 | 3 | INTEGRITY | FABRIC | 1617
2019-03-31 | 124098 | Work Order Description - 124098 - CM | CM | 4 | 378845 | SCHD | NORM-OPS | 2019-03-29 | 2019-02-01 | 2019-07-13 | 2019-07-13 | 3 | INTEGRITY | CONSTRUCTION | 45
2019-03-31 | 124114 | Work Order Description - 124114 - CM | CM | 3 | 266093 | WPLAN | PACK-ISOL | 2017-08-15 | 2019-07-14 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 124191 | Work Order Description - 124191 - PM | PM | 4 | 249644 | WSCHD | EQUIP-ISOL | 2017-07-29 | 2019-11-04 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 124192 | Work Order Description - 124192 - PM | PM | 4 | 249668 | WSCHD | EQUIP-ISOL | 2017-07-29 | 2018-12-28 | 2019-06-22 | 2019-06-22 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 124205 | Work Order Description - 124205 - PM | PM | 4 | 480136 | SCHD | PACK-ISOL | 2018-11-27 | 2019-08-14 | 2019-04-13 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 124207 | Work Order Description - 124207 - PM | PM | 4 | 408345 | SCHD | PACK-ISOL | 2018-11-27 | 2019-05-03 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 124256 | Work Order Description - 124256 - PM | PM | 4 | 261341 | WSCHD | EQUIP-ISOL | 2017-07-29 | 2019-04-14 | 2019-06-29 | 2019-06-29 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 124257 | Work Order Description - 124257 - PM | PM | 4 | 361235 | WSCHD | EQUIP-ISOL | 2017-07-29 | 2019-08-05 | 2019-06-29 | 2019-06-29 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 124272 | Work Order Description - 124272 - PM | PM | 3 | 54418 | WSCHD | EQUIP-ISOL | 2017-07-29 | 2019-12-16 | 2020-03-07 | 2020-03-07 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 124274 | Work Order Description - 124274 - PM | PM | 4 | 54309 | SCHD | PACK-ISOL | 2018-09-03 | 2019-12-01 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 124283 | Work Order Description - 124283 - PM | PM | 3 | 53296 | WSCHD | PACK-ISOL | 2017-07-29 | 2019-04-13 | 2019-09-28 | 2019-09-28 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 124287 | Work Order Description - 124287 - PM | PM | 4 | 54311 | SCHD | PACK-ISOL | 2018-09-17 | 2019-12-12 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 124323 | Work Order Description - 124323 - PM | PM | 3 | 54522 | WSCHD | EQUIP-ISOL | 2017-07-29 | 2019-11-03 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 124324 | Work Order Description - 124324 - PM | PM | 3 | 53333 | WSCHD | EQUIP-ISOL | 2017-07-29 | 2019-08-17 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 124325 | Work Order Description - 124325 - PM | PM | 3 | 409718 | WSCHD | EQUIP-ISOL | 2017-07-29 | 2019-04-21 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 124341 | Work Order Description - 124341 - PM | PM | 4 | 410187 | WSCHD | EQUIP-ISOL | 2017-07-29 | 2019-05-24 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 124348 | Work Order Description - 124348 - PM | PM | 3 | 53663 | WSCHD | EQUIP-ISOL | 2017-07-29 | 2018-12-08 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 124382 | Work Order Description - 124382 - PM | PM | 4 | 547429 | WSCHD | NORM-OPS | 2017-07-29 | 2020-01-09 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | SERVICES | 7
2019-03-31 | 124390 | Work Order Description - 124390 - PM | PM | 4 | 652482 | WSCHD | NORM-OPS | 2017-07-29 | 2019-03-15 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | SERVICES | 7
2019-03-31 | 124402 | Work Order Description - 124402 - PM | PM | 4 | 246173 | WSCHD | NORM-OPS | 2017-07-29 | 2019-03-02 | 2019-05-04 | 2019-05-05 | 1 | MAINTENANCE | SERVICES | 10
2019-03-31 | 124403 | Work Order Description - 124403 - PM | PM | 4 | 546030 | WSCHD | NORM-OPS | 2017-07-29 | 2019-03-28 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | SERVICES | 7
2019-03-31 | 124404 | Work Order Description - 124404 - PM | PM | 4 | 652482 | WSCHD | NORM-OPS | 2017-07-29 | 2019-03-03 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | SERVICES | 7
2019-03-31 | 124405 | Work Order Description - 124405 - PM | PM | 4 | 652482 | WSCHD | NORM-OPS | 2017-07-29 | 2019-08-08 | 2019-05-04 | 2019-05-05 | 1 | MAINTENANCE | SERVICES | 14
2019-03-31 | 124555 | Work Order Description - 124555 - PSPM | PSPM | 1 | 656069 | WSCHD | PACK-ISOL | 2017-07-29 | 2020-01-01 | 2019-10-05 | 2019-10-05 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 124639 | Work Order Description - 124639 - PM | PM | 4 | 656065 | WSCHD | PACK-ISOL | 2018-03-30 | 2019-04-19 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 124646 | Work Order Description - 124646 - PSPM | PSPM | 1 | 361921 | WSCHD | SUBSYS-ISOL | 2017-07-29 | 2022-01-01 | 2019-12-31 | 2020-01-01 | 1 | MAINTENANCE | OPERATIONS | 11
2019-03-31 | 124648 | Work Order Description - 124648 - PSPM | PSPM | 1 | 248307 | WSCHD | EQUIP-ISOL | 2017-12-22 | 2020-06-01 | 2019-12-28 | 2019-12-28 | 1 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 124663 | Work Order Description - 124663 - PSPM | PSPM | 1 | 399590 | WSCHD | PACK-ISOL | 2017-07-29 | 2020-01-01 | 2019-10-05 | 2019-10-05 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 124685 | Work Order Description - 124685 - PM | PM | 3 | 261986 | WSCHD | PACK-ISOL | 2017-07-29 | 2019-10-13 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 124696 | Work Order Description - 124696 - PM | PM | 4 | 656167 | WSCHD | SYS-ISOL | 2017-07-29 | 2020-01-10 | 2020-05-10 | 2020-05-10 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 124718 | Work Order Description - 124718 - PM | PM | 3 | 496741 | WSCHD | SUBSYS-ISOL | 2017-07-29 | 2018-12-20 | 2019-10-26 | 2019-10-26 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 125339 | Work Order Description - 125339 - PM | PM | 4 | 74947 | SCHD | EQUIP-ISOL | 2018-05-25 | 2019-04-04 | 2019-05-25 | 2019-05-26 | 1 | WELLS | INSTRUMENTS | 8
2019-03-31 | 125587 | Work Order Description - 125587 - PM | PM | 4 | 98775 | SCHD | EQUIP-ISOL | 2018-06-21 | 2020-01-02 | 2019-07-13 | 2019-07-17 | 2 | MAINTENANCE | INSTRUMENTS | 31
2019-03-31 | 125733 | Work Order Description - 125733 - PSPM | PSPM | 1 | 595633 | WSCHD | EQUIP-ISOL | 2017-08-01 | 2020-03-30 | 2020-01-17 | 2020-01-17 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 125827 | Work Order Description - 125827 - BR | BR | 4 | 663650 | SCHD | NORM-OPS | 2018-08-02 | 2019-07-31 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 125841 | Work Order Description - 125841 - CM | CM | 4 | 651384 | SCHD | NORM-OPS | 2019-02-03 | 2019-07-31 | 2019-06-08 | 2019-06-08 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 125869 | Work Order Description - 125869 - PSCM | PSCM | 4 | 361979 | WSCHD | SYS-ISOL | 2017-12-07 | 2020-01-01 | 2019-07-24 | 2019-07-24 | 4 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 125874 | Work Order Description - 125874 - BR | BR | 1 | 651390 | WSCHD | NORM-OPS | 2019-03-16 | 2019-08-01 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 125882 | Work Order Description - 125882 - BR | BR | 1 | 651423 | WSCHD | NORM-OPS | 2017-12-29 | 2019-08-01 | 2019-06-08 | 2019-06-10 | 4 | MAINTENANCE | MECHANICAL | 43
2019-03-31 | 125884 | Work Order Description - 125884 - BR | BR | 1 | 272341 | SCHD | NORM-OPS | 2019-02-03 | 2019-08-01 | 2019-06-08 | 2019-06-11 | 4 | MAINTENANCE | MECHANICAL | 60
2019-03-31 | 125886 | Work Order Description - 125886 - BR | BR | 1 | 272342 | SCHD | NORM-OPS | 2019-02-03 | 2019-08-01 | 2019-06-08 | 2019-06-11 | 4 | MAINTENANCE | MECHANICAL | 52
2019-03-31 | 125890 | Work Order Description - 125890 - PM | PM | 4 | 248024 | WSCHD | EQUIP-ISOL | 2017-08-03 | 2020-01-13 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 126093 | Work Order Description - 126093 - PM | PM | 2 | 480203 | WSCHD | PACK-ISOL | 2017-08-04 | 2019-12-10 | 2019-09-14 | 2019-09-14 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 126123 | Work Order Description - 126123 - BR | BR | 3 | 308497 | SCHD | NORM-OPS | 2019-02-06 | 2019-08-01 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 126127 | Work Order Description - 126127 - BR | BR | 4 | 547333 | WSCHD | PACK-ISOL | 2018-04-12 | 2019-08-03 | 2019-08-31 | 2019-09-03 | 4 | MAINTENANCE | CONSTRUCTION | 51
2019-03-31 | 126138 | Work Order Description - 126138 - BR | BR | 4 | 358177 | WSCHD | NORM-OPS | 2017-10-14 | 2019-08-04 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 126145 | Work Order Description - 126145 - BR | BR | 3 | 520589 | WSCHD | SYS-ISOL | 2017-08-07 | 2019-08-05 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 126148 | Work Order Description - 126148 - CM | CM | 3 | 17814 | WPLAN | TPS | 2017-08-16 | 2019-08-06 | 2020-05-03 | 2020-05-09 | 4 | INTEGRITY | CONSTRUCTION | 48
2019-03-31 | 126173 | Work Order Description - 126173 - CM | CM | 4 | 451560 | SCHD | NORM-OPS | 2019-03-09 | 2020-03-06 | 2019-03-16 | 2019-03-16 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 126309 | Work Order Description - 126309 - PM | PM | 3 | 387790 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-01-19 | 2019-07-13 | 2019-07-18 | 2 | MAINTENANCE | MECHANICAL | 57
2019-03-31 | 126353 | Work Order Description - 126353 - BR | BR | 4 | 292662 | WSCHD | NORM-OPS | 2017-08-13 | 2019-08-09 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 126436 | Work Order Description - 126436 - CM | CM | 1 | 324357 | WPLAN | TPS | 2017-08-27 | 2020-08-01 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 64
2019-03-31 | 126448 | Work Order Description - 126448 - PM | PM | 4 | 535884 | SCHD | NORM-OPS | 2018-10-29 | 2020-01-05 | 2019-04-13 | 2019-04-14 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 126471 | Work Order Description - 126471 - PSCM | PSCM | 1 | 399665 | WSCHD | NORM-OPS | 2018-09-04 | 2019-08-12 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 126472 | Work Order Description - 126472 - CM | CM | 3 | 243550 | WPLAN | PACK-ISOL | 2017-12-05 | 2019-11-30 | 2019-06-01 | 2019-06-03 | 4 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 126519 | Work Order Description - 126519 - BR | BR | 3 | 227752 | SCHD | SYS-ISOL | 2018-06-21 | 2019-08-14 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 126531 | Work Order Description - 126531 - PSPM | PSPM | 1 | 248301 | WSCHD | EQUIP-ISOL | 2017-08-16 | 2020-10-01 | 2020-05-02 | 2020-05-02 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 126548 | Work Order Description - 126548 - CM | CM | 1 | 368216 | SCHD | NORM-OPS | 2019-03-11 | 2019-08-15 | 2019-03-30 | 2019-04-07 | 4 | INTEGRITY | FABRIC | 118.5
2019-03-31 | 126641 | Work Order Description - 126641 - CM | CM | 1 | 368216 | SCHD | NORM-OPS | 2018-11-15 | 2019-07-13 | 2019-04-20 | 2019-04-21 | 3 | INTEGRITY | CONSTRUCTION | 168
2019-03-31 | 126642 | Work Order Description - 126642 - CM | CM | 4 | 368216 | WPLAN | NORM-OPS | 2019-03-28 | 2019-09-25 | 2019-05-03 | 2019-05-07 | 3 | INTEGRITY | FABRIC | 186
2019-03-31 | 126643 | Work Order Description - 126643 - PSCM | PSCM | 1 | 155742 | WSCHD | NORM-OPS | 2019-01-14 | 2019-09-01 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | DRILLING | 86
2019-03-31 | 126645 | Work Order Description - 126645 - CM | CM | 1 | 368216 | WPLAN | NORM-OPS | 2017-09-14 | 2018-12-11 | 2019-06-01 | 2019-06-04 | 3 | DRILLING | CONSTRUCTION | 48
2019-03-31 | 126693 | Work Order Description - 126693 - PSPM | PSPM | 1 | 679718 | WSCHD | EQUIP-ISOL | 2017-08-19 | 2020-02-23 | 2021-03-06 | 2021-03-06 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 126730 | Work Order Description - 126730 - CM | CM | 3 | 51688 | WSCHD | NORM-OPS | 2017-09-08 | 2019-08-27 | 2019-07-27 | 2019-07-30 | 4 | MAINTENANCE | SERVICES | 39
2019-03-31 | 126758 | Work Order Description - 126758 - BR | BR | 4 | 227373 | WSCHD | PACK-ISOL | 2017-11-23 | 2019-08-19 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 126783 | Work Order Description - 126783 - CM | CM | 1 | 368279 | WSCHD | PACK-ISOL | 2018-08-30 | 2019-09-01 | 2019-05-18 | 2019-05-18 | 2 | INTEGRITY | CONSTRUCTION | 224
2019-03-31 | 126833 | Work Order Description - 126833 - BR | BR | 1 | 363884 | WSCHD | NORM-OPS | 2017-08-29 | 2019-08-25 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 126838 | Work Order Description - 126838 - PM | PM | 3 | 54313 | SCHD | PACK-ISOL | 2019-03-20 | 2019-10-30 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 126858 | Work Order Description - 126858 - BR | BR | 3 | 51015 | WSCHD | NORM-OPS | 2017-09-18 | 2019-12-19 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 126861 | Work Order Description - 126861 - BR | BR | 3 | 51535 | SCHD | NORM-OPS | 2019-02-11 | 2019-08-31 | 2019-03-30 | 2019-03-31 | 4 | MAINTENANCE | ELECTRICAL | 3.5
2019-03-31 | 126867 | Work Order Description - 126867 - PSCM | PSCM | 1 | 355369 | WMATL | PACK-ISOL | 2018-03-07 | 2019-08-22 | 2019-05-04 | 2019-05-07 | 4 | INTEGRITY | MECHANICAL | 52
2019-03-31 | 126872 | Work Order Description - 126872 - PM | PM | 4 | 399939 | WSCHD | EQUIP-ISOL | 2017-08-24 | 2019-03-05 | 2019-12-28 | 2019-12-29 | 1 | INTEGRITY | CONSTRUCTION | 7
2019-03-31 | 126887 | Work Order Description - 126887 - CM | CM | 3 | 363333 | WSCHD | NORM-OPS | 2017-09-14 | 2019-08-23 | 2019-04-27 | 2019-05-01 | 4 | MAINTENANCE | SERVICES | 35
2019-03-31 | 126909 | Work Order Description - 126909 - BR | BR | 3 | 546583 | WSCHD | TPS | 2018-05-30 | 2019-08-23 | 2020-05-03 | 2020-05-08 | 4 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 126979 | Work Order Description - 126979 - CM | CM | 4 | 545222 | WSCHD | NORM-OPS | 2017-09-13 | 2019-08-25 | 2019-05-04 | 2019-05-07 | 4 | MAINTENANCE | SERVICES | 36
2019-03-31 | 126984 | Work Order Description - 126984 - BR | BR | 3 | 657770 | WSCHD | PACK-ISOL | 2017-09-10 | 2019-09-08 | 2019-05-11 | 2019-05-15 | 3 | MAINTENANCE | MECHANICAL | 59
2019-03-31 | 126985 | Work Order Description - 126985 - BR | BR | 3 | 545222 | WSCHD | PACK-ISOL | 2017-09-12 | 2019-08-23 | 2019-04-27 | 2019-04-29 | 3 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 126987 | Work Order Description - 126987 - PSCM | PSCM | 1 | 677357 | WMATL | PACK-ISOL | 2018-03-07 | 2019-08-25 | 2019-05-04 | 2019-05-09 | 4 | INTEGRITY | MECHANICAL | 80
2019-03-31 | 126989 | Work Order Description - 126989 - BR | BR | 3 | 545222 | WSCHD | PACK-ISOL | 2017-09-11 | 2019-07-29 | 2019-04-27 | 2019-05-07 | 3 | MAINTENANCE | MECHANICAL | 96
2019-03-31 | 127018 | Work Order Description - 127018 - CM | CM | 4 | 469372 | WSCHD | NORM-OPS | 2017-09-08 | 2019-05-24 | 2019-05-25 | 2019-05-26 | 3 | MAINTENANCE | INSTRUMENTS | 31
2019-03-31 | 127021 | Work Order Description - 127021 - BR | BR | 3 | 354602 | SCHD | PACK-ISOL | 2019-01-23 | 2019-02-22 | 2019-05-25 | 2019-05-27 | 3 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 127022 | Work Order Description - 127022 - CM | CM | 4 | 490436 | WSCHD | NORM-OPS | 2017-09-13 | 2019-08-26 | 2019-12-28 | 2019-12-28 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 127051 | Work Order Description - 127051 - BR | BR | 3 | 545266 | WSCHD | PACK-ISOL | 2018-08-05 | 2019-06-13 | 2019-06-29 | 2019-06-30 | 3 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 127111 | Work Order Description - 127111 - CM | CM | 4 | 326805 | WPLAN | TPS | 2017-08-30 | 2020-01-23 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | CONSTRUCTION | 15
2019-03-31 | 127125 | Work Order Description - 127125 - BR | BR | 4 | 238343 | SCHD | NORM-OPS | 2018-09-06 | 2019-09-05 | 2019-09-07 | 2019-09-09 | 3 | MAINTENANCE | ELECTRICAL | 48
2019-03-31 | 127127 | Work Order Description - 127127 - BR | BR | 4 | 652220 | WSCHD | NORM-OPS | 2017-10-09 | 2019-08-29 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | SERVICES | 16
2019-03-31 | 127141 | Work Order Description - 127141 - BR | BR | 3 | 499512 | WPLAN | TPS | 2017-09-12 | 2019-12-18 | 2020-05-02 | 2020-05-05 | 3 | MAINTENANCE | MECHANICAL | 46
2019-03-31 | 127142 | Work Order Description - 127142 - CM | CM | 1 | 484754 | WSCHD | NORM-OPS | 2018-07-13 | 2019-04-01 | 2019-05-25 | 2019-05-31 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 127143 | Work Order Description - 127143 - BR | BR | 3 | 226526 | WPLAN | TPS | 2018-01-28 | 2020-03-18 | 2020-05-02 | 2020-05-05 | 3 | MAINTENANCE | MECHANICAL | 46
2019-03-31 | 130362 | Work Order Description - 130362 - PM | PM | 2 | 595905 | WSCHD | EQUIP-ISOL | 2018-06-08 | 2019-09-29 | 2020-05-03 | 2020-05-06 | 2 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 130404 | Work Order Description - 130404 - BR | BR | 2 | 376682 | SCHD | NORM-OPS | 2018-06-21 | 2019-09-03 | 2019-04-30 | 2019-05-02 | 4 | MAINTENANCE | MECHANICAL | 46
2019-03-31 | 130419 | Work Order Description - 130419 - CM | CM | 1 | 17814 | WSCHD | NORM-OPS | 2018-02-18 | 2019-09-03 | 2019-05-04 | 2019-05-05 | 4 | INTEGRITY | FABRIC | 600
2019-03-31 | 130421 | Work Order Description - 130421 - CM | CM | 4 | 666777 | WSCHD | NORM-OPS | 2017-10-11 | 2019-01-20 | 2019-06-01 | 2019-06-02 | 3 | MAINTENANCE | DRILLING | 12
2019-03-31 | 130422 | Work Order Description - 130422 - CM | CM | 3 | 670209 | SCHD | PACK-ISOL | 2018-06-21 | 2019-02-01 | 2019-05-04 | 2019-05-05 | 2 | MAINTENANCE | ELECTRICAL | 28
2019-03-31 | 130423 | Work Order Description - 130423 - CM | CM | 4 | 307449 | WSCHD | NORM-OPS | 2017-10-13 | 2019-09-07 | 2019-06-01 | 2019-06-02 | 3 | MAINTENANCE | DRILLING | 8
2019-03-31 | 130424 | Work Order Description - 130424 - CM | CM | 2 | 408320 | WPLAN | NORM-OPS | 2017-09-16 | 2019-09-03 | 2019-05-04 | 2019-05-05 | 4 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 130425 | Work Order Description - 130425 - CM | CM | 3 | 323294 | WPLAN | TPS | 2017-12-01 | 2019-12-09 | 2020-12-01 | 2020-12-03 | 3 | MAINTENANCE | MECHANICAL | 29
2019-03-31 | 130426 | Work Order Description - 130426 - CM | CM | 4 | 666780 | WSCHD | NORM-OPS | 2017-10-13 | 2019-02-26 | 2019-06-01 | 2019-06-02 | 3 | MAINTENANCE | DRILLING | 8
2019-03-31 | 130441 | Work Order Description - 130441 - PSPM | PSPM | 3 | 396314 | SCHD | EQUIP-ISOL | 2018-10-05 | 2019-05-26 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 130451 | Work Order Description - 130451 - CM | CM | 4 | 501566 | WPLAN | TPS | 2017-12-17 | 2020-01-05 | 2020-01-28 | 2020-02-01 | 2 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 130453 | Work Order Description - 130453 - CM | CM | 4 | 530985 | WSCHD | NORM-OPS | 2017-09-14 | 2019-08-25 | 2019-07-24 | 2019-07-24 | 3 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 130455 | Work Order Description - 130455 - CM | CM | 1 | 678548 | WSCHD | PACK-ISOL | 2018-09-01 | 2019-07-01 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 9
2019-03-31 | 130514 | Work Order Description - 130514 - CM | CM | 1 | 540547 | WSCHD | NORM-OPS | 2017-09-12 | 2019-09-04 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 130531 | Work Order Description - 130531 - PM | PM | 4 | 527429 | SCHD | PACK-ISOL | 2018-06-21 | 2019-02-24 | 2019-04-30 | 2019-04-30 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 130541 | Work Order Description - 130541 - PM | PM | 4 | 671538 | WSCHD | EQUIP-ISOL | 2017-09-06 | 2019-12-05 | 2019-10-26 | 2019-10-26 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 130582 | Work Order Description - 130582 - CM | CM | 1 | 378817 | SCHD | NORM-OPS | 2019-03-06 | 2019-06-06 | 2019-05-29 | 2019-06-11 | 3 | INTEGRITY | FABRIC | 322
2019-03-31 | 130603 | Work Order Description - 130603 - CM | CM | 4 | 570144 | WSCHD | NORM-OPS | 2019-01-14 | 2019-09-05 | 2019-09-15 | 2019-09-15 | 4 | INTEGRITY | CONSTRUCTION | 81
2019-03-31 | 130650 | Work Order Description - 130650 - BR | BR | 4 | 489534 | WSCHD | NORM-OPS | 2017-09-17 | 2019-01-11 | 2019-12-28 | 2019-12-29 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 130698 | Work Order Description - 130698 - CM | CM | 4 | 70841 | WSCHD | NORM-OPS | 2017-09-25 | 2019-09-06 | 2019-05-25 | 2019-05-27 | 4 | INTEGRITY | FABRIC | 150
2019-03-31 | 130772 | Work Order Description - 130772 - PM | PM | 4 | 54712 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-08-09 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 130773 | Work Order Description - 130773 - PM | PM | 4 | 357476 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-12-13 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 130776 | Work Order Description - 130776 - PM | PM | 4 | 70841 | WSCHD | EQUIP-ISOL | 2017-09-09 | 2019-10-26 | 2019-06-08 | 2019-06-09 | 1 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 130815 | Work Order Description - 130815 - BR | BR | 2 | 686570 | SCHD | PACK-ISOL | 2018-06-21 | 2019-09-08 | 2019-08-11 | 2019-08-20 | 4 | INTEGRITY | MECHANICAL | 152
2019-03-31 | 130916 | Work Order Description - 130916 - CM | CM | 4 | 72685 | WPLAN | ON LINE | 2017-09-21 | 2019-09-09 | 2019-05-27 | 2019-05-29 | 4 | MAINTENANCE | MECHANICAL | 44
2019-03-31 | 130919 | Work Order Description - 130919 - BR | BR | 4 | 457371 | WSCHD | NORM-OPS | 2019-02-18 | 2021-02-16 | 2019-04-27 | 2019-04-27 | 4 | OPERATIONS | OPERATIONS | 1
2019-03-31 | 130948 | Work Order Description - 130948 - PM | PM | 4 | 361287 | SCHD | EQUIP-ISOL | 2018-11-14 | 2019-12-13 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 130998 | Work Order Description - 130998 - CM | CM | 4 | 261670 | WSCHD | TPS | 2017-09-13 | 2019-09-11 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 130999 | Work Order Description - 130999 - CM | CM | 4 | 352979 | WSCHD | TPS | 2017-09-13 | 2019-09-11 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 131000 | Work Order Description - 131000 - CM | CM | 4 | 546365 | WSCHD | TPS | 2017-09-13 | 2019-09-11 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 131001 | Work Order Description - 131001 - CM | CM | 4 | 323137 | WSCHD | TPS | 2017-09-13 | 2019-09-11 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 131002 | Work Order Description - 131002 - CM | CM | 4 | 262054 | WSCHD | TPS | 2017-09-13 | 2019-09-11 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 131003 | Work Order Description - 131003 - CM | CM | 4 | 498545 | WSCHD | TPS | 2017-09-13 | 2019-09-11 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 131004 | Work Order Description - 131004 - CM | CM | 4 | 359476 | WSCHD | TPS | 2017-11-04 | 2019-09-11 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | OPERATIONS | 1
2019-03-31 | 131005 | Work Order Description - 131005 - CM | CM | 4 | 56814 | WSCHD | TPS | 2017-09-13 | 2019-09-11 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 131006 | Work Order Description - 131006 - CM | CM | 4 | 33241 | WSCHD | TPS | 2017-09-13 | 2019-09-11 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 131007 | Work Order Description - 131007 - CM | CM | 4 | 53959 | WSCHD | TPS | 2017-09-13 | 2019-09-11 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 131013 | Work Order Description - 131013 - PM | PM | 4 | 58419 | WSCHD | SUBSYS-ISOL | 2017-09-12 | 2019-07-19 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | OPERATIONS | 3
2019-03-31 | 131090 | Work Order Description - 131090 - BR | BR | 4 | 500646 | WMATL | NORM-OPS | 2018-02-02 | 2019-08-13 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | CONSTRUCTION | 35
2019-03-31 | 131160 | Work Order Description - 131160 - BR | BR | 4 | 362136 | SCHD | NORM-OPS | 2019-03-08 | 2019-09-12 | 2019-04-20 | 2019-04-22 | 4 | MAINTENANCE | MECHANICAL | 19
2019-03-31 | 131189 | Work Order Description - 131189 - BR | BR | 4 | 245320 | SCHD | NORM-OPS | 2019-03-07 | 2019-09-12 | 2019-04-20 | 2019-04-22 | 4 | MAINTENANCE | MECHANICAL | 23
2019-03-31 | 131242 | Work Order Description - 131242 - BR | BR | 4 | 548298 | SCHD | NORM-OPS | 2019-03-07 | 2019-09-13 | 2019-04-20 | 2019-04-22 | 4 | MAINTENANCE | MECHANICAL | 25
2019-03-31 | 131243 | Work Order Description - 131243 - BR | BR | 4 | 545071 | SCHD | NORM-OPS | 2019-03-07 | 2019-09-13 | 2019-04-20 | 2019-04-22 | 4 | MAINTENANCE | MECHANICAL | 25
2019-03-31 | 131244 | Work Order Description - 131244 - BR | BR | 4 | 400258 | SCHD | NORM-OPS | 2019-03-07 | 2019-09-13 | 2019-04-20 | 2019-04-22 | 4 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 131245 | Work Order Description - 131245 - BR | BR | 4 | 245323 | SCHD | NORM-OPS | 2019-03-07 | 2019-09-13 | 2019-04-20 | 2019-04-22 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 131246 | Work Order Description - 131246 - BR | BR | 4 | 400263 | SCHD | NORM-OPS | 2019-03-07 | 2019-09-13 | 2019-04-20 | 2019-04-22 | 4 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 131248 | Work Order Description - 131248 - BR | BR | 4 | 400264 | SCHD | NORM-OPS | 2019-03-07 | 2019-09-13 | 2019-04-20 | 2019-04-22 | 4 | MAINTENANCE | MECHANICAL | 23
2019-03-31 | 131249 | Work Order Description - 131249 - BR | BR | 4 | 400288 | SCHD | NORM-OPS | 2019-03-07 | 2019-09-13 | 2019-04-20 | 2019-04-22 | 4 | MAINTENANCE | MECHANICAL | 23
2019-03-31 | 131283 | Work Order Description - 131283 - CM | CM | 4 | 19008 | WSCHD | NORM-OPS | 2018-03-27 | 2019-09-13 | 2019-08-13 | 2019-08-14 | 4 | INTEGRITY | FABRIC | 60
2019-03-31 | 131284 | Work Order Description - 131284 - BR | BR | 3 | 669095 | WMATL | TPS | 2017-10-20 | 2019-05-10 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 131337 | Work Order Description - 131337 - PRJ | PRJ | 3 | 76032 | WPLAN | SYS-ISOL | 2017-09-15 | 2019-09-14 | 2019-04-21 | 2019-04-25 | 4 | INTEGRITY | CONSTRUCTION | 105
2019-03-31 | 131340 | Work Order Description - 131340 - CM | CM | 3 | 451454 | WPLAN | SYS-ISOL | 2017-09-15 | 2019-01-23 | 2019-05-31 | 2019-07-12 | 3 | INTEGRITY | CONSTRUCTION | 700
2019-03-31 | 131341 | Work Order Description - 131341 - CM | CM | 3 | 383738 | WPLAN | SYS-ISOL | 2017-09-15 | 2019-04-07 | 2019-05-31 | 2019-06-05 | 3 | MAINTENANCE | CONSTRUCTION | 120
2019-03-31 | 131344 | Work Order Description - 131344 - CM | CM | 4 | 520388 | WPLAN | PACK-ISOL | 2018-04-04 | 2018-12-19 | 2019-04-27 | 2019-04-28 | 3 | WELLS | INSTRUMENTS | 8
2019-03-31 | 131345 | Work Order Description - 131345 - BR | BR | 3 | 124384 | SCHD | NORM-OPS | 2018-06-21 | 2019-10-30 | 2019-04-27 | 2019-04-29 | 4 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 131423 | Work Order Description - 131423 - PM | PM | 4 | 652482 | WSCHD | EQUIP-ISOL | 2017-09-17 | 2019-03-09 | 2019-05-04 | 2019-05-06 | 2 | MAINTENANCE | SERVICES | 35
2019-03-31 | 131430 | Work Order Description - 131430 - PSPM | PSPM | 1 | 361156 | WSCHD | EQUIP-ISOL | 2017-09-17 | 2019-12-01 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 131509 | Work Order Description - 131509 - CM | CM | 4 | 375773 | SCHD | NORM-OPS | 2018-12-17 | 2019-09-16 | 2019-12-08 | 2019-12-08 | 4 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 131574 | Work Order Description - 131574 - CM | CM | 4 | 228842 | WPLAN | NORM-OPS | 2018-08-04 | 2020-01-01 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | FABRIC | 438
2019-03-31 | 131623 | Work Order Description - 131623 - BR | BR | 2 | 451498 | SCHD | PACK-ISOL | 2018-06-21 | 2019-09-20 | 2019-07-13 | 2019-07-16 | 4 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 131674 | Work Order Description - 131674 - PSCM | PSCM | 1 | 321203 | WPLAN | NORM-OPS | 2018-04-04 | 2020-01-01 | 2019-06-01 | 2019-06-06 | 4 | MAINTENANCE | MECHANICAL | 80
2019-03-31 | 131749 | Work Order Description - 131749 - BR | BR | 4 | 489534 | WPLAN | SUBSYS-ISOL | 2017-11-05 | 2019-09-20 | 2019-06-01 | 2019-06-02 | 4 | INTEGRITY | CONSTRUCTION | 7
2019-03-31 | 131759 | Work Order Description - 131759 - BR | BR | 1 | 57982 | SCHD | SYS-ISOL | 2018-12-05 | 2020-07-01 | 2019-10-26 | 2019-10-27 | 2 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 131885 | Work Order Description - 131885 - CM | CM | 4 | 322843 | WSCHD | NORM-OPS | 2017-09-24 | 2019-09-21 | 2019-06-01 | 2019-06-04 | 4 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 131892 | Work Order Description - 131892 - PM | PM | 4 | 273658 | SCHD | EQUIP-ISOL | 2018-10-29 | 2018-12-05 | 2019-04-13 | 2019-04-14 | 2 | INTEGRITY | INSTRUMENTS | 8
2019-03-31 | 131943 | Work Order Description - 131943 - CM | CM | 3 | 449086 | SCHD | NORM-OPS | 2018-06-21 | 2019-09-25 | 2019-03-16 | 2019-03-27 | 3 | INTEGRITY | FABRIC | 224
2019-03-31 | 132062 | Work Order Description - 132062 - BR | BR | 3 | 185571 | SCHD | SUBSYS-ISOL | 2019-02-13 | 2019-03-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 132091 | Work Order Description - 132091 - PM | PM | 4 | 666260 | WSCHD | NORM-OPS | 2017-09-25 | 2019-09-20 | 2020-12-12 | 2020-12-12 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 132097 | Work Order Description - 132097 - PM | PM | 4 | 490184 | WSCHD | EQUIP-ISOL | 2017-09-25 | 2019-03-21 | 2020-03-07 | 2020-03-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 132135 | Work Order Description - 132135 - CM | CM | 4 | 674419 | WSCHD | NORM-OPS | 2018-04-27 | 2019-09-24 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 132200 | Work Order Description - 132200 - CM | CM | 3 | 308562 | WSCHD | NORM-OPS | 2017-10-18 | 2019-09-24 | 2019-07-06 | 2019-07-09 | 4 | MAINTENANCE | CONSTRUCTION | 37
2019-03-31 | 132203 | Work Order Description - 132203 - PM | PM | 4 | 545296 | WSCHD | EQUIP-ISOL | 2017-11-06 | 2019-06-14 | 2019-10-26 | 2019-10-27 | 3 | MAINTENANCE | ELECTRICAL | 7
2019-03-31 | 132204 | Work Order Description - 132204 - PM | PM | 4 | 308594 | WSCHD | EQUIP-ISOL | 2017-09-26 | 2019-05-09 | 2019-10-26 | 2019-10-29 | 2 | MAINTENANCE | ELECTRICAL | 53
2019-03-31 | 132234 | Work Order Description - 132234 - BR | BR | 4 | 489534 | WSCHD | NORM-OPS | 2018-01-12 | 2019-09-25 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 132250 | Work Order Description - 132250 - CM | CM | 3 | 665119 | SCHD | NORM-OPS | 2018-06-21 | 2019-08-03 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | ELECTRICAL | 9
2019-03-31 | 132307 | Work Order Description - 132307 - CM | CM | 2 | 653434 | WSCHD | NORM-OPS | 2017-11-05 | 2019-09-26 | 2019-09-23 | 2019-09-26 | 4 | MAINTENANCE | FABRIC | 63
2019-03-31 | 132340 | Work Order Description - 132340 - CM | CM | 4 | 450552 | WPLAN | NORM-OPS | 2017-10-06 | 2019-09-27 | 2019-04-06 | 2019-04-06 | 4 | INTEGRITY | FABRIC | 238
2019-03-31 | 132350 | Work Order Description - 132350 - CM | CM | 2 | 441710 | WPLAN | TPS | 2017-10-06 | 2019-09-28 | 2019-07-13 | 2019-07-13 | 3 | INTEGRITY | INSPECTION | 105
2019-03-31 | 132429 | Work Order Description - 132429 - BR | BR | 3 | 33971 | WSCHD | SUBSYS-ISOL | 2017-10-01 | 2019-06-14 | 2019-05-04 | 2019-05-05 | 2 | MAINTENANCE | OPERATIONS | 16
2019-03-31 | 132435 | Work Order Description - 132435 - PM | PM | 4 | 106148 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-07-07 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 132487 | Work Order Description - 132487 - CM | CM | 2 | 572308 | WSCHD | NORM-OPS | 2018-11-16 | 2019-09-29 | 2019-09-25 | 2019-09-28 | 4 | INTEGRITY | FABRIC | 357
2019-03-31 | 132493 | Work Order Description - 132493 - CM | CM | 4 | 669626 | WPLAN | TPS | 2017-10-06 | 2019-10-01 | 2019-07-13 | 2019-07-20 | 4 | INTEGRITY | FABRIC | 119
2019-03-31 | 132505 | Work Order Description - 132505 - BR | BR | 1 | 547582 | WSCHD | TPS | 2018-08-05 | 2020-01-01 | 2019-10-26 | 2019-10-31 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 132570 | Work Order Description - 132570 - BR | BR | 3 | 302233 | WSCHD | TPS | 2018-06-07 | 2019-12-11 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 23
2019-03-31 | 132576 | Work Order Description - 132576 - BR | BR | 3 | 215165 | WSCHD | NORM-OPS | 2017-11-24 | 2019-12-15 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 132578 | Work Order Description - 132578 - PSCM | PSCM | 1 | 531478 | WSCHD | NORM-OPS | 2018-06-13 | 2019-09-11 | 2019-09-24 | 2019-09-24 | 4 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 132599 | Work Order Description - 132599 - PM | PM | 4 | 357142 | WSCHD | NORM-OPS | 2017-10-02 | 2019-03-27 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 132616 | Work Order Description - 132616 - PM | PM | 4 | 675119 | WSCHD | EQUIP-ISOL | 2017-10-02 | 2019-10-28 | 2019-09-28 | 2019-09-29 | 3 | MAINTENANCE | ELECTRICAL | 7
2019-03-31 | 132617 | Work Order Description - 132617 - PM | PM | 4 | 308812 | WSCHD | EQUIP-ISOL | 2017-10-02 | 2019-01-23 | 2019-09-28 | 2019-09-29 | 3 | MAINTENANCE | ELECTRICAL | 7
2019-03-31 | 132622 | Work Order Description - 132622 - PM | PM | 2 | 321199 | SCHD | PACK-ISOL | 2018-11-11 | 2019-05-22 | 2019-06-29 | 2019-06-29 | 2 | MAINTENANCE | INSTRUMENTS | 11
2019-03-31 | 132654 | Work Order Description - 132654 - BR | BR | 3 | 546585 | WSCHD | TPS | 2018-05-30 | 2019-10-01 | 2020-05-03 | 2020-05-04 | 4 | MAINTENANCE | MECHANICAL | 37.5
2019-03-31 | 132699 | Work Order Description - 132699 - PM | PM | 4 | 358177 | WSCHD | EQUIP-ISOL | 2017-11-06 | 2019-12-11 | 2019-09-24 | 2019-09-24 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 132735 | Work Order Description - 132735 - CM | CM | 1 | 228839 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-02 | 2019-03-23 | 2019-05-07 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 132736 | Work Order Description - 132736 - CM | CM | 1 | 228839 | SCHD | NORM-OPS | 2018-11-02 | 2019-11-02 | 2019-11-02 | 2019-11-19 | 3 | INTEGRITY | CONSTRUCTION | 385.5
2019-03-31 | 132750 | Work Order Description - 132750 - CM | CM | 1 | 677994 | WSCHD | TPS | 2017-10-07 | 2020-08-01 | 2020-05-02 | 2020-05-02 | 3 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 132752 | Work Order Description - 132752 - CM | CM | 1 | 308465 | WSCHD | TPS | 2017-10-07 | 2020-08-01 | 2020-05-02 | 2020-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 40
2019-03-31 | 132789 | Work Order Description - 132789 - PM | PM | 3 | 357458 | WSCHD | EQUIP-ISOL | 2017-10-04 | 2019-01-26 | 2020-06-27 | 2020-06-27 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 132817 | Work Order Description - 132817 - PSPM | PSPM | 1 | 261209 | WSCHD | EQUIP-ISOL | 2017-10-04 | 2019-05-01 | 2019-09-28 | 2019-09-28 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 133692 | Work Order Description - 133692 - CM | CM | 1 | 531852 | WSCHD | ON LINE | 2017-10-07 | 2019-08-01 | 2019-09-07 | 2019-09-09 | 3 | INTEGRITY | INSTRUMENTS | 38
2019-03-31 | 133714 | Work Order Description - 133714 - PM | PM | 3 | 531852 | WSCHD | EQUIP-ISOL | 2017-10-05 | 2019-08-10 | 2019-09-07 | 2019-09-09 | 2 | INTEGRITY | INSTRUMENTS | 36
2019-03-31 | 133758 | Work Order Description - 133758 - PM | PM | 4 | 105565 | SCHD | PACK-ISOL | 2018-06-01 | 2019-07-30 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 133876 | Work Order Description - 133876 - PSPM | PSPM | 1 | 294961 | SCHD | EQUIP-ISOL | 2019-03-05 | 2019-04-19 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 133887 | Work Order Description - 133887 - PM | PM | 3 | 54303 | WSCHD | PACK-ISOL | 2017-10-07 | 2019-07-12 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 134003 | Work Order Description - 134003 - BR | BR | 4 | 355384 | WSCHD | NORM-OPS | 2017-11-23 | 2020-01-07 | 2019-04-13 | 2019-04-14 | 3 | INTEGRITY | MECHANICAL | 54
2019-03-31 | 134008 | Work Order Description - 134008 - BR | BR | 3 | 491600 | WSCHD | TPS | 2018-08-05 | 2019-09-23 | 2020-06-02 | 2020-06-05 | 3 | MAINTENANCE | CONSTRUCTION | 24
2019-03-31 | 134143 | Work Order Description - 134143 - CM | CM | 2 | 363240 | WSCHD | NORM-OPS | 2017-11-22 | 2019-10-09 | 2019-04-20 | 2019-04-21 | 4 | MAINTENANCE | INSTRUMENTS | 9
2019-03-31 | 134249 | Work Order Description - 134249 - PSCM | PSCM | 1 | 697913 | WSCHD | NORM-OPS | 2018-01-18 | 2019-09-01 | 2019-04-20 | 2019-04-22 | 2 | INTEGRITY | CONSTRUCTION | 115
2019-03-31 | 134251 | Work Order Description - 134251 - PSCM | PSCM | 1 | 697913 | SCHD | NORM-OPS | 2019-03-01 | 2019-06-01 | 2019-04-06 | 2019-04-12 | 2 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 134285 | Work Order Description - 134285 - BR | BR | 2 | 51263 | WSCHD | NORM-OPS | 2018-06-08 | 2019-10-11 | 2020-05-03 | 2020-05-08 | 4 | MAINTENANCE | INSTRUMENTS | 54
2019-03-31 | 134359 | Work Order Description - 134359 - BR | BR | 1 | 314396 | WSCHD | NORM-OPS | 2018-01-26 | 2019-10-12 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 134404 | Work Order Description - 134404 - BR | BR | 4 | 671670 | WSCHD | NORM-OPS | 2018-03-30 | 2019-10-12 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | SERVICES | 40
2019-03-31 | 134411 | Work Order Description - 134411 - BR | BR | 4 | 653662 | WSCHD | PACK-ISOL | 2017-11-01 | 2019-10-12 | 2019-07-06 | 2019-07-24 | 4 | MAINTENANCE | MECHANICAL | 293
2019-03-31 | 134415 | Work Order Description - 134415 - BR | BR | 4 | 124225 | SCHD | NORM-OPS | 2018-07-09 | 2019-10-12 | 2019-09-01 | 2019-09-01 | 4 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 134416 | Work Order Description - 134416 - BR | BR | 4 | 276633 | SCHD | NORM-OPS | 2018-06-21 | 2019-10-30 | 2019-04-06 | 2019-04-08 | 4 | MAINTENANCE | CONSTRUCTION | 20
2019-03-31 | 134420 | Work Order Description - 134420 - BR | BR | 4 | 448648 | SCHD | NORM-OPS | 2018-06-21 | 2019-02-25 | 2019-09-07 | 2019-09-12 | 3 | DRILLING | ELECTRICAL | 38
2019-03-31 | 134421 | Work Order Description - 134421 - BR | BR | 4 | 352388 | SCHD | ON LINE | 2019-01-13 | 2019-10-12 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 134422 | Work Order Description - 134422 - BR | BR | 4 | 545261 | WSCHD | PACK-ISOL | 2017-12-11 | 2019-12-01 | 2019-07-06 | 2019-07-10 | 4 | MAINTENANCE | MECHANICAL | 39
2019-03-31 | 134429 | Work Order Description - 134429 - BR | BR | 4 | 448640 | SCHD | NORM-OPS | 2018-06-21 | 2019-10-01 | 2019-04-06 | 2019-04-16 | 3 | DRILLING | DRILLING | 76
2019-03-31 | 134431 | Work Order Description - 134431 - BR | BR | 4 | 448640 | SCHD | NORM-OPS | 2018-06-21 | 2019-01-10 | 2019-04-06 | 2019-04-16 | 3 | DRILLING | DRILLING | 76
2019-03-31 | 134434 | Work Order Description - 134434 - BR | BR | 4 | 448640 | SCHD | NORM-OPS | 2018-06-21 | 2019-10-25 | 2019-04-06 | 2019-04-16 | 3 | DRILLING | DRILLING | 76
2019-03-31 | 134436 | Work Order Description - 134436 - CM | CM | 2 | 666093 | WSCHD | NORM-OPS | 2017-12-09 | 2019-10-12 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 134437 | Work Order Description - 134437 - CM | CM | 3 | 404516 | WSCHD | NORM-OPS | 2018-02-14 | 2019-11-30 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 134438 | Work Order Description - 134438 - PSCM | PSCM | 1 | 679201 | WSCHD | NORM-OPS | 2019-02-26 | 2019-10-12 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | INSTRUMENTS | 60
2019-03-31 | 134480 | Work Order Description - 134480 - BR | BR | 4 | 448640 | SCHD | NORM-OPS | 2018-06-21 | 2019-05-15 | 2019-04-06 | 2019-04-16 | 3 | DRILLING | DRILLING | 76
2019-03-31 | 134482 | Work Order Description - 134482 - BR | BR | 4 | 652160 | WSCHD | PACK-ISOL | 2017-10-19 | 2019-10-13 | 2019-04-20 | 2019-04-21 | 4 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 134498 | Work Order Description - 134498 - BR | BR | 4 | 652246 | WSCHD | PACK-ISOL | 2018-07-12 | 2019-10-13 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | MECHANICAL | 67
2019-03-31 | 134575 | Work Order Description - 134575 - CM | CM | 4 | 110290 | WPLAN | TPS | 2017-11-09 | 2019-10-17 | 2020-01-28 | 2020-01-30 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 134611 | Work Order Description - 134611 - CM | CM | 3 | 248024 | WSCHD | NORM-OPS | 2017-11-10 | 2019-10-15 | 2019-04-27 | 2019-04-27 | 4 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 134635 | Work Order Description - 134635 - CM | CM | 4 | 451342 | SCHD | NORM-OPS | 2019-02-23 | 2020-02-14 | 2019-08-03 | 2019-10-18 | 3 | INTEGRITY | FABRIC | 1683
2019-03-31 | 134638 | Work Order Description - 134638 - CM | CM | 4 | 451342 | INPRG | NORM-OPS | 2019-03-08 | 2020-02-14 | 2019-03-09 | 2019-04-13 | 3 | INTEGRITY | FABRIC | 396
2019-03-31 | 134698 | Work Order Description - 134698 - BR | BR | 4 | 657794 | WSCHD | PACK-ISOL | 2018-03-02 | 2019-10-16 | 2019-04-27 | 2019-05-02 | 4 | MAINTENANCE | MECHANICAL | 41
2019-03-31 | 134703 | Work Order Description - 134703 - CM | CM | 4 | 237406 | SCHD | NORM-OPS | 2019-03-29 | 2020-03-19 | 2019-04-13 | 2019-04-13 | 3 | INTEGRITY | FABRIC | 84
2019-03-31 | 134713 | Work Order Description - 134713 - CM | CM | 4 | 237406 | SCHD | NORM-OPS | 2019-02-18 | 2019-08-16 | 2019-03-23 | 2019-03-23 | 3 | INTEGRITY | FABRIC | 900
2019-03-31 | 134716 | Work Order Description - 134716 - CM | CM | 4 | 237406 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-16 | 2019-03-23 | 2019-05-14 | 3 | INTEGRITY | FABRIC | 932
2019-03-31 | 134723 | Work Order Description - 134723 - CM | CM | 4 | 237448 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-16 | 2019-03-09 | 2019-12-12 | 3 | INTEGRITY | FABRIC | 715
2019-03-31 | 134728 | Work Order Description - 134728 - BR | BR | 4 | 352386 | SCHD | ON LINE | 2019-01-13 | 2019-10-16 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 134733 | Work Order Description - 134733 - PSCM | PSCM | 1 | 535873 | SCHD | NORM-OPS | 2019-01-17 | 2020-05-18 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 134739 | Work Order Description - 134739 - CM | CM | 4 | 127428 | WPLAN | NORM-OPS | 2018-08-04 | 2019-10-16 | 2019-08-03 | 2019-08-03 | 4 | INTEGRITY | FABRIC | 1
2019-03-31 | 134743 | Work Order Description - 134743 - BR | BR | 4 | 653618 | WSCHD | PACK-ISOL | 2017-10-20 | 2019-09-18 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 134863 | Work Order Description - 134863 - CM | CM | 4 | 419551 | INPRG | NORM-OPS | 2019-02-22 | 2019-06-14 | 2019-03-30 | 2019-04-26 | 3 | DRILLING | DRILLING | 295
2019-03-31 | 134864 | Work Order Description - 134864 - CM | CM | 4 | 338628 | INPRG | NORM-OPS | 2019-02-26 | 2019-04-03 | 2019-03-30 | 2019-04-26 | 3 | INTEGRITY | DRILLING | 666
2019-03-31 | 134865 | Work Order Description - 134865 - CM | CM | 4 | 419551 | INPRG | NORM-OPS | 2019-02-26 | 2019-12-30 | 2019-03-30 | 2019-04-26 | 3 | DRILLING | DRILLING | 626.5
2019-03-31 | 134866 | Work Order Description - 134866 - CM | CM | 4 | 419551 | INPRG | NORM-OPS | 2019-02-26 | 2019-09-23 | 2019-03-30 | 2019-04-26 | 3 | DRILLING | DRILLING | 650
2019-03-31 | 134870 | Work Order Description - 134870 - CM | CM | 4 | 419551 | WSCHD | NORM-OPS | 2017-12-21 | 2019-03-12 | 2019-06-01 | 2019-06-01 | 3 | DRILLING | DRILLING | 446
2019-03-31 | 135012 | Work Order Description - 135012 - CM | CM | 3 | 484754 | WPLAN | TPS | 2017-11-04 | 2019-10-18 | 2019-04-27 | 2019-05-01 | 4 | INTEGRITY | CONSTRUCTION | 70
2019-03-31 | 135084 | Work Order Description - 135084 - CM | CM | 4 | 411436 | SCHD | PACK-ISOL | 2018-10-29 | 2020-01-24 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 135088 | Work Order Description - 135088 - CM | CM | 4 | 468114 | SCHD | PACK-ISOL | 2018-10-29 | 2019-10-19 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 135202 | Work Order Description - 135202 - BR | BR | 3 | 502414 | WSCHD | TPS | 2018-06-08 | 2018-12-18 | 2020-05-03 | 2020-05-04 | 2 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 135203 | Work Order Description - 135203 - BR | BR | 3 | 33796 | WPLAN | SYS-ISOL | 2018-04-03 | 2019-09-07 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 135208 | Work Order Description - 135208 - BR | BR | 2 | 520075 | WSCHD | TPS | 2017-10-26 | 2019-08-18 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 135244 | Work Order Description - 135244 - PM | PM | 4 | 359311 | WSCHD | NORM-OPS | 2017-11-06 | 2019-08-20 | 2020-03-01 | 2020-03-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 135260 | Work Order Description - 135260 - PM | PM | 4 | 356946 | WSCHD | EQUIP-ISOL | 2017-10-24 | 2019-08-26 | 2019-12-25 | 2019-12-27 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 135422 | Work Order Description - 135422 - PM | PM | 4 | 487532 | SCHD | SUBSYS-ISOL | 2018-09-06 | 2019-03-20 | 2020-01-04 | 2020-01-04 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 135427 | Work Order Description - 135427 - PM | PM | 4 | 324850 | SCHD | SUBSYS-ISOL | 2018-09-06 | 2019-12-18 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 135461 | Work Order Description - 135461 - PM | PM | 4 | 188482 | SCHD | SUBSYS-ISOL | 2018-09-06 | 2019-06-26 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 135476 | Work Order Description - 135476 - PM | PM | 4 | 188950 | SCHD | NORM-OPS | 2018-09-06 | 2018-12-25 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 135503 | Work Order Description - 135503 - PM | PM | 4 | 487531 | SCHD | SUBSYS-ISOL | 2018-09-06 | 2020-01-17 | 2020-01-04 | 2020-01-04 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 135508 | Work Order Description - 135508 - PM | PM | 4 | 491980 | SCHD | SUBSYS-ISOL | 2018-09-06 | 2019-10-06 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 135640 | Work Order Description - 135640 - PM | PM | 4 | 544001 | SCHD | PACK-ISOL | 2018-09-06 | 2019-08-21 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 135851 | Work Order Description - 135851 - PM | PM | 4 | 256581 | SCHD | EQUIP-ISOL | 2018-03-05 | 2019-07-24 | 2019-03-23 | 2019-03-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 135855 | Work Order Description - 135855 - PM | PM | 4 | 482734 | SCHD | EQUIP-ISOL | 2018-09-06 | 2020-01-01 | 2020-03-07 | 2020-03-07 | 2 | INTEGRITY | INSPECTION | 350
2019-03-31 | 136032 | Work Order Description - 136032 - PM | PM | 4 | 183627 | SCHD | PACK-ISOL | 2018-07-06 | 2019-09-05 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 136091 | Work Order Description - 136091 - PM | PM | 4 | 408677 | SCHD | PACK-ISOL | 2018-05-30 | 2019-08-26 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 136108 | Work Order Description - 136108 - PM | PM | 4 | 320682 | SCHD | PACK-ISOL | 2018-01-19 | 2019-09-17 | 2019-08-17 | 2019-08-17 | 2 | DRILLING | DRILLING | 1
2019-03-31 | 136110 | Work Order Description - 136110 - PM | PM | 4 | 477983 | SCHD | PACK-ISOL | 2018-07-18 | 2019-03-11 | 2019-08-17 | 2019-08-17 | 2 | DRILLING | DRILLING | 17.5
2019-03-31 | 136158 | Work Order Description - 136158 - PM | PM | 4 | 403823 | SCHD | NORM-OPS | 2018-02-09 | 2019-05-19 | 2019-04-13 | 2019-04-13 | 2 | OPERATIONS | SAFETY | 18
2019-03-31 | 136435 | Work Order Description - 136435 - PM | PM | 4 | 262750 | SCHD | NORM-OPS | 2019-02-08 | 2020-01-04 | 2020-04-11 | 2020-04-11 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 136504 | Work Order Description - 136504 - PM | PM | 4 | 30650 | SCHD | PACK-ISOL | 2018-03-01 | 2019-02-08 | 2019-03-02 | 2019-03-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 136507 | Work Order Description - 136507 - PM | PM | 4 | 408810 | SCHD | PACK-ISOL | 2018-06-21 | 2019-12-30 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 136554 | Work Order Description - 136554 - PM | PM | 4 | 303724 | SCHD | PACK-ISOL | 2018-09-06 | 2020-01-05 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 136555 | Work Order Description - 136555 - PM | PM | 4 | 303725 | SCHD | PACK-ISOL | 2018-09-06 | 2019-10-05 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 136609 | Work Order Description - 136609 - PM | PM | 4 | 409268 | SCHD | EQUIP-ISOL | 2018-09-06 | 2020-01-06 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 136610 | Work Order Description - 136610 - PM | PM | 4 | 30478 | SCHD | PACK-ISOL | 2018-09-06 | 2019-12-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 136621 | Work Order Description - 136621 - PM | PM | 4 | 409528 | SCHD | PACK-ISOL | 2018-05-30 | 2018-12-24 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 136622 | Work Order Description - 136622 - PM | PM | 4 | 30599 | SCHD | PACK-ISOL | 2018-05-30 | 2019-05-22 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 136623 | Work Order Description - 136623 - PM | PM | 4 | 30600 | SCHD | PACK-ISOL | 2018-05-30 | 2019-04-07 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 136624 | Work Order Description - 136624 - PM | PM | 4 | 408637 | SCHD | PACK-ISOL | 2018-05-30 | 2019-12-30 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 136625 | Work Order Description - 136625 - PM | PM | 4 | 30601 | SCHD | PACK-ISOL | 2018-05-30 | 2019-01-25 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 136626 | Work Order Description - 136626 - PM | PM | 4 | 409529 | SCHD | PACK-ISOL | 2018-05-30 | 2019-12-31 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 136635 | Work Order Description - 136635 - PM | PM | 4 | 408811 | SCHD | PACK-ISOL | 2018-09-06 | 2019-09-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 136646 | Work Order Description - 136646 - PM | PM | 4 | 408676 | SCHD | PACK-ISOL | 2018-05-30 | 2020-01-19 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 136673 | Work Order Description - 136673 - PM | PM | 4 | 543881 | SCHD | PACK-ISOL | 2018-05-30 | 2019-05-08 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 136674 | Work Order Description - 136674 - PM | PM | 4 | 30609 | SCHD | PACK-ISOL | 2018-05-30 | 2019-07-09 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 136675 | Work Order Description - 136675 - PM | PM | 4 | 30610 | SCHD | PACK-ISOL | 2018-05-30 | 2018-12-24 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 136676 | Work Order Description - 136676 - PM | PM | 4 | 543882 | SCHD | PACK-ISOL | 2018-05-30 | 2019-10-22 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 138712 | Work Order Description - 138712 - CM | CM | 1 | 651078 | WSCHD | NORM-OPS | 2018-09-21 | 2019-10-23 | 2019-06-08 | 2019-06-09 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 138724 | Work Order Description - 138724 - BR | BR | 3 | 218083 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-01 | 2019-07-13 | 2019-07-15 | 3 | MAINTENANCE | INSTRUMENTS | 19
2019-03-31 | 138784 | Work Order Description - 138784 - CM | CM | 2 | 33412 | WSCHD | NORM-OPS | 2018-01-26 | 2019-07-23 | 2019-05-18 | 2019-05-22 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 138785 | Work Order Description - 138785 - CM | CM | 3 | 496734 | WSCHD | NORM-OPS | 2018-01-12 | 2019-10-24 | 2019-09-27 | 2019-09-28 | 4 | INTEGRITY | FABRIC | 176
2019-03-31 | 138939 | Work Order Description - 138939 - PRJ | PRJ | 4 | 32589 | SCHD | NORM-OPS | 2018-07-18 | 2019-07-22 | 2019-04-20 | 2019-04-20 | 3 | DRILLING | DRILLING | 28
2019-03-31 | 138942 | Work Order Description - 138942 - BR | BR | 4 | 123004 | WPLAN | NORM-OPS | 2017-10-31 | 2019-10-25 | 2019-08-31 | 2019-09-04 | 4 | MAINTENANCE | MECHANICAL | 89
2019-03-31 | 138958 | Work Order Description - 138958 - BR | BR | 3 | 56411 | WSCHD | TPS | 2017-11-03 | 2019-02-28 | 2020-05-02 | 2020-05-08 | 3 | MAINTENANCE | CONSTRUCTION | 97
2019-03-31 | 138975 | Work Order Description - 138975 - CM | CM | 3 | 375853 | WPLAN | NORM-OPS | 2017-10-31 | 2019-10-26 | 2019-08-10 | 2019-08-15 | 4 | MAINTENANCE | MECHANICAL | 68
2019-03-31 | 139059 | Work Order Description - 139059 - BR | BR | 3 | 360076 | WSCHD | TPS | 2017-11-03 | 2019-03-24 | 2020-05-02 | 2020-05-06 | 3 | MAINTENANCE | CONSTRUCTION | 58
2019-03-31 | 139060 | Work Order Description - 139060 - BR | BR | 3 | 261313 | WSCHD | TPS | 2017-11-03 | 2019-09-28 | 2020-05-02 | 2020-05-08 | 3 | MAINTENANCE | CONSTRUCTION | 81
2019-03-31 | 139061 | Work Order Description - 139061 - BR | BR | 3 | 48004 | WSCHD | TPS | 2017-11-03 | 2019-01-30 | 2020-05-02 | 2020-05-06 | 3 | MAINTENANCE | CONSTRUCTION | 58
2019-03-31 | 139072 | Work Order Description - 139072 - BR | BR | 1 | 552746 | SCHD | NORM-OPS | 2018-11-05 | 2019-10-26 | 2019-08-31 | 2019-09-05 | 4 | MAINTENANCE | DRILLING | 347
2019-03-31 | 139093 | Work Order Description - 139093 - BR | BR | 3 | 308096 | WSCHD | SYS-ISOL | 2017-11-28 | 2019-05-16 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 139098 | Work Order Description - 139098 - CM | CM | 1 | 677432 | WSCHD | NORM-OPS | 2017-10-28 | 2019-10-26 | 2019-04-27 | 2019-04-28 | 4 | INTEGRITY | MECHANICAL | 32
2019-03-31 | 139100 | Work Order Description - 139100 - BR | BR | 1 | 53584 | SCHD | NORM-OPS | 2018-10-29 | 2019-10-26 | 2019-04-27 | 2019-04-28 | 4 | INTEGRITY | MECHANICAL | 32
2019-03-31 | 139101 | Work Order Description - 139101 - CM | CM | 1 | 18446 | WSCHD | NORM-OPS | 2017-10-28 | 2019-10-26 | 2019-08-03 | 2019-08-04 | 4 | INTEGRITY | MECHANICAL | 32
2019-03-31 | 139102 | Work Order Description - 139102 - BR | BR | 3 | 546658 | WSCHD | TPS | 2017-11-14 | 2019-10-26 | 2020-05-02 | 2020-05-07 | 4 | MAINTENANCE | MECHANICAL | 52
2019-03-31 | 139104 | Work Order Description - 139104 - BR | BR | 3 | 666259 | WSCHD | TPS | 2017-11-13 | 2019-10-26 | 2020-05-02 | 2020-05-06 | 4 | MAINTENANCE | MECHANICAL | 49
2019-03-31 | 139106 | Work Order Description - 139106 - BR | BR | 3 | 33681 | WSCHD | TPS | 2017-11-07 | 2019-10-26 | 2020-05-02 | 2020-05-07 | 4 | MAINTENANCE | MECHANICAL | 54
2019-03-31 | 139107 | Work Order Description - 139107 - BR | BR | 3 | 321841 | WSCHD | TPS | 2017-11-07 | 2019-10-26 | 2020-05-02 | 2020-05-07 | 4 | MAINTENANCE | MECHANICAL | 54
2019-03-31 | 139165 | Work Order Description - 139165 - BR | BR | 4 | 575063 | WSCHD | NORM-OPS | 2017-10-28 | 2019-10-27 | 2019-09-21 | 2019-09-21 | 4 | OPERATIONS | OPERATIONS | 1
2019-03-31 | 139203 | Work Order Description - 139203 - CM | CM | 1 | 378846 | SCHD | NORM-OPS | 2018-03-30 | 2019-10-27 | 2019-03-20 | 2019-03-22 | 4 | INTEGRITY | FABRIC | 42
2019-03-31 | 139283 | Work Order Description - 139283 - CM | CM | 4 | 479632 | SCHD | PACK-ISOL | 2018-09-06 | 2019-10-28 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | DRILLING | 28
2019-03-31 | 139313 | Work Order Description - 139313 - BR | BR | 3 | 671632 | WSCHD | PACK-ISOL | 2017-11-05 | 2019-10-28 | 2019-09-28 | 2019-09-30 | 4 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 139400 | Work Order Description - 139400 - BR | BR | 3 | 249290 | WSCHD | NORM-OPS | 2017-12-22 | 2019-06-04 | 2019-04-20 | 2019-04-21 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 139428 | Work Order Description - 139428 - BR | BR | 4 | 313319 | SCHD | SYS-ISOL | 2018-09-06 | 2019-10-29 | 2019-03-30 | 2019-03-30 | 4 | MAINTENANCE | DRILLING | 254
2019-03-31 | 139431 | Work Order Description - 139431 - BR | BR | 3 | 126951 | SCHD | NORM-OPS | 2018-05-18 | 2019-01-14 | 2019-04-13 | 2019-04-17 | 3 | INTEGRITY | INSPECTION | 1
2019-03-31 | 139532 | Work Order Description - 139532 - PM | PM | 4 | 398462 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-08-02 | 2019-04-28 | 2019-04-29 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 139539 | Work Order Description - 139539 - PM | PM | 4 | 98725 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-05-16 | 2019-07-13 | 2019-07-15 | 2 | MAINTENANCE | INSTRUMENTS | 34
2019-03-31 | 139542 | Work Order Description - 139542 - PM | PM | 4 | 376726 | SCHD | NORM-OPS | 2018-06-21 | 2020-01-18 | 2019-03-24 | 2019-03-24 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 139551 | Work Order Description - 139551 - PM | PM | 4 | 98753 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-04-20 | 2019-04-28 | 2019-04-29 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 139552 | Work Order Description - 139552 - PM | PM | 4 | 98781 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-12-04 | 2019-04-28 | 2019-04-29 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 139556 | Work Order Description - 139556 - PM | PM | 4 | 97786 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-11-10 | 2019-07-13 | 2019-07-22 | 2 | MAINTENANCE | INSTRUMENTS | 70
2019-03-31 | 139622 | Work Order Description - 139622 - CM | CM | 3 | 674847 | WSCHD | ON LINE | 2018-06-24 | 2019-08-14 | 2019-06-01 | 2019-06-02 | 3 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 139704 | Work Order Description - 139704 - PSPM | PSPM | 1 | 360506 | WSCHD | EQUIP-ISOL | 2017-11-01 | 2019-12-02 | 2019-10-26 | 2019-10-26 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 139705 | Work Order Description - 139705 - PSPM | PSPM | 1 | 360506 | WSCHD | EQUIP-ISOL | 2017-11-01 | 2019-12-02 | 2019-10-26 | 2019-10-26 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 139706 | Work Order Description - 139706 - PSPM | PSPM | 1 | 53168 | WSCHD | EQUIP-ISOL | 2017-11-01 | 2019-12-02 | 2019-10-26 | 2019-10-26 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 139852 | Work Order Description - 139852 - PM | PM | 4 | 556432 | SCHD | SYS-ISOL | 2018-09-06 | 2019-05-15 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 140339 | Work Order Description - 140339 - PM | PM | 4 | 176648 | SCHD | EQUIP-ISOL | 2018-07-18 | 2019-01-02 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 140340 | Work Order Description - 140340 - PM | PM | 4 | 176899 | SCHD | EQUIP-ISOL | 2018-07-18 | 2019-11-03 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 140345 | Work Order Description - 140345 - PSPM | PSPM | 1 | 487753 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-06-01 | 2019-04-06 | 2019-04-06 | 1 | INTEGRITY | MECHANICAL | 46
2019-03-31 | 140346 | Work Order Description - 140346 - PSPM | PSPM | 1 | 309196 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-06-01 | 2019-04-06 | 2019-04-06 | 1 | INTEGRITY | MECHANICAL | 46
2019-03-31 | 140359 | Work Order Description - 140359 - PM | PM | 4 | 393152 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-12-04 | 2019-05-04 | 2019-05-04 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 140477 | Work Order Description - 140477 - BR | BR | 3 | 137779 | WSCHD | PACK-ISOL | 2018-05-23 | 2019-05-28 | 2019-10-19 | 2019-11-19 | 3 | MAINTENANCE | MECHANICAL | 422
2019-03-31 | 140479 | Work Order Description - 140479 - BR | BR | 1 | 401866 | SCHD | NORM-OPS | 2018-06-19 | 2020-05-21 | 2019-06-01 | 2019-06-06 | 4 | MAINTENANCE | ELECTRICAL | 80
2019-03-31 | 140480 | Work Order Description - 140480 - BR | BR | 4 | 57460 | WPLAN | NORM-OPS | 2018-06-29 | 2020-05-21 | 2020-03-28 | 2020-03-30 | 4 | INTEGRITY | CONSTRUCTION | 36
2019-03-31 | 140488 | Work Order Description - 140488 - CM | CM | 4 | 402269 | SCHD | NORM-OPS | 2019-01-14 | 2020-05-21 | 2020-03-07 | 2020-03-13 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 140493 | Work Order Description - 140493 - BR | BR | 1 | 554141 | WSCHD | SYS-ISOL | 2018-09-23 | 2019-05-23 | 2020-05-02 | 2020-05-06 | 3 | MAINTENANCE | MECHANICAL | 72
2019-03-31 | 140494 | Work Order Description - 140494 - BR | BR | 1 | 554142 | WSCHD | SYS-ISOL | 2018-12-12 | 2019-05-23 | 2020-05-02 | 2020-05-03 | 3 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 140537 | Work Order Description - 140537 - PM | PM | 4 | 362499 | WSCHD | EQUIP-ISOL | 2018-05-24 | 2019-01-08 | 2019-04-27 | 2019-04-29 | 2 | INTEGRITY | ELECTRICAL | 50
2019-03-31 | 140541 | Work Order Description - 140541 - PM | PM | 2 | 33427 | WSCHD | PACK-ISOL | 2018-05-24 | 2019-04-13 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 140677 | Work Order Description - 140677 - BR | BR | 1 | 399582 | WPLAN | SYS-ISOL | 2018-06-15 | 2020-06-13 | 2021-06-05 | 2021-06-06 | 4 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 140709 | Work Order Description - 140709 - BR | BR | 4 | 584465 | SCHD | NORM-OPS | 2018-05-31 | 2020-05-22 | 2019-05-04 | 2019-05-11 | 4 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 140813 | Work Order Description - 140813 - CM | CM | 4 | 315934 | WSCHD | SYS-ISOL | 2019-03-25 | 2020-07-30 | 2020-02-29 | 2020-02-29 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 140817 | Work Order Description - 140817 - BR | BR | 4 | 29560 | SCHD | TPS | 2018-09-06 | 2019-05-25 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 140820 | Work Order Description - 140820 - BR | BR | 4 | 312924 | SCHD | TPS | 2018-09-06 | 2019-05-25 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 140830 | Work Order Description - 140830 - PM | PM | 3 | 375997 | SCHD | PACK-ISOL | 2018-06-21 | 2019-05-26 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 140831 | Work Order Description - 140831 - PM | PM | 3 | 384014 | SCHD | PACK-ISOL | 2018-06-21 | 2019-05-26 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 140836 | Work Order Description - 140836 - PM | PM | 3 | 375796 | SCHD | PACK-ISOL | 2018-06-21 | 2019-05-26 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | ELECTRICAL | 0
2019-03-31 | 140910 | Work Order Description - 140910 - PSPM | PSPM | 1 | 99634 | SCHD | PACK-ISOL | 2019-03-22 | 2019-07-15 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 140945 | Work Order Description - 140945 - BR | BR | 1 | 468613 | WSCHD | NORM-OPS | 2018-06-22 | 2020-05-23 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 140960 | Work Order Description - 140960 - BR | BR | 4 | 316077 | WPLAN | NORM-OPS | 2018-05-31 | 2019-07-05 | 2019-09-28 | 2019-09-28 | 2 | ENGINEERING | CONSTRUCTION | 7
2019-03-31 | 140966 | Work Order Description - 140966 - BR | BR | 4 | 316077 | WPLAN | NORM-OPS | 2018-06-20 | 2019-04-24 | 2019-04-27 | 2019-04-28 | 2 | ENGINEERING | CONSTRUCTION | 47
2019-03-31 | 140977 | Work Order Description - 140977 - CM | CM | 3 | 537093 | SCHD | SYS-ISOL | 2018-10-09 | 2019-10-30 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | MECHANICAL | 46
2019-03-31 | 140985 | Work Order Description - 140985 - PSPM | PSPM | 1 | 652220 | SCHD | PACK-ISOL | 2019-03-29 | 2019-05-01 | 2019-03-30 | 2019-04-05 | 1 | MAINTENANCE | MECHANICAL | 86.5
2019-03-31 | 141072 | Work Order Description - 141072 - BR | BR | 1 | 435987 | WPLAN | TPS | 2018-06-05 | 2019-05-26 | 2019-07-13 | 2019-07-16 | 3 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 141113 | Work Order Description - 141113 - PSPM | PSPM | 4 | 375482 | SCHD | PACK-ISOL | 2018-09-12 | 2019-08-05 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 141258 | Work Order Description - 141258 - CM | CM | 1 | 481746 | WPLAN | NORM-OPS | 2018-05-31 | 2019-05-30 | 2019-09-07 | 2019-09-08 | 3 | INTEGRITY | CONSTRUCTION | 98
2019-03-31 | 141272 | Work Order Description - 141272 - CM | CM | 4 | 57460 | WPLAN | NORM-OPS | 2018-08-06 | 2019-05-30 | 2020-01-25 | 2020-01-30 | 3 | INTEGRITY | FABRIC | 122
2019-03-31 | 141293 | Work Order Description - 141293 - BR | BR | 4 | 95306 | SCHD | NORM-OPS | 2018-09-06 | 2020-05-25 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 141309 | Work Order Description - 141309 - CM | CM | 1 | 57460 | WPLAN | NORM-OPS | 2018-05-31 | 2019-05-30 | 2019-09-07 | 2019-09-08 | 3 | INTEGRITY | CONSTRUCTION | 44
2019-03-31 | 141310 | Work Order Description - 141310 - CM | CM | 4 | 481744 | SCHD | NORM-OPS | 2019-01-25 | 2020-01-08 | 2019-07-10 | 2019-07-15 | 3 | INTEGRITY | FABRIC | 110
2019-03-31 | 141337 | Work Order Description - 141337 - PSPM | PSPM | 1 | 528193 | SCHD | NORM-OPS | 2018-11-20 | 2019-07-01 | 2019-05-04 | 2019-05-14 | 1 | INTEGRITY | INSPECTION | 150
2019-03-31 | 141429 | Work Order Description - 141429 - BR | BR | 3 | 460423 | SCHD | SYS-ISOL | 2018-09-06 | 2019-05-28 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 43
2019-03-31 | 141432 | Work Order Description - 141432 - BR | BR | 3 | 537058 | WMATL | SYS-ISOL | 2018-06-21 | 2019-05-28 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 39
2019-03-31 | 141433 | Work Order Description - 141433 - BR | BR | 3 | 537092 | SCHD | SYS-ISOL | 2018-09-06 | 2019-05-28 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 47
2019-03-31 | 141440 | Work Order Description - 141440 - CM | CM | 1 | 472493 | WPLAN | NORM-OPS | 2018-06-07 | 2019-05-28 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 141443 | Work Order Description - 141443 - CM | CM | 1 | 472493 | WPLAN | NORM-OPS | 2018-06-07 | 2019-05-28 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 141488 | Work Order Description - 141488 - PM | PM | 3 | 128615 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-12-11 | 2019-07-13 | 2019-07-14 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 141494 | Work Order Description - 141494 - PM | PM | 3 | 128615 | SCHD | TPS | 2019-02-08 | 2019-04-25 | 2019-07-13 | 2019-07-14 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 141516 | Work Order Description - 141516 - PSCM | PSCM | 1 | 57460 | WPLAN | NORM-OPS | 2018-06-29 | 2019-09-01 | 2019-05-04 | 2019-05-04 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 141534 | Work Order Description - 141534 - PM | PM | 4 | 595973 | WSCHD | EQUIP-ISOL | 2018-05-29 | 2019-09-23 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 141535 | Work Order Description - 141535 - PM | PM | 4 | 261948 | WSCHD | EQUIP-ISOL | 2018-05-29 | 2020-01-04 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 141536 | Work Order Description - 141536 - PM | PM | 4 | 359218 | WSCHD | NORM-OPS | 2018-05-29 | 2019-06-21 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 141551 | Work Order Description - 141551 - PM | PM | 3 | 99541 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-06-11 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 141553 | Work Order Description - 141553 - PM | PM | 3 | 99928 | SCHD | TPS | 2018-12-27 | 2019-11-04 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 141556 | Work Order Description - 141556 - PM | PM | 3 | 105755 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-04-09 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 141616 | Work Order Description - 141616 - CM | CM | 1 | 54540 | WPLAN | TPS | 2018-06-12 | 2020-05-27 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 141626 | Work Order Description - 141626 - BR | BR | 3 | 671940 | WPLAN | SYS-ISOL | 2018-08-23 | 2020-05-27 | 2019-05-25 | 2019-05-26 | 4 | MAINTENANCE | INSTRUMENTS | 32
2019-03-31 | 141662 | Work Order Description - 141662 - CM | CM | 1 | 57460 | WPLAN | NORM-OPS | 2018-07-21 | 2019-06-25 | 2019-06-01 | 2019-06-01 | 3 | INTEGRITY | FABRIC | 1568
2019-03-31 | 141675 | Work Order Description - 141675 - PM | PM | 4 | 18972 | WSCHD | EQUIP-ISOL | 2018-05-30 | 2019-01-26 | 2022-12-31 | 2023-01-02 | 2 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 141676 | Work Order Description - 141676 - PM | PM | 4 | 355546 | WSCHD | EQUIP-ISOL | 2018-05-30 | 2019-07-24 | 2022-12-31 | 2023-01-02 | 2 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 141677 | Work Order Description - 141677 - PM | PM | 4 | 314186 | WSCHD | NORM-OPS | 2018-05-30 | 2020-01-15 | 2022-12-31 | 2022-12-31 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 141971 | Work Order Description - 141971 - CM | CM | 4 | 655528 | SCHD | ON LINE | 2018-11-02 | 2020-05-29 | 2019-09-01 | 2019-09-06 | 4 | INTEGRITY | CONSTRUCTION | 72
2019-03-31 | 141973 | Work Order Description - 141973 - CM | CM | 4 | 227759 | WPLAN | NORM-OPS | 2018-06-21 | 2020-05-29 | 2019-08-03 | 2019-08-04 | 4 | OPERATIONS | MECHANICAL | 16
2019-03-31 | 142009 | Work Order Description - 142009 - CM | CM | 1 | 484809 | WSCHD | NORM-OPS | 2018-06-01 | 2020-05-29 | 2019-04-27 | 2019-04-28 | 4 | INTEGRITY | CONSTRUCTION | 140
2019-03-31 | 142047 | Work Order Description - 142047 - PM | PM | 4 | 78631 | SCHD | NORM-OPS | 2018-06-21 | 2019-12-16 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 142101 | Work Order Description - 142101 - PSPM | PSPM | 1 | 357630 | WSCHD | PACK-ISOL | 2018-06-01 | 2019-07-01 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 142103 | Work Order Description - 142103 - PSPM | PSPM | 1 | 653332 | WSCHD | PACK-ISOL | 2018-06-01 | 2019-07-01 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 142107 | Work Order Description - 142107 - PSPM | PSPM | 1 | 357633 | WSCHD | PACK-ISOL | 2018-06-01 | 2019-07-01 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 142209 | Work Order Description - 142209 - PM | PM | 2 | 321218 | WSCHD | PACK-ISOL | 2018-06-02 | 2019-01-11 | 2019-04-13 | 2019-04-19 | 1 | MAINTENANCE | MECHANICAL | 86
2019-03-31 | 142217 | Work Order Description - 142217 - PSPM | PSPM | 1 | 361210 | WSCHD | TPS | 2018-12-27 | 2020-09-01 | 2020-05-02 | 2020-05-03 | 1 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 142220 | Work Order Description - 142220 - PSPM | PSPM | 1 | 409873 | SCHD | EQUIP-ISOL | 2019-03-21 | 2019-07-01 | 2019-04-24 | 2019-04-24 | 1 | INTEGRITY | FABRIC | 52
2019-03-31 | 142223 | Work Order Description - 142223 - PSPM | PSPM | 1 | 363664 | WSCHD | SYS-ISOL | 2018-07-27 | 2019-10-01 | 2019-04-27 | 2019-04-29 | 1 | INTEGRITY | INSPECTION | 3
2019-03-31 | 142249 | Work Order Description - 142249 - PM | PM | 4 | 663490 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-03-30 | 2019-07-13 | 2019-07-13 | 4 | INTEGRITY | INSTRUMENTS | 3
2019-03-31 | 142250 | Work Order Description - 142250 - PM | PM | 4 | 663490 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-01-09 | 2019-07-13 | 2019-07-13 | 3 | INTEGRITY | INSTRUMENTS | 3
2019-03-31 | 142256 | Work Order Description - 142256 - PSPM | PSPM | 1 | 237446 | SCHD | NORM-OPS | 2018-11-02 | 2019-07-01 | 2019-05-04 | 2019-05-04 | 2 | INTEGRITY | INSPECTION | 2
2019-03-31 | 142257 | Work Order Description - 142257 - PSPM | PSPM | 1 | 237446 | SCHD | TPS | 2018-12-27 | 2019-07-01 | 2019-05-04 | 2019-06-17 | 2 | INTEGRITY | INSPECTION | 945
2019-03-31 | 142397 | Work Order Description - 142397 - BR | BR | 2 | 95535 | SCHD | NORM-OPS | 2018-11-05 | 2020-05-31 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | MECHANICAL | 0
2019-03-31 | 142502 | Work Order Description - 142502 - PM | PM | 4 | 656245 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-09-29 | 2019-04-13 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 142508 | Work Order Description - 142508 - PM | PM | 2 | 107668 | SCHD | NORM-OPS | 2018-09-06 | 2018-12-14 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | SUBSEA | 0
2019-03-31 | 142511 | Work Order Description - 142511 - PM | PM | 2 | 108098 | SCHD | NORM-OPS | 2018-09-06 | 2019-01-11 | 2019-08-03 | 2019-08-03 | 1 | INTEGRITY | SUBSEA | 0
2019-03-31 | 142517 | Work Order Description - 142517 - PSPM | PSPM | 1 | 501175 | SCHD | NORM-OPS | 2018-11-05 | 2019-04-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 142554 | Work Order Description - 142554 - PM | PM | 4 | 306721 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-09-27 | 2019-07-06 | 2019-07-06 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 142555 | Work Order Description - 142555 - PM | PM | 4 | 402012 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-09-27 | 2019-07-06 | 2019-07-06 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 142557 | Work Order Description - 142557 - PSPM | PSPM | 1 | 176659 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-12-30 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 142566 | Work Order Description - 142566 - PM | PM | 4 | 487505 | SCHD | TPS | 2019-03-19 | 2019-07-06 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 46
2019-03-31 | 142609 | Work Order Description - 142609 - PM | PM | 4 | 392972 | SCHD | NORM-OPS | 2018-06-21 | 2019-11-10 | 2019-03-30 | 2019-03-30 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 142629 | Work Order Description - 142629 - PM | PM | 2 | 113395 | SCHD | NORM-OPS | 2018-06-21 | 2019-09-19 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | SUBSEA | 4
2019-03-31 | 142630 | Work Order Description - 142630 - PSPM | PSPM | 1 | 125644 | SCHD | NORM-OPS | 2018-11-08 | 2019-11-01 | 2019-08-31 | 2019-09-01 | 2 | INTEGRITY | INSPECTION | 8
2019-03-31 | 142635 | Work Order Description - 142635 - PSPM | PSPM | 1 | 128562 | SCHD | NORM-OPS | 2018-11-19 | 2020-11-01 | 2019-08-31 | 2019-09-01 | 1 | INTEGRITY | INSPECTION | 8
2019-03-31 | 142636 | Work Order Description - 142636 - PSPM | PSPM | 1 | 435781 | SCHD | NORM-OPS | 2018-11-20 | 2020-04-17 | 2019-08-31 | 2019-09-01 | 1 | INTEGRITY | INSPECTION | 8
2019-03-31 | 142640 | Work Order Description - 142640 - PM | PM | 4 | 655946 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-09-27 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 142666 | Work Order Description - 142666 - PM | PM | 4 | 80472 | SCHD | NORM-OPS | 2018-06-21 | 2019-09-11 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 142667 | Work Order Description - 142667 - PM | PM | 4 | 266593 | SCHD | NORM-OPS | 2018-06-21 | 2019-06-28 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 143477 | Work Order Description - 143477 - PSCM | PSCM | 2 | 671828 | SCHD | PACK-ISOL | 2018-08-30 | 2020-06-01 | 2019-04-06 | 2019-04-08 | 4 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 143481 | Work Order Description - 143481 - BR | BR | 1 | 326836 | WPLAN | SYS-ISOL | 2018-06-07 | 2019-06-03 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 143505 | Work Order Description - 143505 - PSCM | PSCM | 1 | 678463 | SCHD | PACK-ISOL | 2018-10-29 | 2020-06-01 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 143518 | Work Order Description - 143518 - PM | PM | 4 | 51505 | WSCHD | NORM-OPS | 2018-06-04 | 2019-10-01 | 2020-12-26 | 2020-12-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 143527 | Work Order Description - 143527 - PM | PM | 4 | 674222 | SCHD | EQUIP-ISOL | 2018-11-14 | 2019-10-02 | 2019-04-27 | 2019-04-28 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 143548 | Work Order Description - 143548 - PM | PM | 4 | 487506 | SCHD | TPS | 2019-03-19 | 2020-01-08 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 88
2019-03-31 | 143603 | Work Order Description - 143603 - PSCM | PSCM | 4 | 503331 | WMATL | PACK-ISOL | 2018-07-06 | 2019-02-10 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 41
2019-03-31 | 143615 | Work Order Description - 143615 - CM | CM | 4 | 479613 | SCHD | PACK-ISOL | 2018-12-05 | 2019-04-09 | 2019-09-14 | 2019-09-14 | 3 | MAINTENANCE | DRILLING | 35
2019-03-31 | 143617 | Work Order Description - 143617 - CM | CM | 4 | 403979 | SCHD | NORM-OPS | 2018-12-05 | 2018-12-02 | 2019-09-14 | 2019-09-14 | 3 | MAINTENANCE | DRILLING | 300
2019-03-31 | 143618 | Work Order Description - 143618 - CM | CM | 4 | 479679 | SCHD | NORM-OPS | 2018-12-05 | 2019-09-20 | 2019-09-14 | 2019-09-14 | 3 | MAINTENANCE | DRILLING | 300
2019-03-31 | 143619 | Work Order Description - 143619 - CM | CM | 4 | 216579 | SCHD | NORM-OPS | 2018-12-05 | 2019-02-21 | 2019-09-14 | 2019-09-14 | 3 | MAINTENANCE | DRILLING | 300
2019-03-31 | 143621 | Work Order Description - 143621 - CM | CM | 4 | 479645 | SCHD | NORM-OPS | 2018-07-18 | 2019-10-21 | 2019-09-14 | 2019-09-15 | 3 | MAINTENANCE | ELECTRICAL | 300
2019-03-31 | 143623 | Work Order Description - 143623 - CM | CM | 4 | 552714 | SCHD | NORM-OPS | 2018-07-18 | 2019-10-28 | 2019-09-14 | 2019-09-16 | 3 | MAINTENANCE | ELECTRICAL | 150
2019-03-31 | 143625 | Work Order Description - 143625 - CM | CM | 4 | 479375 | SCHD | NORM-OPS | 2018-12-05 | 2019-06-16 | 2019-09-14 | 2019-09-14 | 3 | MAINTENANCE | DRILLING | 300
2019-03-31 | 143628 | Work Order Description - 143628 - CM | CM | 4 | 243591 | SCHD | NORM-OPS | 2018-12-05 | 2019-01-16 | 2019-09-14 | 2019-09-14 | 3 | MAINTENANCE | DRILLING | 300
2019-03-31 | 143740 | Work Order Description - 143740 - PM | PM | 4 | 188477 | SCHD | TPS | 2019-03-23 | 2020-01-09 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 50
2019-03-31 | 143749 | Work Order Description - 143749 - PM | PM | 4 | 124459 | SCHD | NORM-OPS | 2018-06-21 | 2020-01-01 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 143764 | Work Order Description - 143764 - PM | PM | 4 | 78302 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-02-03 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 143845 | Work Order Description - 143845 - BR | BR | 3 | 556356 | SCHD | SYS-ISOL | 2018-06-21 | 2019-06-05 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 143850 | Work Order Description - 143850 - CM | CM | 4 | 72765 | SCHD | NORM-OPS | 2018-06-29 | 2020-06-03 | 2019-09-30 | 2019-10-17 | 4 | INTEGRITY | CONSTRUCTION | 240
2019-03-31 | 143925 | Work Order Description - 143925 - PSPM | PSPM | 1 | 652220 | WSCHD | NORM-OPS | 2018-06-06 | 2019-11-08 | 2019-05-04 | 2019-05-05 | 1 | MAINTENANCE | SERVICES | 12
2019-03-31 | 143926 | Work Order Description - 143926 - PM | PM | 2 | 321199 | SCHD | NORM-OPS | 2018-10-29 | 2019-07-19 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 143939 | Work Order Description - 143939 - PM | PM | 4 | 396217 | SCHD | EQUIP-ISOL | 2018-09-19 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 143941 | Work Order Description - 143941 - PM | PM | 3 | 440673 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-08-21 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 144104 | Work Order Description - 144104 - PM | PM | 4 | 308893 | WSCHD | NORM-OPS | 2018-06-07 | 2019-09-05 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 144214 | Work Order Description - 144214 - BR | BR | 3 | 463176 | SCHD | TPS | 2018-11-05 | 2019-06-15 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 49
2019-03-31 | 144223 | Work Order Description - 144223 - PSCM | PSCM | 4 | 540396 | SCHD | TPS | 2018-08-14 | 2020-06-05 | 2020-05-02 | 2020-05-05 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 144225 | Work Order Description - 144225 - PM | PM | 4 | 303804 | SCHD | PACK-ISOL | 2018-06-08 | 2018-12-05 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 144226 | Work Order Description - 144226 - PM | PM | 4 | 401506 | SCHD | PACK-ISOL | 2018-06-08 | 2019-11-04 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 144279 | Work Order Description - 144279 - PSPM | PSPM | 4 | 247295 | SCHD | NORM-OPS | 2019-01-24 | 2019-05-02 | 2019-04-05 | 2019-04-15 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 144280 | Work Order Description - 144280 - PSPM | PSPM | 4 | 361166 | WSCHD | NORM-OPS | 2018-10-29 | 2019-07-01 | 2019-04-27 | 2019-04-30 | 1 | INTEGRITY | INSPECTION | 53
2019-03-31 | 144284 | Work Order Description - 144284 - PM | PM | 4 | 247295 | SCHD | NORM-OPS | 2019-01-24 | 2019-04-23 | 2019-04-05 | 2019-04-15 | 2 | INTEGRITY | INSPECTION | 1
2019-03-31 | 144330 | Work Order Description - 144330 - PSPM | PSPM | 1 | 399424 | WSCHD | SUBSYS-ISOL | 2018-06-08 | 2019-09-16 | 2021-03-06 | 2021-03-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 144331 | Work Order Description - 144331 - PSPM | PSPM | 1 | 653289 | WSCHD | SUBSYS-ISOL | 2018-06-08 | 2019-01-13 | 2021-03-06 | 2021-03-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 144334 | Work Order Description - 144334 - PSPM | PSPM | 1 | 357587 | SCHD | SUBSYS-ISOL | 2018-09-01 | 2019-08-04 | 2021-03-06 | 2021-03-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 144335 | Work Order Description - 144335 - PSPM | PSPM | 1 | 653290 | WSCHD | SUBSYS-ISOL | 2018-09-01 | 2020-01-01 | 2021-03-06 | 2021-03-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 144336 | Work Order Description - 144336 - PSPM | PSPM | 1 | 357586 | WSCHD | SUBSYS-ISOL | 2018-09-01 | 2020-01-01 | 2021-03-06 | 2021-03-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 144483 | Work Order Description - 144483 - CM | CM | 3 | 450985 | SCHD | SYS-ISOL | 2019-02-13 | 2019-06-27 | 2019-07-13 | 2019-07-15 | 2 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 144490 | Work Order Description - 144490 - PSCM | PSCM | 1 | 460840 | SCHD | TPS | 2018-11-05 | 2020-06-19 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 41
2019-03-31 | 144606 | Work Order Description - 144606 - PSCM | PSCM | 1 | 537908 | SCHD | PACK-ISOL | 2018-12-05 | 2019-08-16 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 144647 | Work Order Description - 144647 - PM | PM | 3 | 481323 | SCHD | SUBSYS-ISOL | 2018-11-27 | 2019-04-28 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 144663 | Work Order Description - 144663 - PM | PM | 4 | 361470 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-05-18 | 2021-03-06 | 2021-03-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 144668 | Work Order Description - 144668 - PM | PM | 4 | 595915 | WSCHD | TPS | 2018-06-10 | 2019-12-17 | 2019-07-20 | 2019-07-22 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 144673 | Work Order Description - 144673 - PM | PM | 4 | 355547 | WSCHD | EQUIP-ISOL | 2018-06-10 | 2019-06-07 | 2022-12-31 | 2023-01-02 | 2 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 144674 | Work Order Description - 144674 - PM | PM | 4 | 541035 | WSCHD | NORM-OPS | 2018-06-10 | 2020-01-04 | 2022-12-31 | 2022-12-31 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 144683 | Work Order Description - 144683 - PM | PM | 4 | 323483 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-12-28 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 144684 | Work Order Description - 144684 - PM | PM | 4 | 245880 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-12-02 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 144685 | Work Order Description - 144685 - PM | PM | 4 | 245881 | SCHD | EQUIP-ISOL | 2018-10-29 | 2020-01-09 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 144700 | Work Order Description - 144700 - PM | PM | 4 | 665034 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-02-01 | 2019-05-04 | 2019-05-04 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 144790 | Work Order Description - 144790 - CM | CM | 4 | 670509 | WPLAN | ON LINE | 2018-06-21 | 2019-06-10 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 144792 | Work Order Description - 144792 - BR | BR | 3 | 408313 | WPLAN | PACK-ISOL | 2018-09-10 | 2020-01-12 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 144797 | Work Order Description - 144797 - CM | CM | 1 | 98396 | WPLAN | TPS | 2018-06-20 | 2020-06-08 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 144815 | Work Order Description - 144815 - PM | PM | 4 | 314162 | WSCHD | NORM-OPS | 2018-06-11 | 2019-11-14 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 144880 | Work Order Description - 144880 - PSPM | PSPM | 1 | 363664 | WSCHD | SYS-ISOL | 2018-06-11 | 2021-10-31 | 2021-09-30 | 2021-09-30 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 144882 | Work Order Description - 144882 - PSPM | PSPM | 1 | 676360 | WSCHD | SYS-ISOL | 2018-06-11 | 2020-10-31 | 2020-09-30 | 2020-09-30 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 144891 | Work Order Description - 144891 - CM | CM | 3 | 58001 | WPLAN | ON LINE | 2018-06-12 | 2019-06-11 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 144895 | Work Order Description - 144895 - CM | CM | 3 | 58179 | WPLAN | ON LINE | 2018-06-12 | 2019-06-11 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 144906 | Work Order Description - 144906 - CM | CM | 4 | 263140 | SCHD | NORM-OPS | 2018-07-18 | 2020-06-09 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 144999 | Work Order Description - 144999 - PM | PM | 3 | 652160 | WSCHD | PACK-ISOL | 2018-06-12 | 2019-10-06 | 2019-04-27 | 2019-04-28 | 2 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 145000 | Work Order Description - 145000 - PM | PM | 3 | 656235 | WSCHD | PACK-ISOL | 2018-06-12 | 2020-01-17 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 145019 | Work Order Description - 145019 - PM | PM | 4 | 266220 | SCHD | PACK-ISOL | 2018-06-21 | 2019-11-29 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 145020 | Work Order Description - 145020 - PM | PM | 4 | 266242 | SCHD | PACK-ISOL | 2018-06-21 | 2019-05-18 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 145021 | Work Order Description - 145021 - PM | PM | 4 | 266243 | SCHD | PACK-ISOL | 2018-06-21 | 2019-04-10 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 145022 | Work Order Description - 145022 - PM | PM | 4 | 266246 | SCHD | PACK-ISOL | 2018-06-21 | 2019-01-17 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 145024 | Work Order Description - 145024 - PM | PM | 4 | 443413 | SCHD | PACK-ISOL | 2018-06-21 | 2019-10-06 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 145025 | Work Order Description - 145025 - PM | PM | 4 | 656001 | SCHD | PACK-ISOL | 2018-06-21 | 2019-10-06 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 145029 | Work Order Description - 145029 - PM | PM | 4 | 443409 | SCHD | PACK-ISOL | 2018-06-21 | 2019-10-06 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 145183 | Work Order Description - 145183 - CM | CM | 4 | 484917 | WPLAN | NORM-OPS | 2018-06-13 | 2019-06-12 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 145188 | Work Order Description - 145188 - CM | CM | 4 | 652968 | WPLAN | NORM-OPS | 2018-06-13 | 2020-06-10 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 145208 | Work Order Description - 145208 - CM | CM | 4 | 309603 | SCHD | PACK-ISOL | 2018-09-06 | 2020-06-10 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | MECHANICAL | 45
2019-03-31 | 145289 | Work Order Description - 145289 - CM | CM | 2 | 670511 | WPLAN | PACK-ISOL | 2018-06-21 | 2019-06-13 | 2019-04-14 | 2019-04-18 | 3 | MAINTENANCE | MECHANICAL | 59
2019-03-31 | 145441 | Work Order Description - 145441 - CM | CM | 4 | 126059 | SCHD | NORM-OPS | 2018-07-03 | 2020-06-12 | 2019-04-22 | 2019-04-24 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 145447 | Work Order Description - 145447 - CM | CM | 4 | 34116 | WPLAN | NORM-OPS | 2018-06-18 | 2019-06-14 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | CONSTRUCTION | 4
2019-03-31 | 145449 | Work Order Description - 145449 - CM | CM | 4 | 34117 | WPLAN | NORM-OPS | 2018-06-18 | 2019-06-14 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | CONSTRUCTION | 4
2019-03-31 | 145470 | Work Order Description - 145470 - CM | CM | 3 | 58001 | WPLAN | TPS | 2018-06-15 | 2020-06-12 | 2020-05-02 | 2020-05-06 | 4 | MAINTENANCE | INSTRUMENTS | 25
2019-03-31 | 145485 | Work Order Description - 145485 - PM | PM | 4 | 321177 | SCHD | PACK-ISOL | 2018-10-29 | 2019-11-07 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 145492 | Work Order Description - 145492 - PSPM | PSPM | 1 | 260972 | WSCHD | TPS | 2018-06-15 | 2020-09-01 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 145581 | Work Order Description - 145581 - BR | BR | 3 | 186650 | SCHD | PACK-ISOL | 2018-09-06 | 2019-08-21 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 145604 | Work Order Description - 145604 - PM | PM | 4 | 309936 | SCHD | PACK-ISOL | 2018-09-06 | 2019-02-24 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 10
2019-03-31 | 145705 | Work Order Description - 145705 - BR | BR | 2 | 572237 | WSCHD | NORM-OPS | 2018-11-17 | 2020-06-14 | 2019-04-13 | 2019-04-19 | 4 | INTEGRITY | FABRIC | 48
2019-03-31 | 145707 | Work Order Description - 145707 - CM | CM | 1 | 57460 | WPLAN | NORM-OPS | 2018-06-18 | 2019-06-16 | 2019-11-30 | 2019-11-30 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 145749 | Work Order Description - 145749 - PM | PM | 4 | 547502 | WSCHD | SUBSYS-ISOL | 2018-06-17 | 2019-04-10 | 2019-05-19 | 2019-05-20 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 145759 | Work Order Description - 145759 - PM | PM | 4 | 399771 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-03-16 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 145760 | Work Order Description - 145760 - PM | PM | 4 | 363674 | SCHD | PACK-ISOL | 2018-10-29 | 2019-03-22 | 2019-04-06 | 2019-04-06 | 1 | INTEGRITY | MECHANICAL | 15
2019-03-31 | 145761 | Work Order Description - 145761 - PM | PM | 4 | 56429 | SCHD | PACK-ISOL | 2018-10-29 | 2019-08-10 | 2019-04-06 | 2019-04-06 | 1 | INTEGRITY | MECHANICAL | 15
2019-03-31 | 145762 | Work Order Description - 145762 - PM | PM | 4 | 363675 | SCHD | PACK-ISOL | 2018-10-29 | 2019-09-30 | 2019-04-06 | 2019-04-06 | 1 | INTEGRITY | MECHANICAL | 15
2019-03-31 | 146114 | Work Order Description - 146114 - BR | BR | 4 | 126108 | SCHD | NORM-OPS | 2018-09-12 | 2020-06-15 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 146115 | Work Order Description - 146115 - CM | CM | 4 | 227792 | SCHD | NORM-OPS | 2018-09-12 | 2020-06-15 | 2019-08-24 | 2019-08-25 | 4 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 146129 | Work Order Description - 146129 - CM | CM | 1 | 445789 | SCHD | PACK-ISOL | 2018-07-04 | 2019-06-20 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 146133 | Work Order Description - 146133 - BR | BR | 1 | 215448 | WSCHD | NORM-OPS | 2018-09-28 | 2020-06-15 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 146140 | Work Order Description - 146140 - CM | CM | 4 | 494030 | SCHD | PACK-ISOL | 2018-09-06 | 2019-06-20 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 68
2019-03-31 | 146144 | Work Order Description - 146144 - CM | CM | 4 | 482305 | SCHD | PACK-ISOL | 2018-09-06 | 2019-06-20 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 49
2019-03-31 | 146145 | Work Order Description - 146145 - CM | CM | 3 | 215897 | WPLAN | NORM-OPS | 2018-06-20 | 2019-06-17 | 2019-06-01 | 2019-06-02 | 3 | INTEGRITY | FABRIC | 25
2019-03-31 | 146149 | Work Order Description - 146149 - CM | CM | 4 | 482301 | SCHD | PACK-ISOL | 2018-09-06 | 2019-06-20 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 50
2019-03-31 | 146150 | Work Order Description - 146150 - CM | CM | 3 | 482303 | SCHD | PACK-ISOL | 2018-09-06 | 2020-01-11 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 50
2019-03-31 | 146153 | Work Order Description - 146153 - CM | CM | 4 | 401741 | SCHD | PACK-ISOL | 2018-09-06 | 2019-06-20 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 50
2019-03-31 | 146155 | Work Order Description - 146155 - CM | CM | 4 | 494026 | SCHD | PACK-ISOL | 2018-09-06 | 2019-06-20 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 55
2019-03-31 | 146156 | Work Order Description - 146156 - CM | CM | 4 | 401736 | SCHD | PACK-ISOL | 2018-09-06 | 2019-06-20 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 43
2019-03-31 | 146207 | Work Order Description - 146207 - BR | BR | 3 | 126499 | SCHD | SYS-ISOL | 2018-08-17 | 2019-06-18 | 2019-07-13 | 2019-07-14 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 146209 | Work Order Description - 146209 - BR | BR | 4 | 531937 | WSCHD | NORM-OPS | 2018-06-19 | 2020-06-16 | 2019-04-13 | 2019-04-14 | 4 | INTEGRITY | INSTRUMENTS | 6
2019-03-31 | 146211 | Work Order Description - 146211 - CM | CM | 1 | 678463 | WPLAN | PACK-ISOL | 2018-11-02 | 2019-06-18 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 146239 | Work Order Description - 146239 - CM | CM | 3 | 215897 | SCHD | NORM-OPS | 2018-09-06 | 2020-06-16 | 2020-02-01 | 2020-02-01 | 4 | OPERATIONS | OPERATIONS | 84
2019-03-31 | 146274 | Work Order Description - 146274 - BR | BR | 1 | 668311 | SCHD | NORM-OPS | 2019-02-13 | 2020-06-16 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | INSTRUMENTS | 23
2019-03-31 | 146290 | Work Order Description - 146290 - CM | CM | 3 | 59119 | SCHD | NORM-OPS | 2018-12-20 | 2019-12-18 | 2019-06-18 | 2019-06-18 | 3 | INTEGRITY | FABRIC | 12
2019-03-31 | 146302 | Work Order Description - 146302 - PM | PM | 4 | 18972 | WSCHD | NORM-OPS | 2018-06-19 | 2019-02-17 | 2022-12-31 | 2022-12-31 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 146303 | Work Order Description - 146303 - PM | PM | 4 | 355546 | WSCHD | NORM-OPS | 2018-06-19 | 2019-12-18 | 2022-12-31 | 2022-12-31 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 146304 | Work Order Description - 146304 - PM | PM | 4 | 18973 | WSCHD | NORM-OPS | 2018-06-19 | 2019-08-08 | 2022-12-31 | 2022-12-31 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 146305 | Work Order Description - 146305 - PM | PM | 4 | 355547 | WSCHD | NORM-OPS | 2018-06-19 | 2019-06-20 | 2022-12-31 | 2022-12-31 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 146306 | Work Order Description - 146306 - PM | PM | 4 | 18985 | WSCHD | NORM-OPS | 2018-06-19 | 2019-03-14 | 2022-12-31 | 2022-12-31 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 146307 | Work Order Description - 146307 - PM | PM | 4 | 355548 | WSCHD | NORM-OPS | 2018-06-19 | 2019-07-05 | 2022-12-31 | 2022-12-31 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 146322 | Work Order Description - 146322 - PM | PM | 4 | 124133 | SCHD | EQUIP-ISOL | 2018-06-21 | 2019-01-29 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 146742 | Work Order Description - 146742 - PSCM | PSCM | 1 | 95412 | SCHD | TPS | 2019-03-28 | 2019-06-21 | 2019-07-13 | 2019-07-15 | 3 | MAINTENANCE | INSTRUMENTS | 35
2019-03-31 | 146745 | Work Order Description - 146745 - CM | CM | 4 | 129030 | INPRG | NORM-OPS | 2018-08-29 | 2019-02-25 | 2019-06-08 | 2019-06-15 | 3 | DRILLING | CONSTRUCTION | 300
2019-03-31 | 146980 | Work Order Description - 146980 - CM | CM | 4 | 226434 | WSCHD | NORM-OPS | 2018-06-24 | 2019-06-22 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 146981 | Work Order Description - 146981 - CM | CM | 4 | 328001 | WSCHD | NORM-OPS | 2018-06-24 | 2019-06-22 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 146984 | Work Order Description - 146984 - PSCM | PSCM | 4 | 482270 | SCHD | NORM-OPS | 2018-10-07 | 2019-09-23 | 2019-05-11 | 2019-05-12 | 2 | MAINTENANCE | INSTRUMENTS | 11
2019-03-31 | 147005 | Work Order Description - 147005 - BR | BR | 3 | 105957 | SCHD | NORM-OPS | 2019-02-13 | 2019-11-17 | 2019-04-21 | 2019-04-21 | 3 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 147019 | Work Order Description - 147019 - PSPM | PSPM | 1 | 57149 | SCHD | PACK-ISOL | 2018-10-08 | 2019-03-25 | 2019-08-03 | 2019-08-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 147020 | Work Order Description - 147020 - PSPM | PSPM | 1 | 53297 | WSCHD | PACK-ISOL | 2018-10-08 | 2020-01-01 | 2019-08-03 | 2019-08-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 147021 | Work Order Description - 147021 - PSPM | PSPM | 1 | 54513 | WSCHD | PACK-ISOL | 2018-10-08 | 2020-01-01 | 2019-08-03 | 2019-08-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 147022 | Work Order Description - 147022 - PSPM | PSPM | 1 | 360559 | WSCHD | PACK-ISOL | 2018-10-08 | 2020-01-01 | 2019-08-03 | 2019-08-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 147023 | Work Order Description - 147023 - PSPM | PSPM | 1 | 53301 | WSCHD | PACK-ISOL | 2018-10-08 | 2020-01-01 | 2019-08-03 | 2019-08-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 147024 | Work Order Description - 147024 - PSPM | PSPM | 1 | 53327 | SCHD | PACK-ISOL | 2018-10-08 | 2019-07-19 | 2019-08-03 | 2019-08-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 147027 | Work Order Description - 147027 - PSPM | PSPM | 1 | 54514 | WSCHD | PACK-ISOL | 2018-10-08 | 2020-01-01 | 2019-08-03 | 2019-08-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 147028 | Work Order Description - 147028 - PSPM | PSPM | 1 | 54515 | WSCHD | PACK-ISOL | 2018-10-08 | 2020-01-01 | 2019-08-03 | 2019-08-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 147029 | Work Order Description - 147029 - PSPM | PSPM | 1 | 409691 | WSCHD | PACK-ISOL | 2018-10-08 | 2020-01-01 | 2019-08-03 | 2019-08-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 147030 | Work Order Description - 147030 - PSPM | PSPM | 1 | 54990 | WSCHD | PACK-ISOL | 2018-10-21 | 2020-01-01 | 2019-08-03 | 2019-08-03 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 147031 | Work Order Description - 147031 - PM | PM | 4 | 55009 | SCHD | PACK-ISOL | 2018-10-21 | 2019-04-20 | 2019-08-03 | 2019-08-03 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 147055 | Work Order Description - 147055 - PM | PM | 4 | 376291 | SCHD | EQUIP-ISOL | 2018-07-03 | 2019-10-22 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 147156 | Work Order Description - 147156 - CM | CM | 2 | 13126 | SCHD | PACK-ISOL | 2018-10-09 | 2019-11-06 | 2019-05-04 | 2019-05-05 | 2 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 147172 | Work Order Description - 147172 - CM | CM | 4 | 226434 | WSCHD | NORM-OPS | 2018-06-24 | 2020-06-21 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 147203 | Work Order Description - 147203 - BR | BR | 4 | 360068 | WPLAN | NORM-OPS | 2018-06-24 | 2019-06-23 | 2021-06-26 | 2021-06-27 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 147204 | Work Order Description - 147204 - CM | CM | 4 | 360067 | WPLAN | NORM-OPS | 2018-06-24 | 2019-06-23 | 2021-06-26 | 2021-06-27 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 147207 | Work Order Description - 147207 - CM | CM | 4 | 556469 | WMATL | NORM-OPS | 2018-10-26 | 2019-09-03 | 2019-08-03 | 2019-08-03 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 147209 | Work Order Description - 147209 - CM | CM | 4 | 556469 | SCHD | NORM-OPS | 2018-09-06 | 2020-06-21 | 2019-06-15 | 2019-06-15 | 4 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 147212 | Work Order Description - 147212 - BR | BR | 1 | 272340 | WSCHD | NORM-OPS | 2018-08-08 | 2020-06-21 | 2019-06-08 | 2019-06-08 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 147346 | Work Order Description - 147346 - CM | CM | 3 | 449592 | SCHD | TPS | 2018-09-06 | 2019-06-24 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 147347 | Work Order Description - 147347 - CM | CM | 4 | 448597 | INPRG | NORM-OPS | 2018-07-22 | 2019-03-11 | 2019-09-01 | 2019-09-15 | 3 | INTEGRITY | CONSTRUCTION | 10
2019-03-31 | 147354 | Work Order Description - 147354 - CM | CM | 3 | 184485 | SCHD | TPS | 2018-09-06 | 2019-06-24 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 147359 | Work Order Description - 147359 - CM | CM | 3 | 403007 | SCHD | PACK-ISOL | 2018-09-06 | 2019-06-24 | 2019-05-18 | 2019-05-19 | 3 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 147360 | Work Order Description - 147360 - CM | CM | 3 | 306618 | SCHD | NORM-OPS | 2018-09-06 | 2019-06-24 | 2019-05-18 | 2019-05-19 | 3 | MAINTENANCE | ELECTRICAL | 28
2019-03-31 | 147372 | Work Order Description - 147372 - BR | BR | 1 | 308074 | WPLAN | SYS-ISOL | 2018-06-28 | 2019-08-01 | 2019-05-25 | 2019-05-28 | 3 | MAINTENANCE | INSTRUMENTS | 53
2019-03-31 | 147373 | Work Order Description - 147373 - BR | BR | 1 | 57133 | WPLAN | SYS-ISOL | 2018-06-28 | 2020-06-22 | 2019-05-25 | 2019-05-28 | 4 | MAINTENANCE | INSTRUMENTS | 53
2019-03-31 | 147384 | Work Order Description - 147384 - BR | BR | 4 | 359395 | WPLAN | NORM-OPS | 2018-06-27 | 2020-06-23 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 147409 | Work Order Description - 147409 - PSPM | PSPM | 1 | 248340 | WSCHD | EQUIP-ISOL | 2018-06-25 | 2020-01-01 | 2019-09-07 | 2019-09-07 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 147474 | Work Order Description - 147474 - CM | CM | 1 | 316303 | WPLAN | PACK-ISOL | 2018-06-27 | 2019-06-25 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 147490 | Work Order Description - 147490 - CM | CM | 2 | 479549 | WSCHD | NORM-OPS | 2019-03-25 | 2019-07-31 | 2019-06-01 | 2019-06-01 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 147495 | Work Order Description - 147495 - CM | CM | 3 | 308535 | WPLAN | SYS-ISOL | 2018-06-27 | 2020-06-23 | 2019-05-04 | 2019-05-06 | 4 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 147637 | Work Order Description - 147637 - CM | CM | 4 | 383839 | SCHD | ON LINE | 2019-03-22 | 2020-06-24 | 2019-09-01 | 2019-09-01 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 147643 | Work Order Description - 147643 - CM | CM | 4 | 482733 | SCHD | NORM-OPS | 2018-10-09 | 2019-06-26 | 2019-03-30 | 2019-03-30 | 3 | INTEGRITY | FABRIC | 196
2019-03-31 | 147676 | Work Order Description - 147676 - CM | CM | 3 | 74971 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-06-26 | 2019-04-20 | 2019-04-24 | 3 | MAINTENANCE | MECHANICAL | 93
2019-03-31 | 147677 | Work Order Description - 147677 - CM | CM | 1 | 484754 | WSCHD | NORM-OPS | 2018-11-16 | 2020-06-24 | 2019-11-30 | 2019-12-04 | 4 | INTEGRITY | FABRIC | 117
2019-03-31 | 147691 | Work Order Description - 147691 - CM | CM | 4 | 25711 | WPLAN | NORM-OPS | 2018-08-18 | 2020-06-24 | 2020-03-07 | 2020-03-07 | 4 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 147709 | Work Order Description - 147709 - CM | CM | 1 | 403817 | WPLAN | NORM-OPS | 2018-07-07 | 2019-10-31 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 147711 | Work Order Description - 147711 - CM | CM | 1 | 262382 | WPLAN | NORM-OPS | 2018-07-07 | 2019-10-01 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 147714 | Work Order Description - 147714 - PM | PM | 3 | 261160 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-11-01 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 147870 | Work Order Description - 147870 - CM | CM | 4 | 19141 | WPLAN | NORM-OPS | 2018-07-27 | 2020-06-25 | 2019-04-27 | 2019-04-28 | 4 | INTEGRITY | CONSTRUCTION | 16
2019-03-31 | 147884 | Work Order Description - 147884 - PM | PM | 2 | 480203 | WSCHD | PACK-ISOL | 2018-06-28 | 2019-07-08 | 2019-04-20 | 2019-04-23 | 2 | MAINTENANCE | ELECTRICAL | 48
2019-03-31 | 147886 | Work Order Description - 147886 - PM | PM | 3 | 360349 | SCHD | PACK-ISOL | 2018-10-29 | 2019-09-20 | 2019-03-30 | 2019-03-31 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 147896 | Work Order Description - 147896 - PSPM | PSPM | 1 | 399510 | WSCHD | PACK-ISOL | 2018-10-23 | 2019-11-01 | 2019-08-03 | 2019-08-04 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 147897 | Work Order Description - 147897 - PSPM | PSPM | 1 | 399511 | WSCHD | PACK-ISOL | 2018-10-23 | 2019-11-01 | 2019-08-03 | 2019-08-04 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 147898 | Work Order Description - 147898 - PSPM | PSPM | 1 | 54071 | WSCHD | PACK-ISOL | 2018-10-23 | 2019-11-01 | 2019-08-03 | 2019-08-04 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 147979 | Work Order Description - 147979 - BR | BR | 2 | 122637 | WPLAN | PACK-ISOL | 2018-07-15 | 2019-02-16 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | MECHANICAL | 24
2019-03-31 | 148020 | Work Order Description - 148020 - CM | CM | 4 | 294915 | WSCHD | NORM-OPS | 2018-07-02 | 2019-10-02 | 2019-11-02 | 2019-11-03 | 4 | MAINTENANCE | ELECTRICAL | 16
2019-03-31 | 148022 | Work Order Description - 148022 - CM | CM | 4 | 267674 | SCHD | NORM-OPS | 2018-10-29 | 2020-07-26 | 2019-11-02 | 2019-11-04 | 4 | MAINTENANCE | ELECTRICAL | 48
2019-03-31 | 148037 | Work Order Description - 148037 - PM | PM | 2 | 480203 | SCHD | PACK-ISOL | 2018-11-11 | 2019-02-15 | 2019-04-13 | 2019-04-14 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 148200 | Work Order Description - 148200 - BR | BR | 2 | 256849 | SCHD | NORM-OPS | 2018-12-24 | 2020-06-27 | 2019-04-27 | 2019-04-29 | 4 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 148358 | Work Order Description - 148358 - CM | CM | 1 | 17254 | WSCHD | NORM-OPS | 2018-11-15 | 2019-08-01 | 2019-05-04 | 2019-05-05 | 4 | INTEGRITY | INSPECTION | 48
2019-03-31 | 148363 | Work Order Description - 148363 - BR | BR | 4 | 668417 | INPRG | NORM-OPS | 2018-09-06 | 2019-11-13 | 2019-03-09 | 2019-06-04 | 4 | MAINTENANCE | CONSTRUCTION | 38
2019-03-31 | 148371 | Work Order Description - 148371 - PSCM | PSCM | 1 | 653327 | WSCHD | NORM-OPS | 2018-07-09 | 2020-06-28 | 2019-06-28 | 2019-06-28 | 4 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 148388 | Work Order Description - 148388 - PSPM | PSPM | 1 | 697892 | WSCHD | NORM-OPS | 2018-07-01 | 2019-06-01 | 2019-04-27 | 2019-04-28 | 1 | INTEGRITY | INSPECTION | 12
2019-03-31 | 148401 | Work Order Description - 148401 - PSPM | PSPM | 1 | 54522 | WSCHD | EQUIP-ISOL | 2018-07-01 | 2020-01-01 | 2020-05-02 | 2020-05-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 148557 | Work Order Description - 148557 - PSPM | PSPM | 1 | 54101 | WSCHD | PACK-ISOL | 2018-07-02 | 2019-05-01 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 148584 | Work Order Description - 148584 - PM | PM | 3 | 375808 | SCHD | PACK-ISOL | 2018-07-03 | 2019-09-12 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 148670 | Work Order Description - 148670 - CM | CM | 3 | 467877 | WPLAN | NORM-OPS | 2018-07-05 | 2020-06-30 | 2019-06-01 | 2019-06-02 | 4 | INTEGRITY | CONSTRUCTION | 20
2019-03-31 | 148685 | Work Order Description - 148685 - CM | CM | 4 | 227873 | WPLAN | NORM-OPS | 2018-10-23 | 2020-06-30 | 2019-05-04 | 2019-05-10 | 4 | INTEGRITY | FABRIC | 98
2019-03-31 | 148686 | Work Order Description - 148686 - CM | CM | 4 | 227873 | WPLAN | NORM-OPS | 2018-10-23 | 2020-06-30 | 2019-05-04 | 2019-05-10 | 4 | INTEGRITY | FABRIC | 98
2019-03-31 | 148688 | Work Order Description - 148688 - CM | CM | 4 | 448711 | SCHD | PACK-ISOL | 2019-01-21 | 2020-06-30 | 2019-05-25 | 2019-05-25 | 4 | WELLS | WELLS | 3
2019-03-31 | 148713 | Work Order Description - 148713 - PSCM | PSCM | 1 | 368215 | WSCHD | NORM-OPS | 2018-07-04 | 2020-04-01 | 2019-05-25 | 2019-05-26 | 3 | ENGINEERING | CONSTRUCTION | 42
2019-03-31 | 148717 | Work Order Description - 148717 - PSCM | PSCM | 1 | 368215 | WSCHD | NORM-OPS | 2018-07-09 | 2020-04-01 | 2019-05-25 | 2019-05-26 | 3 | ENGINEERING | CONSTRUCTION | 42
2019-03-31 | 148719 | Work Order Description - 148719 - CM | CM | 1 | 697913 | WSCHD | NORM-OPS | 2018-10-12 | 2019-08-02 | 2019-04-20 | 2019-04-21 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 148735 | Work Order Description - 148735 - BR | BR | 3 | 463213 | WPLAN | SYS-ISOL | 2018-07-05 | 2019-07-05 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 148744 | Work Order Description - 148744 - PM | PM | 2 | 480203 | WSCHD | PACK-ISOL | 2018-07-03 | 2019-05-14 | 2019-04-27 | 2019-04-28 | 2 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 148901 | Work Order Description - 148901 - PSCM | PSCM | 1 | 368215 | WSCHD | NORM-OPS | 2018-07-09 | 2019-05-01 | 2019-05-25 | 2019-05-25 | 3 | ENGINEERING | CONSTRUCTION | 280
2019-03-31 | 148907 | Work Order Description - 148907 - BR | BR | 3 | 322427 | SCHD | PACK-ISOL | 2018-10-18 | 2019-02-18 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | MECHANICAL | 19
2019-03-31 | 148908 | Work Order Description - 148908 - BR | BR | 4 | 19141 | SCHD | PACK-ISOL | 2018-12-10 | 2019-07-03 | 2019-06-29 | 2019-06-29 | 3 | INTEGRITY | MECHANICAL | 345
2019-03-31 | 148919 | Work Order Description - 148919 - BR | BR | 3 | 246940 | WPLAN | NORM-OPS | 2018-07-05 | 2019-09-01 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 148920 | Work Order Description - 148920 - CM | CM | 2 | 534264 | SCHD | SYS-ISOL | 2018-09-13 | 2020-01-03 | 2019-06-01 | 2019-06-07 | 2 | INTEGRITY | SUBSEA | 24
2019-03-31 | 148931 | Work Order Description - 148931 - PM | PM | 4 | 58001 | SCHD | TPS | 2018-10-29 | 2019-09-23 | 2019-06-01 | 2019-06-02 | 1 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 148932 | Work Order Description - 148932 - PM | PM | 4 | 261532 | SCHD | EQUIP-ISOL | 2018-10-19 | 2019-05-14 | 2019-03-30 | 2019-03-31 | 1 | INTEGRITY | CONSTRUCTION | 3
2019-03-31 | 148934 | Work Order Description - 148934 - PM | PM | 2 | 408373 | SCHD | EQUIP-ISOL | 2018-11-27 | 2018-12-30 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 148935 | Work Order Description - 148935 - PM | PM | 4 | 54771 | WSCHD | NORM-OPS | 2019-02-08 | 2019-01-06 | 2019-04-20 | 2019-04-21 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 148965 | Work Order Description - 148965 - PSPM | PSPM | 1 | 399803 | WSCHD | EQUIP-ISOL | 2018-07-04 | 2019-07-01 | 2019-09-07 | 2019-09-07 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 148966 | Work Order Description - 148966 - PM | PM | 4 | 357251 | SCHD | EQUIP-ISOL | 2018-11-11 | 2019-01-19 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 148970 | Work Order Description - 148970 - PM | PM | 4 | 492031 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-10-30 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 148972 | Work Order Description - 148972 - PM | PM | 2 | 312683 | SCHD | PACK-ISOL | 2018-09-06 | 2019-03-06 | 2019-08-24 | 2019-08-24 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 149000 | Work Order Description - 149000 - PM | PM | 4 | 556469 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-03-26 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | ELECTRICAL | 180
2019-03-31 | 149011 | Work Order Description - 149011 - PM | PM | 3 | 499086 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-07-24 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 149051 | Work Order Description - 149051 - PM | PM | 4 | 266557 | SCHD | NORM-OPS | 2018-07-06 | 2019-07-31 | 2019-05-04 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 149065 | Work Order Description - 149065 - PM | PM | 4 | 124146 | SCHD | EQUIP-ISOL | 2018-07-06 | 2019-11-02 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 149066 | Work Order Description - 149066 - PM | PM | 4 | 80354 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-05-07 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 149067 | Work Order Description - 149067 - PM | PM | 4 | 266182 | SCHD | EQUIP-ISOL | 2018-07-06 | 2019-06-05 | 2019-04-21 | 2019-04-24 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 149071 | Work Order Description - 149071 - PSPM | PSPM | 1 | 670506 | SCHD | PACK-ISOL | 2019-02-21 | 2019-04-01 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 9
2019-03-31 | 149689 | Work Order Description - 149689 - BR | BR | 4 | 480203 | WSCHD | PACK-ISOL | 2018-07-05 | 2019-06-06 | 2019-04-13 | 2019-04-14 | 2 | MAINTENANCE | MECHANICAL | 82
2019-03-31 | 149692 | Work Order Description - 149692 - BR | BR | 4 | 449202 | SCHD | ON LINE | 2019-02-13 | 2020-07-02 | 2019-05-04 | 2019-05-07 | 4 | MAINTENANCE | INSTRUMENTS | 23
2019-03-31 | 149707 | Work Order Description - 149707 - BR | BR | 4 | 478300 | INPRG | NORM-OPS | 2019-02-09 | 2019-07-04 | 2019-05-11 | 2019-05-14 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 149749 | Work Order Description - 149749 - BR | BR | 4 | 478300 | INPRG | NORM-OPS | 2019-02-09 | 2019-07-04 | 2019-05-11 | 2019-05-14 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 149753 | Work Order Description - 149753 - BR | BR | 4 | 478300 | INPRG | NORM-OPS | 2019-02-02 | 2019-07-04 | 2019-05-11 | 2019-05-14 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 149869 | Work Order Description - 149869 - BR | BR | 2 | 544405 | SCHD | SYS-ISOL | 2018-09-06 | 2019-07-05 | 2019-05-04 | 2019-05-09 | 3 | MAINTENANCE | INSTRUMENTS | 392
2019-03-31 | 149870 | Work Order Description - 149870 - PSCM | PSCM | 1 | 357017 | SCHD | SYS-ISOL | 2018-10-29 | 2019-07-05 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | INSTRUMENTS | 15
2019-03-31 | 149877 | Work Order Description - 149877 - BR | BR | 3 | 215906 | WPLAN | NORM-OPS | 2018-07-05 | 2019-07-05 | 2020-03-07 | 2020-03-08 | 3 | ENGINEERING | CONSTRUCTION | 196
2019-03-31 | 150017 | Work Order Description - 150017 - CM | CM | 4 | 36126 | SCHD | NORM-OPS | 2018-07-18 | 2020-07-04 | 2019-09-21 | 2019-09-21 | 4 | ENGINEERING | CONSTRUCTION | 100
2019-03-31 | 150024 | Work Order Description - 150024 - BR | BR | 4 | 655986 | SCHD | NORM-OPS | 2018-08-02 | 2020-07-04 | 2019-07-27 | 2019-07-27 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 150025 | Work Order Description - 150025 - BR | BR | 4 | 655739 | SCHD | NORM-OPS | 2018-08-02 | 2019-09-28 | 2019-07-27 | 2019-07-27 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 150026 | Work Order Description - 150026 - BR | BR | 4 | 669194 | WPLAN | NORM-OPS | 2018-08-07 | 2020-07-04 | 2019-07-27 | 2019-07-28 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 150157 | Work Order Description - 150157 - PSCM | PSCM | 3 | 671541 | SCHD | PACK-ISOL | 2019-03-30 | 2019-07-07 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 56
2019-03-31 | 150158 | Work Order Description - 150158 - BR | BR | 3 | 308463 | SCHD | NORM-OPS | 2019-03-30 | 2019-07-07 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 46
2019-03-31 | 150306 | Work Order Description - 150306 - BR | BR | 3 | 501569 | WPLAN | SYS-ISOL | 2018-07-08 | 2020-07-06 | 2020-05-02 | 2020-05-07 | 4 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 150308 | Work Order Description - 150308 - BR | BR | 4 | 321115 | WSCHD | PACK-ISOL | 2018-07-08 | 2020-07-06 | 2019-08-31 | 2019-09-02 | 4 | MAINTENANCE | MECHANICAL | 34
2019-03-31 | 150309 | Work Order Description - 150309 - BR | BR | 4 | 33427 | WSCHD | PACK-ISOL | 2018-07-08 | 2020-07-06 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 150310 | Work Order Description - 150310 - BR | BR | 4 | 480203 | WSCHD | PACK-ISOL | 2018-07-08 | 2020-07-06 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 150311 | Work Order Description - 150311 - BR | BR | 4 | 321199 | WSCHD | PACK-ISOL | 2018-07-08 | 2020-07-06 | 2019-08-31 | 2019-09-01 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 150363 | Work Order Description - 150363 - PM | PM | 3 | 363614 | WSCHD | NORM-OPS | 2018-07-09 | 2019-04-15 | 2019-04-27 | 2019-04-28 | 1 | INTEGRITY | INSTRUMENTS | 2
2019-03-31 | 150417 | Work Order Description - 150417 - PM | PM | 4 | 78529 | SCHD | PACK-ISOL | 2018-07-09 | 2019-01-22 | 2019-03-09 | 2019-03-09 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 150419 | Work Order Description - 150419 - PM | PM | 4 | 100131 | SCHD | PACK-ISOL | 2018-07-09 | 2019-09-22 | 2019-03-09 | 2019-03-09 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 150420 | Work Order Description - 150420 - PSPM | PSPM | 4 | 99960 | SCHD | NORM-OPS | 2018-07-09 | 2019-08-24 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 150425 | Work Order Description - 150425 - PM | PM | 4 | 100131 | SCHD | EQUIP-ISOL | 2018-07-09 | 2018-12-12 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 150471 | Work Order Description - 150471 - CM | CM | 3 | 56415 | WSCHD | SYS-ISOL | 2018-08-02 | 2019-07-09 | 2019-07-06 | 2019-07-06 | 3 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 150476 | Work Order Description - 150476 - CM | CM | 3 | 11933 | SCHD | PACK-ISOL | 2018-08-27 | 2020-08-01 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 150496 | Work Order Description - 150496 - PSCM | PSCM | 1 | 568110 | SCHD | NORM-OPS | 2018-09-06 | 2020-07-07 | 2019-08-17 | 2019-08-17 | 4 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 150503 | Work Order Description - 150503 - CM | CM | 1 | 467877 | WPLAN | NORM-OPS | 2018-08-22 | 2019-07-09 | 2019-04-27 | 2019-04-28 | 3 | INTEGRITY | INSPECTION | 24
2019-03-31 | 150506 | Work Order Description - 150506 - BR | BR | 3 | 672178 | WSCHD | SYS-ISOL | 2018-10-29 | 2020-07-07 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 25
2019-03-31 | 150539 | Work Order Description - 150539 - CM | CM | 2 | 360077 | WSCHD | SYS-ISOL | 2019-02-11 | 2019-07-09 | 2019-05-11 | 2019-05-12 | 3 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 150540 | Work Order Description - 150540 - CM | CM | 4 | 216927 | SCHD | NORM-OPS | 2018-12-24 | 2019-09-01 | 2019-06-08 | 2019-06-16 | 4 | INTEGRITY | INSPECTION | 118
2019-03-31 | 150541 | Work Order Description - 150541 - BR | BR | 1 | 127774 | WPLAN | PACK-ISOL | 2018-08-07 | 2020-07-08 | 2019-05-25 | 2019-05-26 | 4 | WELLS | WELLS | 29
2019-03-31 | 150593 | Work Order Description - 150593 - PM | PM | 4 | 383056 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-06-30 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 150692 | Work Order Description - 150692 - BR | BR | 3 | 179650 | SCHD | SUBSYS-ISOL | 2018-08-14 | 2019-07-10 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 150898 | Work Order Description - 150898 - BR | BR | 4 | 104098 | SCHD | NORM-OPS | 2019-02-13 | 2020-07-09 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 150903 | Work Order Description - 150903 - BR | BR | 4 | 98255 | SCHD | NORM-OPS | 2019-02-13 | 2020-07-09 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 150915 | Work Order Description - 150915 - CM | CM | 1 | 496963 | SCHD | NORM-OPS | 2018-11-13 | 2019-07-11 | 2019-05-25 | 2019-05-30 | 3 | INTEGRITY | INSPECTION | 232
2019-03-31 | 150930 | Work Order Description - 150930 - BR | BR | 4 | 671910 | SCHD | NORM-OPS | 2018-09-03 | 2020-07-09 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 150947 | Work Order Description - 150947 - PM | PM | 4 | 272735 | SCHD | EQUIP-ISOL | 2018-09-25 | 2019-04-21 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 150948 | Work Order Description - 150948 - PM | PM | 4 | 137798 | SCHD | PACK-ISOL | 2018-12-10 | 2019-08-29 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 151022 | Work Order Description - 151022 - BR | BR | 4 | 243771 | SCHD | PACK-ISOL | 2018-07-18 | 2019-08-14 | 2019-04-14 | 2019-04-14 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 151053 | Work Order Description - 151053 - BR | BR | 4 | 216507 | SCHD | PACK-ISOL | 2018-11-20 | 2019-07-30 | 2019-04-14 | 2019-04-14 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 151054 | Work Order Description - 151054 - CM | CM | 4 | 451344 | SCHD | NORM-OPS | 2019-03-15 | 2019-09-06 | 2019-09-05 | 2019-09-05 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 151156 | Work Order Description - 151156 - BR | BR | 3 | 497845 | SCHD | NORM-OPS | 2018-08-30 | 2019-07-13 | 2019-04-20 | 2019-04-20 | 3 | OPERATIONS | OPERATIONS | 48
2019-03-31 | 151157 | Work Order Description - 151157 - BR | BR | 3 | 497845 | SCHD | NORM-OPS | 2018-12-07 | 2019-07-13 | 2019-05-04 | 2019-05-04 | 3 | OPERATIONS | OPERATIONS | 4
2019-03-31 | 151158 | Work Order Description - 151158 - BR | BR | 3 | 497845 | WSCHD | NORM-OPS | 2018-07-13 | 2019-07-13 | 2019-04-20 | 2019-04-20 | 3 | OPERATIONS | OPERATIONS | 48
2019-03-31 | 151297 | Work Order Description - 151297 - BR | BR | 4 | 318309 | WSCHD | TPS | 2018-07-14 | 2020-07-12 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 151312 | Work Order Description - 151312 - BR | BR | 4 | 327420 | SCHD | NORM-OPS | 2018-08-30 | 2019-08-21 | 2019-07-27 | 2019-07-27 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 151339 | Work Order Description - 151339 - BR | BR | 3 | 246757 | SCHD | NORM-OPS | 2019-02-06 | 2019-11-17 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | INSTRUMENTS | 10.5
2019-03-31 | 151340 | Work Order Description - 151340 - CM | CM | 3 | 584600 | WMATL | ON LINE | 2018-11-28 | 2020-07-12 | 2019-08-10 | 2019-08-10 | 4 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 151341 | Work Order Description - 151341 - CM | CM | 3 | 128986 | SCHD | ON LINE | 2019-03-15 | 2019-07-14 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 151433 | Work Order Description - 151433 - BR | BR | 1 | 671272 | WSCHD | NORM-OPS | 2018-07-15 | 2020-07-13 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 151434 | Work Order Description - 151434 - BR | BR | 4 | 322467 | WSCHD | NORM-OPS | 2019-01-22 | 2020-07-13 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 151470 | Work Order Description - 151470 - BR | BR | 2 | 51040 | WSCHD | NORM-OPS | 2018-07-16 | 2019-07-11 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 151564 | Work Order Description - 151564 - CM | CM | 3 | 671397 | WPLAN | ON LINE | 2018-07-24 | 2019-09-14 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 151673 | Work Order Description - 151673 - CM | CM | 4 | 479486 | SCHD | NORM-OPS | 2018-08-18 | 2019-07-17 | 2019-05-11 | 2019-05-11 | 3 | INTEGRITY | FABRIC | 1454.5
2019-03-31 | 151683 | Work Order Description - 151683 - PSCM | PSCM | 1 | 327695 | WSCHD | SYS-ISOL | 2018-08-14 | 2020-07-15 | 2020-05-02 | 2020-05-02 | 4 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 151697 | Work Order Description - 151697 - CM | CM | 4 | 113706 | WPLAN | ON LINE | 2018-09-13 | 2020-07-15 | 2019-07-27 | 2019-07-27 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 151698 | Work Order Description - 151698 - CM | CM | 3 | 214928 | WSCHD | SYS-ISOL | 2018-10-27 | 2019-08-12 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 13
2019-03-31 | 151715 | Work Order Description - 151715 - PSPM | PSPM | 1 | 54773 | SCHD | NORM-OPS | 2019-03-29 | 2019-05-18 | 2019-03-30 | 2019-04-01 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 151832 | Work Order Description - 151832 - PM | PM | 4 | 93113 | SCHD | EQUIP-ISOL | 2018-12-13 | 2019-03-27 | 2019-04-28 | 2019-04-28 | 1 | INTEGRITY | MECHANICAL | 1
2019-03-31 | 151855 | Work Order Description - 151855 - PM | PM | 2 | 527179 | SCHD | PACK-ISOL | 2018-12-17 | 2019-02-02 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 152150 | Work Order Description - 152150 - PM | PM | 4 | 183628 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-03-05 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 152155 | Work Order Description - 152155 - PM | PM | 4 | 556591 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-29 | 2019-08-17 | 2019-08-17 | 2 | DRILLING | DRILLING | 12
2019-03-31 | 152224 | Work Order Description - 152224 - PSCM | PSCM | 1 | 29670 | SCHD | NORM-OPS | 2018-09-06 | 2019-07-21 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 152225 | Work Order Description - 152225 - CM | CM | 3 | 408374 | WPLAN | TPS | 2018-07-24 | 2020-07-17 | 2020-05-02 | 2020-05-02 | 4 | INTEGRITY | INSPECTION | 16
2019-03-31 | 152331 | Work Order Description - 152331 - BR | BR | 3 | 21234 | SCHD | SYS-ISOL | 2019-02-08 | 2019-07-20 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 90
2019-03-31 | 152344 | Work Order Description - 152344 - BR | BR | 3 | 410298 | SCHD | SYS-ISOL | 2018-09-06 | 2020-07-18 | 2020-03-14 | 2020-03-14 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 152361 | Work Order Description - 152361 - BR | BR | 2 | 58075 | WPLAN | PACK-ISOL | 2018-07-25 | 2019-07-25 | 2020-05-08 | 2020-05-08 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 152366 | Work Order Description - 152366 - PM | PM | 2 | 321115 | SCHD | PACK-ISOL | 2018-10-29 | 2019-11-04 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 64
2019-03-31 | 152385 | Work Order Description - 152385 - PSPM | PSPM | 1 | 89823 | SCHD | EQUIP-ISOL | 2019-03-18 | 2019-04-07 | 2019-04-29 | 2019-04-29 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 152386 | Work Order Description - 152386 - PSPM | PSPM | 1 | 664980 | SCHD | EQUIP-ISOL | 2019-01-24 | 2020-01-03 | 2019-04-29 | 2019-04-29 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 152389 | Work Order Description - 152389 - PM | PM | 4 | 227898 | SCHD | NORM-OPS | 2018-08-02 | 2019-08-06 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 152479 | Work Order Description - 152479 - CM | CM | 3 | 553955 | WPLAN | ON LINE | 2018-07-25 | 2019-07-25 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 152487 | Work Order Description - 152487 - CM | CM | 3 | 681410 | WPLAN | ON LINE | 2018-09-18 | 2019-09-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 152500 | Work Order Description - 152500 - CM | CM | 4 | 462436 | SCHD | NORM-OPS | 2018-10-09 | 2019-06-10 | 2019-05-18 | 2019-05-21 | 2 | MAINTENANCE | ELECTRICAL | 72
2019-03-31 | 152505 | Work Order Description - 152505 - BR | BR | 3 | 534329 | SCHD | NORM-OPS | 2018-09-13 | 2019-07-21 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | FABRIC | 14
2019-03-31 | 152510 | Work Order Description - 152510 - CM | CM | 3 | 409743 | WPLAN | SYS-ISOL | 2018-07-24 | 2019-06-25 | 2020-05-02 | 2020-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 15
2019-03-31 | 152536 | Work Order Description - 152536 - PM | PM | 3 | 672480 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-10-20 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 152570 | Work Order Description - 152570 - PM | PM | 4 | 396761 | SCHD | EQUIP-ISOL | 2018-11-14 | 2019-12-04 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 152571 | Work Order Description - 152571 - PM | PM | 4 | 393191 | SCHD | EQUIP-ISOL | 2018-11-14 | 2018-12-08 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 152572 | Work Order Description - 152572 - PM | PM | 4 | 396740 | SCHD | EQUIP-ISOL | 2018-11-14 | 2019-11-01 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 152573 | Work Order Description - 152573 - PM | PM | 4 | 396739 | SCHD | EQUIP-ISOL | 2018-11-14 | 2019-03-01 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 152672 | Work Order Description - 152672 - CM | CM | 4 | 368215 | WSCHD | NORM-OPS | 2019-03-30 | 2019-09-25 | 2019-05-11 | 2019-05-11 | 3 | INTEGRITY | FABRIC | 1382.5
2019-03-31 | 152681 | Work Order Description - 152681 - CM | CM | 3 | 83929 | WPLAN | NORM-OPS | 2018-07-30 | 2020-07-20 | 2019-05-04 | 2019-05-10 | 4 | ENGINEERING | CONSTRUCTION | 96
2019-03-31 | 152694 | Work Order Description - 152694 - CM | CM | 2 | 478251 | WPLAN | NORM-OPS | 2018-08-06 | 2020-08-04 | 2019-09-07 | 2019-09-07 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 152697 | Work Order Description - 152697 - CM | CM | 4 | 266184 | SCHD | ON LINE | 2018-08-02 | 2020-07-20 | 2019-05-19 | 2019-05-20 | 4 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 152699 | Work Order Description - 152699 - CM | CM | 4 | 670503 | SCHD | ON LINE | 2018-08-02 | 2020-07-20 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 152710 | Work Order Description - 152710 - PM | PM | 4 | 544411 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-10-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 152719 | Work Order Description - 152719 - PM | PM | 4 | 216927 | SCHD | NORM-OPS | 2018-09-06 | 2019-07-31 | 2019-03-16 | 2019-03-16 | 2 | OPERATIONS | SAFETY | 10
2019-03-31 | 152827 | Work Order Description - 152827 - CM | CM | 3 | 249467 | WMATL | SYS-ISOL | 2019-01-22 | 2019-09-22 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 152836 | Work Order Description - 152836 - CM | CM | 2 | 447441 | WPLAN | NORM-OPS | 2018-07-24 | 2019-09-23 | 2019-10-05 | 2019-10-11 | 2 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 152877 | Work Order Description - 152877 - PM | PM | 4 | 393066 | SCHD | EQUIP-ISOL | 2018-11-14 | 2019-06-27 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 5
2019-03-31 | 152976 | Work Order Description - 152976 - CM | CM | 4 | 29041 | SCHD | NORM-OPS | 2018-08-27 | 2019-01-13 | 2019-05-18 | 2019-05-18 | 3 | MAINTENANCE | ELECTRICAL | 28
2019-03-31 | 152978 | Work Order Description - 152978 - BR | BR | 4 | 462436 | SCHD | NORM-OPS | 2018-08-27 | 2020-01-25 | 2019-05-18 | 2019-05-20 | 3 | MAINTENANCE | ELECTRICAL | 28
2019-03-31 | 152979 | Work Order Description - 152979 - BR | BR | 4 | 567819 | SCHD | NORM-OPS | 2018-09-06 | 2020-07-22 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | INSTRUMENTS | 324
2019-03-31 | 152981 | Work Order Description - 152981 - CM | CM | 2 | 499126 | WPLAN | NORM-OPS | 2018-08-06 | 2019-07-31 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 153018 | Work Order Description - 153018 - CM | CM | 3 | 51801 | WPLAN | SYS-ISOL | 2018-07-28 | 2019-07-24 | 2019-08-03 | 2019-08-03 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 153020 | Work Order Description - 153020 - CM | CM | 1 | 361593 | WSCHD | SYS-ISOL | 2018-09-28 | 2019-07-24 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 153106 | Work Order Description - 153106 - CM | CM | 3 | 312726 | WMATL | SYS-ISOL | 2018-07-31 | 2020-07-23 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 153115 | Work Order Description - 153115 - CM | CM | 4 | 544351 | SCHD | TPS | 2018-09-06 | 2020-07-23 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | INSTRUMENTS | 40
2019-03-31 | 153137 | Work Order Description - 153137 - CM | CM | 3 | 556360 | WPLAN | TPS | 2018-09-06 | 2020-01-21 | 2019-07-13 | 2019-07-15 | 3 | INTEGRITY | CONSTRUCTION | 77
2019-03-31 | 153142 | Work Order Description - 153142 - CM | CM | 3 | 405043 | WPLAN | SYS-ISOL | 2018-07-28 | 2020-07-23 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 153176 | Work Order Description - 153176 - PM | PM | 4 | 545299 | SCHD | PACK-ISOL | 2018-12-03 | 2019-04-28 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 153186 | Work Order Description - 153186 - PM | PM | 4 | 664999 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 153245 | Work Order Description - 153245 - CM | CM | 3 | 254936 | SCHD | NORM-OPS | 2018-11-05 | 2020-07-24 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 153257 | Work Order Description - 153257 - PM | PM | 4 | 601923 | SCHD | NORM-OPS | 2018-09-06 | 2019-06-24 | 2019-04-06 | 2019-04-06 | 2 | INTEGRITY | OPERATIONS | 60
2019-03-31 | 153267 | Work Order Description - 153267 - BR | BR | 2 | 172653 | WPLAN | NORM-OPS | 2018-07-28 | 2020-07-24 | 2019-05-25 | 2019-05-25 | 4 | ENGINEERING | CONSTRUCTION | 70
2019-03-31 | 153281 | Work Order Description - 153281 - PM | PM | 4 | 476739 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-07 | 2019-08-17 | 2019-08-17 | 2 | DRILLING | DRILLING | 28
2019-03-31 | 153282 | Work Order Description - 153282 - PM | PM | 4 | 320715 | SCHD | PACK-ISOL | 2018-09-06 | 2019-09-28 | 2019-08-17 | 2019-08-17 | 2 | DRILLING | DRILLING | 4
2019-03-31 | 153283 | Work Order Description - 153283 - PM | PM | 4 | 552599 | SCHD | PACK-ISOL | 2018-09-06 | 2019-05-22 | 2019-08-17 | 2019-08-17 | 2 | DRILLING | DRILLING | 28
2019-03-31 | 153284 | Work Order Description - 153284 - PM | PM | 4 | 216594 | SCHD | PACK-ISOL | 2018-09-06 | 2018-12-04 | 2019-08-17 | 2019-08-17 | 2 | INTEGRITY | DRILLING | 24
2019-03-31 | 153285 | Work Order Description - 153285 - PM | PM | 4 | 502362 | SCHD | PACK-ISOL | 2018-09-06 | 2019-01-28 | 2019-08-17 | 2019-08-17 | 2 | INTEGRITY | DRILLING | 21.5
2019-03-31 | 153286 | Work Order Description - 153286 - PM | PM | 4 | 320682 | SCHD | PACK-ISOL | 2018-09-06 | 2018-12-16 | 2019-08-17 | 2019-08-17 | 2 | DRILLING | DRILLING | 70
2019-03-31 | 153287 | Work Order Description - 153287 - PM | PM | 4 | 320682 | SCHD | PACK-ISOL | 2018-09-06 | 2019-10-27 | 2019-08-17 | 2019-08-17 | 2 | DRILLING | DRILLING | 17.5
2019-03-31 | 153288 | Work Order Description - 153288 - PM | PM | 4 | 477983 | SCHD | PACK-ISOL | 2018-09-06 | 2019-11-11 | 2019-08-17 | 2019-08-17 | 2 | DRILLING | DRILLING | 17.5
2019-03-31 | 153289 | Work Order Description - 153289 - PM | PM | 4 | 388120 | SCHD | EQUIP-ISOL | 2018-11-26 | 2019-05-19 | 2019-03-30 | 2019-03-30 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 153380 | Work Order Description - 153380 - CM | CM | 4 | 127428 | WPLAN | NORM-OPS | 2018-08-07 | 2020-07-25 | 2019-03-22 | 2019-03-23 | 4 | ENGINEERING | CONSTRUCTION | 12
2019-03-31 | 153396 | Work Order Description - 153396 - CM | CM | 3 | 308530 | SCHD | SUBSYS-ISOL | 2018-08-21 | 2019-02-11 | 2019-09-07 | 2019-09-09 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 153411 | Work Order Description - 153411 - PM | PM | 4 | 261384 | WSCHD | EQUIP-ISOL | 2018-07-28 | 2019-12-21 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | CONSTRUCTION | 13
2019-03-31 | 153433 | Work Order Description - 153433 - PSPM | PSPM | 4 | 99453 | SCHD | EQUIP-ISOL | 2018-08-02 | 2020-01-12 | 2019-04-09 | 2019-04-09 | 3 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 153605 | Work Order Description - 153605 - PM | PM | 4 | 499127 | SCHD | PACK-ISOL | 2019-01-31 | 2019-08-15 | 2019-02-16 | 2019-02-16 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 153608 | Work Order Description - 153608 - PM | PM | 4 | 325413 | SCHD | PACK-ISOL | 2019-01-31 | 2019-12-02 | 2019-02-16 | 2019-02-16 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 153612 | Work Order Description - 153612 - PSPM | PSPM | 4 | 375482 | SCHD | PACK-ISOL | 2018-08-02 | 2019-02-10 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 153614 | Work Order Description - 153614 - PSPM | PSPM | 4 | 375482 | SCHD | PACK-ISOL | 2018-08-02 | 2019-05-07 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 153615 | Work Order Description - 153615 - PM | PM | 4 | 396574 | SCHD | EQUIP-ISOL | 2018-11-26 | 2019-05-17 | 2019-04-17 | 2019-04-17 | 1 | INTEGRITY | MECHANICAL | 5
2019-03-31 | 153627 | Work Order Description - 153627 - PM | PM | 4 | 665057 | WPLAN | EQUIP-ISOL | 2018-07-29 | 2019-02-20 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 153628 | Work Order Description - 153628 - PM | PM | 4 | 93234 | WPLAN | EQUIP-ISOL | 2018-07-29 | 2019-08-10 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 153629 | Work Order Description - 153629 - PM | PM | 4 | 396492 | WPLAN | EQUIP-ISOL | 2018-07-29 | 2019-05-23 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 153630 | Work Order Description - 153630 - PM | PM | 4 | 388449 | WPLAN | EQUIP-ISOL | 2018-07-29 | 2020-01-25 | 2019-04-14 | 2019-04-14 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 153632 | Work Order Description - 153632 - PM | PM | 4 | 100154 | SCHD | EQUIP-ISOL | 2018-08-02 | 2019-01-16 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 153633 | Work Order Description - 153633 - PM | PM | 4 | 78537 | SCHD | EQUIP-ISOL | 2018-08-02 | 2019-11-22 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 153634 | Work Order Description - 153634 - PM | PM | 4 | 100155 | SCHD | EQUIP-ISOL | 2018-08-02 | 2018-12-30 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 153635 | Work Order Description - 153635 - PM | PM | 4 | 78538 | SCHD | EQUIP-ISOL | 2018-08-02 | 2019-01-08 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 153703 | Work Order Description - 153703 - CM | CM | 4 | 546068 | WPLAN | PACK-ISOL | 2018-07-30 | 2019-07-29 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | SERVICES | 47
2019-03-31 | 153705 | Work Order Description - 153705 - CM | CM | 4 | 546068 | WPLAN | PACK-ISOL | 2018-07-30 | 2019-03-27 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | SERVICES | 44
2019-03-31 | 153711 | Work Order Description - 153711 - CM | CM | 4 | 258310 | SCHD | SYS-ISOL | 2018-09-06 | 2019-07-29 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 153712 | Work Order Description - 153712 - BR | BR | 3 | 463206 | SCHD | SYS-ISOL | 2019-02-08 | 2019-07-29 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 29
2019-03-31 | 153716 | Work Order Description - 153716 - CM | CM | 3 | 539932 | SCHD | PACK-ISOL | 2018-10-09 | 2020-07-27 | 2019-05-04 | 2019-05-05 | 4 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 153717 | Work Order Description - 153717 - CM | CM | 4 | 568108 | SCHD | NORM-OPS | 2018-11-05 | 2020-07-27 | 2019-05-18 | 2019-05-18 | 4 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 153791 | Work Order Description - 153791 - PSPM | PSPM | 1 | 546068 | WSCHD | PACK-ISOL | 2018-07-30 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 153900 | Work Order Description - 153900 - CM | CM | 4 | 399725 | WSCHD | NORM-OPS | 2019-02-27 | 2019-07-30 | 2019-04-13 | 2019-04-13 | 3 | INTEGRITY | OPERATIONS | 8
2019-03-31 | 153901 | Work Order Description - 153901 - CM | CM | 4 | 248339 | SCHD | NORM-OPS | 2018-08-30 | 2019-07-30 | 2019-10-19 | 2019-10-19 | 3 | INTEGRITY | OPERATIONS | 8
2019-03-31 | 153921 | Work Order Description - 153921 - PSCM | PSCM | 1 | 541344 | SCHD | NORM-OPS | 2018-12-10 | 2020-07-29 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | INSTRUMENTS | 40
2019-03-31 | 153925 | Work Order Description - 153925 - CM | CM | 1 | 408076 | SCHD | NORM-OPS | 2018-10-29 | 2020-07-28 | 2019-09-07 | 2019-09-08 | 4 | MAINTENANCE | ELECTRICAL | 25
2019-03-31 | 153957 | Work Order Description - 153957 - PM | PM | 4 | 450665 | WPLAN | EQUIP-ISOL | 2018-07-31 | 2018-12-25 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 153971 | Work Order Description - 153971 - PM | PM | 4 | 98775 | SCHD | NORM-OPS | 2018-08-02 | 2019-06-20 | 2019-03-31 | 2019-04-03 | 2 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 154084 | Work Order Description - 154084 - BR | BR | 4 | 237485 | WPLAN | NORM-OPS | 2018-08-07 | 2020-07-29 | 2019-07-13 | 2019-07-13 | 4 | ENGINEERING | CONSTRUCTION | 0
2019-03-31 | 154128 | Work Order Description - 154128 - CM | CM | 1 | 310068 | SCHD | SYS-ISOL | 2018-11-05 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 154145 | Work Order Description - 154145 - PM | PM | 3 | 188962 | SCHD | NORM-OPS | 2018-09-06 | 2019-06-25 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 154146 | Work Order Description - 154146 - PM | PM | 3 | 325138 | SCHD | NORM-OPS | 2018-09-06 | 2019-09-23 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 154147 | Work Order Description - 154147 - PM | PM | 3 | 188963 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-27 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 154148 | Work Order Description - 154148 - PM | PM | 3 | 188964 | SCHD | NORM-OPS | 2018-09-06 | 2019-06-14 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 154225 | Work Order Description - 154225 - PRJ | PRJ | 4 | 556180 | SCHD | NORM-OPS | 2018-10-03 | 2019-11-15 | 2019-05-25 | 2019-05-25 | 4 | ENGINEERING | MECHANICAL | 225
2019-03-31 | 154234 | Work Order Description - 154234 - CM | CM | 1 | 322278 | WSCHD | NORM-OPS | 2018-08-04 | 2019-08-01 | 2019-05-24 | 2019-05-24 | 3 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 154243 | Work Order Description - 154243 - PSCM | PSCM | 3 | 308493 | WSCHD | SUBSYS-ISOL | 2019-01-20 | 2020-01-25 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | MECHANICAL | 52
2019-03-31 | 154368 | Work Order Description - 154368 - CM | CM | 4 | 375477 | SCHD | NORM-OPS | 2019-02-13 | 2020-07-31 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 154373 | Work Order Description - 154373 - CM | CM | 2 | 464229 | WPLAN | TPS | 2018-08-06 | 2020-07-31 | 2019-07-13 | 2019-07-13 | 4 | INTEGRITY | CONSTRUCTION | 2
2019-03-31 | 154388 | Work Order Description - 154388 - BR | BR | 3 | 478639 | WMATL | PACK-ISOL | 2019-02-04 | 2019-08-03 | 2019-05-04 | 2019-05-05 | 3 | INTEGRITY | MECHANICAL | 16
2019-03-31 | 154411 | Work Order Description - 154411 - PM | PM | 4 | 419551 | WSCHD | NORM-OPS | 2018-08-03 | 2019-08-14 | 2019-05-04 | 2019-05-04 | 2 | DRILLING | DRILLING | 240
2019-03-31 | 154420 | Work Order Description - 154420 - PM | PM | 2 | 408300 | WSCHD | EQUIP-ISOL | 2018-08-03 | 2019-11-02 | 2019-05-25 | 2019-05-25 | 2 | INTEGRITY | INSTRUMENTS | 14
2019-03-31 | 154422 | Work Order Description - 154422 - PM | PM | 3 | 672568 | SCHD | EQUIP-ISOL | 2018-11-13 | 2019-07-17 | 2021-03-06 | 2021-03-06 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 154447 | Work Order Description - 154447 - PM | PM | 4 | 360244 | WSCHD | NORM-OPS | 2018-08-03 | 2018-12-16 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 154448 | Work Order Description - 154448 - PSPM | PSPM | 1 | 361109 | WSCHD | EQUIP-ISOL | 2018-08-03 | 2019-07-01 | 2019-05-04 | 2019-05-04 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 154456 | Work Order Description - 154456 - PM | PM | 2 | 312683 | SCHD | PACK-ISOL | 2018-09-06 | 2018-12-16 | 2019-08-24 | 2019-08-24 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 154471 | Work Order Description - 154471 - PM | PM | 4 | 503248 | SCHD | EQUIP-ISOL | 2018-09-06 | 2018-12-16 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 154505 | Work Order Description - 154505 - PM | PM | 4 | 32616 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-11-18 | 2019-03-16 | 2019-03-16 | 1 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 154509 | Work Order Description - 154509 - PSPM | PSPM | 1 | 95502 | SCHD | PACK-ISOL | 2019-01-16 | 2019-05-03 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 154545 | Work Order Description - 154545 - PM | PM | 3 | 178889 | SCHD | EQUIP-ISOL | 2018-08-14 | 2018-12-27 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 154546 | Work Order Description - 154546 - PM | PM | 3 | 453775 | SCHD | EQUIP-ISOL | 2018-08-14 | 2018-12-11 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 154547 | Work Order Description - 154547 - PM | PM | 3 | 453776 | SCHD | EQUIP-ISOL | 2018-08-14 | 2019-10-07 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 154548 | Work Order Description - 154548 - PM | PM | 3 | 178890 | SCHD | EQUIP-ISOL | 2018-08-14 | 2019-11-12 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 154549 | Work Order Description - 154549 - PM | PM | 3 | 105760 | SCHD | EQUIP-ISOL | 2018-08-14 | 2018-12-28 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 154551 | Work Order Description - 154551 - PM | PM | 3 | 99510 | SCHD | EQUIP-ISOL | 2018-08-14 | 2019-09-04 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 154552 | Work Order Description - 154552 - PM | PM | 3 | 99773 | SCHD | EQUIP-ISOL | 2018-08-14 | 2019-03-16 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 154553 | Work Order Description - 154553 - PSPM | PSPM | 1 | 105934 | SCHD | EQUIP-ISOL | 2019-03-22 | 2019-06-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 154556 | Work Order Description - 154556 - PM | PM | 3 | 105757 | SCHD | EQUIP-ISOL | 2018-08-14 | 2019-04-21 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 154558 | Work Order Description - 154558 - PM | PM | 3 | 78337 | SCHD | SYS-ISOL | 2018-09-06 | 2019-06-07 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 154559 | Work Order Description - 154559 - PM | PM | 3 | 395968 | SCHD | PACK-ISOL | 2018-08-10 | 2020-01-13 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 154560 | Work Order Description - 154560 - PM | PM | 3 | 186661 | SCHD | SYS-ISOL | 2018-09-06 | 2019-12-19 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 154561 | Work Order Description - 154561 - PM | PM | 3 | 449173 | SCHD | SYS-ISOL | 2018-09-06 | 2019-10-11 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 154562 | Work Order Description - 154562 - PM | PM | 3 | 449176 | SCHD | SYS-ISOL | 2018-09-06 | 2019-07-08 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 154563 | Work Order Description - 154563 - PM | PM | 3 | 445055 | SCHD | SYS-ISOL | 2018-09-06 | 2019-10-05 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 154568 | Work Order Description - 154568 - PM | PM | 3 | 527192 | SCHD | SYS-ISOL | 2018-09-06 | 2019-01-31 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 154569 | Work Order Description - 154569 - PM | PM | 3 | 527196 | SCHD | SYS-ISOL | 2018-09-06 | 2019-05-27 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 154570 | Work Order Description - 154570 - PM | PM | 3 | 527255 | SCHD | SYS-ISOL | 2018-09-06 | 2019-04-04 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 155216 | Work Order Description - 155216 - CM | CM | 2 | 227788 | WPLAN | NORM-OPS | 2018-08-07 | 2020-08-01 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 155225 | Work Order Description - 155225 - CM | CM | 3 | 304486 | SCHD | NORM-OPS | 2018-08-27 | 2020-08-03 | 2019-06-22 | 2019-06-22 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 155229 | Work Order Description - 155229 - BR | BR | 4 | 447441 | SCHD | PACK-ISOL | 2018-11-05 | 2019-08-03 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 155230 | Work Order Description - 155230 - CM | CM | 3 | 310015 | SCHD | PACK-ISOL | 2018-08-27 | 2019-07-13 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 155250 | Work Order Description - 155250 - PM | PM | 3 | 309675 | SCHD | NORM-OPS | 2018-09-06 | 2019-11-17 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 155251 | Work Order Description - 155251 - PM | PM | 3 | 309675 | SCHD | NORM-OPS | 2018-09-06 | 2019-03-17 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 155344 | Work Order Description - 155344 - PM | PM | 4 | 671547 | WSCHD | EQUIP-ISOL | 2018-08-05 | 2019-03-22 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | ELECTRICAL | 44
2019-03-31 | 155345 | Work Order Description - 155345 - PM | PM | 4 | 314187 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-05-15 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 155376 | Work Order Description - 155376 - PSPM | PSPM | 1 | 527721 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-02 | 2019-04-28 | 2019-05-03 | 1 | MAINTENANCE | ELECTRICAL | 80
2019-03-31 | 155381 | Work Order Description - 155381 - PM | PM | 4 | 393039 | WPLAN | EQUIP-ISOL | 2018-08-05 | 2019-12-04 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 155382 | Work Order Description - 155382 - PM | PM | 4 | 388450 | WPLAN | EQUIP-ISOL | 2018-08-05 | 2019-12-18 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 155383 | Work Order Description - 155383 - PM | PM | 4 | 396452 | WPLAN | EQUIP-ISOL | 2018-08-05 | 2019-03-03 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 155384 | Work Order Description - 155384 - PM | PM | 4 | 388443 | WPLAN | EQUIP-ISOL | 2018-08-05 | 2019-02-25 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 155455 | Work Order Description - 155455 - PRJ | PRJ | 4 | 312683 | SCHD | PACK-ISOL | 2018-08-27 | 2018-12-31 | 2019-03-23 | 2019-03-23 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 155456 | Work Order Description - 155456 - PRJ | PRJ | 4 | 312718 | SCHD | PACK-ISOL | 2018-08-27 | 2020-01-16 | 2019-03-23 | 2019-03-23 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 155458 | Work Order Description - 155458 - PRJ | PRJ | 4 | 263141 | SCHD | PACK-ISOL | 2018-08-27 | 2019-05-18 | 2019-06-15 | 2019-06-15 | 3 | MAINTENANCE | ELECTRICAL | 42
2019-03-31 | 155459 | Work Order Description - 155459 - BR | BR | 4 | 368215 | WSCHD | NORM-OPS | 2018-10-29 | 2019-11-10 | 2019-09-07 | 2019-09-08 | 2 | MAINTENANCE | ELECTRICAL | 120
2019-03-31 | 155462 | Work Order Description - 155462 - BR | BR | 2 | 402622 | SCHD | PACK-ISOL | 2018-08-27 | 2019-01-20 | 2019-05-18 | 2019-05-24 | 3 | INTEGRITY | SERVICES | 96
2019-03-31 | 155470 | Work Order Description - 155470 - PSCM | PSCM | 1 | 81234 | SCHD | PACK-ISOL | 2018-08-27 | 2020-08-03 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 155476 | Work Order Description - 155476 - PSPM | PSPM | 1 | 653303 | WSCHD | PACK-ISOL | 2018-12-10 | 2019-09-01 | 2019-08-03 | 2019-08-04 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 155478 | Work Order Description - 155478 - PM | PM | 3 | 399514 | SCHD | PACK-ISOL | 2018-11-14 | 2019-01-13 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 155479 | Work Order Description - 155479 - PM | PM | 3 | 399515 | SCHD | PACK-ISOL | 2018-11-14 | 2019-02-20 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 155651 | Work Order Description - 155651 - PM | PM | 4 | 318813 | SCHD | PACK-ISOL | 2018-10-29 | 2019-01-25 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 155656 | Work Order Description - 155656 - CM | CM | 1 | 25820 | SCHD | PACK-ISOL | 2018-09-06 | 2020-08-04 | 2019-08-24 | 2019-08-24 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 155664 | Work Order Description - 155664 - CM | CM | 3 | 554719 | SCHD | TPS | 2018-08-27 | 2019-08-06 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 155684 | Work Order Description - 155684 - PSPM | PSPM | 1 | 228383 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-02 | 2019-04-21 | 2019-04-23 | 1 | MAINTENANCE | ELECTRICAL | 36
2019-03-31 | 155685 | Work Order Description - 155685 - PM | PM | 4 | 105565 | SCHD | PACK-ISOL | 2018-09-06 | 2019-03-03 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 155798 | Work Order Description - 155798 - CM | CM | 4 | 403817 | SCHD | NORM-OPS | 2018-08-27 | 2019-08-07 | 2020-02-22 | 2020-02-22 | 3 | INTEGRITY | FABRIC | 200
2019-03-31 | 155804 | Work Order Description - 155804 - CM | CM | 4 | 501444 | WPLAN | NORM-OPS | 2018-08-14 | 2019-08-07 | 2020-02-29 | 2020-02-29 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 155813 | Work Order Description - 155813 - CM | CM | 2 | 81528 | WPLAN | NORM-OPS | 2018-08-10 | 2019-08-10 | 2019-05-11 | 2019-05-11 | 3 | INTEGRITY | INSPECTION | 1
2019-03-31 | 155814 | Work Order Description - 155814 - CM | CM | 2 | 74474 | WSCHD | NORM-OPS | 2019-03-25 | 2019-10-31 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 156008 | Work Order Description - 156008 - BR | BR | 4 | 527330 | WPLAN | TPS | 2018-08-09 | 2020-08-06 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | INSTRUMENTS | 42
2019-03-31 | 156011 | Work Order Description - 156011 - CM | CM | 1 | 527986 | SCHD | NORM-OPS | 2018-09-06 | 2019-08-16 | 2019-04-14 | 2019-04-18 | 3 | INTEGRITY | CONSTRUCTION | 128
2019-03-31 | 156025 | Work Order Description - 156025 - PM | PM | 4 | 354614 | WSCHD | EQUIP-ISOL | 2018-08-09 | 2019-03-26 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 156026 | Work Order Description - 156026 - PM | PM | 4 | 272743 | WSCHD | EQUIP-ISOL | 2018-08-09 | 2019-03-26 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 156041 | Work Order Description - 156041 - PM | PM | 4 | 492290 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-04-26 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 2
2019-03-31 | 156042 | Work Order Description - 156042 - PM | PM | 4 | 492291 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-09-26 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 2
2019-03-31 | 156043 | Work Order Description - 156043 - PM | PM | 4 | 487777 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-03-23 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 2
2019-03-31 | 156045 | Work Order Description - 156045 - PM | PM | 4 | 534549 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-05-01 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | ELECTRICAL | 84
2019-03-31 | 156053 | Work Order Description - 156053 - PSPM | PSPM | 1 | 395993 | SCHD | PACK-ISOL | 2019-03-22 | 2019-06-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 156182 | Work Order Description - 156182 - PSCM | PSCM | 1 | 368282 | WSCHD | NORM-OPS | 2018-08-10 | 2020-01-01 | 2019-05-11 | 2019-05-11 | 3 | INTEGRITY | FABRIC | 207
2019-03-31 | 156213 | Work Order Description - 156213 - PSCM | PSCM | 1 | 657135 | SCHD | NORM-OPS | 2018-09-03 | 2020-08-07 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 156329 | Work Order Description - 156329 - CM | CM | 1 | 520207 | WSCHD | NORM-OPS | 2018-09-17 | 2020-08-08 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | CONSTRUCTION | 10
2019-03-31 | 156362 | Work Order Description - 156362 - PSPM | PSPM | 1 | 679719 | WSCHD | EQUIP-ISOL | 2018-08-11 | 2019-07-01 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 11
2019-03-31 | 156365 | Work Order Description - 156365 - PM | PM | 4 | 308595 | WSCHD | EQUIP-ISOL | 2018-08-11 | 2019-06-08 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 156392 | Work Order Description - 156392 - PM | PM | 4 | 185438 | SCHD | EQUIP-ISOL | 2018-08-14 | 2019-01-29 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 156395 | Work Order Description - 156395 - PM | PM | 2 | 668780 | SCHD | EQUIP-ISOL | 2018-08-14 | 2019-05-03 | 2019-04-02 | 2019-04-02 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 156522 | Work Order Description - 156522 - PM | PM | 4 | 393233 | WPLAN | EQUIP-ISOL | 2018-08-12 | 2019-12-19 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 156523 | Work Order Description - 156523 - PM | PM | 4 | 93235 | WPLAN | EQUIP-ISOL | 2018-08-12 | 2019-10-03 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 156593 | Work Order Description - 156593 - BR | BR | 1 | 399500 | WPLAN | SYS-ISOL | 2018-08-12 | 2020-08-10 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 156630 | Work Order Description - 156630 - PSPM | PSPM | 1 | 262023 | WSCHD | EQUIP-ISOL | 2018-08-13 | 2019-07-01 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 156631 | Work Order Description - 156631 - PSPM | PSPM | 1 | 54320 | WSCHD | EQUIP-ISOL | 2018-08-13 | 2019-07-01 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 156632 | Work Order Description - 156632 - PSPM | PSPM | 1 | 262026 | WSCHD | EQUIP-ISOL | 2018-08-13 | 2019-07-01 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 156633 | Work Order Description - 156633 - PSPM | PSPM | 1 | 53356 | WSCHD | EQUIP-ISOL | 2018-08-13 | 2019-07-01 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 156634 | Work Order Description - 156634 - PSPM | PSPM | 1 | 360581 | WSCHD | EQUIP-ISOL | 2018-08-13 | 2019-07-01 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 156638 | Work Order Description - 156638 - PSPM | PSPM | 1 | 656100 | WSCHD | PACK-ISOL | 2018-08-13 | 2019-07-01 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 156639 | Work Order Description - 156639 - PSPM | PSPM | 1 | 399619 | WSCHD | PACK-ISOL | 2018-08-13 | 2019-07-01 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 156640 | Work Order Description - 156640 - PSPM | PSPM | 1 | 653331 | WSCHD | PACK-ISOL | 2018-12-09 | 2019-12-01 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 156691 | Work Order Description - 156691 - BR | BR | 4 | 493431 | WPLAN | PACK-ISOL | 2018-08-14 | 2018-12-12 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | CONSTRUCTION | 56
2019-03-31 | 156692 | Work Order Description - 156692 - CM | CM | 3 | 463283 | WMATL | SYS-ISOL | 2018-11-27 | 2019-08-13 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | MECHANICAL | 38
2019-03-31 | 156698 | Work Order Description - 156698 - CM | CM | 1 | 266550 | SCHD | NORM-OPS | 2018-09-06 | 2020-08-11 | 2019-04-14 | 2019-04-14 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 156704 | Work Order Description - 156704 - CM | CM | 1 | 227898 | SCHD | NORM-OPS | 2018-09-06 | 2020-08-11 | 2019-05-19 | 2019-05-19 | 4 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 156715 | Work Order Description - 156715 - CM | CM | 3 | 555453 | WPLAN | ON LINE | 2018-08-14 | 2020-08-11 | 2019-09-07 | 2019-09-07 | 4 | WELLS | MECHANICAL | 2
2019-03-31 | 156746 | Work Order Description - 156746 - PM | PM | 2 | 105621 | SCHD | EQUIP-ISOL | 2018-08-14 | 2019-05-28 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 156817 | Work Order Description - 156817 - PSCM | PSCM | 1 | 260335 | SCHD | NORM-OPS | 2019-03-28 | 2020-08-12 | 2019-03-30 | 2019-03-31 | 4 | MAINTENANCE | INSTRUMENTS | 58
2019-03-31 | 156820 | Work Order Description - 156820 - BR | BR | 2 | 555483 | WMATL | TPS | 2018-08-28 | 2020-08-12 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 156834 | Work Order Description - 156834 - BR | BR | 4 | 247861 | WSCHD | NORM-OPS | 2018-08-31 | 2019-08-14 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 156835 | Work Order Description - 156835 - BR | BR | 1 | 495503 | WSCHD | NORM-OPS | 2018-08-31 | 2019-08-14 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 156870 | Work Order Description - 156870 - PM | PM | 4 | 114066 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-05-07 | 2019-04-07 | 2019-04-07 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 156969 | Work Order Description - 156969 - BR | BR | 3 | 489974 | WPLAN | PACK-ISOL | 2018-08-16 | 2019-08-15 | 2019-09-28 | 2019-09-28 | 3 | MAINTENANCE | MECHANICAL | 132
2019-03-31 | 156970 | Work Order Description - 156970 - PM | PM | 4 | 245662 | SCHD | PACK-ISOL | 2018-11-27 | 2019-08-16 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | MECHANICAL | 87
2019-03-31 | 156971 | Work Order Description - 156971 - PM | PM | 4 | 248776 | SCHD | EQUIP-ISOL | 2018-12-10 | 2019-06-03 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 1
2019-03-31 | 157082 | Work Order Description - 157082 - BR | BR | 4 | 183808 | SCHD | NORM-OPS | 2018-09-12 | 2020-08-14 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 157091 | Work Order Description - 157091 - PM | PM | 4 | 545258 | WSCHD | PACK-ISOL | 2018-08-16 | 2019-06-25 | 2020-03-07 | 2020-03-07 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 157114 | Work Order Description - 157114 - PSPM | PSPM | 1 | 54116 | WSCHD | PACK-ISOL | 2018-12-09 | 2019-09-01 | 2019-07-06 | 2019-07-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 157163 | Work Order Description - 157163 - PM | PM | 2 | 396121 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-04-03 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 157164 | Work Order Description - 157164 - PM | PM | 3 | 105756 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-04-03 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 157168 | Work Order Description - 157168 - PM | PM | 3 | 78363 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-04-02 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 157177 | Work Order Description - 157177 - PM | PM | 3 | 395989 | SCHD | EQUIP-ISOL | 2018-09-06 | 2020-01-04 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 157425 | Work Order Description - 157425 - BR | BR | 4 | 127841 | SCHD | TPS | 2019-03-27 | 2020-08-15 | 2019-07-13 | 2019-07-18 | 4 | WELLS | INSTRUMENTS | 84
2019-03-31 | 157428 | Work Order Description - 157428 - BR | BR | 3 | 81505 | WMATL | EQUIP-ISOL | 2018-08-20 | 2019-07-13 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | ELECTRICAL | 30
2019-03-31 | 157445 | Work Order Description - 157445 - CM | CM | 3 | 503604 | WPLAN | TPS | 2018-08-18 | 2020-08-15 | 2019-07-13 | 2019-07-17 | 4 | MAINTENANCE | CONSTRUCTION | 90
2019-03-31 | 157448 | Work Order Description - 157448 - CM | CM | 1 | 57460 | WPLAN | NORM-OPS | 2018-09-02 | 2019-07-01 | 2019-05-25 | 2019-05-25 | 3 | ENGINEERING | CONSTRUCTION | 1
2019-03-31 | 157481 | Work Order Description - 157481 - PSPM | PSPM | 1 | 361194 | WSCHD | EQUIP-ISOL | 2018-08-18 | 2020-01-01 | 2019-10-05 | 2019-10-05 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 157484 | Work Order Description - 157484 - PM | PM | 2 | 481744 | SCHD | NORM-OPS | 2019-01-25 | 2019-10-01 | 2019-08-03 | 2019-08-03 | 2 | INTEGRITY | INSPECTION | 36
2019-03-31 | 157532 | Work Order Description - 157532 - BR | BR | 1 | 318518 | WPLAN | PACK-ISOL | 2018-08-18 | 2019-08-18 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | INSTRUMENTS | 9
2019-03-31 | 157533 | Work Order Description - 157533 - BR | BR | 1 | 355118 | WPLAN | EQUIP-ISOL | 2018-08-18 | 2020-08-16 | 2020-03-07 | 2020-03-07 | 4 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 157534 | Work Order Description - 157534 - BR | BR | 1 | 400796 | WPLAN | EQUIP-ISOL | 2018-08-18 | 2019-08-18 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 9
2019-03-31 | 157553 | Work Order Description - 157553 - BR | BR | 1 | 127975 | INPRG | NORM-OPS | 2019-02-24 | 2020-08-16 | 2019-11-10 | 2019-12-10 | 4 | OPERATIONS | CONSTRUCTION | 143
2019-03-31 | 157579 | Work Order Description - 157579 - PM | PM | 4 | 314187 | SCHD | NORM-OPS | 2018-12-05 | 2019-02-08 | 2020-12-05 | 2020-12-05 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 157617 | Work Order Description - 157617 - PM | PM | 4 | 388445 | WPLAN | EQUIP-ISOL | 2018-08-19 | 2019-04-28 | 2019-04-17 | 2019-04-17 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 157618 | Work Order Description - 157618 - PM | PM | 4 | 664987 | WPLAN | EQUIP-ISOL | 2018-08-19 | 2019-06-04 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 157619 | Work Order Description - 157619 - PM | PM | 4 | 388411 | WPLAN | EQUIP-ISOL | 2018-08-19 | 2018-12-28 | 2019-04-29 | 2019-04-29 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 157620 | Work Order Description - 157620 - PM | PM | 4 | 388410 | WPLAN | EQUIP-ISOL | 2018-08-19 | 2019-02-18 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 157769 | Work Order Description - 157769 - BR | BR | 4 | 676448 | WSCHD | SUBSYS-ISOL | 2018-08-21 | 2019-08-19 | 2019-08-03 | 2019-08-03 | 3 | MAINTENANCE | INSPECTION | 17
2019-03-31 | 157775 | Work Order Description - 157775 - CM | CM | 4 | 363783 | WSCHD | SYS-ISOL | 2018-09-28 | 2019-08-19 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSPECTION | 17
2019-03-31 | 157777 | Work Order Description - 157777 - BR | BR | 4 | 95535 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-05-19 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 157805 | Work Order Description - 157805 - PM | PM | 3 | 672481 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-04-06 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | ELECTRICAL | 11
2019-03-31 | 157818 | Work Order Description - 157818 - PM | PM | 4 | 106080 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-04-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 157924 | Work Order Description - 157924 - BR | BR | 1 | 98069 | SCHD | EQUIP-ISOL | 2018-10-05 | 2019-08-20 | 2019-07-13 | 2019-07-13 | 3 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 157928 | Work Order Description - 157928 - BR | BR | 4 | 358304 | WSCHD | EQUIP-ISOL | 2018-08-21 | 2019-03-18 | 2019-07-27 | 2019-07-28 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 157936 | Work Order Description - 157936 - BR | BR | 4 | 18386 | WSCHD | NORM-OPS | 2018-08-21 | 2020-08-18 | 2019-04-20 | 2019-04-20 | 4 | INTEGRITY | MECHANICAL | 12
2019-03-31 | 158072 | Work Order Description - 158072 - CM | CM | 3 | 53336 | WSCHD | EQUIP-ISOL | 2018-08-21 | 2020-08-19 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 158094 | Work Order Description - 158094 - PM | PM | 4 | 216158 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-01 | 2019-03-30 | 2019-04-02 | 2 | DRILLING | DRILLING | 240
2019-03-31 | 158101 | Work Order Description - 158101 - CM | CM | 2 | 29238 | WPLAN | NORM-OPS | 2018-08-23 | 2019-08-22 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 158104 | Work Order Description - 158104 - BR | BR | 2 | 323737 | SCHD | SYS-ISOL | 2018-11-05 | 2019-08-22 | 2019-06-08 | 2019-06-08 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 158114 | Work Order Description - 158114 - PSPM | PSPM | 1 | 361184 | WSCHD | EQUIP-ISOL | 2018-08-22 | 2020-01-01 | 2019-08-10 | 2019-08-10 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 158119 | Work Order Description - 158119 - PSPM | PSPM | 1 | 256581 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-04-20 | 2019-03-23 | 2019-03-23 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 158123 | Work Order Description - 158123 - PM | PM | 4 | 403823 | SCHD | NORM-OPS | 2018-09-06 | 2020-01-03 | 2019-04-13 | 2019-04-13 | 2 | OPERATIONS | SAFETY | 18
2019-03-31 | 158134 | Work Order Description - 158134 - PM | PM | 4 | 266392 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-03-14 | 2019-06-07 | 2019-06-07 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 158135 | Work Order Description - 158135 - PM | PM | 4 | 124376 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-07 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 158146 | Work Order Description - 158146 - PM | PM | 4 | 126059 | SCHD | NORM-OPS | 2018-09-06 | 2019-07-06 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 158147 | Work Order Description - 158147 - PM | PM | 4 | 80446 | SCHD | NORM-OPS | 2018-09-06 | 2019-11-15 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 158165 | Work Order Description - 158165 - BR | BR | 2 | 323737 | SCHD | SYS-ISOL | 2018-11-05 | 2019-08-22 | 2019-06-08 | 2019-06-08 | 3 | MAINTENANCE | MECHANICAL | 52
2019-03-31 | 158238 | Work Order Description - 158238 - CM | CM | 2 | 325635 | WPLAN | EQUIP-ISOL | 2018-08-25 | 2020-08-20 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 158255 | Work Order Description - 158255 - BR | BR | 4 | 216084 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-22 | 2019-03-16 | 2019-03-16 | 3 | MAINTENANCE | MECHANICAL | 62
2019-03-31 | 158256 | Work Order Description - 158256 - PSCM | PSCM | 1 | 651862 | SCHD | NORM-OPS | 2018-10-29 | 2020-08-20 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 22
2019-03-31 | 158314 | Work Order Description - 158314 - PM | PM | 4 | 663490 | SCHD | EQUIP-ISOL | 2018-09-06 | 2018-12-21 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSTRUMENTS | 10
2019-03-31 | 158447 | Work Order Description - 158447 - BR | BR | 4 | 481607 | SCHD | NORM-OPS | 2018-08-27 | 2019-12-30 | 2019-08-24 | 2019-08-24 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 158479 | Work Order Description - 158479 - CM | CM | 4 | 535288 | SCHD | NORM-OPS | 2018-08-27 | 2020-08-21 | 2020-03-28 | 2020-03-28 | 4 | INTEGRITY | FABRIC | 64
2019-03-31 | 158483 | Work Order Description - 158483 - CM | CM | 1 | 445660 | SCHD | EQUIP-ISOL | 2018-08-27 | 2019-08-23 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | ELECTRICAL | 50
2019-03-31 | 158489 | Work Order Description - 158489 - PSCM | PSCM | 1 | 656161 | SCHD | NORM-OPS | 2018-10-29 | 2020-08-21 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 158492 | Work Order Description - 158492 - CM | CM | 2 | 493617 | SCHD | NORM-OPS | 2018-08-27 | 2020-08-21 | 2020-05-02 | 2020-05-02 | 4 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 158507 | Work Order Description - 158507 - PM | PM | 4 | 78462 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-09-01 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 158588 | Work Order Description - 158588 - CM | CM | 1 | 659053 | WPLAN | NORM-OPS | 2018-08-28 | 2019-08-24 | 2019-05-01 | 2019-05-10 | 3 | ENGINEERING | CONSTRUCTION | 152
2019-03-31 | 158604 | Work Order Description - 158604 - PRJ | PRJ | 4 | 191898 | WPLAN | NORM-OPS | 2018-09-06 | 2019-07-04 | 2019-08-31 | 2019-09-01 | 4 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 158605 | Work Order Description - 158605 - PSCM | PSCM | 1 | 48395 | WSCHD | NORM-OPS | 2018-08-25 | 2020-08-22 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 158609 | Work Order Description - 158609 - PRJ | PRJ | 4 | 499092 | SCHD | NORM-OPS | 2019-02-28 | 2020-02-01 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | CONSTRUCTION | 118
2019-03-31 | 158611 | Work Order Description - 158611 - PRJ | PRJ | 4 | 191898 | SCHD | NORM-OPS | 2018-10-29 | 2018-12-04 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | ELECTRICAL | 267.5
2019-03-31 | 158731 | Work Order Description - 158731 - BR | BR | 4 | 378820 | SCHD | NORM-OPS | 2018-11-02 | 2020-08-23 | 2019-04-13 | 2019-05-04 | 4 | INTEGRITY | SERVICES | 307.5
2019-03-31 | 158737 | Work Order Description - 158737 - BR | BR | 1 | 75101 | SCHD | TPS | 2019-03-06 | 2019-08-25 | 2019-07-13 | 2019-07-15 | 3 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 158775 | Work Order Description - 158775 - PM | PM | 2 | 321115 | WSCHD | PACK-ISOL | 2018-08-26 | 2019-08-12 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 35
2019-03-31 | 158805 | Work Order Description - 158805 - PM | PM | 4 | 396447 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-04-30 | 2019-04-15 | 2019-04-15 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 158806 | Work Order Description - 158806 - PM | PM | 4 | 388412 | WPLAN | EQUIP-ISOL | 2018-08-26 | 2019-05-31 | 2019-04-29 | 2019-04-29 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 158807 | Work Order Description - 158807 - PM | PM | 4 | 388414 | WPLAN | EQUIP-ISOL | 2018-08-26 | 2019-04-25 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 158808 | Work Order Description - 158808 - PM | PM | 4 | 388413 | WPLAN | EQUIP-ISOL | 2018-08-26 | 2020-01-22 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 158908 | Work Order Description - 158908 - BR | BR | 4 | 548189 | SCHD | SYS-ISOL | 2018-10-29 | 2019-08-26 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 158919 | Work Order Description - 158919 - PSCM | PSCM | 1 | 566783 | SCHD | NORM-OPS | 2018-09-06 | 2020-08-24 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 158920 | Work Order Description - 158920 - CM | CM | 1 | 403920 | SCHD | NORM-OPS | 2018-09-06 | 2020-08-24 | 2019-06-29 | 2019-06-29 | 4 | INTEGRITY | MECHANICAL | 30
2019-03-31 | 158943 | Work Order Description - 158943 - PSPM | PSPM | 1 | 531852 | WPLAN | SUBSYS-ISOL | 2018-08-27 | 2019-12-01 | 2019-10-05 | 2019-10-05 | 1 | INTEGRITY | INSPECTION | 248
2019-03-31 | 159057 | Work Order Description - 159057 - CM | CM | 4 | 368279 | WSCHD | EQUIP-ISOL | 2018-11-17 | 2020-01-01 | 2019-05-17 | 2019-05-17 | 2 | INTEGRITY | FABRIC | 594
2019-03-31 | 159059 | Work Order Description - 159059 - CM | CM | 1 | 502361 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-05-27 | 2019-04-06 | 2019-04-06 | 3 | DRILLING | ELECTRICAL | 12
2019-03-31 | 159063 | Work Order Description - 159063 - BR | BR | 1 | 72395 | SCHD | SUBSYS-ISOL | 2018-11-10 | 2019-08-01 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 159149 | Work Order Description - 159149 - CM | CM | 1 | 403426 | SCHD | NORM-OPS | 2019-03-13 | 2020-03-12 | 2019-04-27 | 2019-04-27 | 3 | OPERATIONS | FABRIC | 46
2019-03-31 | 159154 | Work Order Description - 159154 - PRJ | PRJ | 4 | 266628 | SCHD | NORM-OPS | 2018-10-15 | 2019-11-16 | 2019-04-20 | 2019-04-20 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 159172 | Work Order Description - 159172 - BR | BR | 1 | 53585 | WSCHD | EQUIP-ISOL | 2018-09-05 | 2019-08-28 | 2019-04-13 | 2019-04-13 | 3 | INTEGRITY | MECHANICAL | 22
2019-03-31 | 159173 | Work Order Description - 159173 - CM | CM | 2 | 497452 | WSCHD | EQUIP-ISOL | 2018-08-29 | 2019-08-28 | 2019-06-29 | 2019-06-30 | 3 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 159182 | Work Order Description - 159182 - CM | CM | 4 | 124210 | WPLAN | EQUIP-ISOL | 2018-09-04 | 2020-08-26 | 2019-08-10 | 2019-08-11 | 4 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 159189 | Work Order Description - 159189 - PSPM | PSPM | 1 | 25059 | SCHD | NORM-OPS | 2019-01-31 | 2019-08-01 | 2019-05-04 | 2019-05-04 | 1 | INTEGRITY | MECHANICAL | 15
2019-03-31 | 159191 | Work Order Description - 159191 - PSPM | PSPM | 1 | 59186 | SCHD | NORM-OPS | 2019-01-25 | 2019-07-01 | 2019-05-18 | 2019-05-18 | 1 | INTEGRITY | MECHANICAL | 8
2019-03-31 | 159193 | Work Order Description - 159193 - PSPM | PSPM | 1 | 24934 | SCHD | NORM-OPS | 2019-01-25 | 2019-07-01 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | MECHANICAL | 43
2019-03-31 | 159217 | Work Order Description - 159217 - PM | PM | 4 | 668433 | SCHD | PACK-ISOL | 2018-11-02 | 2019-08-31 | 2019-04-07 | 2019-04-07 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 159274 | Work Order Description - 159274 - CM | CM | 3 | 260570 | WSCHD | NORM-OPS | 2018-08-29 | 2020-08-27 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 159275 | Work Order Description - 159275 - BR | BR | 4 | 17540 | WPLAN | SYS-ISOL | 2018-08-29 | 2020-08-27 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 159276 | Work Order Description - 159276 - CM | CM | 3 | 310626 | WSCHD | NORM-OPS | 2018-08-29 | 2020-08-27 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 159280 | Work Order Description - 159280 - CM | CM | 4 | 185722 | WPLAN | NORM-OPS | 2018-08-31 | 2020-08-29 | 2020-02-01 | 2020-02-01 | 4 | INTEGRITY | FABRIC | 10
2019-03-31 | 159282 | Work Order Description - 159282 - PSCM | PSCM | 3 | 247294 | WSCHD | NORM-OPS | 2018-08-30 | 2019-08-29 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | CONSTRUCTION | 42
2019-03-31 | 159302 | Work Order Description - 159302 - CM | CM | 4 | 462436 | SCHD | NORM-OPS | 2018-09-10 | 2020-08-27 | 2019-05-11 | 2019-05-12 | 4 | MAINTENANCE | FABRIC | 12
2019-03-31 | 159303 | Work Order Description - 159303 - CM | CM | 4 | 29041 | SCHD | NORM-OPS | 2018-09-10 | 2020-08-27 | 2019-05-11 | 2019-05-12 | 4 | MAINTENANCE | FABRIC | 8
2019-03-31 | 159323 | Work Order Description - 159323 - BR | BR | 3 | 361452 | WPLAN | NORM-OPS | 2018-08-30 | 2019-08-29 | 2019-07-27 | 2019-07-27 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 159327 | Work Order Description - 159327 - CM | CM | 1 | 360997 | WMATL | NORM-OPS | 2018-09-02 | 2019-08-29 | 2020-02-02 | 2020-02-02 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 159339 | Work Order Description - 159339 - PM | PM | 4 | 309657 | SCHD | EQUIP-ISOL | 2018-09-24 | 2019-06-12 | 2019-05-11 | 2019-05-11 | 1 | INTEGRITY | MECHANICAL | 10
2019-03-31 | 159455 | Work Order Description - 159455 - CM | CM | 4 | 352925 | SCHD | NORM-OPS | 2019-01-16 | 2020-09-07 | 2019-05-17 | 2019-05-17 | 4 | INTEGRITY | FABRIC | 35
2019-03-31 | 159464 | Work Order Description - 159464 - CM | CM | 4 | 378847 | WPLAN | TPS | 2019-03-23 | 2020-03-19 | 2019-07-13 | 2019-07-13 | 3 | INTEGRITY | FABRIC | 63
2019-03-31 | 159689 | Work Order Description - 159689 - CM | CM | 1 | 262691 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 159710 | Work Order Description - 159710 - CM | CM | 2 | 98421 | SCHD | EQUIP-ISOL | 2018-11-13 | 2020-08-30 | 2019-10-05 | 2019-10-06 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 159728 | Work Order Description - 159728 - CM | CM | 3 | 541363 | WSCHD | EQUIP-ISOL | 2018-11-13 | 2019-09-11 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 159783 | Work Order Description - 159783 - PSPM | PSPM | 1 | 487824 | SCHD | NORM-OPS | 2019-01-25 | 2020-01-01 | 2019-11-02 | 2019-11-02 | 1 | INTEGRITY | MECHANICAL | 33
2019-03-31 | 159786 | Work Order Description - 159786 - PSPM | PSPM | 4 | 262784 | SCHD | NORM-OPS | 2018-09-06 | 2019-04-25 | 2020-01-11 | 2020-01-11 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 159802 | Work Order Description - 159802 - CM | CM | 3 | 541361 | WSCHD | EQUIP-ISOL | 2018-11-13 | 2019-09-02 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 159842 | Work Order Description - 159842 - PM | PM | 4 | 664984 | WPLAN | EQUIP-ISOL | 2018-09-02 | 2019-09-08 | 2019-04-22 | 2019-04-22 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 159843 | Work Order Description - 159843 - PM | PM | 4 | 89826 | WPLAN | EQUIP-ISOL | 2018-09-02 | 2018-12-29 | 2019-04-22 | 2019-04-22 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 159844 | Work Order Description - 159844 - PM | PM | 4 | 393234 | WPLAN | EQUIP-ISOL | 2018-09-02 | 2018-12-07 | 2019-04-22 | 2019-04-22 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 159845 | Work Order Description - 159845 - PM | PM | 4 | 93256 | WPLAN | EQUIP-ISOL | 2018-09-02 | 2019-08-24 | 2019-04-22 | 2019-04-22 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 159901 | Work Order Description - 159901 - CM | CM | 3 | 541362 | WSCHD | EQUIP-ISOL | 2018-11-13 | 2019-09-02 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 160116 | Work Order Description - 160116 - CM | CM | 4 | 671828 | WSCHD | EQUIP-ISOL | 2018-09-05 | 2019-08-22 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 19
2019-03-31 | 160118 | Work Order Description - 160118 - CM | CM | 3 | 387495 | SCHD | PACK-ISOL | 2018-11-13 | 2020-08-31 | 2019-04-14 | 2019-05-26 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 160122 | Work Order Description - 160122 - CM | CM | 3 | 227780 | SCHD | SYS-ISOL | 2019-03-06 | 2019-12-07 | 2019-07-13 | 2019-07-14 | 3 | ENGINEERING | CONSTRUCTION | 26
2019-03-31 | 160126 | Work Order Description - 160126 - PSCM | PSCM | 1 | 262799 | WMATL | NORM-OPS | 2018-10-08 | 2019-09-05 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 160128 | Work Order Description - 160128 - PSCM | PSCM | 4 | 504004 | SCHD | TPS | 2018-10-09 | 2020-08-31 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 160132 | Work Order Description - 160132 - CM | CM | 1 | 520250 | WPLAN | EQUIP-ISOL | 2018-09-05 | 2019-09-02 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | CONSTRUCTION | 28
2019-03-31 | 160134 | Work Order Description - 160134 - CM | CM | 1 | 491779 | WPLAN | EQUIP-ISOL | 2018-09-05 | 2019-09-02 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | CONSTRUCTION | 28
2019-03-31 | 160135 | Work Order Description - 160135 - CM | CM | 4 | 307074 | WMATL | NORM-OPS | 2018-09-17 | 2019-09-15 | 2019-04-20 | 2019-04-21 | 3 | INTEGRITY | ELECTRICAL | 18
2019-03-31 | 160144 | Work Order Description - 160144 - CM | CM | 3 | 227780 | SCHD | SYS-ISOL | 2019-03-06 | 2020-01-20 | 2019-07-13 | 2019-07-14 | 3 | ENGINEERING | CONSTRUCTION | 16
2019-03-31 | 160146 | Work Order Description - 160146 - CM | CM | 3 | 227780 | SCHD | SYS-ISOL | 2019-03-06 | 2019-10-01 | 2019-07-13 | 2019-07-14 | 3 | ENGINEERING | CONSTRUCTION | 24
2019-03-31 | 160147 | Work Order Description - 160147 - CM | CM | 3 | 227780 | SCHD | SYS-ISOL | 2019-03-06 | 2019-09-25 | 2019-07-13 | 2019-07-15 | 3 | ENGINEERING | CONSTRUCTION | 36
2019-03-31 | 160150 | Work Order Description - 160150 - CM | CM | 3 | 227780 | SCHD | SYS-ISOL | 2019-03-06 | 2019-10-01 | 2019-07-13 | 2019-07-16 | 3 | ENGINEERING | CONSTRUCTION | 48
2019-03-31 | 160152 | Work Order Description - 160152 - CM | CM | 3 | 227780 | SCHD | SYS-ISOL | 2019-03-06 | 2019-12-30 | 2019-07-13 | 2019-07-16 | 3 | ENGINEERING | CONSTRUCTION | 50
2019-03-31 | 160157 | Work Order Description - 160157 - CM | CM | 4 | 447441 | SCHD | NORM-OPS | 2018-10-09 | 2020-08-31 | 2019-05-11 | 2019-05-12 | 4 | MAINTENANCE | FABRIC | 16
2019-03-31 | 160173 | Work Order Description - 160173 - PM | PM | 4 | 469328 | WSCHD | NORM-OPS | 2018-09-03 | 2020-01-18 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 160174 | Work Order Description - 160174 - PM | PM | 2 | 530958 | WSCHD | NORM-OPS | 2018-09-03 | 2018-12-11 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 160175 | Work Order Description - 160175 - PM | PM | 4 | 469328 | WSCHD | NORM-OPS | 2018-09-03 | 2019-01-26 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 160176 | Work Order Description - 160176 - PM | PM | 2 | 530958 | WSCHD | NORM-OPS | 2018-09-03 | 2019-09-06 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 160189 | Work Order Description - 160189 - PM | PM | 4 | 357335 | WSCHD | EQUIP-ISOL | 2018-09-03 | 2019-05-08 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 160207 | Work Order Description - 160207 - PM | PM | 3 | 671601 | WSCHD | EQUIP-ISOL | 2018-09-15 | 2019-06-07 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 160208 | Work Order Description - 160208 - PM | PM | 3 | 308530 | WSCHD | EQUIP-ISOL | 2018-09-15 | 2019-01-22 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 160222 | Work Order Description - 160222 - PM | PM | 2 | 312683 | SCHD | PACK-ISOL | 2018-09-06 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | MECHANICAL | 40
2019-03-31 | 160232 | Work Order Description - 160232 - PM | PM | 4 | 479287 | SCHD | NORM-OPS | 2018-09-06 | 2019-04-21 | 2019-04-20 | 2019-04-20 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 160238 | Work Order Description - 160238 - PM | PM | 4 | 458300 | INPRG | NORM-OPS | 2018-12-08 | 2019-05-26 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | ELECTRICAL | 106
2019-03-31 | 160255 | Work Order Description - 160255 - PM | PM | 4 | 409266 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160257 | Work Order Description - 160257 - PM | PM | 2 | 502749 | SCHD | NORM-OPS | 2018-09-06 | 2019-07-31 | 2019-04-13 | 2019-04-13 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 160262 | Work Order Description - 160262 - PM | PM | 4 | 409267 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160288 | Work Order Description - 160288 - PM | PM | 4 | 408464 | SCHD | PACK-ISOL | 2018-09-06 | 2018-12-27 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 160290 | Work Order Description - 160290 - PM | PM | 4 | 409228 | SCHD | PACK-ISOL | 2018-09-06 | 2019-05-22 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 160292 | Work Order Description - 160292 - PM | PM | 4 | 304099 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 160293 | Work Order Description - 160293 - PM | PM | 4 | 304101 | SCHD | PACK-ISOL | 2018-09-06 | 2019-08-07 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 160294 | Work Order Description - 160294 - PM | PM | 4 | 409264 | SCHD | PACK-ISOL | 2018-09-06 | 2019-10-06 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 160295 | Work Order Description - 160295 - PM | PM | 4 | 30472 | SCHD | PACK-ISOL | 2018-09-06 | 2019-03-08 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 160296 | Work Order Description - 160296 - PM | PM | 4 | 30504 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-12-14 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 160298 | Work Order Description - 160298 - PM | PM | 4 | 256384 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-04-20 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160299 | Work Order Description - 160299 - PM | PM | 4 | 408775 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160300 | Work Order Description - 160300 - PM | PM | 4 | 30380 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160301 | Work Order Description - 160301 - PM | PM | 4 | 30381 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160302 | Work Order Description - 160302 - PM | PM | 4 | 256418 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160303 | Work Order Description - 160303 - PM | PM | 4 | 30611 | SCHD | SYS-ISOL | 2018-09-06 | 2019-04-20 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 160304 | Work Order Description - 160304 - PM | PM | 4 | 30616 | SCHD | SYS-ISOL | 2018-09-06 | 2019-04-20 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160305 | Work Order Description - 160305 - PM | PM | 4 | 304265 | SCHD | SYS-ISOL | 2018-09-06 | 2019-04-20 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160306 | Work Order Description - 160306 - PM | PM | 4 | 408702 | SCHD | SYS-ISOL | 2018-09-06 | 2019-04-20 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160307 | Work Order Description - 160307 - PM | PM | 4 | 304290 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160314 | Work Order Description - 160314 - PM | PM | 4 | 30542 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 160316 | Work Order Description - 160316 - PM | PM | 4 | 408462 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 160317 | Work Order Description - 160317 - PM | PM | 4 | 303868 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-04-20 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160318 | Work Order Description - 160318 - PM | PM | 4 | 401529 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-04-20 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160319 | Work Order Description - 160319 - PM | PM | 4 | 409094 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-04-20 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 160321 | Work Order Description - 160321 - PM | PM | 4 | 304070 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160322 | Work Order Description - 160322 - PM | PM | 4 | 408463 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160323 | Work Order Description - 160323 - PM | PM | 4 | 304098 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160324 | Work Order Description - 160324 - PM | PM | 4 | 304100 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160325 | Work Order Description - 160325 - PM | PM | 4 | 408483 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160326 | Work Order Description - 160326 - PM | PM | 4 | 409270 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160327 | Work Order Description - 160327 - PM | PM | 4 | 409271 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160328 | Work Order Description - 160328 - PM | PM | 4 | 304102 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160329 | Work Order Description - 160329 - PM | PM | 4 | 409227 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 160336 | Work Order Description - 160336 - PM | PM | 4 | 409163 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 160337 | Work Order Description - 160337 - PM | PM | 4 | 304069 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 160338 | Work Order Description - 160338 - PM | PM | 4 | 408461 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 160339 | Work Order Description - 160339 - PM | PM | 4 | 30473 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-04-20 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160340 | Work Order Description - 160340 - PM | PM | 4 | 401527 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 160341 | Work Order Description - 160341 - PM | PM | 4 | 409164 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 160342 | Work Order Description - 160342 - PM | PM | 4 | 409224 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 160343 | Work Order Description - 160343 - PM | PM | 4 | 409225 | SCHD | PACK-ISOL | 2018-09-06 | 2019-04-20 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 160344 | Work Order Description - 160344 - PM | PM | 4 | 491540 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-01-08 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 160345 | Work Order Description - 160345 - PM | PM | 4 | 535474 | SCHD | EQUIP-ISOL | 2018-09-06 | 2019-04-20 | 2019-06-01 | 2019-06-01 | 2 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 160347 | Work Order Description - 160347 - PM | PM | 4 | 81493 | SCHD | PACK-ISOL | 2018-09-06 | 2019-11-02 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 160406 | Work Order Description - 160406 - PM | PM | 3 | 179013 | SCHD | NORM-OPS | 2018-09-06 | 2019-03-26 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 160414 | Work Order Description - 160414 - PSPM | PSPM | 1 | 99774 | SCHD | NORM-OPS | 2019-03-22 | 2019-07-16 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 160415 | Work Order Description - 160415 - PM | PM | 3 | 78432 | SCHD | NORM-OPS | 2018-09-06 | 2019-11-26 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 160416 | Work Order Description - 160416 - PM | PM | 4 | 105592 | SCHD | NORM-OPS | 2018-09-06 | 2019-12-08 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 160422 | Work Order Description - 160422 - PM | PM | 3 | 99507 | SCHD | NORM-OPS | 2018-09-06 | 2019-02-19 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 160444 | Work Order Description - 160444 - PM | PM | 4 | 449144 | WPLAN | PACK-ISOL | 2018-09-03 | 2019-06-23 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 160953 | Work Order Description - 160953 - BR | BR | 4 | 407438 | WSCHD | NORM-OPS | 2019-01-22 | 2020-09-09 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | INSTRUMENTS | 22
2019-03-31 | 160970 | Work Order Description - 160970 - CM | CM | 4 | 677395 | WSCHD | NORM-OPS | 2018-11-17 | 2020-01-01 | 2019-10-26 | 2019-10-26 | 3 | INTEGRITY | FABRIC | 127
2019-03-31 | 160988 | Work Order Description - 160988 - BR | BR | 3 | 227780 | SCHD | SYS-ISOL | 2019-03-06 | 2019-04-08 | 2019-07-13 | 2019-07-14 | 3 | ENGINEERING | CONSTRUCTION | 14
2019-03-31 | 161013 | Work Order Description - 161013 - PM | PM | 3 | 51172 | WSCHD | EQUIP-ISOL | 2018-09-27 | 2019-01-06 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 161108 | Work Order Description - 161108 - BR | BR | 3 | 680732 | SCHD | EQUIP-ISOL | 2018-10-16 | 2020-09-02 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | ELECTRICAL | 7
2019-03-31 | 161109 | Work Order Description - 161109 - CM | CM | 3 | 417989 | SCHD | EQUIP-ISOL | 2018-10-19 | 2019-11-13 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 161111 | Work Order Description - 161111 - BR | BR | 3 | 672753 | WPLAN | EQUIP-ISOL | 2018-09-05 | 2020-09-02 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | ELECTRICAL | 7
2019-03-31 | 161157 | Work Order Description - 161157 - CM | CM | 4 | 495004 | SCHD | EQUIP-ISOL | 2018-09-11 | 2019-06-11 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | ELECTRICAL | 18
2019-03-31 | 161158 | Work Order Description - 161158 - CM | CM | 4 | 361985 | WPLAN | SUBSYS-ISOL | 2018-09-11 | 2020-09-02 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 161183 | Work Order Description - 161183 - CM | CM | 4 | 248340 | WSCHD | NORM-OPS | 2018-09-10 | 2019-09-04 | 2019-04-27 | 2019-04-28 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 161185 | Work Order Description - 161185 - CM | CM | 4 | 399803 | WSCHD | NORM-OPS | 2018-09-10 | 2019-09-04 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 161196 | Work Order Description - 161196 - PSPM | PSPM | 1 | 681797 | SCHD | EQUIP-ISOL | 2019-02-08 | 2019-05-20 | 2019-04-20 | 2019-04-21 | 1 | MAINTENANCE | INSTRUMENTS | 14.5
2019-03-31 | 161197 | Work Order Description - 161197 - PM | PM | 3 | 55071 | WSCHD | EQUIP-ISOL | 2018-09-05 | 2019-05-28 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 161198 | Work Order Description - 161198 - PM | PM | 3 | 357434 | WSCHD | EQUIP-ISOL | 2018-09-05 | 2019-07-03 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 161293 | Work Order Description - 161293 - PSCM | PSCM | 1 | 501914 | SCHD | EQUIP-ISOL | 2019-03-28 | 2020-09-03 | 2019-03-30 | 2019-03-31 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 161304 | Work Order Description - 161304 - CM | CM | 1 | 378847 | WPLAN | NORM-OPS | 2018-09-06 | 2019-08-31 | 2019-05-04 | 2019-05-09 | 3 | INTEGRITY | CONSTRUCTION | 36
2019-03-31 | 161348 | Work Order Description - 161348 - PRJ | PRJ | 3 | 656255 | WSCHD | NORM-OPS | 2018-10-16 | 2019-03-30 | 2019-04-20 | 2019-04-20 | 4 | INTEGRITY | CONSTRUCTION | 60
2019-03-31 | 161352 | Work Order Description - 161352 - CM | CM | 1 | 481625 | SCHD | NORM-OPS | 2018-09-10 | 2019-09-06 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 161362 | Work Order Description - 161362 - CM | CM | 4 | 553108 | SCHD | NORM-OPS | 2018-11-05 | 2019-11-01 | 2019-04-27 | 2019-04-28 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 161399 | Work Order Description - 161399 - PSPM | PSPM | 1 | 378466 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-28 | 2019-04-20 | 2019-04-21 | 1 | MAINTENANCE | ELECTRICAL | 44
2019-03-31 | 161462 | Work Order Description - 161462 - PSCM | PSCM | 1 | 679148 | SCHD | NORM-OPS | 2018-12-05 | 2020-09-12 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 161470 | Work Order Description - 161470 - CM | CM | 3 | 55850 | SCHD | EQUIP-ISOL | 2018-09-10 | 2019-09-06 | 2019-08-10 | 2019-08-10 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 161473 | Work Order Description - 161473 - BR | BR | 3 | 55479 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-11-03 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 161534 | Work Order Description - 161534 - PM | PM | 4 | 501105 | SCHD | NORM-OPS | 2018-09-10 | 2019-04-25 | 2019-02-02 | 2019-02-02 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 161536 | Work Order Description - 161536 - PM | PM | 4 | 128236 | SCHD | NORM-OPS | 2018-09-10 | 2019-04-05 | 2019-02-02 | 2019-02-02 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 161646 | Work Order Description - 161646 - CM | CM | 3 | 462534 | SCHD | SYS-ISOL | 2018-09-18 | 2018-12-28 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 161663 | Work Order Description - 161663 - CM | CM | 3 | 362935 | SCHD | NORM-OPS | 2019-03-29 | 2019-10-01 | 2019-03-30 | 2019-04-07 | 2 | INTEGRITY | FABRIC | 906
2019-03-31 | 161735 | Work Order Description - 161735 - PSPM | PSPM | 1 | 18978 | WPLAN | EQUIP-ISOL | 2018-09-08 | 2019-06-19 | 2019-07-06 | 2019-07-06 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 161742 | Work Order Description - 161742 - PSPM | PSPM | 1 | 531757 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-07-01 | 2019-03-30 | 2019-04-01 | 1 | INTEGRITY | INSPECTION | 77
2019-03-31 | 161774 | Work Order Description - 161774 - PM | PM | 4 | 99926 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-09-24 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 161775 | Work Order Description - 161775 - PM | PM | 4 | 83896 | SCHD | EQUIP-ISOL | 2018-09-12 | 2019-04-11 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 161779 | Work Order Description - 161779 - PM | PM | 4 | 83774 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-04-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 161841 | Work Order Description - 161841 - CM | CM | 3 | 480203 | SCHD | EQUIP-ISOL | 2019-02-07 | 2019-09-08 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | MECHANICAL | 54
2019-03-31 | 161846 | Work Order Description - 161846 - CM | CM | 3 | 480203 | SCHD | EQUIP-ISOL | 2019-02-07 | 2020-09-06 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 161848 | Work Order Description - 161848 - CM | CM | 3 | 55840 | SCHD | PACK-ISOL | 2018-11-27 | 2019-02-03 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 161849 | Work Order Description - 161849 - CM | CM | 1 | 292799 | WPLAN | EQUIP-ISOL | 2018-09-18 | 2019-09-08 | 2019-04-13 | 2019-04-14 | 3 | ENGINEERING | CONSTRUCTION | 38
2019-03-31 | 161853 | Work Order Description - 161853 - CM | CM | 3 | 462680 | WMATL | PACK-ISOL | 2018-11-23 | 2019-01-29 | 2019-09-07 | 2019-09-07 | 2 | INTEGRITY | MECHANICAL | 14
2019-03-31 | 161855 | Work Order Description - 161855 - BR | BR | 4 | 480203 | WSCHD | EQUIP-ISOL | 2018-09-11 | 2020-09-06 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 161859 | Work Order Description - 161859 - CM | CM | 4 | 327145 | WPLAN | SYS-ISOL | 2018-09-13 | 2020-09-06 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | CONSTRUCTION | 48
2019-03-31 | 161861 | Work Order Description - 161861 - CM | CM | 3 | 462543 | WPLAN | PACK-ISOL | 2018-09-12 | 2019-08-24 | 2019-05-04 | 2019-05-04 | 2 | OPERATIONS | OPERATIONS | 71
2019-03-31 | 161885 | Work Order Description - 161885 - PM | PM | 4 | 671548 | SCHD | EQUIP-ISOL | 2018-12-27 | 2019-04-26 | 2019-08-24 | 2019-08-24 | 2 | MAINTENANCE | ELECTRICAL | 27
2019-03-31 | 161904 | Work Order Description - 161904 - PM | PM | 4 | 664990 | WPLAN | EQUIP-ISOL | 2018-09-09 | 2019-07-04 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 161905 | Work Order Description - 161905 - PM | PM | 4 | 393040 | WPLAN | EQUIP-ISOL | 2018-09-09 | 2019-03-19 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 161906 | Work Order Description - 161906 - PM | PM | 4 | 665059 | WPLAN | EQUIP-ISOL | 2018-09-09 | 2019-10-16 | 2019-04-14 | 2019-04-14 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 161907 | Work Order Description - 161907 - PM | PM | 4 | 665058 | WPLAN | EQUIP-ISOL | 2018-09-09 | 2019-07-09 | 2019-04-14 | 2019-04-14 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 162000 | Work Order Description - 162000 - CM | CM | 4 | 217846 | SCHD | NORM-OPS | 2018-09-12 | 2019-09-09 | 2019-07-28 | 2019-07-29 | 3 | INTEGRITY | FABRIC | 12
2019-03-31 | 162001 | Work Order Description - 162001 - BR | BR | 3 | 677965 | WSCHD | NORM-OPS | 2018-09-10 | 2020-09-07 | 2019-05-25 | 2019-05-25 | 4 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 162003 | Work Order Description - 162003 - BR | BR | 3 | 677966 | WSCHD | NORM-OPS | 2018-09-10 | 2020-09-07 | 2019-05-25 | 2019-05-25 | 4 | INTEGRITY | MECHANICAL | 0.6
2019-03-31 | 162009 | Work Order Description - 162009 - BR | BR | 3 | 255468 | SCHD | NORM-OPS | 2018-09-24 | 2019-02-16 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 162041 | Work Order Description - 162041 - PM | PM | 4 | 313581 | WSCHD | NORM-OPS | 2018-09-10 | 2019-02-05 | 2021-03-20 | 2021-03-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 162044 | Work Order Description - 162044 - PM | PM | 4 | 674416 | SCHD | NORM-OPS | 2019-01-03 | 2019-12-04 | 2021-03-07 | 2021-03-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 162066 | Work Order Description - 162066 - PM | PM | 4 | 450411 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-09-19 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | SAFETY | 4
2019-03-31 | 162067 | Work Order Description - 162067 - PM | PM | 4 | 446863 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-02-16 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | SAFETY | 4
2019-03-31 | 162075 | Work Order Description - 162075 - PM | PM | 4 | 408677 | SCHD | PACK-ISOL | 2018-09-12 | 2019-12-03 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162078 | Work Order Description - 162078 - PM | PM | 4 | 543907 | SCHD | PACK-ISOL | 2018-09-12 | 2019-05-15 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162079 | Work Order Description - 162079 - PM | PM | 4 | 304263 | SCHD | PACK-ISOL | 2018-09-12 | 2019-09-18 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162080 | Work Order Description - 162080 - PM | PM | 4 | 30602 | SCHD | PACK-ISOL | 2018-09-12 | 2018-12-23 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162081 | Work Order Description - 162081 - PM | PM | 4 | 408676 | SCHD | PACK-ISOL | 2018-09-12 | 2019-06-06 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162082 | Work Order Description - 162082 - PM | PM | 4 | 408682 | SCHD | PACK-ISOL | 2018-09-12 | 2018-12-04 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162084 | Work Order Description - 162084 - PM | PM | 4 | 543908 | SCHD | PACK-ISOL | 2018-09-12 | 2019-11-15 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162085 | Work Order Description - 162085 - PSPM | PSPM | 4 | 30618 | SCHD | PACK-ISOL | 2018-09-12 | 2019-05-24 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162086 | Work Order Description - 162086 - PSPM | PSPM | 4 | 30620 | SCHD | PACK-ISOL | 2018-09-12 | 2019-12-16 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162087 | Work Order Description - 162087 - PM | PM | 4 | 543881 | SCHD | PACK-ISOL | 2018-09-12 | 2019-05-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162088 | Work Order Description - 162088 - PM | PM | 4 | 30609 | SCHD | PACK-ISOL | 2018-09-12 | 2019-03-18 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162089 | Work Order Description - 162089 - PM | PM | 4 | 30610 | SCHD | PACK-ISOL | 2018-09-12 | 2018-12-21 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162090 | Work Order Description - 162090 - PM | PM | 4 | 543882 | SCHD | PACK-ISOL | 2018-09-12 | 2019-10-06 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162091 | Work Order Description - 162091 - PM | PM | 4 | 543884 | SCHD | PACK-ISOL | 2018-09-12 | 2019-03-09 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162092 | Work Order Description - 162092 - PM | PM | 4 | 30612 | SCHD | SYS-ISOL | 2018-09-12 | 2018-12-08 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162093 | Work Order Description - 162093 - PM | PM | 4 | 408681 | SCHD | PACK-ISOL | 2018-09-12 | 2019-12-22 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162094 | Work Order Description - 162094 - PM | PM | 4 | 543904 | SCHD | PACK-ISOL | 2018-09-12 | 2019-06-04 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162095 | Work Order Description - 162095 - PM | PM | 4 | 543906 | SCHD | PACK-ISOL | 2018-09-12 | 2020-01-05 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162096 | Work Order Description - 162096 - PM | PM | 4 | 30617 | SCHD | PACK-ISOL | 2018-09-12 | 2019-03-19 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162098 | Work Order Description - 162098 - PM | PM | 4 | 664887 | WPLAN | EQUIP-ISOL | 2018-09-10 | 2019-04-04 | 2019-04-07 | 2019-04-07 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 162164 | Work Order Description - 162164 - CM | CM | 1 | 204612 | WPLAN | NORM-OPS | 2018-10-01 | 2019-05-31 | 2019-04-13 | 2019-04-13 | 2 | INTEGRITY | INSPECTION | 56
2019-03-31 | 162175 | Work Order Description - 162175 - CM | CM | 3 | 262409 | SCHD | PACK-ISOL | 2018-11-20 | 2019-09-11 | 2019-05-18 | 2019-05-18 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 162179 | Work Order Description - 162179 - BR | BR | 4 | 556244 | SCHD | SYS-ISOL | 2019-03-29 | 2020-09-08 | 2020-07-27 | 2020-07-27 | 4 | MAINTENANCE | ELECTRICAL | 34
2019-03-31 | 162195 | Work Order Description - 162195 - PM | PM | 3 | 595914 | WSCHD | TPS | 2018-09-27 | 2019-06-13 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 162196 | Work Order Description - 162196 - PM | PM | 3 | 671142 | SCHD | EQUIP-ISOL | 2019-01-10 | 2019-06-07 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 162197 | Work Order Description - 162197 - PM | PM | 3 | 308001 | SCHD | EQUIP-ISOL | 2019-01-10 | 2019-03-17 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 162198 | Work Order Description - 162198 - PM | PM | 3 | 246620 | SCHD | EQUIP-ISOL | 2019-01-10 | 2020-01-20 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 162280 | Work Order Description - 162280 - CM | CM | 4 | 527307 | SCHD | NORM-OPS | 2018-12-21 | 2020-09-09 | 2019-04-21 | 2019-04-21 | 4 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 162289 | Work Order Description - 162289 - BR | BR | 1 | 481465 | WSCHD | NORM-OPS | 2018-09-11 | 2020-09-09 | 2019-05-04 | 2019-05-05 | 4 | MAINTENANCE | MECHANICAL | 60
2019-03-31 | 162317 | Work Order Description - 162317 - CM | CM | 1 | 89295 | WPLAN | NORM-OPS | 2018-11-08 | 2020-09-09 | 2019-07-13 | 2019-08-23 | 4 | ENGINEERING | CONSTRUCTION | 288
2019-03-31 | 162318 | Work Order Description - 162318 - CM | CM | 2 | 89295 | WPLAN | NORM-OPS | 2018-11-08 | 2020-09-09 | 2019-07-13 | 2019-09-20 | 4 | ENGINEERING | CONSTRUCTION | 288
2019-03-31 | 162402 | Work Order Description - 162402 - PM | PM | 4 | 360353 | WSCHD | PACK-ISOL | 2018-09-15 | 2019-11-01 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 162424 | Work Order Description - 162424 - PM | PM | 4 | 527185 | SCHD | PACK-ISOL | 2018-12-17 | 2019-04-29 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 162433 | Work Order Description - 162433 - PM | PM | 4 | 375514 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-08-10 | 2019-07-13 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 162505 | Work Order Description - 162505 - CM | CM | 4 | 368215 | SCHD | NORM-OPS | 2018-10-14 | 2020-09-10 | 2019-04-27 | 2019-04-28 | 4 | ENGINEERING | CONSTRUCTION | 1
2019-03-31 | 162571 | Work Order Description - 162571 - CM | CM | 1 | 228839 | WPLAN | NORM-OPS | 2018-09-13 | 2019-09-12 | 2019-09-07 | 2019-09-07 | 3 | ENGINEERING | CONSTRUCTION | 1
2019-03-31 | 162581 | Work Order Description - 162581 - CM | CM | 1 | 228839 | SCHD | NORM-OPS | 2019-03-29 | 2019-06-01 | 2019-04-14 | 2019-05-23 | 3 | ENGINEERING | CONSTRUCTION | 611.5
2019-03-31 | 162584 | Work Order Description - 162584 - BR | BR | 3 | 503134 | WMATL | NORM-OPS | 2018-09-21 | 2020-09-10 | 2019-05-04 | 2019-05-05 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 162587 | Work Order Description - 162587 - CM | CM | 4 | 29697 | SCHD | EQUIP-ISOL | 2018-12-24 | 2020-09-10 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 162607 | Work Order Description - 162607 - PM | PM | 4 | 396520 | WPLAN | EQUIP-ISOL | 2018-09-13 | 2018-12-20 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 162684 | Work Order Description - 162684 - CM | CM | 3 | 549224 | SCHD | SYS-ISOL | 2018-11-05 | 2019-09-15 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MECHANICAL | 40
2019-03-31 | 162698 | Work Order Description - 162698 - PSCM | PSCM | 1 | 305229 | WSCHD | NORM-OPS | 2018-09-23 | 2020-09-11 | 2019-08-03 | 2019-08-03 | 4 | MAINTENANCE | MECHANICAL | 36.5
2019-03-31 | 162699 | Work Order Description - 162699 - PSPM | PSPM | 1 | 261244 | WSCHD | SUBSYS-ISOL | 2018-10-29 | 2020-01-01 | 2019-04-27 | 2019-04-28 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 162736 | Work Order Description - 162736 - BR | BR | 3 | 245878 | WSCHD | PACK-ISOL | 2018-10-27 | 2019-09-13 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 17.5
2019-03-31 | 162737 | Work Order Description - 162737 - BR | BR | 3 | 354675 | WSCHD | PACK-ISOL | 2018-10-31 | 2019-09-13 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 9.5
2019-03-31 | 162740 | Work Order Description - 162740 - PM | PM | 4 | 246202 | WSCHD | EQUIP-ISOL | 2018-09-14 | 2019-05-01 | 2020-01-25 | 2020-01-25 | 2 | MAINTENANCE | ELECTRICAL | 19
2019-03-31 | 162866 | Work Order Description - 162866 - BR | BR | 1 | 468588 | WPLAN | NORM-OPS | 2018-09-21 | 2019-09-14 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 55
2019-03-31 | 162872 | Work Order Description - 162872 - CM | CM | 4 | 259466 | WPLAN | PACK-ISOL | 2018-09-18 | 2018-12-07 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 162874 | Work Order Description - 162874 - CM | CM | 2 | 99232 | WSCHD | EQUIP-ISOL | 2018-12-27 | 2019-09-14 | 2018-12-26 | 2018-12-26 | 3 | MAINTENANCE | SERVICES | 69
2019-03-31 | 162876 | Work Order Description - 162876 - CM | CM | 3 | 492104 | WPLAN | PACK-ISOL | 2018-09-18 | 2019-06-15 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 162877 | Work Order Description - 162877 - CM | CM | 3 | 499348 | WPLAN | EQUIP-ISOL | 2019-02-14 | 2019-08-07 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 162882 | Work Order Description - 162882 - CM | CM | 4 | 259470 | WPLAN | PACK-ISOL | 2018-09-18 | 2019-11-03 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 162883 | Work Order Description - 162883 - CM | CM | 4 | 188010 | WPLAN | SYS-ISOL | 2018-09-18 | 2019-06-10 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 162912 | Work Order Description - 162912 - PM | PM | 2 | 325456 | SCHD | EQUIP-ISOL | 2018-09-18 | 2019-09-14 | 2019-04-27 | 2019-04-27 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 162913 | Work Order Description - 162913 - PM | PM | 4 | 325457 | SCHD | EQUIP-ISOL | 2018-09-18 | 2019-06-09 | 2019-04-27 | 2019-04-27 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 162914 | Work Order Description - 162914 - PM | PM | 4 | 189152 | SCHD | EQUIP-ISOL | 2018-09-18 | 2019-11-14 | 2019-04-20 | 2019-04-20 | 2 | OPERATIONS | OPERATIONS | 7
2019-03-31 | 162994 | Work Order Description - 162994 - PSCM | PSCM | 1 | 542008 | WMATL | TPS | 2018-10-03 | 2019-09-18 | 2019-07-13 | 2019-07-16 | 3 | MAINTENANCE | MECHANICAL | 38
2019-03-31 | 162996 | Work Order Description - 162996 - PSCM | PSCM | 1 | 306253 | SCHD | TPS | 2019-03-29 | 2020-09-13 | 2019-07-13 | 2019-07-16 | 4 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 162998 | Work Order Description - 162998 - CM | CM | 1 | 527307 | SCHD | EQUIP-ISOL | 2018-09-19 | 2020-09-13 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 163007 | Work Order Description - 163007 - BR | BR | 1 | 125515 | SCHD | NORM-OPS | 2019-02-13 | 2020-09-13 | 2019-08-18 | 2019-08-19 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 163012 | Work Order Description - 163012 - CM | CM | 3 | 396150 | WMATL | TPS | 2019-02-12 | 2019-03-03 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 163021 | Work Order Description - 163021 - PSCM | PSCM | 1 | 18763 | WSCHD | EQUIP-ISOL | 2018-09-21 | 2019-09-29 | 2019-05-25 | 2019-05-26 | 3 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 163051 | Work Order Description - 163051 - PM | PM | 4 | 93258 | WPLAN | EQUIP-ISOL | 2018-09-16 | 2019-10-10 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 163052 | Work Order Description - 163052 - PM | PM | 4 | 396791 | WPLAN | EQUIP-ISOL | 2018-09-16 | 2018-12-02 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 163053 | Work Order Description - 163053 - PM | PM | 4 | 393258 | WPLAN | EQUIP-ISOL | 2018-09-16 | 2019-12-22 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 163054 | Work Order Description - 163054 - PM | PM | 4 | 93263 | WPLAN | EQUIP-ISOL | 2018-09-16 | 2020-01-19 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 163145 | Work Order Description - 163145 - CM | CM | 3 | 441751 | WPLAN | TPS | 2018-12-17 | 2019-09-16 | 2019-07-13 | 2019-07-14 | 3 | OPERATIONS | OPERATIONS | 9
2019-03-31 | 163152 | Work Order Description - 163152 - BR | BR | 4 | 661008 | WSCHD | NORM-OPS | 2018-09-21 | 2020-09-14 | 2019-07-20 | 2019-07-21 | 4 | ENGINEERING | CONSTRUCTION | 1
2019-03-31 | 163154 | Work Order Description - 163154 - CM | CM | 4 | 527844 | SCHD | NORM-OPS | 2018-10-16 | 2019-09-16 | 2019-06-09 | 2019-06-09 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 163155 | Work Order Description - 163155 - PSCM | PSCM | 4 | 652220 | WSCHD | EQUIP-ISOL | 2018-09-21 | 2019-08-12 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | SERVICES | 35
2019-03-31 | 163179 | Work Order Description - 163179 - BR | BR | 3 | 490428 | WSCHD | SYS-ISOL | 2018-11-23 | 2020-01-06 | 2020-05-02 | 2020-05-02 | 2 | MAINTENANCE | MECHANICAL | 80
2019-03-31 | 163187 | Work Order Description - 163187 - PM | PM | 4 | 408366 | WSCHD | PACK-ISOL | 2018-09-17 | 2019-05-04 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 163202 | Work Order Description - 163202 - PM | PM | 4 | 481636 | SCHD | NORM-OPS | 2018-09-18 | 2018-12-15 | 2019-02-02 | 2019-02-02 | 3 | OPERATIONS | SAFETY | 15
2019-03-31 | 163203 | Work Order Description - 163203 - PM | PM | 4 | 481637 | SCHD | NORM-OPS | 2018-09-18 | 2018-12-03 | 2019-02-02 | 2019-02-02 | 3 | OPERATIONS | SAFETY | 14
2019-03-31 | 163210 | Work Order Description - 163210 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2018-09-18 | 2019-07-26 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 163224 | Work Order Description - 163224 - PSPM | PSPM | 1 | 180459 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 163240 | Work Order Description - 163240 - PSPM | PSPM | 4 | 409091 | SCHD | EQUIP-ISOL | 2018-09-18 | 2019-10-06 | 2019-07-06 | 2019-07-06 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 163554 | Work Order Description - 163554 - PM | PM | 4 | 261768 | SCHD | NORM-OPS | 2018-12-27 | 2019-07-05 | 2019-04-06 | 2019-04-07 | 2 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 163558 | Work Order Description - 163558 - CM | CM | 1 | 126130 | WPLAN | NORM-OPS | 2018-12-06 | 2020-09-15 | 2019-04-21 | 2019-04-22 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 163564 | Work Order Description - 163564 - CM | CM | 3 | 26663 | SCHD | EQUIP-ISOL | 2018-11-05 | 2020-09-15 | 2020-04-04 | 2020-04-05 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 163574 | Work Order Description - 163574 - BR | BR | 4 | 75008 | SCHD | PACK-ISOL | 2019-02-13 | 2019-12-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 163575 | Work Order Description - 163575 - CM | CM | 3 | 26542 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-03-20 | 2019-05-18 | 2019-05-19 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 163588 | Work Order Description - 163588 - PSCM | PSCM | 1 | 308736 | SCHD | PACK-ISOL | 2018-10-29 | 2019-09-17 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 163634 | Work Order Description - 163634 - PSCM | PSCM | 1 | 361963 | WSCHD | NORM-OPS | 2018-09-21 | 2020-09-15 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 163643 | Work Order Description - 163643 - CM | CM | 3 | 259467 | WMATL | SYS-ISOL | 2018-11-23 | 2019-03-31 | 2019-07-27 | 2019-07-28 | 2 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 163644 | Work Order Description - 163644 - BR | BR | 3 | 318262 | WSCHD | NORM-OPS | 2018-09-23 | 2019-07-26 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 163650 | Work Order Description - 163650 - PM | PM | 2 | 314195 | SCHD | NORM-OPS | 2019-01-09 | 2019-10-09 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 163651 | Work Order Description - 163651 - PM | PM | 3 | 595920 | WSCHD | EQUIP-ISOL | 2018-09-27 | 2018-12-22 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 163652 | Work Order Description - 163652 - PM | PM | 3 | 308030 | SCHD | EQUIP-ISOL | 2019-01-09 | 2019-05-15 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 163742 | Work Order Description - 163742 - BR | BR | 1 | 535929 | WPLAN | NORM-OPS | 2018-09-21 | 2019-09-18 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 45
2019-03-31 | 163759 | Work Order Description - 163759 - CM | CM | 4 | 527192 | SCHD | TPS | 2019-02-13 | 2019-09-18 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 163769 | Work Order Description - 163769 - BR | BR | 4 | 245535 | WSCHD | EQUIP-ISOL | 2018-10-07 | 2020-09-16 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 163790 | Work Order Description - 163790 - BR | BR | 4 | 320031 | SCHD | NORM-OPS | 2018-09-24 | 2021-03-01 | 2019-03-30 | 2019-03-30 | 4 | DRILLING | DRILLING | 1
2019-03-31 | 163791 | Work Order Description - 163791 - CM | CM | 4 | 527192 | WPLAN | PACK-ISOL | 2018-12-25 | 2019-09-18 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 163823 | Work Order Description - 163823 - CM | CM | 2 | 499187 | SCHD | EQUIP-ISOL | 2018-10-15 | 2019-06-04 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 163901 | Work Order Description - 163901 - BR | BR | 4 | 674430 | SCHD | NORM-OPS | 2018-10-29 | 2020-09-17 | 2019-04-20 | 2019-04-21 | 4 | MAINTENANCE | MECHANICAL | 50
2019-03-31 | 163921 | Work Order Description - 163921 - BR | BR | 4 | 651390 | WMATL | NORM-OPS | 2018-09-21 | 2020-09-17 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 163922 | Work Order Description - 163922 - CM | CM | 1 | 363052 | WSCHD | NORM-OPS | 2018-09-21 | 2020-09-17 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | MECHANICAL | 34
2019-03-31 | 163924 | Work Order Description - 163924 - BR | BR | 4 | 538449 | WSCHD | NORM-OPS | 2018-09-21 | 2020-09-17 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 163925 | Work Order Description - 163925 - BR | BR | 4 | 362953 | WSCHD | NORM-OPS | 2018-09-21 | 2019-02-20 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 163926 | Work Order Description - 163926 - CM | CM | 4 | 535905 | WSCHD | NORM-OPS | 2018-09-21 | 2020-09-17 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 163939 | Work Order Description - 163939 - BR | BR | 2 | 555793 | SCHD | EQUIP-ISOL | 2018-09-24 | 2020-09-17 | 2019-05-04 | 2019-05-06 | 4 | MAINTENANCE | INSTRUMENTS | 40
2019-03-31 | 163940 | Work Order Description - 163940 - CM | CM | 2 | 550825 | SCHD | PACK-ISOL | 2019-01-25 | 2020-09-17 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 163941 | Work Order Description - 163941 - BR | BR | 1 | 128026 | SCHD | NORM-OPS | 2019-02-13 | 2020-09-18 | 2019-05-24 | 2019-05-24 | 4 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 164042 | Work Order Description - 164042 - CM | CM | 4 | 29041 | WPLAN | NORM-OPS | 2019-03-28 | 2019-08-02 | 2019-06-15 | 2019-06-15 | 2 | MAINTENANCE | CONSTRUCTION | 96
2019-03-31 | 164046 | Work Order Description - 164046 - BR | BR | 4 | 325096 | SCHD | NORM-OPS | 2018-09-24 | 2020-09-18 | 2019-07-27 | 2019-07-27 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 164050 | Work Order Description - 164050 - BR | BR | 4 | 468648 | WSCHD | NORM-OPS | 2018-11-05 | 2019-09-20 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 164083 | Work Order Description - 164083 - PM | PM | 4 | 188949 | SCHD | NORM-OPS | 2018-09-24 | 2019-05-08 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 164165 | Work Order Description - 164165 - BR | BR | 3 | 542134 | SCHD | NORM-OPS | 2018-10-09 | 2020-09-19 | 2019-09-14 | 2019-09-14 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 164169 | Work Order Description - 164169 - BR | BR | 3 | 491405 | SCHD | EQUIP-ISOL | 2018-09-24 | 2019-01-01 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 0
2019-03-31 | 164172 | Work Order Description - 164172 - CM | CM | 1 | 555307 | SCHD | NORM-OPS | 2018-09-24 | 2019-09-21 | 2019-04-20 | 2019-04-25 | 3 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 164200 | Work Order Description - 164200 - CM | CM | 3 | 318335 | WSCHD | NORM-OPS | 2018-09-25 | 2019-09-25 | 2019-05-25 | 2019-05-26 | 3 | MAINTENANCE | ELECTRICAL | 140
2019-03-31 | 164216 | Work Order Description - 164216 - CM | CM | 3 | 547585 | WPLAN | NORM-OPS | 2018-09-25 | 2019-12-17 | 2019-05-25 | 2019-05-26 | 2 | MAINTENANCE | ELECTRICAL | 140
2019-03-31 | 164229 | Work Order Description - 164229 - PRJ | PRJ | 4 | 368215 | WSCHD | NORM-OPS | 2018-09-22 | 2019-05-24 | 2019-04-20 | 2019-04-21 | 4 | ENGINEERING | CONSTRUCTION | 32
2019-03-31 | 164231 | Work Order Description - 164231 - BR | BR | 3 | 308739 | WSCHD | EQUIP-ISOL | 2018-09-22 | 2020-09-19 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 164241 | Work Order Description - 164241 - BR | BR | 2 | 499535 | WPLAN | EQUIP-ISOL | 2018-09-27 | 2020-09-19 | 2019-05-18 | 2019-05-19 | 4 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 164251 | Work Order Description - 164251 - PSPM | PSPM | 1 | 671828 | SCHD | NORM-OPS | 2019-02-08 | 2019-05-05 | 2019-03-30 | 2019-03-31 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 164256 | Work Order Description - 164256 - PSPM | PSPM | 1 | 545266 | WSCHD | PACK-ISOL | 2018-09-27 | 2019-12-22 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 164257 | Work Order Description - 164257 - PSPM | PSPM | 1 | 545266 | WSCHD | PACK-ISOL | 2018-09-27 | 2019-12-22 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 164268 | Work Order Description - 164268 - PSPM | PSPM | 1 | 545266 | WSCHD | NORM-OPS | 2018-09-22 | 2019-12-22 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 164309 | Work Order Description - 164309 - PM | PM | 4 | 106148 | SCHD | TPS | 2018-12-27 | 2019-03-03 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 164385 | Work Order Description - 164385 - BR | BR | 3 | 671632 | WSCHD | EQUIP-ISOL | 2018-09-22 | 2019-06-26 | 2019-10-05 | 2019-10-05 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 164411 | Work Order Description - 164411 - PM | PM | 4 | 51662 | WSCHD | NORM-OPS | 2018-09-23 | 2019-01-06 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 164422 | Work Order Description - 164422 - PM | PM | 4 | 18972 | WSCHD | NORM-OPS | 2018-09-23 | 2019-04-05 | 2022-03-05 | 2022-03-05 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 164423 | Work Order Description - 164423 - PM | PM | 4 | 355546 | WSCHD | NORM-OPS | 2018-09-23 | 2019-01-20 | 2022-03-05 | 2022-03-05 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 164424 | Work Order Description - 164424 - PM | PM | 4 | 18973 | WSCHD | NORM-OPS | 2018-09-23 | 2019-11-28 | 2022-03-05 | 2022-03-05 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 164425 | Work Order Description - 164425 - PM | PM | 4 | 355547 | WSCHD | NORM-OPS | 2018-09-23 | 2019-07-07 | 2022-03-05 | 2022-03-05 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 164426 | Work Order Description - 164426 - PM | PM | 4 | 18985 | WSCHD | NORM-OPS | 2018-09-23 | 2019-12-07 | 2022-03-05 | 2022-03-05 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 164427 | Work Order Description - 164427 - PM | PM | 4 | 355548 | WSCHD | NORM-OPS | 2018-09-23 | 2018-12-05 | 2022-03-05 | 2022-03-05 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 164430 | Work Order Description - 164430 - PM | PM | 2 | 33427 | WSCHD | NORM-OPS | 2018-09-23 | 2018-12-02 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 164448 | Work Order Description - 164448 - PSPM | PSPM | 1 | 180974 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | MECHANICAL | 8
2019-03-31 | 164455 | Work Order Description - 164455 - PM | PM | 4 | 659870 | SCHD | NORM-OPS | 2018-10-05 | 2020-01-02 | 2019-03-23 | 2019-03-23 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 164460 | Work Order Description - 164460 - PM | PM | 4 | 396795 | WPLAN | EQUIP-ISOL | 2018-09-23 | 2019-04-11 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 164461 | Work Order Description - 164461 - PM | PM | 4 | 665066 | WPLAN | EQUIP-ISOL | 2018-09-23 | 2019-08-17 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 164462 | Work Order Description - 164462 - PM | PM | 4 | 93287 | WPLAN | EQUIP-ISOL | 2018-09-23 | 2019-10-02 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 164463 | Work Order Description - 164463 - PM | PM | 4 | 93286 | WPLAN | EQUIP-ISOL | 2018-09-23 | 2019-03-19 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 164572 | Work Order Description - 164572 - BR | BR | 3 | 671632 | WSCHD | PACK-ISOL | 2018-09-24 | 2019-01-02 | 2019-10-05 | 2019-10-05 | 2 | MAINTENANCE | MECHANICAL | 170
2019-03-31 | 164573 | Work Order Description - 164573 - BR | BR | 3 | 375780 | SCHD | SYS-ISOL | 2019-02-13 | 2019-06-30 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 164587 | Work Order Description - 164587 - BR | BR | 4 | 476885 | WSCHD | PACK-ISOL | 2018-10-30 | 2020-09-21 | 2019-05-11 | 2019-05-12 | 4 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 164613 | Work Order Description - 164613 - BR | BR | 2 | 245662 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-09-23 | 2019-04-06 | 2019-04-07 | 3 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 164629 | Work Order Description - 164629 - BR | BR | 2 | 375612 | WPLAN | EQUIP-ISOL | 2018-09-25 | 2019-09-23 | 2019-04-20 | 2019-04-21 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 164640 | Work Order Description - 164640 - PSPM | PSPM | 1 | 544001 | SCHD | PACK-ISOL | 2018-10-09 | 2019-12-26 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 164648 | Work Order Description - 164648 - PSPM | PSPM | 1 | 408811 | SCHD | PACK-ISOL | 2018-10-09 | 2019-12-17 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 164734 | Work Order Description - 164734 - BR | BR | 3 | 137779 | WSCHD | PACK-ISOL | 2018-09-25 | 2020-09-22 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | SERVICES | 72
2019-03-31 | 164761 | Work Order Description - 164761 - CM | CM | 2 | 393882 | SCHD | EQUIP-ISOL | 2018-10-05 | 2020-09-22 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 164772 | Work Order Description - 164772 - BR | BR | 3 | 137779 | WSCHD | PACK-ISOL | 2018-09-25 | 2020-09-22 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | SERVICES | 36
2019-03-31 | 164774 | Work Order Description - 164774 - BR | BR | 3 | 137779 | WSCHD | PACK-ISOL | 2018-09-25 | 2020-09-22 | 2019-12-07 | 2019-12-07 | 4 | MAINTENANCE | SERVICES | 16
2019-03-31 | 164775 | Work Order Description - 164775 - BR | BR | 3 | 137779 | WSCHD | PACK-ISOL | 2018-09-25 | 2020-09-22 | 2019-12-07 | 2019-12-07 | 4 | MAINTENANCE | SERVICES | 16
2019-03-31 | 164776 | Work Order Description - 164776 - BR | BR | 3 | 137779 | WSCHD | PACK-ISOL | 2018-09-25 | 2020-09-22 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | OPERATIONS | 158
2019-03-31 | 164779 | Work Order Description - 164779 - BR | BR | 1 | 387813 | SCHD | NORM-OPS | 2018-10-05 | 2020-09-22 | 2019-04-20 | 2019-04-22 | 4 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 164787 | Work Order Description - 164787 - BR | BR | 1 | 679184 | WSCHD | EQUIP-ISOL | 2018-12-08 | 2019-06-09 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | INSTRUMENTS | 37
2019-03-31 | 164801 | Work Order Description - 164801 - PM | PM | 4 | 666260 | WSCHD | NORM-OPS | 2018-09-25 | 2019-09-13 | 2020-12-26 | 2020-12-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 164806 | Work Order Description - 164806 - PM | PM | 4 | 490184 | WSCHD | EQUIP-ISOL | 2018-09-25 | 2019-07-26 | 2020-03-07 | 2020-03-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 164811 | Work Order Description - 164811 - PM | PM | 3 | 359313 | WSCHD | NORM-OPS | 2018-09-25 | 2019-08-09 | 2019-06-22 | 2019-06-22 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 164817 | Work Order Description - 164817 - PSPM | PSPM | 1 | 447441 | SCHD | PACK-ISOL | 2019-03-15 | 2019-05-24 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | ELECTRICAL | 160
2019-03-31 | 164878 | Work Order Description - 164878 - BR | BR | 3 | 137779 | WPLAN | PACK-ISOL | 2018-09-25 | 2020-09-23 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | CONSTRUCTION | 116
2019-03-31 | 164880 | Work Order Description - 164880 - BR | BR | 3 | 137779 | WPLAN | PACK-ISOL | 2018-09-25 | 2020-09-23 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | CONSTRUCTION | 116
2019-03-31 | 164916 | Work Order Description - 164916 - BR | BR | 3 | 137779 | WSCHD | PACK-ISOL | 2018-09-26 | 2020-09-23 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | OPERATIONS | 126
2019-03-31 | 164921 | Work Order Description - 164921 - PSCM | PSCM | 3 | 137779 | WSCHD | PACK-ISOL | 2018-09-26 | 2020-09-23 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | OPERATIONS | 57
2019-03-31 | 164925 | Work Order Description - 164925 - BR | BR | 1 | 408363 | WPLAN | EQUIP-ISOL | 2018-09-26 | 2020-09-23 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | ELECTRICAL | 24
2019-03-31 | 164929 | Work Order Description - 164929 - BR | BR | 1 | 308850 | WPLAN | EQUIP-ISOL | 2018-09-26 | 2020-09-23 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 164952 | Work Order Description - 164952 - BR | BR | 2 | 554851 | SCHD | TPS | 2018-12-24 | 2020-09-23 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 164956 | Work Order Description - 164956 - PM | PM | 4 | 450396 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-10-04 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | MECHANICAL | 6
2019-03-31 | 164957 | Work Order Description - 164957 - PM | PM | 4 | 99495 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-06-09 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | MECHANICAL | 6
2019-03-31 | 165035 | Work Order Description - 165035 - PM | PM | 4 | 273658 | WSCHD | EQUIP-ISOL | 2018-09-26 | 2019-01-20 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 165036 | Work Order Description - 165036 - BR | BR | 4 | 126058 | WPLAN | EQUIP-ISOL | 2018-10-28 | 2020-09-24 | 2019-04-21 | 2019-04-22 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 165046 | Work Order Description - 165046 - CM | CM | 3 | 188958 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-08-18 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 165055 | Work Order Description - 165055 - CM | CM | 4 | 491476 | SCHD | EQUIP-ISOL | 2018-10-09 | 2020-09-24 | 2020-03-07 | 2020-03-07 | 4 | MAINTENANCE | ELECTRICAL | 16
2019-03-31 | 165093 | Work Order Description - 165093 - BR | BR | 3 | 188825 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-03-28 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 165095 | Work Order Description - 165095 - BR | BR | 3 | 309635 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-03-28 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 165096 | Work Order Description - 165096 - BR | BR | 3 | 309636 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-03-28 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 165097 | Work Order Description - 165097 - BR | BR | 3 | 324749 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-03-28 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 165118 | Work Order Description - 165118 - BR | BR | 1 | 546698 | WPLAN | EQUIP-ISOL | 2018-10-03 | 2020-09-24 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 56
2019-03-31 | 165121 | Work Order Description - 165121 - PM | PM | 4 | 295957 | WSCHD | EQUIP-ISOL | 2018-10-23 | 2019-01-17 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | OPERATIONS | 4
2019-03-31 | 165125 | Work Order Description - 165125 - PM | PM | 4 | 245662 | WSCHD | EQUIP-ISOL | 2018-09-27 | 2019-05-14 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 11
2019-03-31 | 165127 | Work Order Description - 165127 - PM | PM | 4 | 360358 | SCHD | PACK-ISOL | 2019-01-21 | 2019-06-27 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 165128 | Work Order Description - 165128 - PM | PM | 3 | 409690 | SCHD | PACK-ISOL | 2019-01-21 | 2019-05-14 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 165129 | Work Order Description - 165129 - PM | PM | 3 | 53295 | SCHD | PACK-ISOL | 2019-01-21 | 2019-05-14 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 165130 | Work Order Description - 165130 - PM | PM | 3 | 410142 | SCHD | PACK-ISOL | 2019-01-21 | 2019-07-25 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 165131 | Work Order Description - 165131 - PM | PM | 4 | 357428 | SCHD | PACK-ISOL | 2019-01-21 | 2019-07-25 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 165132 | Work Order Description - 165132 - PM | PM | 4 | 53629 | SCHD | PACK-ISOL | 2019-01-21 | 2019-07-25 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 165133 | Work Order Description - 165133 - PM | PM | 4 | 410178 | SCHD | PACK-ISOL | 2019-01-21 | 2019-07-25 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 165134 | Work Order Description - 165134 - PM | PM | 3 | 54518 | SCHD | PACK-ISOL | 2019-01-21 | 2019-05-14 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 165135 | Work Order Description - 165135 - PM | PM | 3 | 360564 | SCHD | PACK-ISOL | 2019-01-21 | 2019-05-14 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 165137 | Work Order Description - 165137 - PM | PM | 3 | 54234 | WSCHD | PACK-ISOL | 2018-10-19 | 2019-10-27 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 165148 | Work Order Description - 165148 - PM | PM | 4 | 387912 | SCHD | EQUIP-ISOL | 2019-01-21 | 2019-03-11 | 2019-07-13 | 2019-07-14 | 2 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 165149 | Work Order Description - 165149 - PM | PM | 4 | 668417 | SCHD | EQUIP-ISOL | 2019-01-21 | 2019-05-30 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 165223 | Work Order Description - 165223 - BR | BR | 3 | 308307 | SCHD | NORM-OPS | 2018-10-01 | 2019-09-27 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 165225 | Work Order Description - 165225 - BR | BR | 3 | 214603 | WPLAN | SYS-ISOL | 2018-09-29 | 2020-09-25 | 2019-04-28 | 2019-04-29 | 4 | MAINTENANCE | MECHANICAL | 66
2019-03-31 | 165228 | Work Order Description - 165228 - CM | CM | 4 | 188379 | WMATL | NORM-OPS | 2018-10-19 | 2019-09-27 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 13
2019-03-31 | 165232 | Work Order Description - 165232 - PRJ | PRJ | 4 | 490862 | WPLAN | NORM-OPS | 2018-10-23 | 2019-07-06 | 2019-04-27 | 2019-04-28 | 4 | MAINTENANCE | CONSTRUCTION | 21
2019-03-31 | 165242 | Work Order Description - 165242 - BR | BR | 3 | 498449 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-03-29 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 165244 | Work Order Description - 165244 - PSCM | PSCM | 1 | 308850 | SCHD | EQUIP-ISOL | 2019-02-27 | 2020-09-25 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | ELECTRICAL | 40
2019-03-31 | 165246 | Work Order Description - 165246 - BR | BR | 3 | 324721 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-03-29 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 165247 | Work Order Description - 165247 - BR | BR | 3 | 309675 | SCHD | TPS | 2018-10-09 | 2019-03-29 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 165260 | Work Order Description - 165260 - CM | CM | 4 | 126773 | SCHD | NORM-OPS | 2018-10-05 | 2020-09-25 | 2019-04-28 | 2019-04-29 | 4 | MAINTENANCE | CONSTRUCTION | 16
2019-03-31 | 165272 | Work Order Description - 165272 - PSCM | PSCM | 1 | 501444 | SCHD | NORM-OPS | 2018-12-05 | 2019-07-01 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | CONSTRUCTION | 20
2019-03-31 | 165276 | Work Order Description - 165276 - BR | BR | 4 | 501444 | SCHD | NORM-OPS | 2018-11-05 | 2019-10-15 | 2020-02-29 | 2020-02-29 | 3 | INTEGRITY | FABRIC | 20
2019-03-31 | 165283 | Work Order Description - 165283 - BR | BR | 3 | 387747 | SCHD | SYS-ISOL | 2019-03-06 | 2019-09-27 | 2019-07-13 | 2019-07-14 | 3 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 165286 | Work Order Description - 165286 - PM | PM | 2 | 408273 | WSCHD | EQUIP-ISOL | 2018-09-28 | 2019-05-15 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 165367 | Work Order Description - 165367 - BR | BR | 4 | 491476 | SCHD | NORM-OPS | 2018-10-09 | 2020-09-26 | 2020-03-07 | 2020-03-07 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 165398 | Work Order Description - 165398 - BR | BR | 3 | 395488 | WPLAN | TPS | 2018-10-11 | 2019-09-28 | 2019-07-13 | 2019-07-14 | 3 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 165401 | Work Order Description - 165401 - BR | BR | 3 | 113911 | WPLAN | TPS | 2018-10-13 | 2019-09-28 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 165402 | Work Order Description - 165402 - PSCM | PSCM | 1 | 363543 | WSCHD | TPS | 2018-09-30 | 2019-09-29 | 2019-06-01 | 2019-06-02 | 3 | MAINTENANCE | MECHANICAL | 46
2019-03-31 | 165430 | Work Order Description - 165430 - PM | PM | 4 | 450409 | SCHD | EQUIP-ISOL | 2018-10-09 | 2018-12-05 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | SAFETY | 4
2019-03-31 | 165453 | Work Order Description - 165453 - PSPM | PSPM | 4 | 78324 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-10-17 | 2019-04-08 | 2019-04-08 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 165559 | Work Order Description - 165559 - PM | PM | 4 | 355375 | WSCHD | EQUIP-ISOL | 2018-09-30 | 2019-06-22 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 165565 | Work Order Description - 165565 - PM | PM | 4 | 122684 | SCHD | NORM-OPS | 2018-10-09 | 2019-12-13 | 2019-02-02 | 2019-02-02 | 3 | OPERATIONS | SAFETY | 2
2019-03-31 | 165576 | Work Order Description - 165576 - PM | PM | 4 | 396790 | WPLAN | EQUIP-ISOL | 2018-09-30 | 2019-01-18 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 165577 | Work Order Description - 165577 - PM | PM | 4 | 93257 | WPLAN | EQUIP-ISOL | 2018-09-30 | 2019-03-09 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 165578 | Work Order Description - 165578 - PM | PM | 4 | 93288 | WPLAN | EQUIP-ISOL | 2018-09-30 | 2019-06-08 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 165579 | Work Order Description - 165579 - PM | PM | 4 | 393259 | WPLAN | EQUIP-ISOL | 2018-09-30 | 2019-08-26 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 165713 | Work Order Description - 165713 - PSCM | PSCM | 3 | 314373 | SCHD | NORM-OPS | 2018-10-01 | 2019-04-01 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 165725 | Work Order Description - 165725 - CM | CM | 3 | 469472 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-09-30 | 2019-08-24 | 2019-08-24 | 3 | MAINTENANCE | FABRIC | 50
2019-03-31 | 165728 | Work Order Description - 165728 - BR | BR | 4 | 476541 | WSCHD | EQUIP-ISOL | 2018-10-01 | 2020-09-28 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 165734 | Work Order Description - 165734 - BR | BR | 1 | 666132 | WSCHD | SYS-ISOL | 2018-10-07 | 2019-09-30 | 2019-05-25 | 2019-05-26 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 165774 | Work Order Description - 165774 - PM | PM | 4 | 383927 | SCHD | SYS-ISOL | 2018-10-05 | 2019-05-18 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 165839 | Work Order Description - 165839 - BR | BR | 3 | 78273 | WPLAN | TPS | 2018-12-17 | 2019-04-02 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 13
2019-03-31 | 165842 | Work Order Description - 165842 - CM | CM | 3 | 556432 | SCHD | TPS | 2018-10-09 | 2020-09-29 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 1670
2019-03-31 | 165848 | Work Order Description - 165848 - BR | BR | 2 | 449077 | WPLAN | EQUIP-ISOL | 2018-10-11 | 2020-09-29 | 2019-09-29 | 2019-09-29 | 4 | INTEGRITY | MECHANICAL | 3
2019-03-31 | 165863 | Work Order Description - 165863 - PM | PM | 2 | 314214 | SCHD | NORM-OPS | 2019-01-21 | 2019-08-23 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 165864 | Work Order Description - 165864 - PM | PM | 4 | 261950 | WSCHD | EQUIP-ISOL | 2018-10-02 | 2018-12-10 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 165865 | Work Order Description - 165865 - PM | PM | 4 | 249623 | WSCHD | NORM-OPS | 2018-10-02 | 2019-11-09 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 165867 | Work Order Description - 165867 - PM | PM | 4 | 314497 | WSCHD | EQUIP-ISOL | 2018-10-24 | 2019-03-26 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 165868 | Work Order Description - 165868 - PM | PM | 4 | 307605 | WSCHD | EQUIP-ISOL | 2018-10-02 | 2019-03-26 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 165869 | Work Order Description - 165869 - PM | PM | 4 | 546655 | WSCHD | NORM-OPS | 2018-10-02 | 2018-12-20 | 2020-12-19 | 2020-12-19 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 165870 | Work Order Description - 165870 - PM | PM | 4 | 546657 | WSCHD | NORM-OPS | 2018-10-02 | 2019-04-30 | 2022-03-05 | 2022-03-05 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 165871 | Work Order Description - 165871 - PM | PM | 4 | 357142 | WSCHD | NORM-OPS | 2018-10-02 | 2019-04-05 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 165872 | Work Order Description - 165872 - PM | PM | 4 | 356944 | WSCHD | NORM-OPS | 2018-10-02 | 2019-10-30 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 165873 | Work Order Description - 165873 - PM | PM | 4 | 356944 | WSCHD | NORM-OPS | 2018-10-02 | 2018-12-14 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 165874 | Work Order Description - 165874 - PM | PM | 4 | 356944 | WSCHD | NORM-OPS | 2018-10-02 | 2019-01-30 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 165875 | Work Order Description - 165875 - PM | PM | 4 | 308894 | WSCHD | NORM-OPS | 2018-10-02 | 2019-08-22 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 165876 | Work Order Description - 165876 - PM | PM | 4 | 308894 | WSCHD | NORM-OPS | 2018-10-02 | 2019-07-04 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 165877 | Work Order Description - 165877 - PM | PM | 4 | 356944 | WSCHD | NORM-OPS | 2018-10-02 | 2019-11-14 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 165878 | Work Order Description - 165878 - PM | PM | 4 | 356944 | WSCHD | NORM-OPS | 2018-10-02 | 2019-05-01 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 165879 | Work Order Description - 165879 - PM | PM | 4 | 305529 | WSCHD | EQUIP-ISOL | 2018-10-02 | 2019-03-26 | 2020-03-07 | 2020-03-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 165881 | Work Order Description - 165881 - PM | PM | 4 | 595893 | WSCHD | EQUIP-ISOL | 2018-10-02 | 2019-04-29 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 165882 | Work Order Description - 165882 - PM | PM | 4 | 358177 | WSCHD | EQUIP-ISOL | 2018-10-02 | 2019-03-26 | 2020-02-22 | 2020-02-22 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 165890 | Work Order Description - 165890 - PM | PM | 4 | 400132 | SCHD | EQUIP-ISOL | 2019-03-20 | 2019-12-28 | 2019-03-30 | 2019-03-30 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 165906 | Work Order Description - 165906 - PM | PM | 2 | 462658 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-03-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 165908 | Work Order Description - 165908 - PM | PM | 2 | 498292 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-03-26 | 2019-05-18 | 2019-05-18 | 2 | OPERATIONS | OPERATIONS | 7
2019-03-31 | 165914 | Work Order Description - 165914 - PSPM | PSPM | 1 | 378463 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-28 | 2019-04-28 | 2019-04-30 | 1 | MAINTENANCE | ELECTRICAL | 45
2019-03-31 | 165990 | Work Order Description - 165990 - CM | CM | 3 | 358886 | WSCHD | SYS-ISOL | 2018-10-02 | 2019-10-02 | 2019-09-07 | 2019-09-08 | 3 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 166007 | Work Order Description - 166007 - BR | BR | 3 | 404913 | WSCHD | EQUIP-ISOL | 2019-02-19 | 2019-04-03 | 2019-05-11 | 2019-05-12 | 3 | MAINTENANCE | INSTRUMENTS | 61.5
2019-03-31 | 166012 | Work Order Description - 166012 - CM | CM | 4 | 501594 | WPLAN | NORM-OPS | 2018-10-03 | 2020-09-30 | 2020-02-29 | 2020-02-29 | 4 | MAINTENANCE | FABRIC | 1
2019-03-31 | 166015 | Work Order Description - 166015 - BR | BR | 3 | 306406 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-04-03 | 2019-05-18 | 2019-05-19 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 166025 | Work Order Description - 166025 - PM | PM | 2 | 33427 | WSCHD | PACK-ISOL | 2018-10-19 | 2019-05-20 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | ELECTRICAL | 58
2019-03-31 | 166027 | Work Order Description - 166027 - PM | PM | 4 | 660951 | SCHD | NORM-OPS | 2018-11-26 | 2018-12-30 | 2019-04-20 | 2019-04-20 | 3 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 166030 | Work Order Description - 166030 - PM | PM | 2 | 312683 | SCHD | PACK-ISOL | 2019-01-22 | 2019-03-27 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 166036 | Work Order Description - 166036 - PM | PM | 4 | 490496 | SCHD | PACK-ISOL | 2018-10-09 | 2019-09-05 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 166037 | Work Order Description - 166037 - PM | PM | 4 | 29701 | SCHD | PACK-ISOL | 2018-10-09 | 2019-09-05 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 166139 | Work Order Description - 166139 - CM | CM | 1 | 378846 | SCHD | NORM-OPS | 2019-03-15 | 2019-05-29 | 2019-04-10 | 2019-05-05 | 2 | INTEGRITY | CONSTRUCTION | 353
2019-03-31 | 166155 | Work Order Description - 166155 - CM | CM | 4 | 368279 | WPLAN | NORM-OPS | 2018-10-10 | 2019-10-01 | 2019-04-27 | 2019-04-28 | 3 | INTEGRITY | FABRIC | 343
2019-03-31 | 166168 | Work Order Description - 166168 - BR | BR | 1 | 226476 | WPLAN | TPS | 2018-10-06 | 2020-10-01 | 2019-05-04 | 2019-05-05 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 166187 | Work Order Description - 166187 - PSPM | PSPM | 1 | 657134 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-05-31 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 166198 | Work Order Description - 166198 - PM | PM | 4 | 354614 | WSCHD | PACK-ISOL | 2018-10-25 | 2019-11-16 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | MECHANICAL | 110
2019-03-31 | 166199 | Work Order Description - 166199 - PM | PM | 2 | 321115 | WSCHD | PACK-ISOL | 2018-10-26 | 2019-05-21 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | ELECTRICAL | 52
2019-03-31 | 166200 | Work Order Description - 166200 - PM | PM | 3 | 360609 | WSCHD | EQUIP-ISOL | 2018-10-04 | 2019-05-21 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 166201 | Work Order Description - 166201 - PSPM | PSPM | 1 | 54316 | WSCHD | EQUIP-ISOL | 2018-10-04 | 2019-07-01 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 166202 | Work Order Description - 166202 - PSPM | PSPM | 1 | 57185 | WSCHD | EQUIP-ISOL | 2018-10-04 | 2019-07-01 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 166203 | Work Order Description - 166203 - PSPM | PSPM | 1 | 57186 | SCHD | EQUIP-ISOL | 2019-02-08 | 2019-03-26 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 166206 | Work Order Description - 166206 - PM | PM | 4 | 54314 | WSCHD | PACK-ISOL | 2018-10-25 | 2019-02-14 | 2019-10-05 | 2019-10-05 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 166209 | Work Order Description - 166209 - PM | PM | 3 | 262042 | WSCHD | EQUIP-ISOL | 2018-10-04 | 2019-05-08 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 166252 | Work Order Description - 166252 - PSPM | PSPM | 1 | 481651 | SCHD | NORM-OPS | 2019-03-29 | 2019-06-02 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | ELECTRICAL | 54.5
2019-03-31 | 166256 | Work Order Description - 166256 - PM | PM | 4 | 479287 | SCHD | NORM-OPS | 2018-10-09 | 2018-12-23 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | SAFETY | 3
2019-03-31 | 166271 | Work Order Description - 166271 - PSPM | PSPM | 1 | 462783 | SCHD | EQUIP-ISOL | 2018-10-09 | 2020-01-12 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 166274 | Work Order Description - 166274 - PM | PM | 3 | 25159 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-10-09 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 166286 | Work Order Description - 166286 - PM | PM | 4 | 653823 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-02-08 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 166288 | Work Order Description - 166288 - PM | PM | 4 | 95502 | SCHD | PACK-ISOL | 2018-10-09 | 2019-06-24 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 166300 | Work Order Description - 166300 - PM | PM | 4 | 388197 | WPLAN | EQUIP-ISOL | 2018-10-04 | 2020-01-09 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 166302 | Work Order Description - 166302 - PM | PM | 4 | 89617 | WPLAN | EQUIP-ISOL | 2018-10-04 | 2019-05-24 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 166303 | Work Order Description - 166303 - PM | PM | 4 | 396254 | WPLAN | EQUIP-ISOL | 2018-10-04 | 2019-02-24 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 166309 | Work Order Description - 166309 - PSPM | PSPM | 1 | 659515 | SCHD | NORM-OPS | 2019-03-07 | 2019-04-09 | 2019-04-07 | 2019-04-07 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 166912 | Work Order Description - 166912 - CM | CM | 3 | 326000 | WSCHD | EQUIP-ISOL | 2018-10-26 | 2019-10-04 | 2019-04-06 | 2019-04-07 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 166920 | Work Order Description - 166920 - CM | CM | 3 | 554850 | SCHD | EQUIP-ISOL | 2019-01-25 | 2020-10-02 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 22
2019-03-31 | 166929 | Work Order Description - 166929 - CM | CM | 3 | 355366 | WPLAN | PACK-ISOL | 2018-11-05 | 2020-10-02 | 2019-08-03 | 2019-08-03 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 166932 | Work Order Description - 166932 - CM | CM | 3 | 53841 | WPLAN | PACK-ISOL | 2018-11-05 | 2020-01-02 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 166934 | Work Order Description - 166934 - CM | CM | 3 | 18383 | WPLAN | PACK-ISOL | 2018-11-05 | 2020-10-02 | 2019-09-07 | 2019-09-07 | 4 | INTEGRITY | MECHANICAL | 1
2019-03-31 | 166935 | Work Order Description - 166935 - CM | CM | 3 | 53483 | WPLAN | PACK-ISOL | 2018-11-05 | 2019-10-04 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | MECHANICAL | 1
2019-03-31 | 166936 | Work Order Description - 166936 - CM | CM | 3 | 535813 | WPLAN | PACK-ISOL | 2018-11-05 | 2019-10-04 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | CONSTRUCTION | 0
2019-03-31 | 166939 | Work Order Description - 166939 - CM | CM | 3 | 671608 | WPLAN | PACK-ISOL | 2018-11-05 | 2020-10-02 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 166941 | Work Order Description - 166941 - CM | CM | 3 | 357261 | WPLAN | PACK-ISOL | 2018-11-05 | 2019-10-04 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 166946 | Work Order Description - 166946 - CM | CM | 3 | 354611 | WPLAN | PACK-ISOL | 2018-11-05 | 2020-10-02 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 166950 | Work Order Description - 166950 - BR | BR | 4 | 500199 | WMATL | EQUIP-ISOL | 2018-11-12 | 2020-10-02 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 166964 | Work Order Description - 166964 - BR | BR | 3 | 97858 | WPLAN | SYS-ISOL | 2018-10-10 | 2020-10-02 | 2019-07-13 | 2019-07-15 | 4 | MAINTENANCE | MECHANICAL | 35
2019-03-31 | 166965 | Work Order Description - 166965 - BR | BR | 3 | 128663 | SCHD | SYS-ISOL | 2019-02-13 | 2020-10-02 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 166967 | Work Order Description - 166967 - BR | BR | 2 | 33806 | WSCHD | NORM-OPS | 2018-10-30 | 2020-10-02 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 166971 | Work Order Description - 166971 - PM | PM | 3 | 57188 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2019-08-27 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 166972 | Work Order Description - 166972 - PM | PM | 3 | 54525 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2019-05-22 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 166973 | Work Order Description - 166973 - PM | PM | 3 | 53334 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2019-05-22 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 166974 | Work Order Description - 166974 - PM | PM | 3 | 409719 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2019-05-22 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 166975 | Work Order Description - 166975 - PM | PM | 3 | 409721 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2019-05-22 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 166976 | Work Order Description - 166976 - PM | PM | 3 | 54239 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2019-06-08 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 166977 | Work Order Description - 166977 - PM | PM | 3 | 261843 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2020-01-10 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 166978 | Work Order Description - 166978 - PM | PM | 4 | 360360 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2019-10-02 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 166979 | Work Order Description - 166979 - PM | PM | 3 | 360361 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2019-04-16 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 166980 | Work Order Description - 166980 - PM | PM | 4 | 360362 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2019-05-15 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 166981 | Work Order Description - 166981 - PM | PM | 4 | 57184 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2019-10-03 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 166982 | Work Order Description - 166982 - PM | PM | 4 | 360365 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2019-12-03 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 166983 | Work Order Description - 166983 - PM | PM | 3 | 54317 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2020-01-24 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 166984 | Work Order Description - 166984 - PM | PM | 3 | 53664 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2019-08-02 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 166985 | Work Order Description - 166985 - PM | PM | 4 | 409720 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2019-05-22 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 166986 | Work Order Description - 166986 - PM | PM | 3 | 54528 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2019-05-22 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 166987 | Work Order Description - 166987 - PM | PM | 4 | 53666 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2019-06-27 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 166988 | Work Order Description - 166988 - PM | PM | 3 | 55017 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2019-06-27 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 166989 | Work Order Description - 166989 - PM | PM | 4 | 53665 | WSCHD | EQUIP-ISOL | 2018-10-05 | 2019-06-27 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167000 | Work Order Description - 167000 - PM | PM | 4 | 309966 | SCHD | NORM-OPS | 2018-10-09 | 2019-01-24 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 167001 | Work Order Description - 167001 - PM | PM | 4 | 325097 | SCHD | NORM-OPS | 2018-10-09 | 2019-06-14 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 167002 | Work Order Description - 167002 - PM | PM | 4 | 325096 | SCHD | NORM-OPS | 2018-10-09 | 2019-02-21 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 167003 | Work Order Description - 167003 - PM | PM | 4 | 89619 | WPLAN | EQUIP-ISOL | 2018-10-05 | 2019-03-19 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 167125 | Work Order Description - 167125 - PSPM | PSPM | 1 | 676295 | WPLAN | PACK-ISOL | 2018-10-05 | 2019-11-01 | 2019-09-07 | 2019-09-07 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 167130 | Work Order Description - 167130 - CM | CM | 1 | 324482 | SCHD | NORM-OPS | 2018-10-09 | 2020-10-03 | 2019-09-28 | 2019-09-28 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167132 | Work Order Description - 167132 - BR | BR | 3 | 666935 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-04-06 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | ELECTRICAL | 263
2019-03-31 | 167146 | Work Order Description - 167146 - CM | CM | 1 | 477255 | SCHD | NORM-OPS | 2018-10-30 | 2019-10-05 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 167148 | Work Order Description - 167148 - PSCM | PSCM | 3 | 323290 | WMATL | NORM-OPS | 2018-11-08 | 2020-10-03 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 167149 | Work Order Description - 167149 - BR | BR | 3 | 72283 | SCHD | PACK-ISOL | 2019-03-15 | 2021-03-12 | 2019-04-30 | 2019-05-01 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 167152 | Work Order Description - 167152 - PSPM | PSPM | 1 | 57929 | WSCHD | EQUIP-ISOL | 2018-10-06 | 2019-11-01 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 38
2019-03-31 | 167153 | Work Order Description - 167153 - PM | PM | 4 | 399941 | WSCHD | EQUIP-ISOL | 2018-10-19 | 2019-01-09 | 2021-06-12 | 2021-06-12 | 1 | INTEGRITY | CONSTRUCTION | 12
2019-03-31 | 167154 | Work Order Description - 167154 - PM | PM | 3 | 53689 | WSCHD | EQUIP-ISOL | 2018-10-06 | 2019-06-28 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 167155 | Work Order Description - 167155 - PM | PM | 3 | 308533 | WSCHD | EQUIP-ISOL | 2018-10-06 | 2019-03-30 | 2020-05-09 | 2020-05-09 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 167156 | Work Order Description - 167156 - PM | PM | 3 | 57068 | WSCHD | EQUIP-ISOL | 2018-10-24 | 2019-10-15 | 2020-05-09 | 2020-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167157 | Work Order Description - 167157 - PM | PM | 3 | 54625 | WSCHD | EQUIP-ISOL | 2018-10-06 | 2019-05-23 | 2020-05-09 | 2020-05-09 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167158 | Work Order Description - 167158 - PM | PM | 3 | 54629 | WSCHD | EQUIP-ISOL | 2018-10-06 | 2019-05-23 | 2020-05-09 | 2020-05-09 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167159 | Work Order Description - 167159 - PM | PM | 4 | 318577 | WSCHD | EQUIP-ISOL | 2018-10-06 | 2019-07-23 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 167160 | Work Order Description - 167160 - PM | PM | 3 | 409792 | WSCHD | EQUIP-ISOL | 2018-10-06 | 2019-05-13 | 2020-05-09 | 2020-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167161 | Work Order Description - 167161 - PM | PM | 3 | 410216 | WSCHD | EQUIP-ISOL | 2018-10-06 | 2019-05-05 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 167162 | Work Order Description - 167162 - PM | PM | 3 | 410251 | WSCHD | EQUIP-ISOL | 2018-10-06 | 2019-05-05 | 2020-05-09 | 2020-05-09 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 167165 | Work Order Description - 167165 - PM | PM | 3 | 261847 | WSCHD | EQUIP-ISOL | 2018-10-06 | 2019-11-05 | 2020-05-09 | 2020-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167166 | Work Order Description - 167166 - PM | PM | 3 | 674803 | WSCHD | EQUIP-ISOL | 2018-10-06 | 2019-03-30 | 2020-05-09 | 2020-05-09 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167189 | Work Order Description - 167189 - PM | PM | 4 | 555305 | SCHD | NORM-OPS | 2018-10-09 | 2019-02-16 | 2019-02-02 | 2019-02-02 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 167194 | Work Order Description - 167194 - PM | PM | 4 | 310224 | SCHD | PACK-ISOL | 2018-10-09 | 2019-07-16 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 167195 | Work Order Description - 167195 - PM | PM | 4 | 176853 | SCHD | EQUIP-ISOL | 2018-10-09 | 2019-07-16 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 167253 | Work Order Description - 167253 - BR | BR | 3 | 72283 | SCHD | NORM-OPS | 2019-02-13 | 2020-10-04 | 2019-07-07 | 2019-07-07 | 4 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 167259 | Work Order Description - 167259 - CM | CM | 4 | 50999 | WSCHD | EQUIP-ISOL | 2019-02-21 | 2019-06-19 | 2019-04-20 | 2019-04-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 167260 | Work Order Description - 167260 - CM | CM | 3 | 277425 | WPLAN | TPS | 2018-10-20 | 2019-10-06 | 2019-07-13 | 2019-08-03 | 3 | MAINTENANCE | MECHANICAL | 458
2019-03-31 | 167263 | Work Order Description - 167263 - BR | BR | 3 | 405153 | WSCHD | PACK-ISOL | 2018-10-10 | 2019-04-07 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | INSTRUMENTS | 105
2019-03-31 | 167272 | Work Order Description - 167272 - CM | CM | 4 | 462464 | SCHD | NORM-OPS | 2018-10-09 | 2020-10-04 | 2019-08-24 | 2019-08-24 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 167279 | Work Order Description - 167279 - BR | BR | 1 | 681800 | WPLAN | EQUIP-ISOL | 2018-10-07 | 2019-04-07 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 23
2019-03-31 | 167294 | Work Order Description - 167294 - BR | BR | 3 | 248392 | WPLAN | NORM-OPS | 2018-10-07 | 2020-10-04 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 167295 | Work Order Description - 167295 - BR | BR | 1 | 200046 | WPLAN | NORM-OPS | 2018-10-07 | 2020-10-05 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 167310 | Work Order Description - 167310 - PSPM | PSPM | 1 | 545222 | WSCHD | NORM-OPS | 2018-10-07 | 2019-06-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 167311 | Work Order Description - 167311 - PM | PM | 2 | 321199 | WSCHD | NORM-OPS | 2018-10-07 | 2019-04-13 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 167313 | Work Order Description - 167313 - PSPM | PSPM | 1 | 137779 | WSCHD | NORM-OPS | 2018-10-07 | 2019-10-27 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 167314 | Work Order Description - 167314 - PM | PM | 4 | 261980 | SCHD | PACK-ISOL | 2019-02-06 | 2018-12-04 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 167316 | Work Order Description - 167316 - PM | PM | 3 | 409794 | WSCHD | EQUIP-ISOL | 2018-10-07 | 2019-05-24 | 2020-04-10 | 2020-04-10 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167318 | Work Order Description - 167318 - PM | PM | 4 | 357396 | WSCHD | PACK-ISOL | 2018-10-19 | 2019-08-04 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 167319 | Work Order Description - 167319 - PM | PM | 4 | 410057 | WSCHD | PACK-ISOL | 2018-10-19 | 2019-08-04 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 167320 | Work Order Description - 167320 - PM | PM | 3 | 657794 | WSCHD | EQUIP-ISOL | 2018-10-07 | 2019-05-24 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 167321 | Work Order Description - 167321 - PM | PM | 3 | 680550 | SCHD | EQUIP-ISOL | 2018-10-12 | 2019-05-24 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 167322 | Work Order Description - 167322 - PM | PM | 3 | 53231 | WSCHD | PACK-ISOL | 2018-10-19 | 2019-05-24 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167323 | Work Order Description - 167323 - PM | PM | 3 | 53234 | WSCHD | PACK-ISOL | 2018-10-19 | 2019-05-24 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167326 | Work Order Description - 167326 - PM | PM | 3 | 54475 | WSCHD | PACK-ISOL | 2018-10-19 | 2019-05-24 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167327 | Work Order Description - 167327 - PM | PM | 3 | 54476 | WSCHD | PACK-ISOL | 2018-10-19 | 2019-05-24 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167334 | Work Order Description - 167334 - PM | PM | 3 | 54248 | WSCHD | EQUIP-ISOL | 2018-10-07 | 2019-09-11 | 2020-04-04 | 2020-04-04 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167335 | Work Order Description - 167335 - PM | PM | 4 | 261853 | WSCHD | EQUIP-ISOL | 2018-10-07 | 2019-06-01 | 2020-04-04 | 2020-04-04 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167336 | Work Order Description - 167336 - PM | PM | 3 | 57069 | WSCHD | EQUIP-ISOL | 2018-10-07 | 2019-12-25 | 2020-04-04 | 2020-04-04 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167353 | Work Order Description - 167353 - PM | PM | 1 | 665068 | WPLAN | EQUIP-ISOL | 2018-10-07 | 2019-06-05 | 2019-04-14 | 2019-04-14 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 167354 | Work Order Description - 167354 - PM | PM | 4 | 665067 | WPLAN | EQUIP-ISOL | 2018-10-07 | 2018-12-18 | 2019-04-14 | 2019-04-14 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 167355 | Work Order Description - 167355 - PM | PM | 4 | 396797 | WPLAN | EQUIP-ISOL | 2018-10-07 | 2019-06-22 | 2019-04-14 | 2019-04-14 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 167356 | Work Order Description - 167356 - PM | PM | 4 | 396796 | WPLAN | EQUIP-ISOL | 2018-10-07 | 2019-10-12 | 2019-04-14 | 2019-04-14 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 167414 | Work Order Description - 167414 - CM | CM | 1 | 502007 | WMATL | NORM-OPS | 2018-10-29 | 2020-10-05 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 13
2019-03-31 | 167428 | Work Order Description - 167428 - CM | CM | 3 | 361207 | SCHD | NORM-OPS | 2018-10-29 | 2019-10-07 | 2019-08-31 | 2019-09-01 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 167433 | Work Order Description - 167433 - BR | BR | 4 | 457996 | SCHD | EQUIP-ISOL | 2019-01-25 | 2018-12-13 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 167458 | Work Order Description - 167458 - CM | CM | 3 | 308426 | SCHD | EQUIP-ISOL | 2018-10-29 | 2020-10-05 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 167474 | Work Order Description - 167474 - PSPM | PSPM | 1 | 57931 | WSCHD | EQUIP-ISOL | 2018-10-08 | 2019-07-01 | 2019-09-07 | 2019-09-07 | 1 | MAINTENANCE | INSTRUMENTS | 41
2019-03-31 | 167483 | Work Order Description - 167483 - PM | PM | 4 | 501105 | SCHD | NORM-OPS | 2018-10-09 | 2019-04-09 | 2019-02-02 | 2019-02-02 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 167485 | Work Order Description - 167485 - PM | PM | 4 | 128236 | SCHD | NORM-OPS | 2018-10-09 | 2019-10-15 | 2019-02-02 | 2019-02-02 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 167501 | Work Order Description - 167501 - PM | PM | 4 | 664911 | WPLAN | EQUIP-ISOL | 2018-10-08 | 2018-12-17 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 167586 | Work Order Description - 167586 - BR | BR | 3 | 312718 | INPRG | PACK-ISOL | 2019-01-11 | 2019-04-09 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 167587 | Work Order Description - 167587 - CM | CM | 4 | 262784 | WPLAN | NORM-OPS | 2019-01-09 | 2020-01-05 | 2019-07-06 | 2019-07-06 | 3 | INTEGRITY | CONSTRUCTION | 20
2019-03-31 | 167594 | Work Order Description - 167594 - BR | BR | 4 | 568984 | WPLAN | NORM-OPS | 2018-10-08 | 2020-10-06 | 2019-06-08 | 2019-06-08 | 4 | OPERATIONS | FABRIC | 294
2019-03-31 | 167597 | Work Order Description - 167597 - CM | CM | 1 | 204612 | WPLAN | NORM-OPS | 2018-10-14 | 2019-10-31 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | CONSTRUCTION | 252
2019-03-31 | 167600 | Work Order Description - 167600 - BR | BR | 3 | 689066 | WPLAN | TPS | 2018-10-10 | 2019-10-08 | 2019-07-13 | 2019-07-20 | 3 | MAINTENANCE | MECHANICAL | 104
2019-03-31 | 167606 | Work Order Description - 167606 - BR | BR | 4 | 80160 | WPLAN | NORM-OPS | 2018-10-22 | 2020-10-06 | 2020-02-08 | 2020-02-11 | 4 | MAINTENANCE | CONSTRUCTION | 24
2019-03-31 | 167613 | Work Order Description - 167613 - CM | CM | 1 | 204612 | WPLAN | NORM-OPS | 2018-10-10 | 2019-11-01 | 2019-04-20 | 2019-04-21 | 3 | INTEGRITY | CONSTRUCTION | 294
2019-03-31 | 167616 | Work Order Description - 167616 - CM | CM | 4 | 204612 | WSCHD | TPS | 2018-10-10 | 2020-09-01 | 2020-05-02 | 2020-05-02 | 3 | INTEGRITY | FABRIC | 392
2019-03-31 | 167617 | Work Order Description - 167617 - BR | BR | 3 | 438720 | WPLAN | EQUIP-ISOL | 2018-10-08 | 2020-10-06 | 2020-05-02 | 2020-05-03 | 4 | MAINTENANCE | CONSTRUCTION | 12
2019-03-31 | 167629 | Work Order Description - 167629 - CM | CM | 1 | 204612 | WPLAN | TPS | 2018-10-10 | 2020-09-01 | 2020-05-02 | 2020-05-02 | 3 | INTEGRITY | FABRIC | 392
2019-03-31 | 167636 | Work Order Description - 167636 - CM | CM | 1 | 204612 | WPLAN | TPS | 2018-10-14 | 2020-09-01 | 2020-05-02 | 2020-05-02 | 3 | INTEGRITY | FABRIC | 196
2019-03-31 | 167641 | Work Order Description - 167641 - CM | CM | 3 | 671528 | SCHD | EQUIP-ISOL | 2018-10-29 | 2019-11-10 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 167646 | Work Order Description - 167646 - PM | PM | 2 | 540775 | SCHD | EQUIP-ISOL | 2019-01-30 | 2019-04-02 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 56
2019-03-31 | 167651 | Work Order Description - 167651 - PM | PM | 3 | 53717 | SCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-01 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167654 | Work Order Description - 167654 - PM | PM | 3 | 54682 | SCHD | EQUIP-ISOL | 2019-02-06 | 2019-05-26 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 167661 | Work Order Description - 167661 - PSPM | PSPM | 1 | 357643 | WSCHD | PACK-ISOL | 2018-10-23 | 2019-09-30 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 167666 | Work Order Description - 167666 - PM | PM | 4 | 25401 | SCHD | NORM-OPS | 2018-10-09 | 2019-04-17 | 2019-04-13 | 2019-04-13 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 167778 | Work Order Description - 167778 - CM | CM | 3 | 504159 | WMATL | NORM-OPS | 2018-10-16 | 2019-04-10 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 167780 | Work Order Description - 167780 - BR | BR | 1 | 80580 | WPLAN | TPS | 2018-10-13 | 2020-10-07 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 167782 | Work Order Description - 167782 - CM | CM | 1 | 29041 | SCHD | EQUIP-ISOL | 2019-02-08 | 2020-10-07 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 167789 | Work Order Description - 167789 - BR | BR | 1 | 128663 | WMATL | SYS-ISOL | 2019-02-12 | 2019-10-09 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 167790 | Work Order Description - 167790 - BR | BR | 1 | 663789 | WPLAN | TPS | 2018-10-13 | 2020-10-07 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 167797 | Work Order Description - 167797 - BR | BR | 3 | 50985 | WPLAN | NORM-OPS | 2019-02-19 | 2019-04-11 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 104
2019-03-31 | 167808 | Work Order Description - 167808 - CM | CM | 2 | 266550 | SCHD | EQUIP-ISOL | 2018-11-22 | 2019-05-23 | 2019-04-21 | 2019-04-22 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 167814 | Work Order Description - 167814 - BR | BR | 1 | 403920 | SCHD | NORM-OPS | 2018-11-05 | 2020-10-07 | 2019-05-04 | 2019-05-04 | 4 | INTEGRITY | SAFETY | 550.5
2019-03-31 | 167819 | Work Order Description - 167819 - CM | CM | 4 | 29697 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-07-11 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 167822 | Work Order Description - 167822 - PSPM | PSPM | 4 | 411258 | SCHD | NORM-OPS | 2019-03-14 | 2019-04-27 | 2019-04-06 | 2019-04-11 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 167828 | Work Order Description - 167828 - PM | PM | 4 | 601923 | SCHD | NORM-OPS | 2018-11-05 | 2018-12-22 | 2019-04-06 | 2019-04-06 | 2 | OPERATIONS | OPERATIONS | 60
2019-03-31 | 167915 | Work Order Description - 167915 - CM | CM | 1 | 547708 | WSCHD | PACK-ISOL | 2018-10-10 | 2019-10-10 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 167929 | Work Order Description - 167929 - PM | PM | 4 | 482731 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-05-01 | 2019-08-17 | 2019-08-17 | 2 | INTEGRITY | INSPECTION | 318
2019-03-31 | 167938 | Work Order Description - 167938 - PSCM | PSCM | 3 | 273771 | WPLAN | NORM-OPS | 2019-01-17 | 2019-05-14 | 2019-04-20 | 2019-04-21 | 2 | MAINTENANCE | ELECTRICAL | 24
2019-03-31 | 167950 | Work Order Description - 167950 - PSPM | PSPM | 1 | 248069 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-04-13 | 2019-03-30 | 2019-03-30 | 1 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 168044 | Work Order Description - 168044 - CM | CM | 1 | 554688 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-04-12 | 2019-03-30 | 2019-03-30 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 168081 | Work Order Description - 168081 - PM | PM | 4 | 632580 | SCHD | NORM-OPS | 2018-11-05 | 2019-06-27 | 2019-02-02 | 2019-02-02 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 168082 | Work Order Description - 168082 - PM | PM | 4 | 583919 | SCHD | NORM-OPS | 2018-11-05 | 2020-01-09 | 2019-02-02 | 2019-02-02 | 3 | OPERATIONS | SAFETY | 4
2019-03-31 | 168084 | Work Order Description - 168084 - PM | PM | 4 | 583934 | SCHD | NORM-OPS | 2018-11-05 | 2019-06-22 | 2019-02-09 | 2019-02-09 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 168085 | Work Order Description - 168085 - PM | PM | 4 | 583934 | SCHD | NORM-OPS | 2018-11-05 | 2019-08-27 | 2019-02-09 | 2019-02-09 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 168166 | Work Order Description - 168166 - BR | BR | 2 | 392229 | SCHD | PACK-ISOL | 2019-03-29 | 2019-04-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 168185 | Work Order Description - 168185 - BR | BR | 2 | 179478 | SCHD | PACK-ISOL | 2019-03-29 | 2019-04-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 168186 | Work Order Description - 168186 - BR | BR | 2 | 453312 | SCHD | PACK-ISOL | 2019-03-29 | 2019-04-13 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 168187 | Work Order Description - 168187 - BR | BR | 2 | 669708 | WPLAN | PACK-ISOL | 2018-10-13 | 2019-04-13 | 2019-08-25 | 2019-09-02 | 3 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 168192 | Work Order Description - 168192 - BR | BR | 2 | 392140 | WPLAN | PACK-ISOL | 2018-11-13 | 2019-03-15 | 2019-05-25 | 2019-05-26 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 168207 | Work Order Description - 168207 - CM | CM | 4 | 520045 | WPLAN | PACK-ISOL | 2018-10-14 | 2019-04-13 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 92
2019-03-31 | 168209 | Work Order Description - 168209 - CM | CM | 1 | 479576 | WPLAN | NORM-OPS | 2018-10-14 | 2019-10-12 | 2019-05-25 | 2019-05-25 | 3 | INTEGRITY | INSPECTION | 63
2019-03-31 | 168297 | Work Order Description - 168297 - CM | CM | 4 | 672568 | WSCHD | NORM-OPS | 2019-03-04 | 2020-10-11 | 2020-01-04 | 2020-01-05 | 4 | MAINTENANCE | MECHANICAL | 90
2019-03-31 | 168307 | Work Order Description - 168307 - BR | BR | 1 | 407719 | WPLAN | NORM-OPS | 2018-10-14 | 2019-10-13 | 2019-04-20 | 2019-04-21 | 3 | INTEGRITY | INSTRUMENTS | 24
2019-03-31 | 168316 | Work Order Description - 168316 - CM | CM | 3 | 21417 | WMATL | SYS-ISOL | 2018-10-26 | 2019-04-15 | 2019-07-06 | 2019-07-06 | 3 | MAINTENANCE | MECHANICAL | 55
2019-03-31 | 168320 | Work Order Description - 168320 - CM | CM | 3 | 531547 | WPLAN | NORM-OPS | 2018-10-14 | 2019-10-13 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 168341 | Work Order Description - 168341 - PM | PM | 4 | 99471 | SCHD | EQUIP-ISOL | 2018-11-21 | 2020-06-21 | 2019-05-18 | 2019-05-18 | 1 | INTEGRITY | MECHANICAL | 90
2019-03-31 | 168342 | Work Order Description - 168342 - PM | PM | 4 | 188958 | SCHD | NORM-OPS | 2018-11-05 | 2018-12-14 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 168343 | Work Order Description - 168343 - PM | PM | 4 | 464055 | SCHD | NORM-OPS | 2018-11-05 | 2019-10-05 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 168352 | Work Order Description - 168352 - PM | PM | 4 | 460846 | SCHD | EQUIP-ISOL | 2018-11-05 | 2018-12-01 | 2019-02-17 | 2019-02-17 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 168356 | Work Order Description - 168356 - PSPM | PSPM | 1 | 28847 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-08-04 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 168361 | Work Order Description - 168361 - PM | PM | 4 | 93289 | WPLAN | EQUIP-ISOL | 2018-10-14 | 2019-04-14 | 2019-04-22 | 2019-04-22 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 168362 | Work Order Description - 168362 - PM | PM | 4 | 393260 | WPLAN | EQUIP-ISOL | 2018-10-14 | 2019-01-14 | 2019-04-22 | 2019-04-22 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 168363 | Work Order Description - 168363 - PM | PM | 4 | 393261 | WPLAN | EQUIP-ISOL | 2018-10-14 | 2019-05-16 | 2019-04-22 | 2019-04-22 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 168364 | Work Order Description - 168364 - PM | PM | 4 | 93290 | WPLAN | EQUIP-ISOL | 2018-10-14 | 2019-07-31 | 2019-04-22 | 2019-04-22 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 168454 | Work Order Description - 168454 - CM | CM | 1 | 363550 | SCHD | NORM-OPS | 2018-11-26 | 2019-05-05 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 168496 | Work Order Description - 168496 - PM | PM | 4 | 25101 | SCHD | PACK-ISOL | 2018-11-05 | 2019-07-27 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 10
2019-03-31 | 168501 | Work Order Description - 168501 - PSPM | PSPM | 1 | 447441 | SCHD | PACK-ISOL | 2019-03-29 | 2019-06-02 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 159
2019-03-31 | 168569 | Work Order Description - 168569 - PRJ | PRJ | 3 | 481325 | SCHD | NORM-OPS | 2019-03-01 | 2019-03-31 | 2019-04-05 | 2019-04-20 | 4 | ENGINEERING | FABRIC | 220
2019-03-31 | 168571 | Work Order Description - 168571 - PRJ | PRJ | 3 | 481325 | WPLAN | TPS | 2018-10-24 | 2021-08-01 | 2019-08-03 | 2019-08-03 | 4 | ENGINEERING | CONSTRUCTION | 259
2019-03-31 | 168591 | Work Order Description - 168591 - CM | CM | 1 | 450482 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-04-16 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 168592 | Work Order Description - 168592 - CM | CM | 1 | 475335 | WPLAN | NORM-OPS | 2018-10-19 | 2019-10-15 | 2020-03-28 | 2020-03-28 | 3 | MAINTENANCE | FABRIC | 830
2019-03-31 | 168725 | Work Order Description - 168725 - BR | BR | 3 | 249413 | SCHD | EQUIP-ISOL | 2018-10-29 | 2020-10-14 | 2019-04-06 | 2019-04-09 | 4 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 168727 | Work Order Description - 168727 - PSPM | PSPM | 1 | 361190 | WSCHD | EQUIP-ISOL | 2018-10-29 | 2020-01-01 | 2019-09-07 | 2019-09-07 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 168733 | Work Order Description - 168733 - PM | PM | 4 | 660951 | SCHD | NORM-OPS | 2018-11-26 | 2020-01-08 | 2019-04-13 | 2019-04-13 | 3 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 168745 | Work Order Description - 168745 - PM | PM | 4 | 127817 | SCHD | EQUIP-ISOL | 2018-10-19 | 2019-04-10 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 168747 | Work Order Description - 168747 - PM | PM | 4 | 74910 | SCHD | EQUIP-ISOL | 2018-10-19 | 2019-06-03 | 2019-05-05 | 2019-05-05 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 168748 | Work Order Description - 168748 - PM | PM | 4 | 448882 | SCHD | EQUIP-ISOL | 2018-10-19 | 2019-06-03 | 2019-05-05 | 2019-05-05 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 168882 | Work Order Description - 168882 - CM | CM | 1 | 479578 | WPLAN | NORM-OPS | 2018-10-19 | 2019-07-01 | 2019-10-12 | 2019-11-16 | 2 | INTEGRITY | FABRIC | 500
2019-03-31 | 168891 | Work Order Description - 168891 - PRJ | PRJ | 3 | 450542 | SCHD | PACK-ISOL | 2019-01-21 | 2021-01-12 | 2019-07-13 | 2019-07-15 | 4 | ENGINEERING | CONSTRUCTION | 25
2019-03-31 | 168895 | Work Order Description - 168895 - CM | CM | 4 | 671829 | WPLAN | EQUIP-ISOL | 2018-10-24 | 2020-10-15 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 168905 | Work Order Description - 168905 - CM | CM | 4 | 663478 | WPLAN | NORM-OPS | 2019-01-08 | 2020-10-15 | 2019-10-06 | 2019-10-07 | 4 | INTEGRITY | FABRIC | 28
2019-03-31 | 168959 | Work Order Description - 168959 - PM | PM | 4 | 481636 | SCHD | NORM-OPS | 2018-11-05 | 2019-09-16 | 2019-02-16 | 2019-02-16 | 3 | OPERATIONS | SAFETY | 15
2019-03-31 | 168960 | Work Order Description - 168960 - PM | PM | 4 | 481637 | SCHD | NORM-OPS | 2018-11-05 | 2018-12-31 | 2019-02-16 | 2019-02-16 | 3 | OPERATIONS | SAFETY | 14
2019-03-31 | 168961 | Work Order Description - 168961 - PM | PM | 4 | 552011 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-05-14 | 2019-04-06 | 2019-04-06 | 2 | DRILLING | DRILLING | 60
2019-03-31 | 168969 | Work Order Description - 168969 - PM | PM | 4 | 243411 | SCHD | EQUIP-ISOL | 2018-11-05 | 2020-02-11 | 2019-04-27 | 2019-04-27 | 2 | DRILLING | DRILLING | 12
2019-03-31 | 168972 | Work Order Description - 168972 - PM | PM | 4 | 316568 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-04-11 | 2019-02-15 | 2019-02-15 | 2 | DRILLING | DRILLING | 8
2019-03-31 | 169001 | Work Order Description - 169001 - PM | PM | 4 | 127775 | SCHD | PACK-ISOL | 2018-12-17 | 2019-09-16 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 169007 | Work Order Description - 169007 - PM | PM | 4 | 99572 | SCHD | EQUIP-ISOL | 2018-10-19 | 2019-05-17 | 2019-04-19 | 2019-04-19 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 169303 | Work Order Description - 169303 - BR | BR | 2 | 672869 | WPLAN | NORM-OPS | 2018-10-23 | 2019-10-18 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 169307 | Work Order Description - 169307 - CM | CM | 3 | 51697 | SCHD | EQUIP-ISOL | 2019-03-26 | 2020-10-16 | 2019-03-30 | 2019-03-31 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 169312 | Work Order Description - 169312 - CM | CM | 1 | 479578 | WPLAN | NORM-OPS | 2018-10-19 | 2020-01-01 | 2019-11-02 | 2019-12-21 | 2 | INTEGRITY | FABRIC | 1050
2019-03-31 | 169315 | Work Order Description - 169315 - CM | CM | 1 | 479578 | WPLAN | NORM-OPS | 2018-10-19 | 2021-01-01 | 2020-06-30 | 2020-08-04 | 3 | INTEGRITY | FABRIC | 750
2019-03-31 | 169320 | Work Order Description - 169320 - CM | CM | 1 | 479578 | WPLAN | NORM-OPS | 2018-10-19 | 2020-07-01 | 2020-02-01 | 2020-02-22 | 3 | INTEGRITY | FABRIC | 450
2019-03-31 | 169324 | Work Order Description - 169324 - CM | CM | 3 | 254761 | SCHD | EQUIP-ISOL | 2019-02-08 | 2019-10-19 | 2019-11-16 | 2019-11-17 | 3 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 169364 | Work Order Description - 169364 - CM | CM | 4 | 464992 | WPLAN | PACK-ISOL | 2018-10-27 | 2020-10-16 | 2019-05-18 | 2019-05-18 | 4 | WELLS | INSTRUMENTS | 4
2019-03-31 | 169382 | Work Order Description - 169382 - BR | BR | 3 | 310177 | WMATL | NORM-OPS | 2018-10-22 | 2019-04-07 | 2019-08-31 | 2019-08-31 | 2 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 169393 | Work Order Description - 169393 - PM | PM | 4 | 262750 | SCHD | NORM-OPS | 2018-11-05 | 2019-06-10 | 2019-04-13 | 2019-04-13 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 169473 | Work Order Description - 169473 - BR | BR | 3 | 29562 | WPLAN | NORM-OPS | 2018-12-04 | 2019-08-26 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 169502 | Work Order Description - 169502 - PSCM | PSCM | 1 | 666331 | WSCHD | TPS | 2018-11-05 | 2019-11-05 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 169503 | Work Order Description - 169503 - CM | CM | 4 | 578832 | WPLAN | SYS-ISOL | 2018-10-23 | 2019-04-20 | 2019-04-13 | 2019-04-13 | 3 | WELLS | INSTRUMENTS | 7
2019-03-31 | 169511 | Work Order Description - 169511 - CM | CM | 4 | 568123 | SCHD | NORM-OPS | 2018-11-05 | 2020-10-17 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 169518 | Work Order Description - 169518 - PSPM | PSPM | 1 | 361881 | WSCHD | SUBSYS-ISOL | 2018-10-24 | 2019-03-11 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 169619 | Work Order Description - 169619 - CM | CM | 4 | 217888 | WPLAN | TPS | 2018-11-05 | 2020-10-18 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 9
2019-03-31 | 169629 | Work Order Description - 169629 - PSCM | PSCM | 1 | 584282 | SCHD | NORM-OPS | 2019-01-25 | 2019-04-26 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 169633 | Work Order Description - 169633 - CM | CM | 4 | 125898 | WPLAN | NORM-OPS | 2018-10-22 | 2020-10-18 | 2019-04-20 | 2019-04-21 | 4 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 169638 | Work Order Description - 169638 - CM | CM | 3 | 546302 | WPLAN | NORM-OPS | 2018-10-23 | 2019-04-21 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 169661 | Work Order Description - 169661 - PSPM | PSPM | 1 | 680809 | WSCHD | PACK-ISOL | 2018-11-16 | 2019-03-21 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 169663 | Work Order Description - 169663 - PSPM | PSPM | 1 | 680809 | WSCHD | PACK-ISOL | 2018-11-16 | 2019-03-21 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 169672 | Work Order Description - 169672 - PM | PM | 4 | 99500 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-03-21 | 2019-04-06 | 2019-04-06 | 1 | INTEGRITY | SAFETY | 4
2019-03-31 | 169697 | Work Order Description - 169697 - PM | PM | 4 | 393262 | WPLAN | EQUIP-ISOL | 2018-10-21 | 2019-03-21 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 169698 | Work Order Description - 169698 - PM | PM | 4 | 665069 | WPLAN | EQUIP-ISOL | 2018-10-21 | 2019-03-21 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 169699 | Work Order Description - 169699 - PM | PM | 4 | 93291 | WPLAN | EQUIP-ISOL | 2018-10-21 | 2019-03-21 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 169700 | Work Order Description - 169700 - PM | PM | 4 | 393263 | WPLAN | EQUIP-ISOL | 2018-10-21 | 2019-03-21 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 169815 | Work Order Description - 169815 - PRJ | PRJ | 3 | 51920 | WPLAN | EQUIP-ISOL | 2018-10-23 | 2020-10-01 | 2019-04-30 | 2019-04-30 | 3 | ENGINEERING | CONSTRUCTION | 84
2019-03-31 | 169819 | Work Order Description - 169819 - CM | CM | 4 | 631474 | WMATL | EQUIP-ISOL | 2018-10-26 | 2020-10-19 | 2019-06-22 | 2019-06-22 | 4 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 169837 | Work Order Description - 169837 - CM | CM | 1 | 29669 | SCHD | NORM-OPS | 2018-11-05 | 2019-10-23 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | OPERATIONS | 56
2019-03-31 | 169846 | Work Order Description - 169846 - PM | PM | 4 | 359311 | WSCHD | NORM-OPS | 2018-10-22 | 2019-03-22 | 2020-04-04 | 2020-04-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 169854 | Work Order Description - 169854 - PSPM | PSPM | 1 | 680808 | WSCHD | PACK-ISOL | 2018-11-16 | 2019-03-22 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 169855 | Work Order Description - 169855 - PSPM | PSPM | 1 | 680808 | WSCHD | PACK-ISOL | 2018-11-16 | 2019-03-22 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 169856 | Work Order Description - 169856 - PSPM | PSPM | 1 | 57929 | WSCHD | EQUIP-ISOL | 2018-10-22 | 2019-07-07 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 42
2019-03-31 | 169859 | Work Order Description - 169859 - PSPM | PSPM | 1 | 361116 | WSCHD | EQUIP-ISOL | 2018-10-29 | 2019-03-22 | 2019-04-06 | 2019-04-06 | 1 | INTEGRITY | CONSTRUCTION | 2.3
2019-03-31 | 169879 | Work Order Description - 169879 - PM | PM | 4 | 499149 | SCHD | NORM-OPS | 2018-11-05 | 2019-03-22 | 2019-02-19 | 2019-02-19 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 169999 | Work Order Description - 169999 - CM | CM | 1 | 322138 | WPLAN | NORM-OPS | 2018-10-26 | 2019-04-27 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 170001 | Work Order Description - 170001 - BR | BR | 1 | 322139 | WPLAN | NORM-OPS | 2018-10-26 | 2019-04-26 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 170007 | Work Order Description - 170007 - CM | CM | 4 | 476739 | WPLAN | EQUIP-ISOL | 2019-01-09 | 2021-01-07 | 2020-01-08 | 2020-01-08 | 4 | DRILLING | WELLS | 32
2019-03-31 | 170008 | Work Order Description - 170008 - CM | CM | 4 | 80461 | WPLAN | EQUIP-ISOL | 2018-12-13 | 2019-10-22 | 2019-04-22 | 2019-04-25 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 170022 | Work Order Description - 170022 - BR | BR | 3 | 311476 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-06-21 | 2019-07-13 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 170027 | Work Order Description - 170027 - BR | BR | 1 | 406627 | WSCHD | NORM-OPS | 2018-11-09 | 2019-04-23 | 2019-04-13 | 2019-04-14 | 3 | MAINTENANCE | ELECTRICAL | 18
2019-03-31 | 170035 | Work Order Description - 170035 - CM | CM | 1 | 310481 | WMATL | EQUIP-ISOL | 2018-10-29 | 2020-10-20 | 2019-04-20 | 2019-04-21 | 4 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 170068 | Work Order Description - 170068 - PM | PM | 4 | 58420 | WSCHD | SUBSYS-ISOL | 2018-10-24 | 2019-03-23 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 170069 | Work Order Description - 170069 - PM | PM | 4 | 58418 | WSCHD | SUBSYS-ISOL | 2018-10-24 | 2019-03-23 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 170070 | Work Order Description - 170070 - PM | PM | 3 | 54626 | WSCHD | EQUIP-ISOL | 2018-10-23 | 2019-06-09 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 170071 | Work Order Description - 170071 - PM | PM | 3 | 360602 | WSCHD | EQUIP-ISOL | 2018-10-23 | 2019-06-09 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 170076 | Work Order Description - 170076 - PM | PM | 3 | 399760 | WSCHD | EQUIP-ISOL | 2018-10-29 | 2019-03-23 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 170077 | Work Order Description - 170077 - PM | PM | 4 | 325633 | SCHD | PACK-ISOL | 2018-11-05 | 2019-03-23 | 2019-02-20 | 2019-02-20 | 1 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 170079 | Work Order Description - 170079 - PSPM | PSPM | 1 | 216946 | SCHD | NORM-OPS | 2018-11-05 | 2019-03-23 | 2019-04-13 | 2019-04-13 | 1 | OPERATIONS | SAFETY | 8
2019-03-31 | 170083 | Work Order Description - 170083 - PSPM | PSPM | 1 | 122617 | SCHD | NORM-OPS | 2018-11-05 | 2019-03-23 | 2019-04-13 | 2019-04-13 | 1 | OPERATIONS | SAFETY | 6
2019-03-31 | 170211 | Work Order Description - 170211 - PSCM | PSCM | 2 | 520388 | WMATL | EQUIP-ISOL | 2019-03-18 | 2019-09-16 | 2019-04-20 | 2019-04-20 | 3 | WELLS | MECHANICAL | 28
2019-03-31 | 170238 | Work Order Description - 170238 - PM | PM | 4 | 18972 | WSCHD | NORM-OPS | 2018-10-24 | 2019-03-24 | 2020-03-07 | 2020-03-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 170239 | Work Order Description - 170239 - PM | PM | 4 | 355546 | WSCHD | NORM-OPS | 2018-10-24 | 2019-03-24 | 2020-03-07 | 2020-03-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 170240 | Work Order Description - 170240 - PM | PM | 4 | 18973 | WSCHD | NORM-OPS | 2018-10-24 | 2019-03-24 | 2020-03-07 | 2020-03-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 170241 | Work Order Description - 170241 - PM | PM | 4 | 355547 | WSCHD | NORM-OPS | 2018-10-24 | 2019-03-24 | 2020-03-07 | 2020-03-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 170242 | Work Order Description - 170242 - PM | PM | 4 | 18985 | WSCHD | NORM-OPS | 2018-10-24 | 2019-03-24 | 2020-03-07 | 2020-03-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 170243 | Work Order Description - 170243 - PM | PM | 4 | 355548 | WSCHD | NORM-OPS | 2018-10-24 | 2019-03-24 | 2020-03-07 | 2020-03-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 170246 | Work Order Description - 170246 - PSPM | PSPM | 1 | 57929 | SCHD | EQUIP-ISOL | 2019-03-20 | 2019-05-11 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 42
2019-03-31 | 170247 | Work Order Description - 170247 - PM | PM | 4 | 363762 | WSCHD | NORM-OPS | 2018-10-26 | 2019-03-24 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | MECHANICAL | 65
2019-03-31 | 170256 | Work Order Description - 170256 - PM | PM | 4 | 601923 | SCHD | NORM-OPS | 2018-11-05 | 2019-03-24 | 2019-04-20 | 2019-04-20 | 2 | OPERATIONS | OPERATIONS | 60
2019-03-31 | 170388 | Work Order Description - 170388 - CM | CM | 4 | 243352 | SCHD | EQUIP-ISOL | 2019-03-29 | 2020-10-22 | 2019-09-07 | 2019-09-07 | 4 | MAINTENANCE | DRILLING | 68
2019-03-31 | 170394 | Work Order Description - 170394 - CM | CM | 3 | 677997 | WSCHD | EQUIP-ISOL | 2019-01-21 | 2019-10-26 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | CONSTRUCTION | 24
2019-03-31 | 170410 | Work Order Description - 170410 - BR | BR | 3 | 553957 | WPLAN | NORM-OPS | 2018-10-26 | 2020-10-22 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 170441 | Work Order Description - 170441 - PM | PM | 4 | 376244 | WPLAN | PACK-ISOL | 2018-11-05 | 2019-03-25 | 2019-05-18 | 2019-05-19 | 2 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 170442 | Work Order Description - 170442 - PM | PM | 4 | 376243 | SCHD | PACK-ISOL | 2018-11-02 | 2019-03-25 | 2019-07-13 | 2019-07-14 | 2 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 170443 | Work Order Description - 170443 - PM | PM | 4 | 453807 | SCHD | EQUIP-ISOL | 2018-11-02 | 2019-03-25 | 2019-03-31 | 2019-03-31 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 170531 | Work Order Description - 170531 - CM | CM | 4 | 535884 | WSCHD | EQUIP-ISOL | 2018-10-26 | 2020-10-23 | 2019-04-20 | 2019-04-20 | 4 | INTEGRITY | CONSTRUCTION | 20
2019-03-31 | 170549 | Work Order Description - 170549 - BR | BR | 3 | 307605 | WPLAN | EQUIP-ISOL | 2018-10-26 | 2020-10-23 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 170571 | Work Order Description - 170571 - PSPM | PSPM | 1 | 259533 | SCHD | TPS | 2018-11-05 | 2019-03-26 | 2019-07-13 | 2019-07-13 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 170573 | Work Order Description - 170573 - PM | PM | 4 | 556432 | SCHD | PACK-ISOL | 2018-11-05 | 2019-03-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 144
2019-03-31 | 170576 | Work Order Description - 170576 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-26 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 170577 | Work Order Description - 170577 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-26 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 170647 | Work Order Description - 170647 - BR | BR | 3 | 176539 | SCHD | TPS | 2018-11-05 | 2019-04-27 | 2019-07-13 | 2019-07-14 | 3 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 170673 | Work Order Description - 170673 - PSCM | PSCM | 1 | 310312 | WSCHD | TPS | 2018-11-05 | 2019-09-01 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 170715 | Work Order Description - 170715 - PM | PM | 3 | 408686 | SCHD | PACK-ISOL | 2018-11-05 | 2019-09-21 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 170716 | Work Order Description - 170716 - PM | PM | 3 | 408699 | SCHD | PACK-ISOL | 2018-11-05 | 2019-08-15 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 170717 | Work Order Description - 170717 - PM | PM | 3 | 408700 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-07-25 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 170718 | Work Order Description - 170718 - PSPM | PSPM | 1 | 30623 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-11-19 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 170720 | Work Order Description - 170720 - PSPM | PSPM | 1 | 543965 | SCHD | TPS | 2019-03-15 | 2019-07-28 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 170724 | Work Order Description - 170724 - PM | PM | 4 | 303803 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-12-04 | 2019-07-06 | 2019-07-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 170725 | Work Order Description - 170725 - PM | PM | 4 | 409031 | SCHD | PACK-ISOL | 2018-11-20 | 2019-05-19 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 170727 | Work Order Description - 170727 - PM | PM | 4 | 30495 | SCHD | PACK-ISOL | 2018-11-05 | 2019-11-28 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 170728 | Work Order Description - 170728 - PM | PM | 4 | 303835 | SCHD | PACK-ISOL | 2018-11-05 | 2019-06-30 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 170729 | Work Order Description - 170729 - PM | PM | 4 | 303861 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-04-17 | 2019-07-06 | 2019-07-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 170730 | Work Order Description - 170730 - PM | PM | 4 | 409060 | SCHD | PACK-ISOL | 2018-11-20 | 2020-01-16 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 170731 | Work Order Description - 170731 - PM | PM | 4 | 401510 | SCHD | PACK-ISOL | 2018-11-20 | 2018-12-26 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 170732 | Work Order Description - 170732 - PM | PM | 4 | 30499 | SCHD | PACK-ISOL | 2018-11-05 | 2019-11-16 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 170733 | Work Order Description - 170733 - PM | PM | 4 | 409065 | SCHD | EQUIP-ISOL | 2018-11-05 | 2018-12-28 | 2019-07-06 | 2019-07-06 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 170734 | Work Order Description - 170734 - PM | PM | 4 | 303865 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-01-31 | 2019-07-06 | 2019-07-06 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 170735 | Work Order Description - 170735 - PM | PM | 4 | 409067 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-12-29 | 2019-07-06 | 2019-07-06 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 170736 | Work Order Description - 170736 - PM | PM | 4 | 409088 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-10-06 | 2019-07-06 | 2019-07-06 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 170737 | Work Order Description - 170737 - PM | PM | 4 | 30502 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-07-12 | 2019-07-06 | 2019-07-06 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 170748 | Work Order Description - 170748 - PM | PM | 4 | 320150 | SCHD | NORM-OPS | 2018-11-05 | 2019-03-05 | 2019-02-02 | 2019-02-02 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 170752 | Work Order Description - 170752 - PM | PM | 2 | 262443 | SCHD | EQUIP-ISOL | 2018-11-05 | 2018-12-09 | 2019-02-23 | 2019-02-23 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 170758 | Work Order Description - 170758 - PRJ | PRJ | 4 | 73639 | SCHD | NORM-OPS | 2018-11-05 | 2019-11-24 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | ELECTRICAL | 28
2019-03-31 | 170769 | Work Order Description - 170769 - PM | PM | 2 | 408300 | WSCHD | EQUIP-ISOL | 2018-10-29 | 2019-03-27 | 2019-11-23 | 2019-11-23 | 1 | INTEGRITY | MECHANICAL | 60
2019-03-31 | 170919 | Work Order Description - 170919 - PM | PM | 4 | 668715 | SCHD | NORM-OPS | 2018-12-17 | 2019-03-28 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 170920 | Work Order Description - 170920 - PM | PM | 4 | 98044 | SCHD | NORM-OPS | 2018-12-17 | 2019-03-28 | 2019-04-14 | 2019-04-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 170921 | Work Order Description - 170921 - PM | PM | 4 | 664986 | WPLAN | EQUIP-ISOL | 2018-10-28 | 2019-03-28 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 170922 | Work Order Description - 170922 - PM | PM | 4 | 89855 | WPLAN | EQUIP-ISOL | 2018-10-28 | 2019-03-28 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 170923 | Work Order Description - 170923 - PM | PM | 4 | 396485 | WPLAN | EQUIP-ISOL | 2018-10-28 | 2019-03-28 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 170924 | Work Order Description - 170924 - PM | PM | 4 | 388446 | WPLAN | EQUIP-ISOL | 2018-10-28 | 2019-03-28 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 171041 | Work Order Description - 171041 - BR | BR | 1 | 313925 | WSCHD | NORM-OPS | 2018-10-29 | 2019-04-29 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | ELECTRICAL | 18
2019-03-31 | 171043 | Work Order Description - 171043 - BR | BR | 1 | 313863 | WSCHD | NORM-OPS | 2018-10-29 | 2019-04-29 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | ELECTRICAL | 18
2019-03-31 | 171044 | Work Order Description - 171044 - BR | BR | 1 | 307692 | WSCHD | NORM-OPS | 2018-10-29 | 2019-04-29 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | ELECTRICAL | 18
2019-03-31 | 171045 | Work Order Description - 171045 - BR | BR | 1 | 407466 | WSCHD | NORM-OPS | 2018-10-29 | 2019-04-29 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 171046 | Work Order Description - 171046 - BR | BR | 1 | 697913 | WPLAN | NORM-OPS | 2019-01-22 | 2019-07-24 | 2019-06-01 | 2019-06-01 | 3 | INTEGRITY | ELECTRICAL | 150
2019-03-31 | 171055 | Work Order Description - 171055 - CM | CM | 4 | 555582 | SCHD | NORM-OPS | 2018-12-24 | 2019-10-06 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | ELECTRICAL | 21
2019-03-31 | 171059 | Work Order Description - 171059 - CM | CM | 4 | 650841 | WSCHD | EQUIP-ISOL | 2018-10-29 | 2020-10-26 | 2019-06-22 | 2019-06-22 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 171062 | Work Order Description - 171062 - BR | BR | 4 | 553319 | SCHD | EQUIP-ISOL | 2018-11-07 | 2020-10-26 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 171072 | Work Order Description - 171072 - BR | BR | 1 | 464229 | SCHD | NORM-OPS | 2018-11-05 | 2019-10-28 | 2019-09-07 | 2019-09-07 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 171073 | Work Order Description - 171073 - BR | BR | 1 | 464229 | SCHD | TPS | 2018-11-05 | 2019-10-28 | 2019-07-13 | 2019-07-13 | 3 | INTEGRITY | MECHANICAL | 0
2019-03-31 | 171074 | Work Order Description - 171074 - BR | BR | 1 | 464229 | WPLAN | TPS | 2018-10-31 | 2019-10-28 | 2019-07-13 | 2019-07-13 | 3 | INTEGRITY | MECHANICAL | 48
2019-03-31 | 171080 | Work Order Description - 171080 - PSPM | PSPM | 1 | 261165 | WSCHD | EQUIP-ISOL | 2018-10-29 | 2019-03-29 | 2019-04-06 | 2019-04-06 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 171088 | Work Order Description - 171088 - PM | PM | 4 | 320150 | SCHD | NORM-OPS | 2018-11-05 | 2019-03-29 | 2019-03-23 | 2019-03-23 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 171089 | Work Order Description - 171089 - PM | PM | 4 | 527844 | WPLAN | PACK-ISOL | 2018-11-05 | 2019-03-29 | 2019-04-28 | 2019-04-29 | 2 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 171095 | Work Order Description - 171095 - PSPM | PSPM | 1 | 392054 | SCHD | PACK-ISOL | 2018-12-17 | 2019-03-29 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 171098 | Work Order Description - 171098 - PSPM | PSPM | 1 | 392054 | SCHD | PACK-ISOL | 2018-12-17 | 2019-03-29 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 171152 | Work Order Description - 171152 - BR | BR | 4 | 655884 | SCHD | NORM-OPS | 2019-02-13 | 2019-04-30 | 2019-06-29 | 2019-06-29 | 3 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 171153 | Work Order Description - 171153 - CM | CM | 4 | 226476 | WSCHD | NORM-OPS | 2019-03-04 | 2019-04-30 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 171154 | Work Order Description - 171154 - CM | CM | 1 | 520045 | WSCHD | SYS-ISOL | 2018-11-03 | 2019-10-29 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 55
2019-03-31 | 171160 | Work Order Description - 171160 - PSCM | PSCM | 1 | 567748 | SCHD | EQUIP-ISOL | 2018-11-05 | 2020-10-27 | 2019-08-31 | 2019-08-31 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 171161 | Work Order Description - 171161 - PSCM | PSCM | 1 | 472970 | SCHD | EQUIP-ISOL | 2018-11-05 | 2020-10-27 | 2019-08-31 | 2019-08-31 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 171172 | Work Order Description - 171172 - CM | CM | 1 | 631962 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-30 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | ELECTRICAL | 355
2019-03-31 | 171200 | Work Order Description - 171200 - CM | CM | 1 | 303851 | SCHD | NORM-OPS | 2018-12-24 | 2020-10-27 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 171214 | Work Order Description - 171214 - PM | PM | 2 | 480203 | WSCHD | PACK-ISOL | 2018-10-30 | 2019-03-30 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 171216 | Work Order Description - 171216 - PSPM | PSPM | 1 | 652220 | SCHD | PACK-ISOL | 2019-03-20 | 2019-03-30 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 171219 | Work Order Description - 171219 - PM | PM | 4 | 99497 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-03-30 | 2019-04-06 | 2019-04-06 | 1 | INTEGRITY | SAFETY | 4
2019-03-31 | 171221 | Work Order Description - 171221 - PSPM | PSPM | 1 | 457948 | SCHD | NORM-OPS | 2018-11-05 | 2019-03-30 | 2019-02-23 | 2019-02-23 | 1 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 171222 | Work Order Description - 171222 - PSPM | PSPM | 1 | 395982 | SCHD | PACK-ISOL | 2018-11-05 | 2019-07-22 | 2019-07-13 | 2019-07-13 | 3 | WELLS | WELLS | 6
2019-03-31 | 171223 | Work Order Description - 171223 - PSPM | PSPM | 1 | 665667 | SCHD | PACK-ISOL | 2018-11-05 | 2019-07-22 | 2019-07-13 | 2019-07-13 | 3 | WELLS | WELLS | 6
2019-03-31 | 171224 | Work Order Description - 171224 - PSPM | PSPM | 1 | 395983 | SCHD | PACK-ISOL | 2018-11-05 | 2019-07-22 | 2019-07-13 | 2019-07-13 | 3 | WELLS | WELLS | 6
2019-03-31 | 171230 | Work Order Description - 171230 - PSPM | PSPM | 1 | 392054 | SCHD | PACK-ISOL | 2019-02-13 | 2019-03-30 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 171234 | Work Order Description - 171234 - PSPM | PSPM | 1 | 392054 | SCHD | PACK-ISOL | 2019-02-13 | 2019-03-30 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171327 | Work Order Description - 171327 - PSCM | PSCM | 1 | 681833 | WSCHD | SYS-ISOL | 2018-11-05 | 2020-11-03 | 2019-08-24 | 2019-08-24 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 171354 | Work Order Description - 171354 - BR | BR | 3 | 502434 | WPLAN | EQUIP-ISOL | 2018-11-22 | 2020-10-28 | 2020-03-14 | 2020-03-14 | 4 | WELLS | INSTRUMENTS | 4
2019-03-31 | 171356 | Work Order Description - 171356 - CM | CM | 2 | 179186 | SCHD | NORM-OPS | 2018-11-20 | 2020-10-28 | 2019-08-24 | 2019-08-24 | 4 | MAINTENANCE | MECHANICAL | 35
2019-03-31 | 171358 | Work Order Description - 171358 - CM | CM | 3 | 246510 | WSCHD | EQUIP-ISOL | 2018-10-31 | 2020-10-28 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 171370 | Work Order Description - 171370 - PM | PM | 4 | 321115 | WSCHD | PACK-ISOL | 2018-11-03 | 2019-06-17 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 112
2019-03-31 | 171371 | Work Order Description - 171371 - PM | PM | 4 | 137808 | WSCHD | PACK-ISOL | 2018-11-16 | 2019-03-31 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 171372 | Work Order Description - 171372 - PM | PM | 4 | 660951 | SCHD | NORM-OPS | 2018-11-26 | 2019-03-31 | 2019-04-20 | 2019-04-20 | 3 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 171376 | Work Order Description - 171376 - PSPM | PSPM | 1 | 409934 | SCHD | NORM-OPS | 2019-03-13 | 2019-03-31 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 171379 | Work Order Description - 171379 - PM | PM | 4 | 54763 | SCHD | PACK-ISOL | 2018-11-29 | 2019-03-31 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 171380 | Work Order Description - 171380 - PSPM | PSPM | 1 | 459098 | SCHD | PACK-ISOL | 2018-11-05 | 2019-03-31 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 171381 | Work Order Description - 171381 - PSPM | PSPM | 1 | 459098 | SCHD | PACK-ISOL | 2018-11-05 | 2019-03-31 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171392 | Work Order Description - 171392 - PM | PM | 4 | 449384 | SCHD | NORM-OPS | 2018-11-05 | 2019-03-31 | 2019-02-23 | 2019-02-23 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 171394 | Work Order Description - 171394 - PSPM | PSPM | 1 | 665668 | SCHD | PACK-ISOL | 2018-11-05 | 2019-07-23 | 2019-07-13 | 2019-07-13 | 3 | WELLS | WELLS | 6
2019-03-31 | 171395 | Work Order Description - 171395 - PM | PM | 4 | 323665 | SCHD | NORM-OPS | 2018-11-05 | 2019-04-24 | 2019-02-28 | 2019-02-28 | 2 | OPERATIONS | OPERATIONS | 21
2019-03-31 | 171416 | Work Order Description - 171416 - PM | PM | 4 | 126542 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-31 | 2019-05-26 | 2019-05-27 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 171417 | Work Order Description - 171417 - PM | PM | 4 | 98421 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-31 | 2019-05-26 | 2019-05-27 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 171418 | Work Order Description - 171418 - PM | PM | 4 | 78492 | SCHD | EQUIP-ISOL | 2018-11-02 | 2019-06-17 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171419 | Work Order Description - 171419 - PM | PM | 4 | 442354 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-31 | 2019-05-26 | 2019-05-27 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 171421 | Work Order Description - 171421 - PM | PM | 4 | 98775 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-04-24 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 171422 | Work Order Description - 171422 - PM | PM | 4 | 100017 | SCHD | EQUIP-ISOL | 2018-11-02 | 2019-06-17 | 2019-04-07 | 2019-04-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171423 | Work Order Description - 171423 - PM | PM | 4 | 668934 | SCHD | EQUIP-ISOL | 2018-11-02 | 2019-04-24 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 171424 | Work Order Description - 171424 - PM | PM | 4 | 97755 | SCHD | EQUIP-ISOL | 2018-11-02 | 2019-04-24 | 2019-04-28 | 2019-04-30 | 2 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 171425 | Work Order Description - 171425 - PM | PM | 4 | 393597 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-31 | 2019-05-26 | 2019-05-27 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 171426 | Work Order Description - 171426 - PM | PM | 4 | 398470 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-31 | 2019-05-26 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 49
2019-03-31 | 171427 | Work Order Description - 171427 - PM | PM | 4 | 393027 | SCHD | EQUIP-ISOL | 2018-11-02 | 2019-04-24 | 2019-04-28 | 2019-04-30 | 2 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 171428 | Work Order Description - 171428 - PM | PM | 4 | 378579 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-31 | 2019-05-26 | 2019-05-26 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 171429 | Work Order Description - 171429 - PM | PM | 4 | 98781 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-04-24 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 171430 | Work Order Description - 171430 - PM | PM | 4 | 98775 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-31 | 2019-05-26 | 2019-05-29 | 2 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 171431 | Work Order Description - 171431 - PM | PM | 4 | 377283 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-31 | 2019-05-26 | 2019-05-27 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 171432 | Work Order Description - 171432 - PM | PM | 4 | 98725 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-04-24 | 2019-04-28 | 2019-04-30 | 2 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 171434 | Work Order Description - 171434 - PM | PM | 4 | 72317 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-31 | 2019-05-26 | 2019-05-28 | 2 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 171435 | Work Order Description - 171435 - PM | PM | 4 | 376726 | SCHD | NORM-OPS | 2018-11-02 | 2019-04-24 | 2019-05-26 | 2019-05-26 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 171436 | Work Order Description - 171436 - PM | PM | 4 | 398462 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-04-24 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 171437 | Work Order Description - 171437 - PM | PM | 4 | 440837 | SCHD | EQUIP-ISOL | 2018-11-02 | 2019-06-17 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171438 | Work Order Description - 171438 - PM | PM | 4 | 98273 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-31 | 2019-05-26 | 2019-05-31 | 2 | MAINTENANCE | INSTRUMENTS | 42
2019-03-31 | 171439 | Work Order Description - 171439 - PM | PM | 4 | 668959 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-31 | 2019-05-18 | 2019-05-19 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 171441 | Work Order Description - 171441 - PM | PM | 4 | 398918 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-31 | 2019-05-26 | 2019-05-26 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 171442 | Work Order Description - 171442 - PM | PM | 4 | 96050 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-31 | 2019-05-26 | 2019-05-26 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 171443 | Work Order Description - 171443 - PM | PM | 4 | 98689 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-31 | 2019-05-26 | 2019-05-27 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 171445 | Work Order Description - 171445 - PM | PM | 4 | 98753 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-04-24 | 2019-05-26 | 2019-05-27 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 171446 | Work Order Description - 171446 - PM | PM | 4 | 373565 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-31 | 2019-05-26 | 2019-05-26 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 171447 | Work Order Description - 171447 - PM | PM | 4 | 377702 | SCHD | NORM-OPS | 2018-11-02 | 2019-03-31 | 2019-05-26 | 2019-05-27 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 171449 | Work Order Description - 171449 - PM | PM | 4 | 97786 | SCHD | EQUIP-ISOL | 2018-11-02 | 2019-04-24 | 2019-07-13 | 2019-07-22 | 2 | MAINTENANCE | INSTRUMENTS | 70
2019-03-31 | 171614 | Work Order Description - 171614 - BR | BR | 4 | 545266 | WSCHD | EQUIP-ISOL | 2018-12-07 | 2020-10-29 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 171623 | Work Order Description - 171623 - CM | CM | 1 | 403604 | WSCHD | NORM-OPS | 2018-10-31 | 2019-05-02 |  |  | 3 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 171626 | Work Order Description - 171626 - BR | BR | 3 | 83872 | SCHD | TPS | 2019-02-13 | 2019-10-31 | 2019-07-13 | 2019-07-14 | 3 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 171643 | Work Order Description - 171643 - PSCM | PSCM | 1 | 541279 | WPLAN | NORM-OPS | 2018-11-10 | 2020-10-29 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 171664 | Work Order Description - 171664 - CM | CM | 3 | 463284 | WMATL | SYS-ISOL | 2018-11-27 | 2019-04-03 | 2019-05-25 | 2019-05-26 | 2 | MAINTENANCE | MECHANICAL | 38
2019-03-31 | 171669 | Work Order Description - 171669 - PSPM | PSPM | 1 | 399465 | WSCHD | SUBSYS-ISOL | 2018-11-17 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 171670 | Work Order Description - 171670 - PSPM | PSPM | 1 | 679183 | SCHD | PACK-ISOL | 2019-03-21 | 2019-04-01 | 2019-04-02 | 2019-04-02 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 171674 | Work Order Description - 171674 - PSPM | PSPM | 1 | 273469 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-04-01 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 171677 | Work Order Description - 171677 - PSPM | PSPM | 1 | 408320 | SCHD | PACK-ISOL | 2019-03-19 | 2019-04-01 | 2019-04-17 | 2019-04-17 | 1 | MAINTENANCE | SERVICES | 24
2019-03-31 | 171678 | Work Order Description - 171678 - PM | PM | 2 | 580380 | SCHD | NORM-OPS | 2019-03-29 | 2019-04-01 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 171679 | Work Order Description - 171679 - PM | PM | 2 | 305395 | WSCHD | NORM-OPS | 2018-11-01 | 2019-04-01 | 2019-04-13 | 2019-04-13 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 171680 | Work Order Description - 171680 - PSPM | PSPM | 1 | 418083 | WSCHD | PACK-ISOL | 2018-11-16 | 2019-04-01 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 171681 | Work Order Description - 171681 - PSPM | PSPM | 1 | 418083 | WSCHD | PACK-ISOL | 2018-11-16 | 2019-04-01 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171683 | Work Order Description - 171683 - PM | PM | 3 | 360584 | WSCHD | EQUIP-ISOL | 2018-11-01 | 2019-06-18 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171686 | Work Order Description - 171686 - PSPM | PSPM | 1 | 360368 | SCHD | EQUIP-ISOL | 2019-03-05 | 2019-04-01 | 2019-07-20 | 2019-07-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171687 | Work Order Description - 171687 - PM | PM | 3 | 57140 | WSCHD | EQUIP-ISOL | 2018-11-01 | 2019-04-01 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 171688 | Work Order Description - 171688 - PM | PM | 3 | 57189 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-04-01 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 171700 | Work Order Description - 171700 - PM | PM | 3 | 55038 | WSCHD | EQUIP-ISOL | 2018-11-01 | 2019-08-29 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 171702 | Work Order Description - 171702 - PM | PM | 4 | 572011 | WSCHD | EQUIP-ISOL | 2018-11-01 | 2019-04-01 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 171703 | Work Order Description - 171703 - PM | PM | 3 | 53150 | WSCHD | EQUIP-ISOL | 2018-11-01 | 2019-06-18 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171704 | Work Order Description - 171704 - PM | PM | 3 | 54601 | WSCHD | EQUIP-ISOL | 2018-11-01 | 2019-06-18 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171708 | Work Order Description - 171708 - PM | PM | 2 | 408374 | WSCHD | EQUIP-ISOL | 2018-11-01 | 2019-06-18 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 171711 | Work Order Description - 171711 - PM | PM | 4 | 545662 | WSCHD | PACK-ISOL | 2018-11-16 | 2019-04-01 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 171729 | Work Order Description - 171729 - PSPM | PSPM | 1 | 248131 | WSCHD | EQUIP-ISOL | 2018-11-19 | 2020-06-07 | 2020-01-01 | 2020-01-01 | 1 | INTEGRITY | CONSTRUCTION | 9
2019-03-31 | 171730 | Work Order Description - 171730 - PSPM | PSPM | 1 | 357605 | WSCHD | SUBSYS-ISOL | 2018-11-17 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 171731 | Work Order Description - 171731 - PSPM | PSPM | 1 | 399464 | WSCHD | SUBSYS-ISOL | 2018-11-17 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 171732 | Work Order Description - 171732 - PSPM | PSPM | 1 | 54068 | WSCHD | SUBSYS-ISOL | 2018-11-17 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 171733 | Work Order Description - 171733 - PSPM | PSPM | 1 | 399466 | WSCHD | SUBSYS-ISOL | 2018-11-17 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 171734 | Work Order Description - 171734 - PSPM | PSPM | 1 | 260930 | WSCHD | EQUIP-ISOL | 2018-11-19 | 2019-04-01 | 2019-04-06 | 2019-04-06 | 1 | INTEGRITY | CONSTRUCTION | 9
2019-03-31 | 171739 | Work Order Description - 171739 - PM | PM | 4 | 547509 | WSCHD | PACK-ISOL | 2018-11-17 | 2019-04-01 | 2019-10-26 | 2019-10-26 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 171740 | Work Order Description - 171740 - PM | PM | 4 | 671828 | WSCHD | PACK-ISOL | 2018-11-17 | 2019-04-16 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 171749 | Work Order Description - 171749 - PSPM | PSPM | 1 | 491403 | SCHD | TPS | 2019-03-15 | 2019-04-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 123
2019-03-31 | 171762 | Work Order Description - 171762 - PM | PM | 4 | 383750 | INPRG | NORM-OPS | 2019-03-07 | 2019-05-13 | 2019-03-07 | 2019-03-07 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 171764 | Work Order Description - 171764 - PSPM | PSPM | 4 | 383657 | SCHD | NORM-OPS | 2018-11-05 | 2019-04-01 | 2019-02-23 | 2019-02-23 | 1 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 171770 | Work Order Description - 171770 - PM | PM | 4 | 469912 | SCHD | EQUIP-ISOL | 2018-11-05 | 2020-02-25 | 2019-06-29 | 2019-06-29 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 171775 | Work Order Description - 171775 - PM | PM | 3 | 403810 | SCHD | EQUIP-ISOL | 2018-11-05 | 2020-02-25 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 171795 | Work Order Description - 171795 - PSPM | PSPM | 1 | 306618 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-04-01 | 2019-06-22 | 2019-06-22 | 1 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 171797 | Work Order Description - 171797 - PM | PM | 3 | 403755 | SCHD | EQUIP-ISOL | 2018-11-05 | 2020-02-25 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 171799 | Work Order Description - 171799 - PM | PM | 3 | 403351 | SCHD | EQUIP-ISOL | 2018-11-05 | 2020-02-25 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 171802 | Work Order Description - 171802 - PM | PM | 3 | 323646 | SCHD | PACK-ISOL | 2018-11-05 | 2019-04-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 171803 | Work Order Description - 171803 - PM | PM | 3 | 479325 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-04-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 171804 | Work Order Description - 171804 - PSPM | PSPM | 4 | 203179 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-04-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 171805 | Work Order Description - 171805 - PM | PM | 4 | 556432 | SCHD | SYS-ISOL | 2018-11-05 | 2019-04-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 171807 | Work Order Description - 171807 - PSPM | PSPM | 1 | 458749 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-04-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 27
2019-03-31 | 171808 | Work Order Description - 171808 - PSPM | PSPM | 1 | 490862 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-04-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 171809 | Work Order Description - 171809 - PSPM | PSPM | 1 | 25682 | SCHD | EQUIP-ISOL | 2018-11-05 | 2019-04-01 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 171815 | Work Order Description - 171815 - PM | PM | 4 | 81494 | SCHD | PACK-ISOL | 2018-11-05 | 2019-04-01 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 171823 | Work Order Description - 171823 - PM | PM | 2 | 128836 | SCHD | PACK-ISOL | 2019-03-22 | 2019-04-25 | 2019-04-13 | 2019-04-23 | 2 | MAINTENANCE | ELECTRICAL | 74
2019-03-31 | 171824 | Work Order Description - 171824 - PM | PM | 4 | 96159 | SCHD | NORM-OPS | 2018-11-02 | 2019-06-18 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 171825 | Work Order Description - 171825 - PM | PM | 4 | 96159 | SCHD | NORM-OPS | 2018-11-02 | 2019-06-18 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 171826 | Work Order Description - 171826 - PM | PM | 4 | 96159 | SCHD | NORM-OPS | 2018-11-02 | 2019-06-18 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 171827 | Work Order Description - 171827 - PM | PM | 4 | 96159 | SCHD | NORM-OPS | 2018-11-02 | 2019-06-18 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 171828 | Work Order Description - 171828 - PM | PM | 4 | 375927 | SCHD | PACK-ISOL | 2018-12-17 | 2019-04-25 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 171830 | Work Order Description - 171830 - PM | PM | 4 | 96159 | SCHD | NORM-OPS | 2018-11-02 | 2019-06-18 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 171841 | Work Order Description - 171841 - PM | PM | 3 | 128614 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-01 | 2019-03-31 | 2019-03-31 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 171843 | Work Order Description - 171843 - PM | PM | 2 | 449172 | SCHD | PACK-ISOL | 2019-03-06 | 2019-04-01 | 2019-06-01 | 2019-06-10 | 1 | MAINTENANCE | MECHANICAL | 140
2019-03-31 | 171844 | Work Order Description - 171844 - PM | PM | 2 | 527194 | SCHD | PACK-ISOL | 2019-03-06 | 2019-04-01 | 2019-06-01 | 2019-06-10 | 1 | MAINTENANCE | MECHANICAL | 140
2019-03-31 | 171845 | Work Order Description - 171845 - PM | PM | 2 | 75010 | SCHD | PACK-ISOL | 2019-03-06 | 2019-04-01 | 2019-06-01 | 2019-06-10 | 1 | MAINTENANCE | MECHANICAL | 140
2019-03-31 | 171846 | Work Order Description - 171846 - PM | PM | 4 | 277246 | SCHD | PACK-ISOL | 2019-03-15 | 2019-04-01 | 2019-04-30 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 171847 | Work Order Description - 171847 - PM | PM | 4 | 92712 | SCHD | PACK-ISOL | 2019-03-15 | 2019-04-01 | 2019-04-30 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 171855 | Work Order Description - 171855 - PM | PM | 2 | 450548 | SCHD | NORM-OPS | 2018-11-02 | 2019-04-01 | 2019-04-06 | 2019-04-06 | 2 | OPERATIONS | OPERATIONS | 7
2019-03-31 | 171866 | Work Order Description - 171866 - PSPM | PSPM | 1 | 449172 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 171867 | Work Order Description - 171867 - PSPM | PSPM | 1 | 527194 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 171868 | Work Order Description - 171868 - PSPM | PSPM | 1 | 75010 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 171870 | Work Order Description - 171870 - PSPM | PSPM | 1 | 449172 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171871 | Work Order Description - 171871 - PSPM | PSPM | 1 | 527194 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171872 | Work Order Description - 171872 - PSPM | PSPM | 1 | 75010 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171873 | Work Order Description - 171873 - PSPM | PSPM | 1 | 128836 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-01 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171874 | Work Order Description - 171874 - PSPM | PSPM | 1 | 128836 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-01 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171875 | Work Order Description - 171875 - PSPM | PSPM | 1 | 449172 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171876 | Work Order Description - 171876 - PSPM | PSPM | 1 | 527194 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171877 | Work Order Description - 171877 - PSPM | PSPM | 1 | 75010 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171878 | Work Order Description - 171878 - PSPM | PSPM | 1 | 449172 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171879 | Work Order Description - 171879 - PSPM | PSPM | 1 | 527194 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171886 | Work Order Description - 171886 - PSPM | PSPM | 1 | 75010 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171888 | Work Order Description - 171888 - PSPM | PSPM | 1 | 227958 | SCHD | NORM-OPS | 2018-11-02 | 2019-04-01 | 2019-05-02 | 2019-05-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171889 | Work Order Description - 171889 - PM | PM | 4 | 95325 | SCHD | NORM-OPS | 2018-11-02 | 2019-04-01 | 2019-05-26 | 2019-05-26 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 171890 | Work Order Description - 171890 - PM | PM | 4 | 383147 | SCHD | PACK-ISOL | 2018-12-17 | 2019-06-18 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 171891 | Work Order Description - 171891 - PM | PM | 2 | 395877 | SCHD | EQUIP-ISOL | 2018-11-02 | 2019-04-25 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 171893 | Work Order Description - 171893 - PM | PM | 4 | 377244 | SCHD | EQUIP-ISOL | 2018-11-02 | 2019-04-25 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 172420 | Work Order Description - 172420 - BR | BR | 3 | 545421 | WSCHD | PACK-ISOL | 2019-03-18 | 2019-05-03 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 172442 | Work Order Description - 172442 - PSCM | PSCM | 1 | 357609 | WSCHD | EQUIP-ISOL | 2018-11-02 | 2020-10-30 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 172451 | Work Order Description - 172451 - PSCM | PSCM | 1 | 81148 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-10-30 | 2019-09-14 | 2019-09-14 | 4 | MAINTENANCE | INSTRUMENTS | 43
2019-03-31 | 172454 | Work Order Description - 172454 - CM | CM | 1 | 697913 | WSCHD | NORM-OPS | 2018-11-03 | 2020-06-01 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | CONSTRUCTION | 476
2019-03-31 | 172456 | Work Order Description - 172456 - CM | CM | 3 | 375682 | SCHD | PACK-ISOL | 2019-01-07 | 2020-10-30 | 2019-10-31 | 2019-11-02 | 4 | MAINTENANCE | ELECTRICAL | 22
2019-03-31 | 172461 | Work Order Description - 172461 - CM | CM | 1 | 697913 | WSCHD | NORM-OPS | 2018-11-03 | 2019-11-01 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | CONSTRUCTION | 466.5
2019-03-31 | 172462 | Work Order Description - 172462 - CM | CM | 1 | 697913 | WSCHD | NORM-OPS | 2018-11-03 | 2019-11-01 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | CONSTRUCTION | 314
2019-03-31 | 172479 | Work Order Description - 172479 - PM | PM | 4 | 309718 | SCHD | PACK-ISOL | 2018-11-05 | 2019-04-02 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | MECHANICAL | 42
2019-03-31 | 172483 | Work Order Description - 172483 - PM | PM | 4 | 310064 | SCHD | NORM-OPS | 2018-11-05 | 2019-04-02 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 172484 | Work Order Description - 172484 - PM | PM | 4 | 188987 | SCHD | NORM-OPS | 2018-11-05 | 2019-04-02 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 172496 | Work Order Description - 172496 - PSPM | PSPM | 1 | 527744 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-20 | 2019-04-20 | 2019-04-23 | 1 | MAINTENANCE | ELECTRICAL | 96
2019-03-31 | 172574 | Work Order Description - 172574 - CM | CM | 1 | 136887 | WPLAN | SYS-ISOL | 2018-11-10 | 2020-10-31 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 172595 | Work Order Description - 172595 - CM | CM | 4 | 697913 | WSCHD | NORM-OPS | 2018-11-03 | 2019-11-02 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | FABRIC | 196
2019-03-31 | 172596 | Work Order Description - 172596 - CM | CM | 4 | 697913 | WSCHD | NORM-OPS | 2018-11-03 | 2020-05-31 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | FABRIC | 196
2019-03-31 | 172605 | Work Order Description - 172605 - CM | CM | 4 | 697913 | WSCHD | NORM-OPS | 2018-11-03 | 2020-05-31 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | FABRIC | 196
2019-03-31 | 172606 | Work Order Description - 172606 - CM | CM | 4 | 697913 | SCHD | NORM-OPS | 2019-03-31 | 2019-11-02 | 2019-04-06 | 2019-04-27 | 3 | INTEGRITY | FABRIC | 9.5
2019-03-31 | 172607 | Work Order Description - 172607 - CM | CM | 4 | 697913 | SCHD | NORM-OPS | 2019-03-31 | 2019-11-02 | 2019-04-06 | 2019-04-27 | 3 | INTEGRITY | FABRIC | 196
2019-03-31 | 172609 | Work Order Description - 172609 - CM | CM | 4 | 697913 | WSCHD | NORM-OPS | 2018-11-03 | 2020-05-31 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | FABRIC | 140
2019-03-31 | 172625 | Work Order Description - 172625 - PM | PM | 4 | 314186 | WSCHD | NORM-OPS | 2018-11-03 | 2019-04-03 | 2020-12-19 | 2020-12-19 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 172627 | Work Order Description - 172627 - PM | PM | 2 | 674380 | WSCHD | TPS | 2018-11-03 | 2019-04-03 | 2019-07-20 | 2019-07-20 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 172637 | Work Order Description - 172637 - PSPM | PSPM | 1 | 399574 | WSCHD | PACK-ISOL | 2018-11-19 | 2019-04-03 | 2019-04-06 | 2019-04-06 | 1 | INTEGRITY | CONSTRUCTION | 9
2019-03-31 | 172639 | Work Order Description - 172639 - PSPM | PSPM | 1 | 24937 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-03 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 172641 | Work Order Description - 172641 - PSPM | PSPM | 1 | 59191 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-03 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 172661 | Work Order Description - 172661 - PSPM | PSPM | 1 | 259535 | SCHD | SYS-ISOL | 2018-11-20 | 2019-04-03 | 2019-04-06 | 2019-04-06 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 172662 | Work Order Description - 172662 - PSPM | PSPM | 1 | 632455 | INPRG | NORM-OPS | 2019-03-08 | 2019-04-03 | 2019-03-08 | 2019-03-08 | 1 | MAINTENANCE | OPERATIONS | 12
2019-03-31 | 172667 | Work Order Description - 172667 - PM | PM | 4 | 401751 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-02-27 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 172668 | Work Order Description - 172668 - PM | PM | 4 | 544162 | SCHD | PACK-ISOL | 2018-11-20 | 2019-04-03 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 172756 | Work Order Description - 172756 - BR | BR | 3 | 393495 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-05 | 2019-07-13 | 2019-07-14 | 3 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 172758 | Work Order Description - 172758 - BR | BR | 3 | 392510 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-05 | 2019-04-28 | 2019-04-29 | 3 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 172759 | Work Order Description - 172759 - BR | BR | 3 | 185490 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-05 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 172766 | Work Order Description - 172766 - BR | BR | 4 | 19008 | INPRG | PACK-ISOL | 2019-03-28 | 2020-11-01 | 2019-03-30 | 2019-04-13 | 4 | INTEGRITY | OPERATIONS | 1
2019-03-31 | 172768 | Work Order Description - 172768 - BR | BR | 4 | 19008 | SCHD | PACK-ISOL | 2018-11-27 | 2020-11-01 | 2019-06-01 | 2019-06-01 | 4 | INTEGRITY | OPERATIONS | 36
2019-03-31 | 172770 | Work Order Description - 172770 - BR | BR | 4 | 19008 | SCHD | PACK-ISOL | 2019-03-05 | 2020-11-01 | 2019-04-06 | 2019-04-06 | 4 | INTEGRITY | OPERATIONS | 81
2019-03-31 | 172772 | Work Order Description - 172772 - BR | BR | 4 | 19008 | WSCHD | PACK-ISOL | 2018-11-04 | 2020-11-01 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | OPERATIONS | 93
2019-03-31 | 172782 | Work Order Description - 172782 - BR | BR | 3 | 262705 | WSCHD | SUBSYS-ISOL | 2019-03-29 | 2019-06-11 | 2019-04-27 | 2019-05-02 | 2 | INTEGRITY | SERVICES | 1376
2019-03-31 | 172791 | Work Order Description - 172791 - BR | BR | 4 | 547275 | SCHD | NORM-OPS | 2019-01-18 | 2020-11-01 | 2019-04-20 | 2019-04-21 | 4 | OPERATIONS | ELECTRICAL | 4
2019-03-31 | 172794 | Work Order Description - 172794 - CM | CM | 3 | 29625 | SCHD | NORM-OPS | 2018-11-20 | 2020-11-01 | 2019-11-09 | 2019-11-09 | 4 | MAINTENANCE | ELECTRICAL | 60
2019-03-31 | 172796 | Work Order Description - 172796 - BR | BR | 2 | 546245 | WSCHD | NORM-OPS | 2018-11-04 | 2019-05-06 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 172813 | Work Order Description - 172813 - PM | PM | 4 | 676326 | WSCHD | NORM-OPS | 2018-11-04 | 2019-04-04 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 172819 | Work Order Description - 172819 - PM | PM | 4 | 188855 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-04 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 172820 | Work Order Description - 172820 - PM | PM | 4 | 188858 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-04 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 172844 | Work Order Description - 172844 - PM | PM | 4 | 309736 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-04 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 172856 | Work Order Description - 172856 - PM | PM | 4 | 498465 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-04 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 172857 | Work Order Description - 172857 - PM | PM | 4 | 309712 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-04 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 172858 | Work Order Description - 172858 - PM | PM | 4 | 309713 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-04 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 172859 | Work Order Description - 172859 - PM | PM | 4 | 188857 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-04 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 172860 | Work Order Description - 172860 - PM | PM | 4 | 498464 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-04 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 172861 | Work Order Description - 172861 - PM | PM | 4 | 188855 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-04 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 172862 | Work Order Description - 172862 - PM | PM | 4 | 324811 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-04 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 172863 | Work Order Description - 172863 - PM | PM | 4 | 324812 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-04 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 172864 | Work Order Description - 172864 - PM | PM | 4 | 309735 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-04 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 172888 | Work Order Description - 172888 - PSPM | PSPM | 1 | 81212 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-04 | 2019-03-16 | 2019-03-16 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 172898 | Work Order Description - 172898 - PM | PM | 4 | 78409 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-06-03 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 172900 | Work Order Description - 172900 - PM | PM | 4 | 93259 | WPLAN | EQUIP-ISOL | 2018-11-04 | 2019-04-04 | 2019-04-16 | 2019-04-16 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 172901 | Work Order Description - 172901 - PM | PM | 4 | 396792 | WPLAN | EQUIP-ISOL | 2018-11-04 | 2019-04-04 | 2019-04-16 | 2019-04-16 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 172902 | Work Order Description - 172902 - PM | PM | 4 | 393059 | WPLAN | EQUIP-ISOL | 2018-11-04 | 2019-04-04 | 2019-04-16 | 2019-04-16 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 172903 | Work Order Description - 172903 - PM | PM | 4 | 89883 | WPLAN | EQUIP-ISOL | 2018-11-04 | 2019-04-04 | 2019-04-16 | 2019-04-16 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 172904 | Work Order Description - 172904 - PSPM | PSPM | 1 | 450986 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-04 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 172973 | Work Order Description - 172973 - BR | BR | 1 | 546068 | WSCHD | EQUIP-ISOL | 2018-11-04 | 2020-11-02 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | SERVICES | 16
2019-03-31 | 172981 | Work Order Description - 172981 - CM | CM | 2 | 98491 | WSCHD | EQUIP-ISOL | 2018-11-05 | 2019-11-04 |  |  | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 172984 | Work Order Description - 172984 - CM | CM | 4 | 495196 | WSCHD | NORM-OPS | 2018-11-05 | 2020-11-02 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | CONSTRUCTION | 48
2019-03-31 | 173000 | Work Order Description - 173000 - BR | BR | 1 | 326674 | WSCHD | NORM-OPS | 2018-11-10 | 2020-11-02 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 173004 | Work Order Description - 173004 - BR | BR | 1 | 262343 | WPLAN | EQUIP-ISOL | 2018-11-05 | 2020-11-02 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 173005 | Work Order Description - 173005 - BR | BR | 1 | 410879 | WPLAN | EQUIP-ISOL | 2018-11-05 | 2020-11-02 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 173006 | Work Order Description - 173006 - BR | BR | 1 | 410880 | WPLAN | EQUIP-ISOL | 2018-11-05 | 2020-11-02 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 173007 | Work Order Description - 173007 - BR | BR | 1 | 262344 | WPLAN | EQUIP-ISOL | 2018-11-05 | 2020-11-02 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 173023 | Work Order Description - 173023 - BR | BR | 4 | 256740 | SCHD | EQUIP-ISOL | 2019-02-13 | 2020-11-02 | 2019-11-16 | 2019-11-17 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 173024 | Work Order Description - 173024 - BR | BR | 3 | 98486 | SCHD | TPS | 2019-03-12 | 2019-05-06 | 2019-07-13 | 2019-07-21 | 3 | MAINTENANCE | INSTRUMENTS | 91
2019-03-31 | 173026 | Work Order Description - 173026 - PSPM | PSPM | 1 | 679201 | SCHD | EQUIP-ISOL | 2019-03-05 | 2019-04-05 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 173035 | Work Order Description - 173035 - PSPM | PSPM | 1 | 310193 | SCHD | PACK-ISOL | 2018-11-20 | 2019-04-05 | 2019-09-21 | 2019-09-21 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 173037 | Work Order Description - 173037 - PSPM | PSPM | 1 | 189031 | SCHD | PACK-ISOL | 2018-11-20 | 2019-04-05 | 2019-09-28 | 2019-09-28 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 173038 | Work Order Description - 173038 - PSPM | PSPM | 1 | 189031 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-05 | 2019-09-28 | 2019-09-28 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 173048 | Work Order Description - 173048 - PM | PM | 4 | 544163 | SCHD | PACK-ISOL | 2018-11-20 | 2019-04-05 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 173053 | Work Order Description - 173053 - PM | PM | 4 | 527315 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-29 | 2019-04-07 | 2019-04-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 173135 | Work Order Description - 173135 - CM | CM | 3 | 80476 | SCHD | PACK-ISOL | 2018-11-21 | 2019-02-04 | 2019-04-27 | 2019-05-03 | 2 | MAINTENANCE | MECHANICAL | 114
2019-03-31 | 173152 | Work Order Description - 173152 - CM | CM | 3 | 655471 | WPLAN | TPS | 2018-12-11 | 2019-09-30 | 2019-07-13 | 2019-07-18 | 2 | INTEGRITY | CONSTRUCTION | 190
2019-03-31 | 173154 | Work Order Description - 173154 - PM | PM | 4 | 401566 | SCHD | PACK-ISOL | 2018-11-20 | 2020-01-04 | 2019-03-16 | 2019-03-16 | 4 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 173192 | Work Order Description - 173192 - PM | PM | 4 | 294918 | WSCHD | NORM-OPS | 2018-11-16 | 2019-04-06 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | MECHANICAL | 10.5
2019-03-31 | 173196 | Work Order Description - 173196 - PSPM | PSPM | 4 | 25401 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-06 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 173217 | Work Order Description - 173217 - PSPM | PSPM | 4 | 448885 | SCHD | SYS-ISOL | 2018-11-20 | 2019-04-06 | 2019-04-14 | 2019-04-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 173218 | Work Order Description - 173218 - PM | PM | 4 | 74910 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-04-30 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 173223 | Work Order Description - 173223 - PSPM | PSPM | 1 | 227941 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-06 | 2019-03-17 | 2019-03-17 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 173299 | Work Order Description - 173299 - CM | CM | 1 | 457948 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-08 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | ELECTRICAL | 40
2019-03-31 | 173303 | Work Order Description - 173303 - PSCM | PSCM | 1 | 697913 | WSCHD | NORM-OPS | 2018-11-10 | 2019-12-01 | 2019-05-04 | 2019-05-04 | 3 | INTEGRITY | CONSTRUCTION | 184
2019-03-31 | 173310 | Work Order Description - 173310 - PSCM | PSCM | 1 | 204612 | WSCHD | TPS | 2018-11-10 | 2020-09-01 | 2019-08-03 | 2019-08-03 | 3 | INTEGRITY | CONSTRUCTION | 196
2019-03-31 | 173330 | Work Order Description - 173330 - CM | CM | 4 | 237448 | SCHD | NORM-OPS | 2018-11-20 | 2020-11-04 | 2019-04-27 | 2019-05-01 | 4 | INTEGRITY | ELECTRICAL | 78
2019-03-31 | 173339 | Work Order Description - 173339 - BR | BR | 3 | 56382 | WPLAN | PACK-ISOL | 2018-11-10 | 2019-05-08 | 2019-07-27 | 2019-07-27 | 3 | MAINTENANCE | MECHANICAL | 38
2019-03-31 | 173342 | Work Order Description - 173342 - CM | CM | 1 | 204611 | WPLAN | NORM-OPS | 2018-11-10 | 2020-06-01 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | CONSTRUCTION | 14
2019-03-31 | 173343 | Work Order Description - 173343 - CM | CM | 3 | 556432 | WPLAN | NORM-OPS | 2018-11-08 | 2019-09-23 | 2019-07-13 | 2019-07-14 | 2 | MAINTENANCE | FABRIC | 12
2019-03-31 | 173359 | Work Order Description - 173359 - PSPM | PSPM | 1 | 657140 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-04-07 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 173362 | Work Order Description - 173362 - PM | PM | 2 | 575051 | WSCHD | PACK-ISOL | 2018-11-16 | 2019-04-07 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 173367 | Work Order Description - 173367 - PM | PM | 4 | 601923 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-07 | 2019-04-13 | 2019-04-13 | 2 | OPERATIONS | OPERATIONS | 60
2019-03-31 | 173378 | Work Order Description - 173378 - PM | PM | 4 | 436495 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173380 | Work Order Description - 173380 - PM | PM | 4 | 436470 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173381 | Work Order Description - 173381 - PM | PM | 4 | 664283 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173382 | Work Order Description - 173382 - PM | PM | 4 | 655999 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173383 | Work Order Description - 173383 - PM | PM | 4 | 664292 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173384 | Work Order Description - 173384 - PM | PM | 4 | 655997 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173385 | Work Order Description - 173385 - PM | PM | 4 | 656025 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173386 | Work Order Description - 173386 - PM | PM | 4 | 664278 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173387 | Work Order Description - 173387 - PM | PM | 4 | 436495 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173388 | Work Order Description - 173388 - PM | PM | 4 | 443381 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173389 | Work Order Description - 173389 - PM | PM | 4 | 655947 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173390 | Work Order Description - 173390 - PM | PM | 4 | 443384 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173391 | Work Order Description - 173391 - PM | PM | 4 | 664293 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173392 | Work Order Description - 173392 - PM | PM | 4 | 655943 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173393 | Work Order Description - 173393 - PM | PM | 4 | 436449 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173394 | Work Order Description - 173394 - PM | PM | 4 | 443386 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173395 | Work Order Description - 173395 - PM | PM | 4 | 443439 | SCHD | PACK-ISOL | 2018-12-17 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173396 | Work Order Description - 173396 - PM | PM | 4 | 664273 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-03-02 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173397 | Work Order Description - 173397 - PM | PM | 4 | 443387 | SCHD | PACK-ISOL | 2018-12-17 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173398 | Work Order Description - 173398 - PM | PM | 4 | 655996 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-03-02 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173399 | Work Order Description - 173399 - PM | PM | 4 | 443361 | SCHD | PACK-ISOL | 2018-12-17 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173400 | Work Order Description - 173400 - PM | PM | 4 | 436446 | SCHD | PACK-ISOL | 2018-12-17 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173401 | Work Order Description - 173401 - PM | PM | 4 | 655968 | SCHD | PACK-ISOL | 2018-12-17 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173402 | Work Order Description - 173402 - PM | PM | 4 | 436525 | SCHD | PACK-ISOL | 2018-12-17 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173403 | Work Order Description - 173403 - PM | PM | 4 | 664284 | SCHD | PACK-ISOL | 2018-12-17 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173404 | Work Order Description - 173404 - PM | PM | 4 | 443360 | SCHD | PACK-ISOL | 2018-12-17 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173405 | Work Order Description - 173405 - PM | PM | 4 | 664270 | SCHD | PACK-ISOL | 2018-12-17 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173406 | Work Order Description - 173406 - PM | PM | 4 | 664271 | SCHD | PACK-ISOL | 2018-12-17 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173407 | Work Order Description - 173407 - PM | PM | 4 | 655975 | SCHD | PACK-ISOL | 2018-12-17 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173408 | Work Order Description - 173408 - PM | PM | 4 | 664295 | SCHD | PACK-ISOL | 2018-12-17 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173409 | Work Order Description - 173409 - PM | PM | 4 | 664296 | SCHD | PACK-ISOL | 2018-12-17 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173410 | Work Order Description - 173410 - PM | PM | 4 | 664274 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173411 | Work Order Description - 173411 - PM | PM | 4 | 436467 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173412 | Work Order Description - 173412 - PM | PM | 4 | 436445 | SCHD | PACK-ISOL | 2018-12-17 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173413 | Work Order Description - 173413 - PM | PM | 4 | 436447 | SCHD | PACK-ISOL | 2018-12-17 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173414 | Work Order Description - 173414 - PM | PM | 4 | 443387 | SCHD | PACK-ISOL | 2018-12-17 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173415 | Work Order Description - 173415 - PM | PM | 4 | 664294 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173416 | Work Order Description - 173416 - PM | PM | 4 | 656028 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173417 | Work Order Description - 173417 - PM | PM | 4 | 443380 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173418 | Work Order Description - 173418 - PM | PM | 4 | 443382 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173419 | Work Order Description - 173419 - PM | PM | 4 | 436451 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173420 | Work Order Description - 173420 - PM | PM | 4 | 443384 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173421 | Work Order Description - 173421 - PM | PM | 4 | 436524 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173422 | Work Order Description - 173422 - PM | PM | 4 | 436405 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173423 | Work Order Description - 173423 - PM | PM | 4 | 655944 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173424 | Work Order Description - 173424 - PM | PM | 4 | 436466 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173425 | Work Order Description - 173425 - PM | PM | 4 | 443383 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173426 | Work Order Description - 173426 - PM | PM | 4 | 443357 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-03-02 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173427 | Work Order Description - 173427 - PM | PM | 4 | 655945 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-03-02 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173428 | Work Order Description - 173428 - PM | PM | 4 | 436450 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-03-02 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173429 | Work Order Description - 173429 - PM | PM | 4 | 436526 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-03-02 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173430 | Work Order Description - 173430 - PM | PM | 4 | 664269 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173431 | Work Order Description - 173431 - PM | PM | 4 | 436448 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173432 | Work Order Description - 173432 - PM | PM | 4 | 655967 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173433 | Work Order Description - 173433 - PM | PM | 4 | 443414 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173434 | Work Order Description - 173434 - PM | PM | 4 | 436527 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173435 | Work Order Description - 173435 - PM | PM | 4 | 664297 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173436 | Work Order Description - 173436 - PM | PM | 4 | 664286 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173437 | Work Order Description - 173437 - PM | PM | 4 | 664285 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173438 | Work Order Description - 173438 - PM | PM | 4 | 656027 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173439 | Work Order Description - 173439 - PM | PM | 4 | 664275 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173440 | Work Order Description - 173440 - PM | PM | 4 | 443438 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173441 | Work Order Description - 173441 - PM | PM | 4 | 436491 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173442 | Work Order Description - 173442 - PM | PM | 4 | 436492 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173443 | Work Order Description - 173443 - PM | PM | 4 | 443417 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173444 | Work Order Description - 173444 - PM | PM | 4 | 436497 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 173536 | Work Order Description - 173536 - BR | BR | 4 | 316419 | SCHD | NORM-OPS | 2018-11-20 | 2020-11-05 | 2019-08-24 | 2019-08-24 | 4 | DRILLING | DRILLING | 1
2019-03-31 | 173541 | Work Order Description - 173541 - BR | BR | 4 | 378359 | SCHD | NORM-OPS | 2019-02-13 | 2020-11-05 | 2019-08-31 | 2019-08-31 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 173544 | Work Order Description - 173544 - BR | BR | 3 | 72312 | SCHD | NORM-OPS | 2019-02-13 | 2019-11-12 | 2019-04-28 | 2019-04-28 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 173550 | Work Order Description - 173550 - BR | BR | 4 | 652244 | WSCHD | EQUIP-ISOL | 2018-11-08 | 2020-11-05 | 2020-08-08 | 2020-08-08 | 4 | MAINTENANCE | MECHANICAL | 148
2019-03-31 | 173575 | Work Order Description - 173575 - CM | CM | 4 | 358271 | SCHD | NORM-OPS | 2018-11-26 | 2020-11-05 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 173584 | Work Order Description - 173584 - PM | PM | 4 | 261768 | WSCHD | NORM-OPS | 2018-11-16 | 2019-04-08 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 173588 | Work Order Description - 173588 - PM | PM | 4 | 25099 | SCHD | PACK-ISOL | 2018-11-20 | 2019-04-08 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 28
2019-03-31 | 173589 | Work Order Description - 173589 - PM | PM | 4 | 403562 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-02 | 2019-02-23 | 2019-02-23 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 173598 | Work Order Description - 173598 - PM | PM | 4 | 262750 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-08 | 2019-04-13 | 2019-04-13 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 173599 | Work Order Description - 173599 - PM | PM | 4 | 262750 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-08 | 2020-02-15 | 2020-02-15 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 173600 | Work Order Description - 173600 - PM | PM | 4 | 262750 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-08 | 2020-02-15 | 2020-02-15 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 173601 | Work Order Description - 173601 - PM | PM | 4 | 183847 | SCHD | PACK-ISOL | 2018-11-20 | 2019-08-18 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 173602 | Work Order Description - 173602 - PM | PM | 4 | 183848 | SCHD | PACK-ISOL | 2018-11-20 | 2019-08-18 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 173603 | Work Order Description - 173603 - PM | PM | 4 | 494962 | SCHD | SUBSYS-ISOL | 2018-11-20 | 2019-10-11 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 173604 | Work Order Description - 173604 - PM | PM | 4 | 491543 | SCHD | SUBSYS-ISOL | 2018-11-20 | 2019-10-11 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 173605 | Work Order Description - 173605 - PM | PM | 4 | 491544 | SCHD | SUBSYS-ISOL | 2018-11-20 | 2019-10-11 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 173606 | Work Order Description - 173606 - PM | PM | 4 | 263391 | SCHD | PACK-ISOL | 2018-11-20 | 2019-10-11 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 173607 | Work Order Description - 173607 - PM | PM | 4 | 499177 | SCHD | PACK-ISOL | 2018-11-20 | 2019-10-11 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 173608 | Work Order Description - 173608 - PM | PM | 4 | 499178 | SCHD | PACK-ISOL | 2018-11-20 | 2019-10-11 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 173609 | Work Order Description - 173609 - PM | PM | 4 | 499179 | SCHD | PACK-ISOL | 2018-11-20 | 2019-10-11 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 173610 | Work Order Description - 173610 - PM | PM | 4 | 323993 | SCHD | PACK-ISOL | 2018-11-20 | 2019-10-11 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 173611 | Work Order Description - 173611 - PM | PM | 4 | 29712 | SCHD | PACK-ISOL | 2018-11-20 | 2019-10-11 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 173612 | Work Order Description - 173612 - PM | PM | 4 | 263392 | SCHD | PACK-ISOL | 2018-11-20 | 2019-10-11 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 173613 | Work Order Description - 173613 - PM | PM | 4 | 499180 | SCHD | PACK-ISOL | 2018-11-20 | 2019-10-11 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 173620 | Work Order Description - 173620 - PSPM | PSPM | 1 | 378443 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-20 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | ELECTRICAL | 18
2019-03-31 | 173680 | Work Order Description - 173680 - BR | BR | 1 | 311009 | WSCHD | EQUIP-ISOL | 2018-11-10 | 2020-11-06 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 173687 | Work Order Description - 173687 - CM | CM | 3 | 20477 | WPLAN | SYS-ISOL | 2019-01-30 | 2019-06-19 | 2019-03-16 | 2019-03-16 | 2 | INTEGRITY | OPERATIONS | 28
2019-03-31 | 173704 | Work Order Description - 173704 - CM | CM | 4 | 262054 | WPLAN | NORM-OPS | 2018-11-10 | 2019-11-08 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | ELECTRICAL | 420
2019-03-31 | 173712 | Work Order Description - 173712 - CM | CM | 4 | 352979 | WSCHD | NORM-OPS | 2018-11-10 | 2019-11-08 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | ELECTRICAL | 204
2019-03-31 | 173714 | Work Order Description - 173714 - BR | BR | 3 | 545261 | WSCHD | EQUIP-ISOL | 2018-11-10 | 2019-11-08 | 2019-09-06 | 2019-09-06 | 3 | MAINTENANCE | MECHANICAL | 35
2019-03-31 | 173715 | Work Order Description - 173715 - BR | BR | 4 | 545261 | WPLAN | EQUIP-ISOL | 2018-11-10 | 2020-11-06 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | MECHANICAL | 31
2019-03-31 | 173743 | Work Order Description - 173743 - PM | PM | 4 | 137798 | SCHD | PACK-ISOL | 2018-12-03 | 2019-04-09 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 173744 | Work Order Description - 173744 - PM | PM | 4 | 450363 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-04-09 | 2019-04-06 | 2019-04-06 | 3 | INTEGRITY | MECHANICAL | 8
2019-03-31 | 173745 | Work Order Description - 173745 - PM | PM | 4 | 325186 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-09 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 173746 | Work Order Description - 173746 - PM | PM | 4 | 325159 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-09 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 173747 | Work Order Description - 173747 - PM | PM | 4 | 310065 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-09 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 173748 | Work Order Description - 173748 - PM | PM | 4 | 498834 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-09 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 173749 | Work Order Description - 173749 - PM | PM | 4 | 325160 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-09 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 173751 | Work Order Description - 173751 - PM | PM | 4 | 216163 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-04-09 | 2019-04-13 | 2019-04-13 | 2 | DRILLING | DRILLING | 60
2019-03-31 | 173768 | Work Order Description - 173768 - PM | PM | 4 | 376271 | SCHD | EQUIP-ISOL | 2019-03-18 | 2019-04-09 | 2019-03-17 | 2019-03-17 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 173770 | Work Order Description - 173770 - PM | PM | 4 | 78406 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-08-01 | 2019-04-03 | 2019-04-03 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 173771 | Work Order Description - 173771 - PM | PM | 4 | 393058 | WPLAN | EQUIP-ISOL | 2018-11-09 | 2019-04-09 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 173773 | Work Order Description - 173773 - PM | PM | 2 | 227830 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-09 | 2019-04-14 | 2019-04-14 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 173775 | Work Order Description - 173775 - PSPM | PSPM | 1 | 664940 | WPLAN | EQUIP-ISOL | 2018-11-09 | 2019-04-09 | 2019-04-06 | 2019-04-20 | 1 | INTEGRITY | MECHANICAL | 6
2019-03-31 | 173776 | Work Order Description - 173776 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-09 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 173777 | Work Order Description - 173777 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-09 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 173847 | Work Order Description - 173847 - CM | CM | 4 | 465449 | WPLAN | PACK-ISOL | 2018-11-10 | 2020-11-07 | 2019-07-06 | 2019-07-06 | 4 | WELLS | MECHANICAL | 6
2019-03-31 | 173855 | Work Order Description - 173855 - CM | CM | 1 | 501176 | WSCHD | NORM-OPS | 2018-11-09 | 2019-07-11 |  |  | 3 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 173856 | Work Order Description - 173856 - BR | BR | 4 | 216158 | SCHD | NORM-OPS | 2018-12-03 | 2020-11-07 | 2019-08-24 | 2019-08-24 | 4 | DRILLING | DRILLING | 1
2019-03-31 | 173857 | Work Order Description - 173857 - BR | BR | 3 | 520307 | WPLAN | SYS-ISOL | 2018-11-10 | 2019-11-09 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | MECHANICAL | 17
2019-03-31 | 173862 | Work Order Description - 173862 - CM | CM | 1 | 481654 | WSCHD | NORM-OPS | 2018-11-09 | 2019-07-18 |  |  | 3 | MAINTENANCE | ELECTRICAL | 24
2019-03-31 | 173865 | Work Order Description - 173865 - PRJ | PRJ | 3 | 480073 | INPRG | NORM-OPS | 2019-03-23 | 2019-07-25 | 2019-03-30 | 2019-04-13 | 4 | ENGINEERING | OPERATIONS | 1
2019-03-31 | 173867 | Work Order Description - 173867 - CM | CM | 4 | 668445 | WPLAN | EQUIP-ISOL | 2018-11-13 | 2019-11-13 | 2019-07-13 | 2019-07-14 | 3 | MAINTENANCE | MECHANICAL | 29
2019-03-31 | 173869 | Work Order Description - 173869 - CM | CM | 4 | 668447 | WPLAN | EQUIP-ISOL | 2018-11-13 | 2019-11-13 | 2019-07-13 | 2019-07-14 | 3 | MAINTENANCE | MECHANICAL | 29
2019-03-31 | 173871 | Work Order Description - 173871 - BR | BR | 4 | 313319 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-11-07 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | DRILLING | 1
2019-03-31 | 173906 | Work Order Description - 173906 - PM | PM | 4 | 248546 | WSCHD | EQUIP-ISOL | 2018-11-19 | 2019-04-10 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | CONSTRUCTION | 13
2019-03-31 | 173914 | Work Order Description - 173914 - PM | PM | 4 | 324805 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-04 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 173915 | Work Order Description - 173915 - PM | PM | 4 | 498466 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-04 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 173919 | Work Order Description - 173919 - PM | PM | 4 | 324805 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-04 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 173920 | Work Order Description - 173920 - PM | PM | 4 | 498466 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-04 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 173924 | Work Order Description - 173924 - PM | PM | 4 | 324805 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-04 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 173925 | Work Order Description - 173925 - PM | PM | 4 | 498466 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-04 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 173930 | Work Order Description - 173930 - PM | PM | 4 | 476067 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-10-13 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 173931 | Work Order Description - 173931 - PM | PM | 4 | 306490 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-10-13 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 174012 | Work Order Description - 174012 - CM | CM | 1 | 356351 | WPLAN | EQUIP-ISOL | 2018-11-10 | 2019-11-10 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 174035 | Work Order Description - 174035 - CM | CM | 3 | 355580 | WPLAN | PACK-ISOL | 2018-11-14 | 2020-11-08 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 174050 | Work Order Description - 174050 - PM | PM | 4 | 249497 | WSCHD | EQUIP-ISOL | 2018-11-11 | 2019-08-03 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | INSTRUMENTS | 22
2019-03-31 | 174051 | Work Order Description - 174051 - PM | PM | 4 | 248335 | WSCHD | EQUIP-ISOL | 2018-11-19 | 2019-04-11 | 2019-04-06 | 2019-04-11 | 1 | INTEGRITY | CONSTRUCTION | 6
2019-03-31 | 174055 | Work Order Description - 174055 - PSPM | PSPM | 1 | 477561 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-11 | 2019-03-09 | 2019-03-09 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 174056 | Work Order Description - 174056 - PM | PM | 4 | 567233 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-11 | 2019-05-25 | 2019-05-25 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 174061 | Work Order Description - 174061 - PM | PM | 4 | 125212 | WPLAN | EQUIP-ISOL | 2019-03-27 | 2019-04-11 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | DRILLING | 4
2019-03-31 | 174062 | Work Order Description - 174062 - PM | PM | 4 | 89882 | WPLAN | EQUIP-ISOL | 2018-11-11 | 2019-04-11 | 2019-04-22 | 2019-04-22 | 1 | INTEGRITY | DRILLING | 4
2019-03-31 | 174065 | Work Order Description - 174065 - PM | PM | 4 | 89884 | WPLAN | EQUIP-ISOL | 2018-11-11 | 2019-04-11 | 2019-04-22 | 2019-04-22 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 174066 | Work Order Description - 174066 - PM | PM | 4 | 396542 | WPLAN | EQUIP-ISOL | 2018-11-11 | 2019-04-11 | 2019-04-22 | 2019-04-22 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 174067 | Work Order Description - 174067 - PSPM | PSPM | 1 | 93260 | WPLAN | EQUIP-ISOL | 2018-11-11 | 2019-04-11 | 2019-04-08 | 2019-04-08 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 174068 | Work Order Description - 174068 - PSPM | PSPM | 1 | 665060 | WPLAN | EQUIP-ISOL | 2018-11-11 | 2019-04-11 | 2019-04-08 | 2019-04-08 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 174196 | Work Order Description - 174196 - BR | BR | 3 | 383838 | SCHD | EQUIP-ISOL | 2018-11-13 | 2019-05-13 | 2019-07-13 | 2019-07-14 | 3 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 174198 | Work Order Description - 174198 - PSCM | PSCM | 1 | 258495 | SCHD | NORM-OPS | 2018-11-20 | 2020-11-09 | 2019-06-08 | 2019-06-08 | 4 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 174210 | Work Order Description - 174210 - BR | BR | 3 | 671541 | WPLAN | PACK-ISOL | 2018-11-12 | 2019-05-13 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 180
2019-03-31 | 174221 | Work Order Description - 174221 - PSPM | PSPM | 1 | 180965 | SCHD | TPS | 2018-11-20 | 2019-04-12 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 70
2019-03-31 | 174225 | Work Order Description - 174225 - PSPM | PSPM | 1 | 477562 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-12 | 2019-03-09 | 2019-03-09 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 174234 | Work Order Description - 174234 - PM | PM | 4 | 527315 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-06 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 174236 | Work Order Description - 174236 - PM | PM | 4 | 396283 | WPLAN | EQUIP-ISOL | 2018-11-12 | 2019-04-12 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 5
2019-03-31 | 174240 | Work Order Description - 174240 - PSPM | PSPM | 1 | 527367 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-12 | 2019-04-07 | 2019-04-07 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 174282 | Work Order Description - 174282 - BR | BR | 3 | 128823 | WPLAN | EQUIP-ISOL | 2018-11-12 | 2019-05-14 | 2019-05-25 | 2019-05-26 | 3 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 174290 | Work Order Description - 174290 - BR | BR | 3 | 678020 | WSCHD | TPS | 2018-11-14 | 2020-11-10 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | CONSTRUCTION | 22
2019-03-31 | 174295 | Work Order Description - 174295 - CM | CM | 3 | 678515 | WPLAN | SUBSYS-ISOL | 2018-11-14 | 2019-12-18 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 174300 | Work Order Description - 174300 - CM | CM | 1 | 671601 | WPLAN | EQUIP-ISOL | 2018-11-23 | 2019-11-12 | 2019-08-03 | 2019-08-03 | 3 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 174302 | Work Order Description - 174302 - CM | CM | 1 | 308530 | WSCHD | EQUIP-ISOL | 2019-02-04 | 2019-11-12 | 2019-08-03 | 2019-08-03 | 3 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 174303 | Work Order Description - 174303 - CM | CM | 1 | 671602 | WPLAN | EQUIP-ISOL | 2018-11-23 | 2019-11-12 | 2019-08-03 | 2019-08-03 | 3 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 174307 | Work Order Description - 174307 - CM | CM | 1 | 671603 | WPLAN | EQUIP-ISOL | 2018-11-23 | 2019-11-12 | 2019-08-03 | 2019-08-03 | 3 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 174311 | Work Order Description - 174311 - BR | BR | 1 | 657681 | SCHD | EQUIP-ISOL | 2019-03-24 | 2021-02-11 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 174312 | Work Order Description - 174312 - CM | CM | 2 | 578830 | SCHD | EQUIP-ISOL | 2018-12-05 | 2020-11-10 | 2020-02-15 | 2020-02-16 | 4 | WELLS | INSTRUMENTS | 102
2019-03-31 | 174316 | Work Order Description - 174316 - BR | BR | 3 | 499511 | WPLAN | PACK-ISOL | 2018-11-13 | 2019-11-12 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 174338 | Work Order Description - 174338 - PM | PM | 4 | 675037 | SCHD | PACK-ISOL | 2019-03-13 | 2019-04-13 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | ELECTRICAL | 7
2019-03-31 | 174339 | Work Order Description - 174339 - PSPM | PSPM | 1 | 399725 | WSCHD | PACK-ISOL | 2018-11-19 | 2019-04-13 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | CONSTRUCTION | 9
2019-03-31 | 174342 | Work Order Description - 174342 - PM | PM | 4 | 487761 | SCHD | PACK-ISOL | 2018-11-20 | 2019-04-13 | 2019-04-06 | 2019-04-06 | 1 | INTEGRITY | MECHANICAL | 3
2019-03-31 | 174349 | Work Order Description - 174349 - PM | PM | 3 | 449117 | SCHD | PACK-ISOL | 2018-12-17 | 2019-04-13 | 2019-07-13 | 2019-07-21 | 2 | INTEGRITY | MECHANICAL | 60
2019-03-31 | 174350 | Work Order Description - 174350 - PSPM | PSPM | 1 | 450957 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-13 | 2019-04-03 | 2019-04-03 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 174351 | Work Order Description - 174351 - PSPM | PSPM | 1 | 450957 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-13 | 2019-04-03 | 2019-04-03 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 174422 | Work Order Description - 174422 - PRJ | PRJ | 4 | 509879 | SCHD | NORM-OPS | 2018-12-05 | 2019-01-04 | 2019-04-23 | 2019-04-23 | 4 | MAINTENANCE | DRILLING | 144
2019-03-31 | 174424 | Work Order Description - 174424 - BR | BR | 4 | 98077 | SCHD | EQUIP-ISOL | 2019-02-13 | 2020-11-11 | 2019-04-02 | 2019-04-04 | 4 | MAINTENANCE | INSTRUMENTS | 19
2019-03-31 | 174425 | Work Order Description - 174425 - CM | CM | 4 | 481552 | WMATL | EQUIP-ISOL | 2019-02-08 | 2020-11-11 | 2019-07-13 | 2019-07-13 | 4 | OPERATIONS | MECHANICAL | 14
2019-03-31 | 174427 | Work Order Description - 174427 - CM | CM | 4 | 260966 | WSCHD | NORM-OPS | 2019-01-28 | 2019-11-13 | 2019-10-05 | 2019-10-05 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 174429 | Work Order Description - 174429 - CM | CM | 1 | 392310 | SCHD | NORM-OPS | 2018-11-20 | 2020-11-11 | 2019-04-20 | 2019-04-25 | 4 | MAINTENANCE | MECHANICAL | 40
2019-03-31 | 174435 | Work Order Description - 174435 - PM | PM | 4 | 262784 | SCHD | NORM-OPS | 2019-03-15 | 2019-05-01 | 2019-09-14 | 2019-09-14 | 2 | INTEGRITY | INSPECTION | 1
2019-03-31 | 174441 | Work Order Description - 174441 - PM | PM | 3 | 186576 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-04-15 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 174445 | Work Order Description - 174445 - CM | CM | 3 | 499057 | SCHD | PACK-ISOL | 2018-11-20 | 2019-05-15 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 126
2019-03-31 | 174447 | Work Order Description - 174447 - PM | PM | 4 | 375509 | SCHD | EQUIP-ISOL | 2018-11-13 | 2019-03-28 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 174448 | Work Order Description - 174448 - PM | PM | 4 | 74899 | SCHD | PACK-ISOL | 2018-12-17 | 2019-07-26 | 2019-07-20 | 2019-07-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 174449 | Work Order Description - 174449 - PM | PM | 4 | 127873 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-02-09 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 174451 | Work Order Description - 174451 - PSPM | PSPM | 4 | 375482 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-01-22 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 174460 | Work Order Description - 174460 - PSPM | PSPM | 1 | 441402 | WSCHD | NORM-OPS | 2018-11-13 | 2019-04-01 | 2019-04-13 | 2019-04-13 | 1 | WELLS | WELLS | 3
2019-03-31 | 174464 | Work Order Description - 174464 - PM | PM | 4 | 307616 | SCHD | EQUIP-ISOL | 2019-02-27 | 2020-02-25 | 2019-11-02 | 2019-11-02 | 2 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 174465 | Work Order Description - 174465 - PM | PM | 4 | 307616 | SCHD | NORM-OPS | 2019-02-27 | 2019-06-18 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 174468 | Work Order Description - 174468 - PM | PM | 4 | 408048 | WSCHD | NORM-OPS | 2018-11-13 | 2019-04-18 | 2019-11-02 | 2019-11-02 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 174472 | Work Order Description - 174472 - PM | PM | 4 | 308112 | WSCHD | EQUIP-ISOL | 2018-11-13 | 2020-02-25 | 2019-11-02 | 2019-11-02 | 2 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 174473 | Work Order Description - 174473 - PM | PM | 4 | 308112 | WSCHD | NORM-OPS | 2018-11-13 | 2019-06-18 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 174474 | Work Order Description - 174474 - PM | PM | 4 | 54773 | SCHD | PACK-ISOL | 2018-12-05 | 2019-09-07 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 174475 | Work Order Description - 174475 - PM | PM | 4 | 54774 | WSCHD | PACK-ISOL | 2018-11-16 | 2019-07-16 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 174487 | Work Order Description - 174487 - PM | PM | 4 | 407411 | SCHD | EQUIP-ISOL | 2019-02-27 | 2020-02-25 | 2019-11-02 | 2019-11-02 | 2 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 174488 | Work Order Description - 174488 - PM | PM | 4 | 407411 | SCHD | NORM-OPS | 2019-02-27 | 2019-06-18 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 174490 | Work Order Description - 174490 - PM | PM | 4 | 74913 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-05-26 | 2019-04-16 | 2019-04-16 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 174491 | Work Order Description - 174491 - PM | PM | 4 | 74917 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-05-26 | 2019-04-16 | 2019-04-16 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 174492 | Work Order Description - 174492 - PM | PM | 4 | 127907 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-05-26 | 2019-04-16 | 2019-04-16 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 174511 | Work Order Description - 174511 - BR | BR | 2 | 670451 | SCHD | TPS | 2018-12-21 | 2020-11-11 | 2019-07-13 | 2019-07-19 | 4 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 174512 | Work Order Description - 174512 - PM | PM | 4 | 660951 | WSCHD | NORM-OPS | 2018-11-14 | 2019-04-14 | 2019-04-13 | 2019-04-13 | 3 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 174514 | Work Order Description - 174514 - PSPM | PSPM | 1 | 652220 | SCHD | NORM-OPS | 2019-03-14 | 2019-04-14 | 2019-07-06 | 2019-07-09 | 1 | MAINTENANCE | MECHANICAL | 74
2019-03-31 | 174515 | Work Order Description - 174515 - PSPM | PSPM | 1 | 652220 | SCHD | NORM-OPS | 2019-03-14 | 2019-04-14 | 2019-07-06 | 2019-07-09 | 1 | MAINTENANCE | MECHANICAL | 252
2019-03-31 | 174516 | Work Order Description - 174516 - PSPM | PSPM | 4 | 478285 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-04-14 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 174526 | Work Order Description - 174526 - PM | PM | 3 | 124264 | SCHD | PACK-ISOL | 2018-12-17 | 2019-05-26 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 174527 | Work Order Description - 174527 - PM | PM | 3 | 266328 | SCHD | PACK-ISOL | 2018-12-17 | 2019-05-26 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 174528 | Work Order Description - 174528 - PM | PM | 3 | 670547 | SCHD | PACK-ISOL | 2018-12-17 | 2019-05-26 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 174529 | Work Order Description - 174529 - PM | PM | 3 | 375994 | SCHD | PACK-ISOL | 2018-12-17 | 2019-05-26 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 174530 | Work Order Description - 174530 - PM | PM | 3 | 670579 | SCHD | PACK-ISOL | 2018-12-21 | 2019-05-26 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 174532 | Work Order Description - 174532 - PSPM | PSPM | 1 | 451166 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-28 | 2019-04-21 | 2019-04-23 | 1 | MAINTENANCE | ELECTRICAL | 48
2019-03-31 | 174533 | Work Order Description - 174533 - PM | PM | 4 | 375789 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-13 | 2019-06-01 | 2019-06-04 | 4 | MAINTENANCE | MECHANICAL | 72
2019-03-31 | 174534 | Work Order Description - 174534 - PM | PM | 4 | 670511 | WPLAN | PACK-ISOL | 2018-11-14 | 2019-06-13 | 2019-06-01 | 2019-06-04 | 4 | MAINTENANCE | MECHANICAL | 72
2019-03-31 | 174538 | Work Order Description - 174538 - PSPM | PSPM | 1 | 110977 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-14 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 174539 | Work Order Description - 174539 - PSPM | PSPM | 1 | 375917 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-14 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 174655 | Work Order Description - 174655 - PSCM | PSCM | 1 | 155742 | WSCHD | NORM-OPS | 2018-11-17 | 2020-11-12 | 2019-04-20 | 2019-04-20 | 4 | INTEGRITY | FABRIC | 51
2019-03-31 | 174658 | Work Order Description - 174658 - PSCM | PSCM | 1 | 155742 | WSCHD | NORM-OPS | 2018-11-17 | 2020-11-12 | 2019-04-20 | 2019-04-20 | 4 | INTEGRITY | FABRIC | 17
2019-03-31 | 174663 | Work Order Description - 174663 - CM | CM | 3 | 320440 | WRISKREV | PACK-ISOL | 2019-03-31 | 2019-04-30 | 2019-04-27 | 2019-04-27 | 2 | INTEGRITY | DRILLING | 3
2019-03-31 | 174671 | Work Order Description - 174671 - PSCM | PSCM | 1 | 155742 | WSCHD | NORM-OPS | 2018-11-17 | 2020-11-12 | 2019-05-18 | 2019-05-18 | 4 | INTEGRITY | FABRIC | 20
2019-03-31 | 174685 | Work Order Description - 174685 - PSCM | PSCM | 1 | 155742 | WSCHD | NORM-OPS | 2018-11-17 | 2020-11-12 | 2019-05-18 | 2019-05-18 | 4 | INTEGRITY | FABRIC | 8.5
2019-03-31 | 174687 | Work Order Description - 174687 - PSCM | PSCM | 1 | 155742 | WSCHD | NORM-OPS | 2018-11-17 | 2020-11-12 | 2019-05-18 | 2019-05-18 | 4 | INTEGRITY | FABRIC | 17
2019-03-31 | 174695 | Work Order Description - 174695 - PSPM | PSPM | 1 | 399417 | WSCHD | SUBSYS-ISOL | 2018-11-16 | 2019-04-15 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 174699 | Work Order Description - 174699 - PM | PM | 3 | 360459 | WSCHD | EQUIP-ISOL | 2018-11-15 | 2019-07-02 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 174700 | Work Order Description - 174700 - PM | PM | 3 | 54417 | WSCHD | EQUIP-ISOL | 2018-11-15 | 2019-07-02 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 174701 | Work Order Description - 174701 - PM | PM | 3 | 57366 | WSCHD | EQUIP-ISOL | 2018-11-15 | 2019-07-02 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 174702 | Work Order Description - 174702 - PM | PM | 4 | 48611 | WSCHD | EQUIP-ISOL | 2018-11-15 | 2019-04-15 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 174703 | Work Order Description - 174703 - PM | PM | 3 | 360337 | WSCHD | EQUIP-ISOL | 2018-11-15 | 2019-04-15 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 174704 | Work Order Description - 174704 - PM | PM | 3 | 57125 | WSCHD | EQUIP-ISOL | 2018-11-15 | 2019-04-15 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 174705 | Work Order Description - 174705 - PM | PM | 4 | 261933 | WSCHD | EQUIP-ISOL | 2018-11-15 | 2019-04-15 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 174706 | Work Order Description - 174706 - PM | PM | 3 | 261936 | WSCHD | EQUIP-ISOL | 2018-11-15 | 2019-04-15 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 174707 | Work Order Description - 174707 - PM | PM | 3 | 54272 | WSCHD | EQUIP-ISOL | 2018-11-15 | 2019-04-15 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 174708 | Work Order Description - 174708 - PM | PM | 3 | 54273 | WSCHD | EQUIP-ISOL | 2018-11-15 | 2019-04-15 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 174709 | Work Order Description - 174709 - PM | PM | 3 | 261934 | WSCHD | EQUIP-ISOL | 2018-11-15 | 2019-04-15 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 174710 | Work Order Description - 174710 - PM | PM | 4 | 360665 | WSCHD | EQUIP-ISOL | 2018-11-15 | 2019-09-12 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 174711 | Work Order Description - 174711 - PM | PM | 3 | 54422 | WSCHD | EQUIP-ISOL | 2018-11-15 | 2019-07-02 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 174712 | Work Order Description - 174712 - PM | PM | 3 | 360666 | WSCHD | EQUIP-ISOL | 2018-11-15 | 2019-08-07 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 174713 | Work Order Description - 174713 - PM | PM | 4 | 409961 | WSCHD | EQUIP-ISOL | 2018-11-15 | 2019-08-07 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 174718 | Work Order Description - 174718 - PSPM | PSPM | 1 | 675037 | SCHD | NORM-OPS | 2019-03-26 | 2019-04-15 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 174731 | Work Order Description - 174731 - PSPM | PSPM | 1 | 53984 | WSCHD | PACK-ISOL | 2018-11-16 | 2019-04-15 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 174732 | Work Order Description - 174732 - PSPM | PSPM | 1 | 357574 | WSCHD | PACK-ISOL | 2018-11-16 | 2019-08-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 174733 | Work Order Description - 174733 - PSPM | PSPM | 1 | 357577 | WSCHD | SUBSYS-ISOL | 2018-11-16 | 2019-08-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 174734 | Work Order Description - 174734 - PSPM | PSPM | 1 | 653284 | WSCHD | SUBSYS-ISOL | 2018-11-16 | 2019-08-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 174735 | Work Order Description - 174735 - PSPM | PSPM | 1 | 53986 | WSCHD | PACK-ISOL | 2018-11-16 | 2019-08-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 174739 | Work Order Description - 174739 - PM | PM | 4 | 404412 | SCHD | NORM-OPS | 2019-02-21 | 2019-05-09 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 174746 | Work Order Description - 174746 - PSPM | PSPM | 1 | 29721 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-15 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 174752 | Work Order Description - 174752 - PSPM | PSPM | 1 | 128338 | INPRG | NORM-OPS | 2019-03-15 | 2019-04-15 | 2019-03-15 | 2019-03-15 | 1 | OPERATIONS | OPERATIONS | 4
2019-03-31 | 174755 | Work Order Description - 174755 - PM | PM | 4 | 177556 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-10-18 | 2019-07-20 | 2019-07-20 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 174756 | Work Order Description - 174756 - PM | PM | 4 | 469472 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-08-25 | 2019-06-08 | 2019-06-08 | 2 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 174759 | Work Order Description - 174759 - PM | PM | 4 | 324405 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-08-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 174761 | Work Order Description - 174761 - PM | PM | 4 | 262750 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-15 | 2020-02-22 | 2020-02-22 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 174762 | Work Order Description - 174762 - PM | PM | 4 | 262750 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-15 | 2020-02-22 | 2020-02-22 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 174763 | Work Order Description - 174763 - PM | PM | 4 | 256923 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-08-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 174764 | Work Order Description - 174764 - PM | PM | 4 | 183845 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-08-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 174765 | Work Order Description - 174765 - PM | PM | 4 | 475857 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-10-18 | 2019-07-20 | 2019-07-20 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 174766 | Work Order Description - 174766 - PM | PM | 4 | 402013 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-10-18 | 2019-07-20 | 2019-07-20 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 174767 | Work Order Description - 174767 - PM | PM | 4 | 402035 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-10-18 | 2019-07-20 | 2019-07-20 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 174768 | Work Order Description - 174768 - PM | PM | 4 | 476232 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-10-18 | 2019-07-20 | 2019-07-20 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 174769 | Work Order Description - 174769 - PM | PM | 4 | 34146 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-10-18 | 2019-07-20 | 2019-07-20 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 174770 | Work Order Description - 174770 - PM | PM | 4 | 29874 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-08-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 174771 | Work Order Description - 174771 - PM | PM | 4 | 323515 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-08-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 174772 | Work Order Description - 174772 - PM | PM | 4 | 253424 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-08-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 174773 | Work Order Description - 174773 - PM | PM | 4 | 253425 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-08-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 174774 | Work Order Description - 174774 - PM | PM | 4 | 253426 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-08-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 174775 | Work Order Description - 174775 - PM | PM | 4 | 29875 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-08-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 174776 | Work Order Description - 174776 - PM | PM | 4 | 253427 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-08-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 174777 | Work Order Description - 174777 - PM | PM | 4 | 323516 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-08-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 174778 | Work Order Description - 174778 - PM | PM | 4 | 253450 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-08-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 174779 | Work Order Description - 174779 - PM | PM | 4 | 29876 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-08-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 174780 | Work Order Description - 174780 - PM | PM | 4 | 323541 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-08-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 174796 | Work Order Description - 174796 - PM | PM | 4 | 128976 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-05-09 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 174804 | Work Order Description - 174804 - PM | PM | 4 | 670525 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-15 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 174805 | Work Order Description - 174805 - PM | PM | 4 | 375852 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-15 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 175023 | Work Order Description - 175023 - BR | BR | 3 | 75139 | SCHD | SUBSYS-ISOL | 2019-02-13 | 2019-05-17 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 175024 | Work Order Description - 175024 - BR | BR | 3 | 669060 | WPLAN | TPS | 2018-11-19 | 2020-11-13 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 175033 | Work Order Description - 175033 - PSCM | PSCM | 1 | 138087 | SCHD | NORM-OPS | 2019-03-13 | 2020-11-13 | 2019-06-01 | 2019-06-02 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 175044 | Work Order Description - 175044 - BR | BR | 3 | 321790 | WPLAN | SYS-ISOL | 2018-11-16 | 2019-05-15 | 2019-05-04 | 2019-05-05 | 2 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 175046 | Work Order Description - 175046 - PSCM | PSCM | 1 | 520395 | WSCHD | PACK-ISOL | 2018-11-19 | 2019-11-15 | 2019-04-20 | 2019-04-20 | 3 | WELLS | WELLS | 12
2019-03-31 | 175048 | Work Order Description - 175048 - CM | CM | 1 | 650752 | WPLAN | EQUIP-ISOL | 2018-11-16 | 2019-11-15 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 175051 | Work Order Description - 175051 - CM | CM | 3 | 464999 | SCHD | PACK-ISOL | 2018-12-24 | 2020-11-13 | 2019-10-05 | 2019-10-05 | 4 | WELLS | INSTRUMENTS | 2
2019-03-31 | 175052 | Work Order Description - 175052 - BR | BR | 3 | 375517 | SCHD | TPS | 2019-02-13 | 2019-12-07 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 175056 | Work Order Description - 175056 - PSPM | PSPM | 1 | 441400 | WSCHD | NORM-OPS | 2018-11-15 | 2019-04-15 | 2019-04-13 | 2019-04-13 | 1 | WELLS | WELLS | 3
2019-03-31 | 175096 | Work Order Description - 175096 - PRJ | PRJ | 4 | 580769 | WSCHD | NORM-OPS | 2018-11-16 | 2019-11-13 | 2019-04-06 | 2019-04-06 | 4 | ENGINEERING | OPERATIONS | 48
2019-03-31 | 175097 | Work Order Description - 175097 - CM | CM | 2 | 78376 | SCHD | PACK-ISOL | 2018-11-20 | 2020-11-14 | 2019-07-13 | 2019-07-14 | 4 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 175099 | Work Order Description - 175099 - CM | CM | 4 | 476739 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-11-14 | 2019-08-17 | 2019-08-25 | 4 | DRILLING | DRILLING | 1
2019-03-31 | 175101 | Work Order Description - 175101 - PSPM | PSPM | 1 | 293116 | WSCHD | NORM-OPS | 2018-11-16 | 2019-04-16 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | SAFETY | 3
2019-03-31 | 175105 | Work Order Description - 175105 - PM | PM | 4 | 450362 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-04-16 | 2019-04-06 | 2019-04-06 | 3 | INTEGRITY | INSTRUMENTS | 2
2019-03-31 | 175106 | Work Order Description - 175106 - PM | PM | 3 | 325161 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-16 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 175107 | Work Order Description - 175107 - PM | PM | 4 | 498831 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-16 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 175108 | Work Order Description - 175108 - PM | PM | 4 | 188982 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-16 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 175109 | Work Order Description - 175109 - PM | PM | 4 | 498832 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-16 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 175110 | Work Order Description - 175110 - PM | PM | 4 | 188983 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-16 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 175113 | Work Order Description - 175113 - PSPM | PSPM | 1 | 260187 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-04-16 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 175114 | Work Order Description - 175114 - PSPM | PSPM | 1 | 458754 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-04-16 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 175296 | Work Order Description - 175296 - BR | BR | 4 | 476739 | SCHD | EQUIP-ISOL | 2018-11-20 | 2020-11-14 | 2019-08-17 | 2019-08-17 | 4 | DRILLING | DRILLING | 1
2019-03-31 | 175298 | Work Order Description - 175298 - CM | CM | 4 | 476739 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-11-16 | 2019-08-17 | 2019-08-17 | 3 | DRILLING | DRILLING | 22
2019-03-31 | 175307 | Work Order Description - 175307 - CM | CM | 3 | 401553 | WPLAN | EQUIP-ISOL | 2018-11-16 | 2020-11-14 | 2019-07-27 | 2019-07-27 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 175318 | Work Order Description - 175318 - PRJ | PRJ | 3 | 375761 | SCHD | NORM-OPS | 2019-03-22 | 2019-01-16 | 2019-03-12 | 2019-03-29 | 3 | MAINTENANCE | CONSTRUCTION | 54
2019-03-31 | 175320 | Work Order Description - 175320 - BR | BR | 1 | 126058 | SCHD | EQUIP-ISOL | 2018-11-21 | 2019-05-18 | 2019-04-21 | 2019-05-13 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 175351 | Work Order Description - 175351 - PM | PM | 4 | 314187 | WSCHD | NORM-OPS | 2018-11-17 | 2019-04-17 | 2020-12-26 | 2020-12-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175352 | Work Order Description - 175352 - PM | PM | 4 | 666277 | WSCHD | TPS | 2018-11-17 | 2019-04-17 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175353 | Work Order Description - 175353 - PM | PM | 4 | 546702 | WSCHD | TPS | 2018-11-17 | 2019-04-17 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175359 | Work Order Description - 175359 - PM | PM | 4 | 314187 | WSCHD | NORM-OPS | 2018-11-17 | 2019-04-17 | 2020-12-26 | 2020-12-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175363 | Work Order Description - 175363 - PM | PM | 4 | 671166 | WSCHD | EQUIP-ISOL | 2018-11-19 | 2019-05-11 | 2019-08-17 | 2019-08-17 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 175367 | Work Order Description - 175367 - PM | PM | 4 | 51697 | WSCHD | PACK-ISOL | 2018-11-19 | 2019-04-17 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 175368 | Work Order Description - 175368 - PM | PM | 4 | 309736 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-11 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175369 | Work Order Description - 175369 - PM | PM | 4 | 324806 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-11 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175370 | Work Order Description - 175370 - PM | PM | 4 | 309708 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-11 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175371 | Work Order Description - 175371 - PM | PM | 4 | 188856 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-11 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175372 | Work Order Description - 175372 - PM | PM | 4 | 309709 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-11 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175373 | Work Order Description - 175373 - PM | PM | 4 | 324806 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-11 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175374 | Work Order Description - 175374 - PM | PM | 4 | 309736 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-11 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175375 | Work Order Description - 175375 - PM | PM | 4 | 324806 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-11 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175376 | Work Order Description - 175376 - PM | PM | 4 | 309708 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-11 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175377 | Work Order Description - 175377 - PM | PM | 4 | 188856 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-11 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175378 | Work Order Description - 175378 - PM | PM | 4 | 309709 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-11 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175379 | Work Order Description - 175379 - PM | PM | 4 | 309736 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-11 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175380 | Work Order Description - 175380 - PM | PM | 4 | 324806 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-11 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175381 | Work Order Description - 175381 - PM | PM | 4 | 309708 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-11 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175382 | Work Order Description - 175382 - PM | PM | 4 | 188856 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-11 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175383 | Work Order Description - 175383 - PM | PM | 4 | 309709 | SCHD | NORM-OPS | 2018-11-20 | 2019-05-11 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175386 | Work Order Description - 175386 - PSPM | PSPM | 1 | 29041 | SCHD | PACK-ISOL | 2018-11-20 | 2019-04-17 | 2019-03-16 | 2019-03-16 | 1 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 175390 | Work Order Description - 175390 - PSPM | PSPM | 1 | 527317 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-17 | 2019-04-07 | 2019-04-07 | 1 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 175391 | Work Order Description - 175391 - PSPM | PSPM | 1 | 659514 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-17 | 2019-04-02 | 2019-04-02 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 175392 | Work Order Description - 175392 - PSPM | PSPM | 1 | 659514 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-17 | 2019-03-31 | 2019-03-31 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 175397 | Work Order Description - 175397 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-17 | 2019-04-07 | 2019-04-07 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 175398 | Work Order Description - 175398 - PSPM | PSPM | 1 | 659514 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-17 | 2019-03-31 | 2019-03-31 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 175465 | Work Order Description - 175465 - BR | BR | 3 | 308463 | WPLAN | EQUIP-ISOL | 2018-11-18 | 2019-11-17 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 88
2019-03-31 | 175467 | Work Order Description - 175467 - CM | CM | 3 | 113097 | SCHD | PACK-ISOL | 2018-11-20 | 2019-04-07 | 2019-03-14 | 2019-03-15 | 2 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 175476 | Work Order Description - 175476 - CM | CM | 4 | 312087 | SCHD | NORM-OPS | 2018-12-05 | 2020-11-15 | 2019-08-03 | 2019-08-03 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 175506 | Work Order Description - 175506 - PSPM | PSPM | 1 | 671828 | SCHD | NORM-OPS | 2019-03-15 | 2019-04-18 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 175508 | Work Order Description - 175508 - PM | PM | 4 | 450481 | SCHD | PACK-ISOL | 2018-11-20 | 2019-04-18 | 2019-03-23 | 2019-03-23 | 1 | MAINTENANCE | ELECTRICAL | 48
2019-03-31 | 175509 | Work Order Description - 175509 - PSPM | PSPM | 1 | 309166 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-18 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 43
2019-03-31 | 175510 | Work Order Description - 175510 - PM | PM | 4 | 73604 | SCHD | PACK-ISOL | 2018-11-20 | 2019-04-18 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 16
2019-03-31 | 175513 | Work Order Description - 175513 - PSPM | PSPM | 1 | 81212 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-18 | 2019-03-30 | 2019-03-30 | 1 | OPERATIONS | OPERATIONS | 1
2019-03-31 | 175514 | Work Order Description - 175514 - PM | PM | 4 | 256187 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-18 | 2019-03-30 | 2019-03-30 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 175519 | Work Order Description - 175519 - PM | PM | 4 | 80369 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-18 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 175521 | Work Order Description - 175521 - PM | PM | 4 | 125898 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-04-18 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 175522 | Work Order Description - 175522 - PM | PM | 4 | 124210 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-04-18 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 175524 | Work Order Description - 175524 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-18 | 2019-03-18 | 2019-03-18 | 3 | MAINTENANCE | MECHANICAL | 0
2019-03-31 | 175525 | Work Order Description - 175525 - PSPM | PSPM | 1 | 93261 | WPLAN | EQUIP-ISOL | 2018-11-18 | 2019-04-18 | 2019-04-17 | 2019-04-17 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 175526 | Work Order Description - 175526 - PSPM | PSPM | 1 | 665061 | WPLAN | EQUIP-ISOL | 2018-11-18 | 2019-04-18 | 2019-04-17 | 2019-04-17 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 175527 | Work Order Description - 175527 - PSPM | PSPM | 1 | 665063 | WPLAN | EQUIP-ISOL | 2018-11-18 | 2019-04-18 | 2019-04-17 | 2019-04-17 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 175528 | Work Order Description - 175528 - PSPM | PSPM | 1 | 665062 | WPLAN | EQUIP-ISOL | 2018-11-18 | 2019-04-18 | 2019-04-17 | 2019-04-17 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 175529 | Work Order Description - 175529 - PSPM | PSPM | 1 | 450986 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-18 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 175659 | Work Order Description - 175659 - PSCM | PSCM | 1 | 321876 | SCHD | NORM-OPS | 2018-12-05 | 2020-11-16 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 175675 | Work Order Description - 175675 - BR | BR | 1 | 395271 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-11-18 | 2019-04-21 | 2019-04-27 | 3 | MAINTENANCE | ELECTRICAL | 109.5
2019-03-31 | 175684 | Work Order Description - 175684 - PSPM | PSPM | 4 | 326081 | WSCHD | EQUIP-ISOL | 2018-12-11 | 2019-04-19 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 175685 | Work Order Description - 175685 - PM | PM | 4 | 680945 | WSCHD | NORM-OPS | 2018-11-19 | 2019-04-19 | 2021-03-06 | 2021-03-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175687 | Work Order Description - 175687 - PM | PM | 4 | 680945 | WSCHD | NORM-OPS | 2018-11-19 | 2019-04-19 | 2021-03-06 | 2021-03-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175696 | Work Order Description - 175696 - PM | PM | 4 | 308896 | WSCHD | NORM-OPS | 2018-11-19 | 2019-04-19 | 2020-12-19 | 2020-12-19 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175701 | Work Order Description - 175701 - PM | PM | 4 | 305553 | WSCHD | EQUIP-ISOL | 2018-11-19 | 2019-05-13 | 2020-03-07 | 2020-03-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 175702 | Work Order Description - 175702 - PM | PM | 4 | 540636 | WSCHD | EQUIP-ISOL | 2018-12-04 | 2019-05-13 | 2021-03-06 | 2021-03-06 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 175703 | Work Order Description - 175703 - PM | PM | 4 | 361404 | WSCHD | EQUIP-ISOL | 2018-11-19 | 2019-04-19 | 2021-03-06 | 2021-03-06 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 175704 | Work Order Description - 175704 - PM | PM | 4 | 359214 | WSCHD | NORM-OPS | 2018-11-19 | 2019-04-19 | 2021-03-06 | 2021-03-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175705 | Work Order Description - 175705 - PM | PM | 4 | 680945 | WSCHD | NORM-OPS | 2018-11-19 | 2019-04-19 | 2021-03-06 | 2021-03-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175706 | Work Order Description - 175706 - PM | PM | 4 | 680945 | WSCHD | NORM-OPS | 2018-11-19 | 2019-04-19 | 2021-03-06 | 2021-03-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175708 | Work Order Description - 175708 - PSPM | PSPM | 1 | 294959 | SCHD | NORM-OPS | 2019-02-21 | 2019-04-19 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175710 | Work Order Description - 175710 - PM | PM | 4 | 296002 | WSCHD | NORM-OPS | 2018-11-19 | 2019-04-19 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | SAFETY | 1
2019-03-31 | 175711 | Work Order Description - 175711 - PSPM | PSPM | 1 | 531920 | SCHD | NORM-OPS | 2019-03-20 | 2019-04-19 | 2019-03-30 | 2019-03-30 | 1 | INTEGRITY | INSPECTION | 12
2019-03-31 | 175713 | Work Order Description - 175713 - PM | PM | 4 | 462436 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-19 | 2019-03-30 | 2019-03-30 | 2 | INTEGRITY | INSPECTION | 8
2019-03-31 | 175724 | Work Order Description - 175724 - PM | PM | 4 | 383656 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-04-19 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 175727 | Work Order Description - 175727 - PM | PM | 4 | 499149 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-19 | 2019-03-16 | 2019-03-16 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 175730 | Work Order Description - 175730 - PM | PM | 4 | 383143 | SCHD | PACK-ISOL | 2018-12-17 | 2019-05-13 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 175733 | Work Order Description - 175733 - PSPM | PSPM | 1 | 179515 | SCHD | NORM-OPS | 2018-12-22 | 2019-04-19 | 2019-04-07 | 2019-04-08 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 175734 | Work Order Description - 175734 - PSPM | PSPM | 1 | 527315 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-19 | 2019-04-07 | 2019-04-07 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 175736 | Work Order Description - 175736 - PSPM | PSPM | 1 | 659551 | SCHD | NORM-OPS | 2019-03-22 | 2019-04-19 | 2019-04-18 | 2019-04-18 | 1 | OPERATIONS | OPERATIONS | 7
2019-03-31 | 175738 | Work Order Description - 175738 - PSPM | PSPM | 1 | 450986 | SCHD | NORM-OPS | 2019-03-22 | 2019-04-19 | 2019-04-18 | 2019-04-18 | 1 | OPERATIONS | OPERATIONS | 7
2019-03-31 | 175776 | Work Order Description - 175776 - CM | CM | 1 | 375805 | SCHD | EQUIP-ISOL | 2019-02-13 | 2020-11-17 | 2019-06-02 | 2019-06-02 | 4 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 175777 | Work Order Description - 175777 - BR | BR | 3 | 555571 | SCHD | NORM-OPS | 2018-12-24 | 2019-04-23 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 175786 | Work Order Description - 175786 - BR | BR | 3 | 498377 | SCHD | TPS | 2019-01-25 | 2020-11-17 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175800 | Work Order Description - 175800 - BR | BR | 1 | 237448 | SCHD | NORM-OPS | 2018-11-20 | 2020-11-17 | 2019-05-12 | 2019-05-18 | 4 | INTEGRITY | ELECTRICAL | 90
2019-03-31 | 175801 | Work Order Description - 175801 - CM | CM | 4 | 403920 | WPLAN | NORM-OPS | 2018-11-20 | 2019-11-19 | 2020-01-25 | 2020-02-08 | 3 | INTEGRITY | FABRIC | 100
2019-03-31 | 175804 | Work Order Description - 175804 - BR | BR | 3 | 356852 | WPLAN | TPS | 2018-12-15 | 2020-11-17 | 2019-11-18 | 2019-11-23 | 4 | MAINTENANCE | MECHANICAL | 208
2019-03-31 | 175814 | Work Order Description - 175814 - CM | CM | 4 | 95254 | SCHD | EQUIP-ISOL | 2018-12-24 | 2020-11-17 | 2019-04-20 | 2019-04-21 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 175826 | Work Order Description - 175826 - PM | PM | 4 | 481335 | WSCHD | NORM-OPS | 2018-11-20 | 2019-04-20 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | SAFETY | 3
2019-03-31 | 175828 | Work Order Description - 175828 - PM | PM | 4 | 321175 | WSCHD | PACK-ISOL | 2018-12-04 | 2019-04-20 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 175832 | Work Order Description - 175832 - PM | PM | 3 | 499086 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-07-07 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 175837 | Work Order Description - 175837 - PM | PM | 4 | 403822 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-14 | 2019-03-23 | 2019-03-23 | 2 | MAINTENANCE | SAFETY | 5
2019-03-31 | 175838 | Work Order Description - 175838 - PM | PM | 4 | 403821 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-14 | 2019-03-30 | 2019-03-30 | 2 | OPERATIONS | OPERATIONS | 15
2019-03-31 | 175848 | Work Order Description - 175848 - PM | PM | 4 | 100022 | SCHD | EQUIP-ISOL | 2018-11-20 | 2019-07-07 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 175863 | Work Order Description - 175863 - PM | PM | 4 | 266218 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-20 | 2019-04-02 | 2019-04-02 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 175864 | Work Order Description - 175864 - PSPM | PSPM | 1 | 228455 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-28 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 175865 | Work Order Description - 175865 - PSPM | PSPM | 1 | 451165 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-28 | 2019-04-28 | 2019-04-29 | 1 | MAINTENANCE | ELECTRICAL | 27
2019-03-31 | 175866 | Work Order Description - 175866 - PSPM | PSPM | 1 | 659551 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-20 | 2019-03-27 | 2019-03-27 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 175867 | Work Order Description - 175867 - PSPM | PSPM | 1 | 227941 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-20 | 2019-04-03 | 2019-04-03 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 175868 | Work Order Description - 175868 - PSPM | PSPM | 1 | 527317 | SCHD | NORM-OPS | 2018-11-20 | 2019-04-20 | 2019-04-06 | 2019-04-08 | 1 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 175873 | Work Order Description - 175873 - PM | PM | 2 | 670212 | WPLAN | PACK-ISOL | 2018-11-20 | 2019-05-14 | 2019-04-27 | 2019-05-06 | 2 | MAINTENANCE | MECHANICAL | 140
2019-03-31 | 175964 | Work Order Description - 175964 - CM | CM | 4 | 125850 | SCHD | EQUIP-ISOL | 2018-11-26 | 2019-11-20 | 2019-04-28 | 2019-04-29 | 3 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 175967 | Work Order Description - 175967 - CM | CM | 1 | 446461 | WPLAN | EQUIP-ISOL | 2018-11-24 | 2020-11-18 | 2019-11-09 | 2019-11-09 | 4 | MAINTENANCE | INSTRUMENTS | 42
2019-03-31 | 175975 | Work Order Description - 175975 - CM | CM | 3 | 549247 | SCHD | NORM-OPS | 2018-12-24 | 2020-11-22 | 2019-09-14 | 2019-09-14 | 4 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 175978 | Work Order Description - 175978 - CM | CM | 4 | 378847 | WPLAN | NORM-OPS | 2018-12-06 | 2019-11-20 | 2019-05-21 | 2019-06-11 | 3 | INTEGRITY | FABRIC | 150
2019-03-31 | 175997 | Work Order Description - 175997 - PRJ | PRJ | 3 | 463245 | SCHD | PACK-ISOL | 2018-12-05 | 2019-11-24 | 2019-06-01 | 2019-06-04 | 3 | MAINTENANCE | INSTRUMENTS | 56
2019-03-31 | 176012 | Work Order Description - 176012 - PM | PM | 4 | 51662 | WSCHD | NORM-OPS | 2018-11-21 | 2019-04-21 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 176013 | Work Order Description - 176013 - PM | PM | 4 | 18972 | WSCHD | NORM-OPS | 2018-11-21 | 2019-04-21 | 2021-03-26 | 2021-03-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176014 | Work Order Description - 176014 - PM | PM | 4 | 355546 | WSCHD | NORM-OPS | 2018-11-21 | 2019-04-21 | 2021-03-26 | 2021-03-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176015 | Work Order Description - 176015 - PM | PM | 4 | 18973 | WSCHD | NORM-OPS | 2018-11-21 | 2019-04-21 | 2021-03-26 | 2021-03-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176016 | Work Order Description - 176016 - PM | PM | 4 | 355547 | WSCHD | NORM-OPS | 2018-11-21 | 2019-04-21 | 2021-03-26 | 2021-03-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176017 | Work Order Description - 176017 - PM | PM | 4 | 18985 | WSCHD | NORM-OPS | 2018-11-21 | 2019-04-21 | 2021-03-26 | 2021-03-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176018 | Work Order Description - 176018 - PM | PM | 4 | 355548 | WSCHD | NORM-OPS | 2018-11-21 | 2019-04-21 | 2021-03-26 | 2021-03-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176019 | Work Order Description - 176019 - PM | PM | 4 | 260757 | WSCHD | EQUIP-ISOL | 2018-12-04 | 2019-04-21 | 2019-05-25 | 2019-05-25 | 1 | INTEGRITY | CONSTRUCTION | 17
2019-03-31 | 176020 | Work Order Description - 176020 - PM | PM | 4 | 267676 | WSCHD | NORM-OPS | 2018-11-21 | 2019-04-21 | 2019-04-06 | 2019-04-06 | 2 | OPERATIONS | SAFETY | 2
2019-03-31 | 176021 | Work Order Description - 176021 - PM | PM | 4 | 363762 | WSCHD | NORM-OPS | 2018-12-04 | 2019-04-21 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | MECHANICAL | 65
2019-03-31 | 176023 | Work Order Description - 176023 - PM | PM | 2 | 33427 | WSCHD | PACK-ISOL | 2018-12-04 | 2019-04-21 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 176024 | Work Order Description - 176024 - PM | PM | 4 | 601923 | INPRG | NORM-OPS | 2019-03-30 | 2019-04-21 | 2019-03-30 | 2019-03-30 | 2 | OPERATIONS | OPERATIONS | 54
2019-03-31 | 176025 | Work Order Description - 176025 - PM | PM | 2 | 309647 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-04-21 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 8
2019-03-31 | 176030 | Work Order Description - 176030 - PSPM | PSPM | 1 | 659514 | SCHD | NORM-OPS | 2018-11-21 | 2019-04-21 | 2019-03-31 | 2019-03-31 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176204 | Work Order Description - 176204 - BR | BR | 4 | 178856 | WMATL | EQUIP-ISOL | 2019-03-29 | 2020-11-19 | 2019-05-04 | 2019-05-05 | 4 | MAINTENANCE | INSTRUMENTS | 13
2019-03-31 | 176221 | Work Order Description - 176221 - BR | BR | 3 | 462624 | WPLAN | NORM-OPS | 2018-11-24 | 2019-01-18 | 2019-09-28 | 2019-09-28 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176222 | Work Order Description - 176222 - BR | BR | 3 | 29081 | WPLAN | NORM-OPS | 2018-11-24 | 2019-06-26 | 2019-09-28 | 2019-09-28 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176226 | Work Order Description - 176226 - PSCM | PSCM | 1 | 679184 | WSCHD | EQUIP-ISOL | 2018-11-26 | 2019-05-23 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 176227 | Work Order Description - 176227 - CM | CM | 4 | 462436 | WPLAN | EQUIP-ISOL | 2018-11-24 | 2020-11-19 | 2020-02-01 | 2020-02-04 | 4 | MAINTENANCE | CONSTRUCTION | 24
2019-03-31 | 176236 | Work Order Description - 176236 - PSPM | PSPM | 1 | 546068 | SCHD | NORM-OPS | 2019-03-26 | 2019-04-22 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | SERVICES | 19
2019-03-31 | 176237 | Work Order Description - 176237 - PSPM | PSPM | 1 | 309463 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-21 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 176238 | Work Order Description - 176238 - PSPM | PSPM | 1 | 59213 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-21 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 176239 | Work Order Description - 176239 - PSPM | PSPM | 1 | 309176 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-21 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 176240 | Work Order Description - 176240 - PSPM | PSPM | 1 | 24943 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-21 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 176241 | Work Order Description - 176241 - PSPM | PSPM | 1 | 309175 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-21 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 176243 | Work Order Description - 176243 - PSPM | PSPM | 1 | 447441 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-22 | 2019-03-16 | 2019-03-16 | 1 | MAINTENANCE | MECHANICAL | 0
2019-03-31 | 176262 | Work Order Description - 176262 - PSPM | PSPM | 1 | 99232 | INPRG | PACK-ISOL | 2019-03-29 | 2019-04-22 | 2019-04-13 | 2019-04-18 | 1 | MAINTENANCE | SERVICES | 33
2019-03-31 | 176323 | Work Order Description - 176323 - BR | BR | 3 | 441064 | WPLAN | EQUIP-ISOL | 2018-11-22 | 2019-10-25 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 176334 | Work Order Description - 176334 - BR | BR | 3 | 185256 | WPLAN | TPS | 2018-11-22 | 2019-09-01 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 176337 | Work Order Description - 176337 - PSCM | PSCM | 1 | 356358 | WSCHD | NORM-OPS | 2018-12-15 | 2019-11-22 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 15
2019-03-31 | 176339 | Work Order Description - 176339 - PRJ | PRJ | 3 | 480137 | SCHD | SYS-ISOL | 2018-11-23 | 2019-04-19 | 2019-04-13 | 2019-04-14 | 4 | ENGINEERING | CONSTRUCTION | 8
2019-03-31 | 176342 | Work Order Description - 176342 - CM | CM | 3 | 249668 | SCHD | NORM-OPS | 2018-11-23 | 2020-11-20 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | FABRIC | 81
2019-03-31 | 176358 | Work Order Description - 176358 - BR | BR | 3 | 555360 | SCHD | NORM-OPS | 2018-12-24 | 2020-12-03 | 2019-12-04 | 2019-12-04 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 176363 | Work Order Description - 176363 - CM | CM | 3 | 215233 | WSCHD | TPS | 2019-02-23 | 2019-05-24 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 176366 | Work Order Description - 176366 - CM | CM | 4 | 215627 | WSCHD | NORM-OPS | 2018-11-23 | 2019-11-23 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 176373 | Work Order Description - 176373 - CM | CM | 1 | 680866 | WPLAN | NORM-OPS | 2018-11-23 | 2019-11-22 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 68
2019-03-31 | 176375 | Work Order Description - 176375 - BR | BR | 4 | 540397 | WRISKQ | NORM-OPS | 2019-01-14 | 2020-11-20 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 176381 | Work Order Description - 176381 - CM | CM | 3 | 248328 | WSCHD | TPS | 2019-02-23 | 2019-05-24 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 176384 | Work Order Description - 176384 - CM | CM | 2 | 383838 | SCHD | EQUIP-ISOL | 2018-11-26 | 2020-11-21 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 176385 | Work Order Description - 176385 - PSPM | PSPM | 1 | 457538 | WSCHD | NORM-OPS | 2018-11-23 | 2019-04-23 | 2019-04-06 | 2019-04-06 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 176386 | Work Order Description - 176386 - PM | PM | 4 | 356945 | WSCHD | NORM-OPS | 2018-11-23 | 2019-04-23 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176387 | Work Order Description - 176387 - PM | PM | 2 | 321115 | SCHD | NORM-OPS | 2019-03-20 | 2019-04-23 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 176388 | Work Order Description - 176388 - PSPM | PSPM | 1 | 681802 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-04-23 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 50
2019-03-31 | 176393 | Work Order Description - 176393 - PM | PM | 4 | 545299 | SCHD | PACK-ISOL | 2018-12-10 | 2019-04-23 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 176394 | Work Order Description - 176394 - PM | PM | 4 | 310066 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-23 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176395 | Work Order Description - 176395 - PM | PM | 4 | 325181 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-23 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176396 | Work Order Description - 176396 - PM | PM | 4 | 188985 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-23 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176397 | Work Order Description - 176397 - PM | PM | 4 | 498833 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-23 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176398 | Work Order Description - 176398 - PM | PM | 4 | 325182 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-23 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176409 | Work Order Description - 176409 - PM | PM | 4 | 436494 | SCHD | PACK-ISOL | 2019-03-22 | 2020-03-18 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 176476 | Work Order Description - 176476 - BR | BR | 3 | 533483 | WPLAN | PACK-ISOL | 2018-12-04 | 2019-03-17 | 2019-11-16 | 2019-11-16 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 176485 | Work Order Description - 176485 - CM | CM | 3 | 246535 | WSCHD | TPS | 2019-02-23 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 176487 | Work Order Description - 176487 - CM | CM | 3 | 520350 | WSCHD | TPS | 2019-02-23 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 176491 | Work Order Description - 176491 - CM | CM | 3 | 491908 | WSCHD | TPS | 2019-02-23 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | CONSTRUCTION | 2
2019-03-31 | 176493 | Work Order Description - 176493 - CM | CM | 3 | 215226 | WSCHD | TPS | 2019-02-23 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | CONSTRUCTION | 2
2019-03-31 | 176495 | Work Order Description - 176495 - CM | CM | 3 | 499480 | WSCHD | TPS | 2019-02-23 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | CONSTRUCTION | 0
2019-03-31 | 176496 | Work Order Description - 176496 - CM | CM | 3 | 226487 | WSCHD | TPS | 2019-02-23 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | CONSTRUCTION | 0
2019-03-31 | 176505 | Work Order Description - 176505 - CM | CM | 3 | 249290 | WPLAN | NORM-OPS | 2018-11-24 | 2019-05-25 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 176508 | Work Order Description - 176508 - CM | CM | 3 | 215224 | WSCHD | TPS | 2019-02-23 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | CONSTRUCTION | 2
2019-03-31 | 176509 | Work Order Description - 176509 - PSCM | PSCM | 1 | 541275 | WSCHD | EQUIP-ISOL | 2018-11-25 | 2019-11-23 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 15
2019-03-31 | 176513 | Work Order Description - 176513 - CM | CM | 3 | 520355 | WSCHD | TPS | 2019-02-23 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | CONSTRUCTION | 2
2019-03-31 | 176524 | Work Order Description - 176524 - CM | CM | 3 | 401257 | SCHD | SUBSYS-ISOL | 2018-12-24 | 2020-11-22 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 176527 | Work Order Description - 176527 - PSPM | PSPM | 1 | 356352 | SCHD | EQUIP-ISOL | 2019-03-20 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176528 | Work Order Description - 176528 - PSPM | PSPM | 1 | 356352 | SCHD | EQUIP-ISOL | 2019-03-20 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176529 | Work Order Description - 176529 - PSPM | PSPM | 1 | 356352 | SCHD | EQUIP-ISOL | 2019-03-20 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 176530 | Work Order Description - 176530 - PSPM | PSPM | 1 | 356352 | SCHD | EQUIP-ISOL | 2019-03-20 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 176533 | Work Order Description - 176533 - PSPM | PSPM | 1 | 545260 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176534 | Work Order Description - 176534 - PSPM | PSPM | 1 | 545260 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176535 | Work Order Description - 176535 - PM | PM | 4 | 54308 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 176536 | Work Order Description - 176536 - PM | PM | 3 | 360534 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-07-11 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176537 | Work Order Description - 176537 - PSPM | PSPM | 1 | 261983 | SCHD | PACK-ISOL | 2019-03-26 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176538 | Work Order Description - 176538 - PSPM | PSPM | 1 | 409656 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176539 | Work Order Description - 176539 - PSPM | PSPM | 1 | 360537 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176540 | Work Order Description - 176540 - PSPM | PSPM | 1 | 409658 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176541 | Work Order Description - 176541 - PSPM | PSPM | 1 | 360538 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176542 | Work Order Description - 176542 - PSPM | PSPM | 1 | 409685 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176543 | Work Order Description - 176543 - PSPM | PSPM | 1 | 54486 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176544 | Work Order Description - 176544 - PSPM | PSPM | 1 | 360544 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176545 | Work Order Description - 176545 - PSPM | PSPM | 1 | 53259 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176546 | Work Order Description - 176546 - PM | PM | 3 | 54948 | WSCHD | EQUIP-ISOL | 2018-11-24 | 2019-09-21 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 176547 | Work Order Description - 176547 - PM | PM | 3 | 53603 | WSCHD | EQUIP-ISOL | 2018-11-24 | 2019-09-21 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 176548 | Work Order Description - 176548 - PSPM | PSPM | 1 | 54951 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 176549 | Work Order Description - 176549 - PM | PM | 4 | 357410 | WSCHD | EQUIP-ISOL | 2018-11-24 | 2019-09-21 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 176550 | Work Order Description - 176550 - PM | PM | 4 | 410113 | WSCHD | EQUIP-ISOL | 2018-11-24 | 2019-09-21 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 176551 | Work Order Description - 176551 - PSPM | PSPM | 1 | 410111 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 176552 | Work Order Description - 176552 - PM | PM | 3 | 652246 | SCHD | PACK-ISOL | 2019-03-05 | 2019-07-11 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 176557 | Work Order Description - 176557 - PM | PM | 4 | 212354 | WSCHD | NORM-OPS | 2018-11-24 | 2019-04-24 | 2019-04-20 | 2019-04-20 | 2 | INTEGRITY | INSPECTION | 2
2019-03-31 | 176558 | Work Order Description - 176558 - PM | PM | 3 | 360305 | SCHD | PACK-ISOL | 2019-03-29 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 176561 | Work Order Description - 176561 - PSPM | PSPM | 1 | 463677 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-24 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 176562 | Work Order Description - 176562 - PSPM | PSPM | 1 | 555233 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | OPERATIONS | OPERATIONS | 4
2019-03-31 | 176563 | Work Order Description - 176563 - PM | PM | 4 | 188853 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-18 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176564 | Work Order Description - 176564 - PM | PM | 4 | 324807 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-18 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176565 | Work Order Description - 176565 - PM | PM | 4 | 498463 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-18 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176566 | Work Order Description - 176566 - PM | PM | 4 | 309711 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-18 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176567 | Work Order Description - 176567 - PM | PM | 4 | 324808 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-18 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176568 | Work Order Description - 176568 - PM | PM | 4 | 188853 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-18 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176569 | Work Order Description - 176569 - PM | PM | 4 | 324807 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-18 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176570 | Work Order Description - 176570 - PM | PM | 4 | 498463 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-18 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176571 | Work Order Description - 176571 - PM | PM | 4 | 309711 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-18 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176572 | Work Order Description - 176572 - PM | PM | 4 | 324808 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-18 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176573 | Work Order Description - 176573 - PM | PM | 4 | 188853 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-18 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176574 | Work Order Description - 176574 - PM | PM | 4 | 324807 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-18 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176575 | Work Order Description - 176575 - PM | PM | 4 | 498463 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-18 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176576 | Work Order Description - 176576 - PM | PM | 4 | 309711 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-18 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176577 | Work Order Description - 176577 - PM | PM | 4 | 324808 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-18 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176578 | Work Order Description - 176578 - PSPM | PSPM | 1 | 447441 | SCHD | PACK-ISOL | 2018-12-05 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | MECHANICAL | 88
2019-03-31 | 176580 | Work Order Description - 176580 - PSPM | PSPM | 1 | 176661 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-04-24 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 176584 | Work Order Description - 176584 - PSPM | PSPM | 1 | 663475 | SCHD | PACK-ISOL | 2019-03-29 | 2019-12-02 | 2019-11-16 | 2019-11-16 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 176585 | Work Order Description - 176585 - PM | PM | 4 | 97916 | SCHD | EQUIP-ISOL | 2018-11-26 | 2019-04-24 | 2019-03-31 | 2019-03-31 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 176587 | Work Order Description - 176587 - PSPM | PSPM | 1 | 227935 | SCHD | NORM-OPS | 2018-11-26 | 2019-04-24 | 2019-04-04 | 2019-04-04 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 176595 | Work Order Description - 176595 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2018-11-26 | 2019-04-24 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 176597 | Work Order Description - 176597 - PM | PM | 4 | 383013 | SCHD | EQUIP-ISOL | 2018-11-26 | 2019-05-18 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176684 | Work Order Description - 176684 - CM | CM | 1 | 378820 | WPLAN | NORM-OPS | 2018-11-26 | 2019-11-26 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | SERVICES | 6
2019-03-31 | 176703 | Work Order Description - 176703 - BR | BR | 4 | 227957 | SCHD | NORM-OPS | 2018-11-26 | 2020-11-22 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 176724 | Work Order Description - 176724 - PSPM | PSPM | 1 | 632581 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-25 | 2019-04-06 | 2019-04-06 | 1 | OPERATIONS | SAFETY | 5
2019-03-31 | 176725 | Work Order Description - 176725 - PM | PM | 4 | 489981 | SCHD | PACK-ISOL | 2018-12-05 | 2019-09-04 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 176726 | Work Order Description - 176726 - PM | PM | 4 | 489981 | SCHD | PACK-ISOL | 2018-12-05 | 2019-09-04 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 176733 | Work Order Description - 176733 - PM | PM | 4 | 393235 | WPLAN | EQUIP-ISOL | 2018-11-25 | 2019-04-25 | 2019-04-29 | 2019-04-29 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 176734 | Work Order Description - 176734 - PM | PM | 4 | 93262 | WPLAN | EQUIP-ISOL | 2018-11-25 | 2019-04-25 | 2019-04-29 | 2019-04-29 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 176735 | Work Order Description - 176735 - PM | PM | 4 | 89876 | WPLAN | EQUIP-ISOL | 2018-11-25 | 2019-04-25 | 2019-04-29 | 2019-04-29 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 176736 | Work Order Description - 176736 - PM | PM | 4 | 396514 | WPLAN | EQUIP-ISOL | 2018-11-25 | 2019-04-25 | 2019-04-21 | 2019-04-21 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 176857 | Work Order Description - 176857 - CM | CM | 3 | 520397 | SCHD | TPS | 2019-02-15 | 2019-05-27 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | CONSTRUCTION | 2
2019-03-31 | 176858 | Work Order Description - 176858 - CM | CM | 3 | 248368 | SCHD | TPS | 2019-02-15 | 2019-05-27 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | CONSTRUCTION | 2
2019-03-31 | 176861 | Work Order Description - 176861 - CM | CM | 3 | 491912 | SCHD | TPS | 2019-02-15 | 2019-05-27 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 176862 | Work Order Description - 176862 - CM | CM | 3 | 491913 | WSCHD | TPS | 2019-02-23 | 2019-05-27 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | CONSTRUCTION | 12
2019-03-31 | 176866 | Work Order Description - 176866 - CM | CM | 3 | 35224 | WPLAN | EQUIP-ISOL | 2018-11-27 | 2019-10-07 | 2019-05-04 | 2019-05-05 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 176868 | Work Order Description - 176868 - CM | CM | 3 | 327459 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-27 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | CONSTRUCTION | 6
2019-03-31 | 176874 | Work Order Description - 176874 - CM | CM | 3 | 520348 | SCHD | TPS | 2019-01-17 | 2019-05-27 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 176875 | Work Order Description - 176875 - CM | CM | 3 | 215214 | SCHD | TPS | 2019-01-17 | 2019-05-27 | 2019-04-27 | 2019-04-28 | 3 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 176881 | Work Order Description - 176881 - PSCM | PSCM | 1 | 356364 | SCHD | EQUIP-ISOL | 2018-11-27 | 2020-11-23 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 176894 | Work Order Description - 176894 - BR | BR | 1 | 403920 | WPLAN | NORM-OPS | 2018-11-27 | 2019-05-27 | 2019-06-01 | 2019-06-01 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 176904 | Work Order Description - 176904 - PM | PM | 4 | 540665 | WSCHD | EQUIP-ISOL | 2018-12-04 | 2019-05-20 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 176905 | Work Order Description - 176905 - PM | PM | 4 | 595973 | WSCHD | EQUIP-ISOL | 2018-11-26 | 2019-04-26 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 176906 | Work Order Description - 176906 - PM | PM | 4 | 261948 | WSCHD | EQUIP-ISOL | 2018-11-26 | 2019-04-26 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 176907 | Work Order Description - 176907 - PM | PM | 4 | 359218 | WSCHD | NORM-OPS | 2018-11-26 | 2019-04-26 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 176910 | Work Order Description - 176910 - PM | PM | 4 | 321174 | WSCHD | PACK-ISOL | 2018-12-04 | 2019-04-26 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | MECHANICAL | 10
2019-03-31 | 176913 | Work Order Description - 176913 - PSPM | PSPM | 1 | 462436 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-26 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 176919 | Work Order Description - 176919 - PM | PM | 4 | 320150 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-26 | 2019-03-23 | 2019-03-23 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 176921 | Work Order Description - 176921 - PM | PM | 4 | 527339 | SCHD | NORM-OPS | 2018-11-26 | 2019-04-26 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 176989 | Work Order Description - 176989 - BR | BR | 3 | 411162 | SCHD | TPS | 2018-12-05 | 2019-02-09 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 176993 | Work Order Description - 176993 - BR | BR | 2 | 541233 | WPLAN | NORM-OPS | 2018-12-02 | 2019-11-26 | 2019-05-27 | 2019-05-27 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 176994 | Work Order Description - 176994 - BR | BR | 3 | 320085 | WPLAN | EQUIP-ISOL | 2018-11-29 | 2019-07-15 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | MECHANICAL | 1
2019-03-31 | 176995 | Work Order Description - 176995 - BR | BR | 1 | 320085 | SCHD | EQUIP-ISOL | 2019-01-25 | 2020-11-27 | 2019-11-28 | 2019-11-28 | 4 | INTEGRITY | MECHANICAL | 14
2019-03-31 | 176996 | Work Order Description - 176996 - BR | BR | 1 | 320085 | WPLAN | EQUIP-ISOL | 2018-11-29 | 2020-11-27 | 2019-11-28 | 2019-11-28 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 177005 | Work Order Description - 177005 - PRJ | PRJ | 4 | 451268 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-20 | 2019-04-21 | 2019-04-28 | 4 | ENGINEERING | SERVICES | 150
2019-03-31 | 177018 | Work Order Description - 177018 - CM | CM | 1 | 237441 | WPLAN | NORM-OPS | 2018-11-26 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 177021 | Work Order Description - 177021 - BR | BR | 1 | 322641 | WPLAN | TPS | 2018-11-27 | 2019-11-27 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | MECHANICAL | 96
2019-03-31 | 177029 | Work Order Description - 177029 - BR | BR | 3 | 33971 | WPLAN | TPS | 2018-11-27 | 2019-11-26 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | MECHANICAL | 78
2019-03-31 | 177057 | Work Order Description - 177057 - PM | PM | 4 | 546698 | WSCHD | NORM-OPS | 2018-11-27 | 2019-04-27 | 2019-07-20 | 2019-07-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177058 | Work Order Description - 177058 - PM | PM | 4 | 308926 | WSCHD | NORM-OPS | 2018-11-27 | 2019-04-27 | 2019-07-20 | 2019-07-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177060 | Work Order Description - 177060 - PM | PM | 4 | 540739 | WSCHD | TPS | 2018-12-04 | 2019-04-27 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 177061 | Work Order Description - 177061 - PM | PM | 4 | 357106 | SCHD | NORM-OPS | 2019-03-22 | 2019-04-27 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 177062 | Work Order Description - 177062 - PM | PM | 4 | 308005 | SCHD | NORM-OPS | 2019-03-22 | 2019-04-27 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 177063 | Work Order Description - 177063 - PM | PM | 4 | 410635 | SCHD | NORM-OPS | 2019-03-22 | 2019-04-27 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 177064 | Work Order Description - 177064 - PM | PM | 4 | 546053 | SCHD | NORM-OPS | 2019-03-22 | 2019-04-27 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177065 | Work Order Description - 177065 - PM | PM | 4 | 314186 | WSCHD | NORM-OPS | 2018-11-27 | 2019-04-27 | 2020-12-19 | 2020-12-19 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177070 | Work Order Description - 177070 - PSPM | PSPM | 1 | 51662 | WSCHD | EQUIP-ISOL | 2018-11-27 | 2019-04-27 | 2019-12-21 | 2019-12-21 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177071 | Work Order Description - 177071 - PSPM | PSPM | 1 | 51662 | WSCHD | EQUIP-ISOL | 2018-11-27 | 2019-04-27 | 2019-12-21 | 2019-12-21 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177073 | Work Order Description - 177073 - PM | PM | 4 | 480105 | WSCHD | EQUIP-ISOL | 2018-11-27 | 2019-08-19 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | ELECTRICAL | 21
2019-03-31 | 177074 | Work Order Description - 177074 - PM | PM | 4 | 261982 | WSCHD | EQUIP-ISOL | 2018-11-27 | 2019-04-27 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 177075 | Work Order Description - 177075 - PM | PM | 3 | 360533 | WSCHD | EQUIP-ISOL | 2018-11-27 | 2019-07-14 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177076 | Work Order Description - 177076 - PM | PM | 3 | 360355 | WSCHD | EQUIP-ISOL | 2018-11-27 | 2019-04-27 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177078 | Work Order Description - 177078 - PM | PM | 4 | 261308 | WSCHD | EQUIP-ISOL | 2018-12-05 | 2019-04-27 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 177083 | Work Order Description - 177083 - PSPM | PSPM | 1 | 409663 | WSCHD | EQUIP-ISOL | 2018-11-27 | 2019-04-27 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177087 | Work Order Description - 177087 - PM | PM | 4 | 410110 | WSCHD | EQUIP-ISOL | 2018-11-27 | 2019-09-24 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 177088 | Work Order Description - 177088 - PM | PM | 4 | 357414 | WSCHD | EQUIP-ISOL | 2018-11-27 | 2019-09-24 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 177089 | Work Order Description - 177089 - PM | PM | 3 | 652244 | WSCHD | PACK-ISOL | 2018-12-04 | 2019-07-14 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 177090 | Work Order Description - 177090 - PM | PM | 3 | 53288 | WSCHD | EQUIP-ISOL | 2018-11-27 | 2019-07-14 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177091 | Work Order Description - 177091 - PM | PM | 4 | 360541 | WSCHD | EQUIP-ISOL | 2018-11-27 | 2019-07-14 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177092 | Work Order Description - 177092 - PM | PM | 3 | 53614 | WSCHD | EQUIP-ISOL | 2018-11-27 | 2019-08-19 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177093 | Work Order Description - 177093 - PM | PM | 4 | 267676 | WSCHD | NORM-OPS | 2018-11-27 | 2019-04-27 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | SAFETY | 4
2019-03-31 | 177094 | Work Order Description - 177094 - PM | PM | 3 | 360304 | WSCHD | PACK-ISOL | 2018-12-04 | 2019-04-27 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 177095 | Work Order Description - 177095 - PM | PM | 4 | 545259 | WSCHD | EQUIP-ISOL | 2018-11-27 | 2019-07-14 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 177097 | Work Order Description - 177097 - PSPM | PSPM | 1 | 260937 | WSCHD | EQUIP-ISOL | 2018-12-04 | 2019-04-27 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 177099 | Work Order Description - 177099 - PM | PM | 4 | 99579 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-27 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177154 | Work Order Description - 177154 - CM | CM | 1 | 58927 | SCHD | PACK-ISOL | 2018-12-05 | 2019-11-27 | 2019-05-28 | 2019-05-28 | 3 | INTEGRITY | INSTRUMENTS | 3
2019-03-31 | 177165 | Work Order Description - 177165 - BR | BR | 1 | 671142 | WPLAN | SYS-ISOL | 2019-02-28 | 2020-02-28 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | INSTRUMENTS | 82
2019-03-31 | 177169 | Work Order Description - 177169 - BR | BR | 4 | 327469 | WPLAN | SYS-ISOL | 2018-11-28 | 2020-11-25 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 177172 | Work Order Description - 177172 - BR | BR | 4 | 326190 | WPLAN | SYS-ISOL | 2018-11-28 | 2018-12-02 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 177177 | Work Order Description - 177177 - BR | BR | 4 | 595916 | WPLAN | NORM-OPS | 2018-11-28 | 2019-11-28 | 2019-05-06 | 2019-05-07 | 3 | MAINTENANCE | FABRIC | 90
2019-03-31 | 177190 | Work Order Description - 177190 - CM | CM | 2 | 502661 | WMATL | NORM-OPS | 2018-11-30 | 2020-11-25 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177191 | Work Order Description - 177191 - BR | BR | 3 | 540739 | WPLAN | NORM-OPS | 2018-11-28 | 2020-11-25 | 2019-05-09 | 2019-05-10 | 4 | MAINTENANCE | FABRIC | 90
2019-03-31 | 177194 | Work Order Description - 177194 - BR | BR | 3 | 595915 | WPLAN | NORM-OPS | 2018-11-28 | 2020-11-25 | 2019-05-12 | 2019-05-13 | 4 | MAINTENANCE | FABRIC | 90
2019-03-31 | 177197 | Work Order Description - 177197 - CM | CM | 4 | 305411 | WSCHD | SYS-ISOL | 2018-11-30 | 2020-11-26 | 2019-11-27 | 2019-11-27 | 4 | MAINTENANCE | INSTRUMENTS | 9
2019-03-31 | 177205 | Work Order Description - 177205 - PM | PM | 4 | 660951 | WSCHD | NORM-OPS | 2018-11-28 | 2019-04-28 | 2019-04-13 | 2019-04-13 | 3 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 177206 | Work Order Description - 177206 - PM | PM | 2 | 363762 | WSCHD | NORM-OPS | 2018-12-10 | 2019-04-28 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | MECHANICAL | 3.5
2019-03-31 | 177208 | Work Order Description - 177208 - PSPM | PSPM | 1 | 259531 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-28 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177209 | Work Order Description - 177209 - PSPM | PSPM | 1 | 583857 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-28 | 2019-04-13 | 2019-04-13 | 1 | OPERATIONS | SAFETY | 7
2019-03-31 | 177210 | Work Order Description - 177210 - PSPM | PSPM | 1 | 632645 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-28 | 2019-04-13 | 2019-04-13 | 1 | OPERATIONS | SAFETY | 5
2019-03-31 | 177211 | Work Order Description - 177211 - PSPM | PSPM | 1 | 122684 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-28 | 2019-04-20 | 2019-04-20 | 1 | OPERATIONS | SAFETY | 5
2019-03-31 | 177212 | Work Order Description - 177212 - PM | PM | 4 | 122684 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-28 | 2019-04-20 | 2019-04-20 | 3 | OPERATIONS | SAFETY | 2
2019-03-31 | 177213 | Work Order Description - 177213 - PM | PM | 4 | 122684 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-04 | 2019-04-27 | 2019-04-27 | 3 | OPERATIONS | SAFETY | 2
2019-03-31 | 177214 | Work Order Description - 177214 - PM | PM | 4 | 632577 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-04 | 2019-04-20 | 2019-04-20 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 177225 | Work Order Description - 177225 - PSPM | PSPM | 4 | 99232 | SCHD | NORM-OPS | 2018-12-17 | 2019-04-28 | 2019-04-13 | 2019-04-14 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 177226 | Work Order Description - 177226 - PM | PM | 4 | 527749 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-04-28 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 177227 | Work Order Description - 177227 - PM | PM | 4 | 124129 | SCHD | EQUIP-ISOL | 2019-01-24 | 2019-09-07 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 177231 | Work Order Description - 177231 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2018-12-17 | 2019-04-28 | 2019-03-28 | 2019-03-28 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 177340 | Work Order Description - 177340 - PRJ | PRJ | 4 | 555973 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-27 | 2019-04-07 | 2019-04-07 | 4 | ENGINEERING | CONSTRUCTION | 1
2019-03-31 | 177341 | Work Order Description - 177341 - PRJ | PRJ | 3 | 320082 | SCHD | SUBSYS-ISOL | 2018-12-05 | 2020-01-25 | 2019-02-09 | 2019-02-09 | 3 | ENGINEERING | ELECTRICAL | 61
2019-03-31 | 177342 | Work Order Description - 177342 - CM | CM | 4 | 81490 | WMATL | SYS-ISOL | 2019-01-14 | 2019-07-23 | 2019-08-10 | 2019-08-10 | 2 | MAINTENANCE | ELECTRICAL | 24
2019-03-31 | 177365 | Work Order Description - 177365 - PSPM | PSPM | 1 | 675037 | WSCHD | NORM-OPS | 2018-11-29 | 2019-04-29 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 177368 | Work Order Description - 177368 - PM | PM | 4 | 73597 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-04-29 | 2019-05-25 | 2019-05-25 | 3 | INTEGRITY | MECHANICAL | 22
2019-03-31 | 177369 | Work Order Description - 177369 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-29 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177371 | Work Order Description - 177371 - PSPM | PSPM | 1 | 401359 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-04-29 | 2019-03-16 | 2019-03-16 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177374 | Work Order Description - 177374 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-29 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 177375 | Work Order Description - 177375 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-29 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 177380 | Work Order Description - 177380 - PSPM | PSPM | 1 | 396251 | WPLAN | EQUIP-ISOL | 2018-11-29 | 2019-04-29 | 2019-04-07 | 2019-04-07 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 177381 | Work Order Description - 177381 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2018-12-17 | 2019-04-29 | 2019-03-30 | 2019-04-01 | 3 | MAINTENANCE | MEDIC | 12
2019-03-31 | 177414 | Work Order Description - 177414 - BR | BR | 3 | 465926 | SCHD | NORM-OPS | 2018-12-24 | 2020-11-27 | 2019-11-28 | 2019-11-28 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177416 | Work Order Description - 177416 - BR | BR | 3 | 465925 | SCHD | NORM-OPS | 2018-12-24 | 2020-11-28 | 2019-11-29 | 2019-11-29 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177417 | Work Order Description - 177417 - CM | CM | 1 | 155742 | WPLAN | NORM-OPS | 2018-12-05 | 2019-11-29 | 2019-05-30 | 2019-05-30 | 3 | INTEGRITY | CONSTRUCTION | 242
2019-03-31 | 177424 | Work Order Description - 177424 - CM | CM | 1 | 155742 | WPLAN | NORM-OPS | 2018-12-05 | 2019-11-29 | 2019-05-30 | 2019-05-30 | 3 | INTEGRITY | CONSTRUCTION | 28
2019-03-31 | 177426 | Work Order Description - 177426 - CM | CM | 1 | 453190 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-31 | 2019-04-14 | 2019-04-17 | 3 | INTEGRITY | CONSTRUCTION | 58
2019-03-31 | 177434 | Work Order Description - 177434 - CM | CM | 1 | 685304 | WPLAN | PACK-ISOL | 2018-11-30 | 2019-06-01 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | CONSTRUCTION | 91
2019-03-31 | 177441 | Work Order Description - 177441 - CM | CM | 1 | 155742 | WPLAN | NORM-OPS | 2018-12-05 | 2019-11-29 | 2019-05-30 | 2019-05-30 | 3 | INTEGRITY | CONSTRUCTION | 216.5
2019-03-31 | 177459 | Work Order Description - 177459 - PSPM | PSPM | 1 | 314421 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-04-30 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 177460 | Work Order Description - 177460 - PSPM | PSPM | 1 | 321203 | SCHD | NORM-OPS | 2019-03-26 | 2019-04-30 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 177461 | Work Order Description - 177461 - PSPM | PSPM | 1 | 321218 | SCHD | NORM-OPS | 2019-03-26 | 2019-04-30 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 177462 | Work Order Description - 177462 - PSPM | PSPM | 1 | 399406 | SCHD | NORM-OPS | 2019-03-29 | 2019-04-30 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177463 | Work Order Description - 177463 - PM | PM | 2 | 363762 | WSCHD | NORM-OPS | 2018-12-10 | 2019-04-30 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | MECHANICAL | 37.5
2019-03-31 | 177464 | Work Order Description - 177464 - PM | PM | 4 | 653434 | WSCHD | EQUIP-ISOL | 2018-11-30 | 2019-05-24 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 177465 | Work Order Description - 177465 - PM | PM | 4 | 294916 | SCHD | NORM-OPS | 2019-03-26 | 2019-04-30 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 177466 | Work Order Description - 177466 - PM | PM | 4 | 403408 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-04-30 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 177467 | Work Order Description - 177467 - PM | PM | 4 | 324741 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-30 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177468 | Work Order Description - 177468 - PM | PM | 4 | 324741 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-30 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177469 | Work Order Description - 177469 - PM | PM | 4 | 324741 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-30 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177470 | Work Order Description - 177470 - PM | PM | 4 | 188986 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-30 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177471 | Work Order Description - 177471 - PM | PM | 4 | 310067 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-30 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177472 | Work Order Description - 177472 - PM | PM | 4 | 325183 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-30 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177473 | Work Order Description - 177473 - PM | PM | 4 | 325187 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-30 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177474 | Work Order Description - 177474 - PM | PM | 4 | 310068 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-30 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177475 | Work Order Description - 177475 - PSPM | PSPM | 1 | 555234 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-30 | 2019-04-06 | 2019-04-06 | 1 | OPERATIONS | OPERATIONS | 12
2019-03-31 | 177476 | Work Order Description - 177476 - PM | PM | 4 | 324741 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-30 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177477 | Work Order Description - 177477 - PM | PM | 4 | 324741 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-30 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177478 | Work Order Description - 177478 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2018-12-05 | 2019-04-30 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 177479 | Work Order Description - 177479 - PSPM | PSPM | 1 | 255862 | SCHD | PACK-ISOL | 2018-12-05 | 2019-04-30 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 177480 | Work Order Description - 177480 - PSPM | PSPM | 1 | 27343 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-04-30 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 177481 | Work Order Description - 177481 - PSPM | PSPM | 1 | 256013 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-04-30 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 177482 | Work Order Description - 177482 - PSPM | PSPM | 1 | 451794 | SCHD | PACK-ISOL | 2018-12-05 | 2019-04-30 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 177483 | Work Order Description - 177483 - PSPM | PSPM | 1 | 447162 | SCHD | PACK-ISOL | 2018-12-05 | 2019-04-30 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 177484 | Work Order Description - 177484 - PM | PM | 4 | 403408 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-04-30 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 177486 | Work Order Description - 177486 - PM | PM | 4 | 256849 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 177487 | Work Order Description - 177487 - PM | PM | 4 | 183808 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 177488 | Work Order Description - 177488 - PM | PM | 3 | 323726 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-24 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 177490 | Work Order Description - 177490 - PM | PM | 3 | 99450 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-07-17 | 2019-03-31 | 2019-03-31 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177491 | Work Order Description - 177491 - PM | PM | 3 | 445118 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-07-17 | 2019-03-31 | 2019-03-31 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177492 | Work Order Description - 177492 - PM | PM | 3 | 445141 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-07-17 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177493 | Work Order Description - 177493 - PM | PM | 3 | 178966 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-07-17 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177494 | Work Order Description - 177494 - PSPM | PSPM | 1 | 527548 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-04-30 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 177495 | Work Order Description - 177495 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2018-12-17 | 2019-04-30 | 2019-04-01 | 2019-04-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177496 | Work Order Description - 177496 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2018-12-17 | 2019-04-30 | 2019-03-30 | 2019-03-30 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 177497 | Work Order Description - 177497 - PSPM | PSPM | 1 | 449144 | SCHD | PACK-ISOL | 2019-03-06 | 2019-04-30 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 177498 | Work Order Description - 177498 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2018-12-17 | 2019-04-30 | 2019-03-30 | 2019-03-30 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 177566 | Work Order Description - 177566 - CM | CM | 1 | 685304 | WPLAN | PACK-ISOL | 2018-12-01 | 2019-06-01 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | CONSTRUCTION | 91
2019-03-31 | 177580 | Work Order Description - 177580 - BR | BR | 3 | 128561 | SCHD | TPS | 2019-03-06 | 2019-06-14 | 2019-07-13 | 2019-08-03 | 3 | INTEGRITY | MECHANICAL | 204
2019-03-31 | 177584 | Work Order Description - 177584 - CM | CM | 4 | 570144 | WPLAN | NORM-OPS | 2018-12-05 | 2020-11-28 | 2019-11-29 | 2019-11-29 | 4 | INTEGRITY | CONSTRUCTION | 70
2019-03-31 | 177585 | Work Order Description - 177585 - CM | CM | 1 | 685304 | WPLAN | PACK-ISOL | 2018-12-01 | 2019-06-01 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | CONSTRUCTION | 91
2019-03-31 | 177586 | Work Order Description - 177586 - PRJ | PRJ | 4 | 555932 | SCHD | NORM-OPS | 2018-12-13 | 2019-08-15 | 2019-06-08 | 2019-06-08 | 4 | ENGINEERING | DRILLING | 96
2019-03-31 | 177588 | Work Order Description - 177588 - CM | CM | 4 | 155742 | WPLAN | NORM-OPS | 2018-12-05 | 2020-11-28 | 2019-11-29 | 2019-11-29 | 4 | INTEGRITY | FABRIC | 112
2019-03-31 | 177589 | Work Order Description - 177589 - CM | CM | 4 | 273876 | WPLAN | NORM-OPS | 2018-12-01 | 2019-12-01 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | MECHANICAL | 182
2019-03-31 | 177591 | Work Order Description - 177591 - CM | CM | 4 | 651077 | SCHD | NORM-OPS | 2019-02-03 | 2019-06-02 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 177598 | Work Order Description - 177598 - CM | CM | 4 | 570144 | WSCHD | NORM-OPS | 2019-03-30 | 2019-09-20 | 2020-01-31 | 2020-01-31 | 3 | INTEGRITY | FABRIC | 224
2019-03-31 | 177622 | Work Order Description - 177622 - BR | BR | 1 | 126130 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-06-01 | 2019-04-07 | 2019-04-08 | 3 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 177629 | Work Order Description - 177629 - CM | CM | 3 | 189117 | SCHD | SYS-ISOL | 2018-12-24 | 2019-12-04 | 2019-06-04 | 2019-06-04 | 3 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 177633 | Work Order Description - 177633 - PSCM | PSCM | 1 | 360341 | WRISKQ | SYS-ISOL | 2018-12-07 | 2019-03-02 |  |  | 3 | MAINTENANCE | MECHANICAL | 53
2019-03-31 | 177634 | Work Order Description - 177634 - BR | BR | 3 | 446864 | SCHD | EQUIP-ISOL | 2018-12-24 | 2020-11-28 | 2019-11-29 | 2019-11-29 | 4 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 177642 | Work Order Description - 177642 - PM | PM | 2 | 572308 | INPRG | NORM-OPS | 2019-03-31 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 2 | OPERATIONS | OPERATIONS | 1
2019-03-31 | 177643 | Work Order Description - 177643 - PM | PM | 4 | 580762 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 177644 | Work Order Description - 177644 - PM | PM | 4 | 324810 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177645 | Work Order Description - 177645 - PM | PM | 4 | 498465 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177646 | Work Order Description - 177646 - PM | PM | 4 | 309712 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177647 | Work Order Description - 177647 - PM | PM | 4 | 309713 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177648 | Work Order Description - 177648 - PM | PM | 4 | 324809 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177649 | Work Order Description - 177649 - PM | PM | 4 | 324810 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177650 | Work Order Description - 177650 - PM | PM | 4 | 498465 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177651 | Work Order Description - 177651 - PM | PM | 4 | 309712 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177652 | Work Order Description - 177652 - PM | PM | 4 | 309713 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177653 | Work Order Description - 177653 - PM | PM | 4 | 324809 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177654 | Work Order Description - 177654 - PM | PM | 4 | 324810 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177655 | Work Order Description - 177655 - PM | PM | 4 | 498465 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177656 | Work Order Description - 177656 - PM | PM | 4 | 309712 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177657 | Work Order Description - 177657 - PM | PM | 4 | 309713 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177658 | Work Order Description - 177658 - PM | PM | 4 | 324809 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-25 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177659 | Work Order Description - 177659 - PM | PM | 1 | 446516 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-01 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 177660 | Work Order Description - 177660 - PSPM | PSPM | 1 | 29041 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 177661 | Work Order Description - 177661 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 2 | MAINTENANCE | SAFETY | 5.5
2019-03-31 | 177662 | Work Order Description - 177662 - PM | PM | 4 | 228279 | WPLAN | PACK-ISOL | 2018-12-01 | 2019-05-01 | 2019-04-21 | 2019-04-29 | 2 | INTEGRITY | MECHANICAL | 60
2019-03-31 | 177663 | Work Order Description - 177663 - PSPM | PSPM | 1 | 451271 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 177665 | Work Order Description - 177665 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 177666 | Work Order Description - 177666 - PSPM | PSPM | 1 | 669726 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 177667 | Work Order Description - 177667 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-01 | 2019-04-03 | 2019-04-03 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 177668 | Work Order Description - 177668 - PM | PM | 2 | 78301 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 177669 | Work Order Description - 177669 - PM | PM | 2 | 113097 | SCHD | PACK-ISOL | 2019-03-18 | 2019-05-25 | 2019-04-20 | 2019-04-29 | 2 | MAINTENANCE | MECHANICAL | 140
2019-03-31 | 177723 | Work Order Description - 177723 - CM | CM | 2 | 248141 | WPLAN | NORM-OPS | 2018-12-02 | 2020-11-29 | 2019-11-30 | 2019-11-30 | 4 | MAINTENANCE | CONSTRUCTION | 14
2019-03-31 | 177731 | Work Order Description - 177731 - BR | BR | 3 | 438720 | SCHD | EQUIP-ISOL | 2018-12-24 | 2020-11-29 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 177732 | Work Order Description - 177732 - PRJ | PRJ | 2 | 489629 | WPLAN | NORM-OPS | 2018-12-02 | 2019-06-26 | 2019-04-27 | 2019-04-27 | 4 | ENGINEERING | FABRIC | 36
2019-03-31 | 177755 | Work Order Description - 177755 - CM | CM | 3 | 361018 | WPLAN | EQUIP-ISOL | 2018-12-02 | 2020-11-29 | 2019-11-30 | 2019-11-30 | 4 | MAINTENANCE | CONSTRUCTION | 42
2019-03-31 | 177758 | Work Order Description - 177758 - CM | CM | 3 | 409977 | WPLAN | EQUIP-ISOL | 2018-12-02 | 2019-12-01 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | CONSTRUCTION | 42
2019-03-31 | 177767 | Work Order Description - 177767 - BR | BR | 3 | 311294 | WPLAN | NORM-OPS | 2018-12-04 | 2019-12-01 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177781 | Work Order Description - 177781 - PM | PM | 4 | 272070 | WSCHD | NORM-OPS | 2018-12-02 | 2019-06-13 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 177782 | Work Order Description - 177782 - PM | PM | 4 | 672639 | WSCHD | NORM-OPS | 2018-12-02 | 2019-06-13 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 177783 | Work Order Description - 177783 - PM | PM | 4 | 361492 | WSCHD | EQUIP-ISOL | 2018-12-02 | 2019-06-13 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177784 | Work Order Description - 177784 - PM | PM | 4 | 246690 | WSCHD | EQUIP-ISOL | 2018-12-02 | 2019-06-13 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177785 | Work Order Description - 177785 - PM | PM | 4 | 246691 | WSCHD | EQUIP-ISOL | 2018-12-02 | 2019-06-13 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177786 | Work Order Description - 177786 - PM | PM | 4 | 361493 | WSCHD | EQUIP-ISOL | 2018-12-02 | 2019-06-13 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177787 | Work Order Description - 177787 - PM | PM | 4 | 481417 | WSCHD | NORM-OPS | 2018-12-02 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 177788 | Work Order Description - 177788 - PSPM | PSPM | 1 | 273469 | WSCHD | EQUIP-ISOL | 2019-03-28 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 51
2019-03-31 | 177791 | Work Order Description - 177791 - PM | PM | 4 | 666316 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177792 | Work Order Description - 177792 - PM | PM | 4 | 417521 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177797 | Work Order Description - 177797 - PSPM | PSPM | 1 | 273469 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 177798 | Work Order Description - 177798 - PM | PM | 4 | 540667 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177799 | Work Order Description - 177799 - PM | PM | 4 | 678551 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177802 | Work Order Description - 177802 - PM | PM | 2 | 580380 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 177803 | Work Order Description - 177803 - PSPM | PSPM | 1 | 519759 | WSCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-30 | 2019-04-30 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 177804 | Work Order Description - 177804 - PM | PM | 2 | 138001 | WSCHD | NORM-OPS | 2018-12-02 | 2019-06-13 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 177806 | Work Order Description - 177806 - PM | PM | 4 | 469328 | WSCHD | NORM-OPS | 2018-12-02 | 2019-05-02 | 2019-04-27 | 2019-04-27 | 2 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 177807 | Work Order Description - 177807 - PM | PM | 2 | 530958 | WSCHD | NORM-OPS | 2018-12-02 | 2019-05-02 | 2019-04-27 | 2019-04-27 | 2 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 177808 | Work Order Description - 177808 - PSPM | PSPM | 1 | 671548 | WSCHD | PACK-ISOL | 2018-12-07 | 2019-05-02 | 2019-08-31 | 2019-08-31 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177809 | Work Order Description - 177809 - PSPM | PSPM | 1 | 308468 | SCHD | PACK-ISOL | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177812 | Work Order Description - 177812 - PM | PM | 3 | 411162 | WSCHD | TPS | 2018-12-02 | 2019-05-26 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 177814 | Work Order Description - 177814 - PSPM | PSPM | 1 | 441402 | WSCHD | NORM-OPS | 2018-12-02 | 2019-05-02 | 2019-04-20 | 2019-04-20 | 1 | WELLS | WELLS | 3
2019-03-31 | 177815 | Work Order Description - 177815 - PM | PM | 4 | 51474 | SCHD | NORM-OPS | 2019-03-14 | 2019-05-02 | 2019-04-02 | 2019-04-12 | 2 | MAINTENANCE | ELECTRICAL | 60
2019-03-31 | 177816 | Work Order Description - 177816 - PSPM | PSPM | 1 | 595638 | WSCHD | EQUIP-ISOL | 2018-12-02 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 177818 | Work Order Description - 177818 - PM | PM | 3 | 272052 | WSCHD | EQUIP-ISOL | 2018-12-02 | 2019-07-19 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 177819 | Work Order Description - 177819 - PM | PM | 4 | 547429 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 177821 | Work Order Description - 177821 - PSPM | PSPM | 1 | 671548 | WSCHD | NORM-OPS | 2018-12-02 | 2019-05-02 | 2019-10-26 | 2019-10-26 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 177823 | Work Order Description - 177823 - PM | PM | 4 | 295994 | WSCHD | NORM-OPS | 2018-12-02 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 1 | OPERATIONS | MEDIC | 10
2019-03-31 | 177824 | Work Order Description - 177824 - PSPM | PSPM | 1 | 470877 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 177825 | Work Order Description - 177825 - PSPM | PSPM | 1 | 273468 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 177826 | Work Order Description - 177826 - PSPM | PSPM | 1 | 470878 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 177828 | Work Order Description - 177828 - PM | PM | 4 | 457525 | WSCHD | NORM-OPS | 2018-12-02 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | SAFETY | 3
2019-03-31 | 177829 | Work Order Description - 177829 - PSPM | PSPM | 1 | 538631 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 177830 | Work Order Description - 177830 - PSPM | PSPM | 1 | 273470 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 177831 | Work Order Description - 177831 - PSPM | PSPM | 1 | 538632 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 177832 | Work Order Description - 177832 - PSPM | PSPM | 1 | 671828 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 177833 | Work Order Description - 177833 - PM | PM | 4 | 535884 | WSCHD | NORM-OPS | 2018-12-02 | 2019-05-02 | 2019-04-20 | 2019-04-20 | 1 | OPERATIONS | MEDIC | 3
2019-03-31 | 177834 | Work Order Description - 177834 - PM | PM | 4 | 676326 | WSCHD | NORM-OPS | 2018-12-02 | 2019-05-02 | 2019-04-20 | 2019-04-20 | 1 | OPERATIONS | MEDIC | 2
2019-03-31 | 177836 | Work Order Description - 177836 - PSPM | PSPM | 1 | 547275 | WSCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 13
2019-03-31 | 177837 | Work Order Description - 177837 - PSPM | PSPM | 1 | 547276 | WSCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 177838 | Work Order Description - 177838 - PSPM | PSPM | 1 | 519760 | WSCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 177839 | Work Order Description - 177839 - PSPM | PSPM | 1 | 547298 | WSCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 177840 | Work Order Description - 177840 - PSPM | PSPM | 1 | 410324 | WSCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 177841 | Work Order Description - 177841 - PSPM | PSPM | 1 | 361798 | WSCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 177842 | Work Order Description - 177842 - PSPM | PSPM | 1 | 361799 | WSCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 177843 | Work Order Description - 177843 - PSPM | PSPM | 1 | 361803 | WSCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 177844 | Work Order Description - 177844 - PSPM | PSPM | 1 | 547298 | WSCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 177845 | Work Order Description - 177845 - PSPM | PSPM | 1 | 361799 | WSCHD | NORM-OPS | 2018-12-10 | 2019-05-02 | 2019-04-30 | 2019-04-30 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 177847 | Work Order Description - 177847 - PM | PM | 2 | 321199 | WSCHD | PACK-ISOL | 2018-12-10 | 2019-05-02 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 177848 | Work Order Description - 177848 - PM | PM | 4 | 360243 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 177849 | Work Order Description - 177849 - PM | PM | 4 | 307915 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 177850 | Work Order Description - 177850 - PM | PM | 3 | 671601 | WSCHD | EQUIP-ISOL | 2018-12-10 | 2019-05-02 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 177851 | Work Order Description - 177851 - PM | PM | 3 | 308530 | WSCHD | EQUIP-ISOL | 2018-12-10 | 2019-05-02 | 2019-09-07 | 2019-09-07 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 177852 | Work Order Description - 177852 - PSPM | PSPM | 1 | 457527 | SCHD | NORM-OPS | 2019-03-21 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | OPERATIONS | SAFETY | 6
2019-03-31 | 177853 | Work Order Description - 177853 - PSPM | PSPM | 1 | 267870 | SCHD | NORM-OPS | 2019-03-21 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | OPERATIONS | SAFETY | 6
2019-03-31 | 177854 | Work Order Description - 177854 - PSPM | PSPM | 1 | 292659 | SCHD | NORM-OPS | 2019-03-21 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | OPERATIONS | SAFETY | 6
2019-03-31 | 177855 | Work Order Description - 177855 - PM | PM | 4 | 416374 | WSCHD | NORM-OPS | 2018-12-02 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | SAFETY | 3
2019-03-31 | 177856 | Work Order Description - 177856 - PSPM | PSPM | 1 | 546068 | WPLAN | PACK-ISOL | 2018-12-02 | 2019-05-02 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | MECHANICAL | 770
2019-03-31 | 177859 | Work Order Description - 177859 - PM | PM | 4 | 410352 | WSCHD | NORM-OPS | 2018-12-02 | 2019-05-26 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 177860 | Work Order Description - 177860 - PM | PM | 4 | 399771 | WSCHD | EQUIP-ISOL | 2018-12-02 | 2019-05-26 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 11
2019-03-31 | 177861 | Work Order Description - 177861 - PM | PM | 4 | 481408 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-26 | 4 | MAINTENANCE | MEDIC | 25
2019-03-31 | 177862 | Work Order Description - 177862 - PM | PM | 4 | 295994 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-02 | 2019-04-01 | 2019-04-27 | 2 | MAINTENANCE | MEDIC | 20
2019-03-31 | 177863 | Work Order Description - 177863 - PSPM | PSPM | 1 | 552280 | SCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177864 | Work Order Description - 177864 - PSPM | PSPM | 1 | 552280 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 177865 | Work Order Description - 177865 - PSPM | PSPM | 1 | 481607 | SCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-08-31 | 2019-08-31 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 177866 | Work Order Description - 177866 - PSPM | PSPM | 1 | 481607 | SCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-08-31 | 2019-08-31 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177867 | Work Order Description - 177867 - PSPM | PSPM | 1 | 481607 | SCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-08-31 | 2019-08-31 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177868 | Work Order Description - 177868 - PSPM | PSPM | 1 | 481607 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-08-31 | 2019-08-31 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 177869 | Work Order Description - 177869 - PSPM | PSPM | 1 | 481608 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 177870 | Work Order Description - 177870 - PSPM | PSPM | 1 | 183779 | SCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177871 | Work Order Description - 177871 - PSPM | PSPM | 1 | 183779 | SCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 177872 | Work Order Description - 177872 - PSPM | PSPM | 1 | 552280 | SCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 177877 | Work Order Description - 177877 - PM | PM | 4 | 259169 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 177881 | Work Order Description - 177881 - PSPM | PSPM | 1 | 479264 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 1 | OPERATIONS | OPERATIONS | 16
2019-03-31 | 177882 | Work Order Description - 177882 - PM | PM | 4 | 29137 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 177883 | Work Order Description - 177883 - PSPM | PSPM | 1 | 29137 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 177884 | Work Order Description - 177884 - PM | PM | 2 | 29721 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 177885 | Work Order Description - 177885 - PSPM | PSPM | 1 | 189054 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 1 | OPERATIONS | OPERATIONS | 0
2019-03-31 | 177886 | Work Order Description - 177886 - PSPM | PSPM | 1 | 325633 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 177887 | Work Order Description - 177887 - PSPM | PSPM | 1 | 81212 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 177888 | Work Order Description - 177888 - PM | PM | 4 | 479286 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | SAFETY | 3
2019-03-31 | 177889 | Work Order Description - 177889 - PM | PM | 4 | 479287 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-04-20 | 2019-04-20 | 3 | OPERATIONS | SAFETY | 4
2019-03-31 | 177890 | Work Order Description - 177890 - PM | PM | 4 | 501106 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-08 | 2019-04-13 | 2019-04-13 | 3 | OPERATIONS | SAFETY | 2
2019-03-31 | 177891 | Work Order Description - 177891 - PSPM | PSPM | 1 | 401613 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177892 | Work Order Description - 177892 - PSPM | PSPM | 1 | 409192 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 177893 | Work Order Description - 177893 - PSPM | PSPM | 1 | 30523 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177894 | Work Order Description - 177894 - PSPM | PSPM | 1 | 401608 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177895 | Work Order Description - 177895 - PSPM | PSPM | 1 | 401609 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177896 | Work Order Description - 177896 - PSPM | PSPM | 1 | 401610 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177897 | Work Order Description - 177897 - PSPM | PSPM | 1 | 409190 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177898 | Work Order Description - 177898 - PSPM | PSPM | 1 | 303990 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177899 | Work Order Description - 177899 - PSPM | PSPM | 1 | 29669 | SCHD | SUBSYS-ISOL | 2018-12-05 | 2019-05-02 | 2019-03-16 | 2019-03-16 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177900 | Work Order Description - 177900 - PSPM | PSPM | 1 | 323861 | SCHD | SUBSYS-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177901 | Work Order Description - 177901 - PSPM | PSPM | 1 | 263334 | SCHD | SUBSYS-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 177906 | Work Order Description - 177906 - PSPM | PSPM | 1 | 472612 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | SAFETY | 10
2019-03-31 | 177907 | Work Order Description - 177907 - PSPM | PSPM | 4 | 383657 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 177908 | Work Order Description - 177908 - PSPM | PSPM | 1 | 447441 | SCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 50
2019-03-31 | 177909 | Work Order Description - 177909 - PSPM | PSPM | 1 | 447441 | SCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 60
2019-03-31 | 177913 | Work Order Description - 177913 - PM | PM | 4 | 445685 | SCHD | PACK-ISOL | 2018-12-05 | 2019-05-17 | 2019-12-07 | 2019-12-07 | 4 | MAINTENANCE | MECHANICAL | 56
2019-03-31 | 177914 | Work Order Description - 177914 - PM | PM | 4 | 450481 | SCHD | PACK-ISOL | 2018-12-05 | 2019-05-17 | 2019-12-07 | 2019-12-07 | 4 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 177917 | Work Order Description - 177917 - PM | PM | 4 | 450520 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 177918 | Work Order Description - 177918 - PSPM | PSPM | 1 | 551282 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 177919 | Work Order Description - 177919 - PSPM | PSPM | 1 | 255838 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 177920 | Work Order Description - 177920 - PM | PM | 4 | 552015 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 177921 | Work Order Description - 177921 - PM | PM | 4 | 216454 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-26 | 2019-03-30 | 2019-03-30 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 177922 | Work Order Description - 177922 - PM | PM | 4 | 479476 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-26 | 2019-03-30 | 2019-03-30 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 177923 | Work Order Description - 177923 - PM | PM | 4 | 316567 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-26 | 2019-04-06 | 2019-04-06 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 177924 | Work Order Description - 177924 - PM | PM | 4 | 243671 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-26 | 2019-04-06 | 2019-04-06 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 177925 | Work Order Description - 177925 - PM | PM | 4 | 216540 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-26 | 2019-03-30 | 2019-03-30 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 177926 | Work Order Description - 177926 - PM | PM | 4 | 316374 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-26 | 2019-03-30 | 2019-03-30 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 177927 | Work Order Description - 177927 - PM | PM | 4 | 243162 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 177928 | Work Order Description - 177928 - PM | PM | 4 | 243211 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-26 | 2019-03-30 | 2019-03-30 | 2 | DRILLING | DRILLING | 3
2019-03-31 | 177929 | Work Order Description - 177929 - PM | PM | 4 | 502253 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-26 | 2019-03-30 | 2019-03-30 | 2 | DRILLING | DRILLING | 3
2019-03-31 | 177930 | Work Order Description - 177930 - PM | PM | 4 | 216509 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 177931 | Work Order Description - 177931 - PM | PM | 4 | 482308 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 2 | DRILLING | DRILLING | 28
2019-03-31 | 177932 | Work Order Description - 177932 - PM | PM | 4 | 316288 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 2 | DRILLING | DRILLING | 48
2019-03-31 | 177933 | Work Order Description - 177933 - PM | PM | 2 | 552280 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 2 | DRILLING | DRILLING | 18
2019-03-31 | 177934 | Work Order Description - 177934 - PM | PM | 4 | 320540 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 2 | DRILLING | DRILLING | 9
2019-03-31 | 177935 | Work Order Description - 177935 - PM | PM | 2 | 502749 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 177936 | Work Order Description - 177936 - PSPM | PSPM | 1 | 259478 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177937 | Work Order Description - 177937 - PSPM | PSPM | 1 | 260185 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 177938 | Work Order Description - 177938 - PSPM | PSPM | 1 | 555589 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 177939 | Work Order Description - 177939 - PSPM | PSPM | 1 | 555588 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 177940 | Work Order Description - 177940 - PSPM | PSPM | 1 | 265558 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177941 | Work Order Description - 177941 - PSPM | PSPM | 1 | 533449 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177942 | Work Order Description - 177942 - PSPM | PSPM | 1 | 253464 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177943 | Work Order Description - 177943 - PM | PM | 4 | 263395 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 177944 | Work Order Description - 177944 - PM | PM | 4 | 556260 | INPRG | NORM-OPS | 2019-03-30 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 177945 | Work Order Description - 177945 - PSPM | PSPM | 1 | 477476 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177946 | Work Order Description - 177946 - PSPM | PSPM | 1 | 25748 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 177947 | Work Order Description - 177947 - PSPM | PSPM | 1 | 539655 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 177948 | Work Order Description - 177948 - PSPM | PSPM | 1 | 253538 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177949 | Work Order Description - 177949 - PSPM | PSPM | 1 | 539654 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 177950 | Work Order Description - 177950 - PSPM | PSPM | 1 | 539608 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 177951 | Work Order Description - 177951 - PM | PM | 2 | 216011 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 177952 | Work Order Description - 177952 - PSPM | PSPM | 1 | 477468 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 50
2019-03-31 | 177953 | Work Order Description - 177953 - PSPM | PSPM | 1 | 401159 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-08-03 | 2019-08-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 177954 | Work Order Description - 177954 - PM | PM | 4 | 401412 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-07-19 | 2019-08-03 | 2019-08-03 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 177957 | Work Order Description - 177957 - PM | PM | 2 | 95306 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-06-13 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 177958 | Work Order Description - 177958 - PM | PM | 4 | 320026 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 177959 | Work Order Description - 177959 - PSPM | PSPM | 1 | 176659 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 177960 | Work Order Description - 177960 - PM | PM | 4 | 216158 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 177961 | Work Order Description - 177961 - PM | PM | 4 | 568873 | SCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 177962 | Work Order Description - 177962 - PM | PM | 4 | 81493 | SCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 177964 | Work Order Description - 177964 - PM | PM | 4 | 312489 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 177965 | Work Order Description - 177965 - PM | PM | 4 | 99564 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 50
2019-03-31 | 177966 | Work Order Description - 177966 - PM | PM | 4 | 95502 | SCHD | PACK-ISOL | 2018-12-05 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 177967 | Work Order Description - 177967 - PM | PM | 2 | 189148 | SCHD | EQUIP-ISOL | 2018-12-05 | 2019-06-13 | 2019-04-01 | 2019-04-01 | 3 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 177968 | Work Order Description - 177968 - PM | PM | 4 | 99579 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-26 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 22
2019-03-31 | 177969 | Work Order Description - 177969 - PM | PM | 4 | 481647 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 177970 | Work Order Description - 177970 - PM | PM | 4 | 555301 | INPRG | NORM-OPS | 2019-03-30 | 2019-05-02 | 2019-03-30 | 2019-03-30 | 4 | MAINTENANCE | MEDIC | 21
2019-03-31 | 177995 | Work Order Description - 177995 - PSPM | PSPM | 1 | 127844 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-03 | 2019-04-03 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 177996 | Work Order Description - 177996 - PM | PM | 4 | 80349 | SCHD | PACK-ISOL | 2018-12-17 | 2019-05-26 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 177997 | Work Order Description - 177997 - PM | PM | 4 | 450947 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-05-28 | 2019-05-28 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 177999 | Work Order Description - 177999 - PSPM | PSPM | 1 | 450992 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | SAFETY | 4
2019-03-31 | 178000 | Work Order Description - 178000 - PM | PM | 4 | 528193 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-01 | 2019-04-04 | 1 | INTEGRITY | INSPECTION | 34
2019-03-31 | 178004 | Work Order Description - 178004 - PSPM | PSPM | 1 | 92712 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 178006 | Work Order Description - 178006 - PSPM | PSPM | 1 | 396754 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 178008 | Work Order Description - 178008 - PSPM | PSPM | 1 | 99232 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | SERVICES | 4
2019-03-31 | 178009 | Work Order Description - 178009 - PSPM | PSPM | 1 | 99434 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | SERVICES | 4
2019-03-31 | 178010 | Work Order Description - 178010 - PSPM | PSPM | 1 | 392310 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-24 | 2019-04-24 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 178011 | Work Order Description - 178011 - PSPM | PSPM | 1 | 227869 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-05 | 2019-04-05 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 178012 | Work Order Description - 178012 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 178013 | Work Order Description - 178013 - PSPM | PSPM | 1 | 127636 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 178014 | Work Order Description - 178014 - PSPM | PSPM | 1 | 450947 | SCHD | PACK-ISOL | 2019-03-06 | 2019-05-02 | 2019-04-28 | 2019-05-03 | 1 | MAINTENANCE | ELECTRICAL | 108
2019-03-31 | 178016 | Work Order Description - 178016 - PM | PM | 4 | 528189 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 178017 | Work Order Description - 178017 - PSPM | PSPM | 1 | 527746 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-28 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 178018 | Work Order Description - 178018 - PM | PM | 4 | 451612 | WPLAN | PACK-ISOL | 2018-12-02 | 2019-05-26 | 2019-04-22 | 2019-04-23 | 2 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 178019 | Work Order Description - 178019 - PM | PM | 4 | 376682 | WPLAN | PACK-ISOL | 2018-12-02 | 2019-05-26 | 2019-04-22 | 2019-04-24 | 2 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 178021 | Work Order Description - 178021 - PM | PM | 4 | 78580 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-07-19 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178022 | Work Order Description - 178022 - PM | PM | 4 | 383244 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-07-19 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178023 | Work Order Description - 178023 - PM | PM | 4 | 441132 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-07-19 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178024 | Work Order Description - 178024 - PM | PM | 4 | 100293 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-07-19 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178025 | Work Order Description - 178025 - PM | PM | 4 | 441233 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-07-19 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178026 | Work Order Description - 178026 - PM | PM | 4 | 383245 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-07-19 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178027 | Work Order Description - 178027 - PM | PM | 4 | 383246 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-07-19 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178028 | Work Order Description - 178028 - PM | PM | 4 | 100294 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-07-19 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178029 | Work Order Description - 178029 - PM | PM | 4 | 441328 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-05-26 | 2019-04-01 | 2019-04-01 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 178030 | Work Order Description - 178030 - PSPM | PSPM | 1 | 227791 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-03-17 | 2019-03-17 | 1 | MAINTENANCE | MECHANICAL | 0
2019-03-31 | 178031 | Work Order Description - 178031 - PSPM | PSPM | 1 | 659338 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-08 | 2019-04-08 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 178032 | Work Order Description - 178032 - PSPM | PSPM | 1 | 659339 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 178033 | Work Order Description - 178033 - PSPM | PSPM | 1 | 450926 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 178034 | Work Order Description - 178034 - PM | PM | 4 | 227826 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-08 | 2019-04-22 | 2 | MAINTENANCE | ELECTRICAL | 100
2019-03-31 | 178035 | Work Order Description - 178035 - PM | PM | 3 | 266661 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-02 | 2019-04-15 | 2019-04-17 | 2 | MAINTENANCE | MECHANICAL | 17
2019-03-31 | 178036 | Work Order Description - 178036 - PM | PM | 4 | 665064 | WPLAN | EQUIP-ISOL | 2018-12-02 | 2019-05-02 | 2019-04-14 | 2019-04-14 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 178037 | Work Order Description - 178037 - PM | PM | 4 | 396793 | WPLAN | EQUIP-ISOL | 2018-12-02 | 2019-05-02 | 2019-04-14 | 2019-04-14 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 178038 | Work Order Description - 178038 - PM | PM | 4 | 393236 | WPLAN | EQUIP-ISOL | 2018-12-02 | 2019-05-02 | 2019-04-14 | 2019-04-14 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 178039 | Work Order Description - 178039 - PM | PM | 4 | 396794 | WPLAN | EQUIP-ISOL | 2018-12-02 | 2019-05-02 | 2019-04-14 | 2019-04-14 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 178041 | Work Order Description - 178041 - PSPM | PSPM | 1 | 450986 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 178042 | Work Order Description - 178042 - PM | PM | 4 | 78493 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-05-26 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178043 | Work Order Description - 178043 - PM | PM | 4 | 100018 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-05-26 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 178044 | Work Order Description - 178044 - PM | PM | 4 | 80472 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 178045 | Work Order Description - 178045 - PM | PM | 4 | 266593 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-02 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 178709 | Work Order Description - 178709 - BR | BR | 1 | 51014 | WSCHD | EQUIP-ISOL | 2018-12-05 | 2019-08-09 | 2019-07-27 | 2019-07-27 | 2 | MAINTENANCE | INSTRUMENTS | 120
2019-03-31 | 178736 | Work Order Description - 178736 - PSPM | PSPM | 1 | 657129 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-05-03 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 178737 | Work Order Description - 178737 - PSPM | PSPM | 1 | 574925 | WSCHD | NORM-OPS | 2018-12-03 | 2019-05-03 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 178738 | Work Order Description - 178738 - PM | PM | 4 | 356945 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-03 | 2019-04-02 | 2019-04-02 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178739 | Work Order Description - 178739 - PM | PM | 4 | 246510 | WSCHD | EQUIP-ISOL | 2018-12-03 | 2019-05-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 178740 | Work Order Description - 178740 - PM | PM | 4 | 353493 | WSCHD | NORM-OPS | 2018-12-03 | 2019-05-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 178741 | Work Order Description - 178741 - PM | PM | 4 | 356945 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-03 | 2019-04-02 | 2019-04-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178742 | Work Order Description - 178742 - PM | PM | 4 | 51505 | WSCHD | NORM-OPS | 2018-12-03 | 2019-05-03 | 2020-12-12 | 2020-12-12 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178743 | Work Order Description - 178743 - PM | PM | 4 | 546656 | WSCHD | NORM-OPS | 2018-12-03 | 2019-05-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178744 | Work Order Description - 178744 - PM | PM | 4 | 674413 | WSCHD | NORM-OPS | 2018-12-03 | 2019-05-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178745 | Work Order Description - 178745 - PM | PM | 4 | 308893 | WSCHD | NORM-OPS | 2018-12-03 | 2019-05-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178746 | Work Order Description - 178746 - PM | PM | 4 | 137564 | WSCHD | EQUIP-ISOL | 2018-12-03 | 2019-05-27 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 178750 | Work Order Description - 178750 - PM | PM | 4 | 308893 | WSCHD | NORM-OPS | 2018-12-03 | 2019-05-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178752 | Work Order Description - 178752 - PM | PM | 4 | 305527 | WSCHD | EQUIP-ISOL | 2018-12-03 | 2019-05-27 | 2020-03-07 | 2020-03-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178753 | Work Order Description - 178753 - PM | PM | 4 | 674222 | WSCHD | EQUIP-ISOL | 2018-12-03 | 2019-05-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 178754 | Work Order Description - 178754 - PM | PM | 4 | 359218 | WSCHD | NORM-OPS | 2018-12-03 | 2019-05-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178755 | Work Order Description - 178755 - PM | PM | 4 | 356945 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-03 | 2019-04-02 | 2019-04-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178756 | Work Order Description - 178756 - PSPM | PSPM | 1 | 575050 | WSCHD | PACK-ISOL | 2018-12-10 | 2019-05-03 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 178757 | Work Order Description - 178757 - PSPM | PSPM | 1 | 575050 | WSCHD | PACK-ISOL | 2018-12-10 | 2019-05-03 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 33
2019-03-31 | 178758 | Work Order Description - 178758 - PSPM | PSPM | 1 | 575050 | WSCHD | PACK-ISOL | 2018-12-10 | 2019-05-03 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 178759 | Work Order Description - 178759 - PSPM | PSPM | 1 | 575050 | WSCHD | PACK-ISOL | 2018-12-10 | 2019-05-03 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 25
2019-03-31 | 178760 | Work Order Description - 178760 - PSPM | PSPM | 1 | 575050 | WSCHD | PACK-ISOL | 2018-12-10 | 2019-05-03 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 178761 | Work Order Description - 178761 - PSPM | PSPM | 1 | 293229 | WSCHD | NORM-OPS | 2018-12-03 | 2019-05-03 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 178762 | Work Order Description - 178762 - PSPM | PSPM | 1 | 249507 | WSCHD | PACK-ISOL | 2018-12-10 | 2019-05-03 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 178763 | Work Order Description - 178763 - PSPM | PSPM | 1 | 249507 | WSCHD | PACK-ISOL | 2018-12-10 | 2019-05-03 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 178764 | Work Order Description - 178764 - PSPM | PSPM | 1 | 575050 | WSCHD | NORM-OPS | 2018-12-03 | 2019-05-03 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 178765 | Work Order Description - 178765 - PSPM | PSPM | 1 | 293228 | WSCHD | NORM-OPS | 2018-12-03 | 2019-05-03 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 178766 | Work Order Description - 178766 - PM | PM | 4 | 361277 | WSCHD | EQUIP-ISOL | 2018-12-11 | 2019-05-03 | 2019-04-06 | 2019-04-06 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 178767 | Work Order Description - 178767 - PM | PM | 4 | 400129 | WSCHD | EQUIP-ISOL | 2018-12-11 | 2019-05-03 | 2019-04-06 | 2019-04-06 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 178768 | Work Order Description - 178768 - PSPM | PSPM | 1 | 575051 | WSCHD | NORM-OPS | 2018-12-03 | 2019-05-03 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 178769 | Work Order Description - 178769 - PM | PM | 2 | 321115 | SCHD | PACK-ISOL | 2019-03-26 | 2019-05-27 | 2019-04-02 | 2019-04-02 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 178770 | Work Order Description - 178770 - PM | PM | 2 | 480203 | WSCHD | PACK-ISOL | 2018-12-11 | 2019-05-27 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 178772 | Work Order Description - 178772 - PM | PM | 4 | 361798 | SCHD | PACK-ISOL | 2019-03-26 | 2019-05-03 | 2019-04-02 | 2019-04-02 | 1 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 178773 | Work Order Description - 178773 - PSPM | PSPM | 1 | 410324 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-03 | 2019-04-02 | 2019-04-02 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 178775 | Work Order Description - 178775 - PM | PM | 4 | 574924 | SCHD | NORM-OPS | 2019-03-21 | 2019-05-03 | 2019-04-02 | 2019-04-02 | 1 | OPERATIONS | SAFETY | 2
2019-03-31 | 178776 | Work Order Description - 178776 - PM | PM | 4 | 481609 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-03 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 178777 | Work Order Description - 178777 - PM | PM | 4 | 476154 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-03 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 178778 | Work Order Description - 178778 - PM | PM | 4 | 403849 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-03 | 2019-04-02 | 2019-04-02 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 178779 | Work Order Description - 178779 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-03 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 178780 | Work Order Description - 178780 - PSPM | PSPM | 1 | 540268 | SCHD | PACK-ISOL | 2018-12-05 | 2019-05-03 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 178781 | Work Order Description - 178781 - PM | PM | 1 | 501092 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-03 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | SAFETY | 6
2019-03-31 | 178782 | Work Order Description - 178782 - PSPM | PSPM | 4 | 403503 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-03 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 29
2019-03-31 | 178784 | Work Order Description - 178784 - PM | PM | 4 | 670583 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-03 | 2019-04-02 | 2019-04-02 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 178786 | Work Order Description - 178786 - PSPM | PSPM | 1 | 378245 | WPLAN | EQUIP-ISOL | 2018-12-03 | 2019-05-03 | 2019-04-14 | 2019-04-14 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 178787 | Work Order Description - 178787 - PSPM | PSPM | 1 | 659058 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-03 | 2019-04-02 | 2019-04-02 | 1 | OPERATIONS | SAFETY | 1
2019-03-31 | 178789 | Work Order Description - 178789 - PSPM | PSPM | 1 | 378244 | WPLAN | EQUIP-ISOL | 2018-12-03 | 2019-05-03 | 2019-04-14 | 2019-04-14 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 178790 | Work Order Description - 178790 - PSPM | PSPM | 1 | 72277 | WPLAN | EQUIP-ISOL | 2018-12-03 | 2019-05-03 | 2019-04-14 | 2019-04-14 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 178791 | Work Order Description - 178791 - PSPM | PSPM | 1 | 392215 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-03 | 2019-04-02 | 2019-04-02 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 178792 | Work Order Description - 178792 - PSPM | PSPM | 1 | 228843 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-03 | 2019-04-02 | 2019-04-02 | 1 | MAINTENANCE | SAFETY | 4
2019-03-31 | 178793 | Work Order Description - 178793 - PM | PM | 4 | 450880 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-03 | 2019-04-02 | 2019-04-02 | 1 | OPERATIONS | SAFETY | 2
2019-03-31 | 178827 | Work Order Description - 178827 - BR | BR | 3 | 534323 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-04 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 178835 | Work Order Description - 178835 - CM | CM | 1 | 671087 | WSCHD | NORM-OPS | 2018-12-04 | 2019-12-04 | 2019-06-04 | 2019-06-04 | 3 | OPERATIONS | SAFETY | 1
2019-03-31 | 178838 | Work Order Description - 178838 - CM | CM | 2 | 677357 | WPLAN | NORM-OPS | 2018-12-05 | 2019-12-03 | 2019-06-03 | 2019-06-03 | 3 | INTEGRITY | FABRIC | 51
2019-03-31 | 178839 | Work Order Description - 178839 - CM | CM | 3 | 322466 | WPLAN | TPS | 2018-12-03 | 2019-06-08 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 178847 | Work Order Description - 178847 - CM | CM | 4 | 322466 | WSCHD | NORM-OPS | 2018-12-04 | 2019-06-04 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 178849 | Work Order Description - 178849 - CM | CM | 4 | 322466 | WSCHD | NORM-OPS | 2018-12-04 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 178851 | Work Order Description - 178851 - CM | CM | 2 | 355369 | WPLAN | NORM-OPS | 2018-12-04 | 2019-12-03 | 2019-06-03 | 2019-06-03 | 3 | INTEGRITY | FABRIC | 51
2019-03-31 | 178852 | Work Order Description - 178852 - BR | BR | 3 | 34728 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-01-12 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 178854 | Work Order Description - 178854 - PRJ | PRJ | 3 | 66963 | WPLAN | NORM-OPS | 2018-12-04 | 2019-09-22 | 2019-04-27 | 2019-04-27 | 4 | ENGINEERING | FABRIC | 36
2019-03-31 | 178855 | Work Order Description - 178855 - CM | CM | 2 | 11368 | SCHD | NORM-OPS | 2018-12-05 | 2019-12-03 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 178856 | Work Order Description - 178856 - PRJ | PRJ | 4 | 478652 | SCHD | NORM-OPS | 2018-12-13 | 2019-05-15 | 2019-09-14 | 2019-09-14 | 4 | INTEGRITY | CONSTRUCTION | 6
2019-03-31 | 178869 | Work Order Description - 178869 - PSPM | PSPM | 1 | 481656 | SCHD | NORM-OPS | 2018-12-05 | 2019-08-01 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 48
2019-03-31 | 178870 | Work Order Description - 178870 - PSPM | PSPM | 1 | 501179 | SCHD | NORM-OPS | 2018-12-05 | 2019-08-01 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 198
2019-03-31 | 178871 | Work Order Description - 178871 - PSPM | PSPM | 1 | 501203 | SCHD | NORM-OPS | 2018-12-05 | 2019-09-01 | 2019-08-01 | 2019-08-01 | 1 | MAINTENANCE | ELECTRICAL | 270
2019-03-31 | 178872 | Work Order Description - 178872 - PSPM | PSPM | 1 | 481657 | SCHD | NORM-OPS | 2018-12-05 | 2019-09-01 | 2019-08-01 | 2019-08-01 | 1 | MAINTENANCE | ELECTRICAL | 156
2019-03-31 | 178873 | Work Order Description - 178873 - PSPM | PSPM | 1 | 479365 | SCHD | NORM-OPS | 2018-12-05 | 2019-10-02 | 2019-09-01 | 2019-09-01 | 1 | MAINTENANCE | ELECTRICAL | 194
2019-03-31 | 178874 | Work Order Description - 178874 - PSPM | PSPM | 1 | 403605 | SCHD | NORM-OPS | 2018-12-05 | 2019-10-02 | 2019-09-01 | 2019-09-01 | 1 | MAINTENANCE | ELECTRICAL | 144
2019-03-31 | 178875 | Work Order Description - 178875 - PSPM | PSPM | 1 | 479388 | SCHD | NORM-OPS | 2018-12-05 | 2019-11-01 | 2019-10-01 | 2019-10-01 | 1 | MAINTENANCE | ELECTRICAL | 207
2019-03-31 | 178876 | Work Order Description - 178876 - PSPM | PSPM | 1 | 481658 | SCHD | NORM-OPS | 2018-12-05 | 2019-11-01 | 2019-10-01 | 2019-10-01 | 1 | MAINTENANCE | ELECTRICAL | 88
2019-03-31 | 178879 | Work Order Description - 178879 - PSPM | PSPM | 1 | 403636 | INPRG | NORM-OPS | 2018-12-21 | 2019-06-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 178881 | Work Order Description - 178881 - PSPM | PSPM | 1 | 481670 | SCHD | NORM-OPS | 2018-12-05 | 2019-06-01 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | ELECTRICAL | 18
2019-03-31 | 178901 | Work Order Description - 178901 - CM | CM | 2 | 308730 | SCHD | NORM-OPS | 2018-12-10 | 2019-06-04 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 178909 | Work Order Description - 178909 - BR | BR | 1 | 411122 | WSCHD | NORM-OPS | 2018-12-05 | 2020-12-01 | 2019-12-02 | 2019-12-02 | 4 | MAINTENANCE | CONSTRUCTION | 15
2019-03-31 | 178912 | Work Order Description - 178912 - BR | BR | 1 | 80747 | WMATL | TPS | 2019-03-27 | 2019-12-03 | 2019-07-13 | 2019-07-16 | 3 | MAINTENANCE | MECHANICAL | 80
2019-03-31 | 178914 | Work Order Description - 178914 - BR | BR | 3 | 54763 | SCHD | PACK-ISOL | 2018-12-10 | 2019-12-05 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 178921 | Work Order Description - 178921 - PSPM | PSPM | 1 | 679178 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-05-04 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 178923 | Work Order Description - 178923 - PSPM | PSPM | 1 | 657142 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-05-04 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 178924 | Work Order Description - 178924 - PM | PM | 4 | 540691 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-04 | 2019-04-03 | 2019-04-03 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 178926 | Work Order Description - 178926 - PSPM | PSPM | 1 | 650444 | WSCHD | NORM-OPS | 2018-12-04 | 2019-05-04 | 2019-04-17 | 2019-04-17 | 1 | OPERATIONS | OPERATIONS | 5
2019-03-31 | 178927 | Work Order Description - 178927 - PSPM | PSPM | 1 | 675036 | SCHD | NORM-OPS | 2019-03-21 | 2019-05-04 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 178928 | Work Order Description - 178928 - PM | PM | 4 | 547275 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-04 | 2019-04-03 | 2019-04-03 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 178929 | Work Order Description - 178929 - PSPM | PSPM | 1 | 361798 | SCHD | NORM-OPS | 2019-03-21 | 2019-05-04 | 2019-04-03 | 2019-04-03 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 178930 | Work Order Description - 178930 - PSPM | PSPM | 1 | 320057 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-04 | 2019-04-03 | 2019-04-03 | 1 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 178931 | Work Order Description - 178931 - PM | PM | 4 | 555305 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-04 | 2019-04-13 | 2019-04-13 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 178932 | Work Order Description - 178932 - PSPM | PSPM | 1 | 492109 | SCHD | SYS-ISOL | 2018-12-24 | 2019-05-04 | 2019-04-20 | 2019-04-20 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 178939 | Work Order Description - 178939 - PM | PM | 4 | 460846 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-04 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 178944 | Work Order Description - 178944 - PSPM | PSPM | 1 | 659510 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-04 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 178945 | Work Order Description - 178945 - PSPM | PSPM | 1 | 78362 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-05-28 | 2019-04-03 | 2019-04-03 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 178946 | Work Order Description - 178946 - PSPM | PSPM | 1 | 453789 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-05-28 | 2019-04-03 | 2019-04-03 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 178947 | Work Order Description - 178947 - PSPM | PSPM | 1 | 445117 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-05-28 | 2019-04-03 | 2019-04-03 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 178948 | Work Order Description - 178948 - PM | PM | 3 | 453790 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-05-28 | 2019-04-03 | 2019-04-03 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 178949 | Work Order Description - 178949 - PM | PM | 4 | 124434 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-04 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 178950 | Work Order Description - 178950 - PM | PM | 4 | 124459 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-04 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 178951 | Work Order Description - 178951 - PSPM | PSPM | 1 | 527364 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-04 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 178952 | Work Order Description - 178952 - PSPM | PSPM | 1 | 527364 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-04 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 178953 | Work Order Description - 178953 - PSPM | PSPM | 1 | 527364 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-04 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 178954 | Work Order Description - 178954 - PSPM | PSPM | 1 | 527364 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-04 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 178955 | Work Order Description - 178955 - PM | PM | 4 | 659496 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-04 | 2019-04-10 | 2019-04-10 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 178956 | Work Order Description - 178956 - PSPM | PSPM | 1 | 659551 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-04 | 2019-04-03 | 2019-04-03 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 178957 | Work Order Description - 178957 - PM | PM | 4 | 124590 | SCHD | NORM-OPS | 2018-12-17 | 2019-09-13 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 178958 | Work Order Description - 178958 - PSPM | PSPM | 1 | 527364 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-04 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 178959 | Work Order Description - 178959 - PSPM | PSPM | 1 | 227941 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-04 | 2019-04-17 | 2019-04-17 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 179030 | Work Order Description - 179030 - BR | BR | 3 | 184916 | WPLAN | EQUIP-ISOL | 2018-12-09 | 2019-06-08 | 2019-05-04 | 2019-05-04 | 3 | INTEGRITY | CONSTRUCTION | 6
2019-03-31 | 179032 | Work Order Description - 179032 - CM | CM | 1 | 403920 | WPLAN | NORM-OPS | 2018-12-04 | 2019-12-04 | 2019-06-04 | 2019-06-04 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 179037 | Work Order Description - 179037 - CM | CM | 4 | 261384 | SCHD | EQUIP-ISOL | 2018-12-10 | 2019-12-04 | 2019-05-04 | 2019-05-04 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 179044 | Work Order Description - 179044 - CM | CM | 4 | 248546 | SCHD | EQUIP-ISOL | 2019-03-20 | 2019-12-04 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 179049 | Work Order Description - 179049 - CM | CM | 4 | 448706 | INPRG | NORM-OPS | 2019-01-23 | 2020-12-02 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 179050 | Work Order Description - 179050 - BR | BR | 4 | 419551 | INPRG | NORM-OPS | 2019-02-20 | 2020-12-02 | 2019-03-30 | 2019-04-08 | 4 | DRILLING | DRILLING | 250.5
2019-03-31 | 179053 | Work Order Description - 179053 - BR | BR | 3 | 325930 | WPLAN | SYS-ISOL | 2018-12-05 | 2018-12-30 | 2019-07-27 | 2019-07-27 | 2 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 179055 | Work Order Description - 179055 - CM | CM | 3 | 663968 | WRISKQ | TPS | 2018-12-06 | 2020-12-02 |  |  | 4 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 179057 | Work Order Description - 179057 - CM | CM | 3 | 664013 | WRISKQ | SUBSYS-ISOL | 2018-12-06 | 2020-12-02 |  |  | 4 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 179058 | Work Order Description - 179058 - BR | BR | 3 | 490721 | WPLAN | SYS-ISOL | 2018-12-05 | 2019-12-19 | 2019-07-27 | 2019-07-27 | 2 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 179061 | Work Order Description - 179061 - BR | BR | 1 | 308094 | SCHD | TPS | 2019-01-11 | 2019-04-21 | 2019-07-13 | 2019-07-14 | 2 | MAINTENANCE | MECHANICAL | 7.5
2019-03-31 | 179069 | Work Order Description - 179069 - BR | BR | 3 | 58163 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-12-04 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 365250 | Work Order Description - 365250 - PSPM | PSPM | 1 | 679153 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-05-05 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 365252 | Work Order Description - 365252 - PSPM | PSPM | 1 | 679153 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-05-05 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 365254 | Work Order Description - 365254 - PSPM | PSPM | 1 | 679153 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-05-05 | 2019-04-06 | 2019-04-07 | 1 | MAINTENANCE | INSTRUMENTS | 50
2019-03-31 | 365256 | Work Order Description - 365256 - PSPM | PSPM | 1 | 679153 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-05-05 | 2019-04-06 | 2019-04-07 | 1 | MAINTENANCE | INSTRUMENTS | 50
2019-03-31 | 365258 | Work Order Description - 365258 - PSPM | PSPM | 1 | 679153 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-05-05 | 2019-04-06 | 2019-04-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 365260 | Work Order Description - 365260 - PM | PM | 4 | 481466 | SCHD | EQUIP-ISOL | 2019-03-26 | 2019-05-05 | 2019-04-04 | 2019-04-05 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 365262 | Work Order Description - 365262 - PSPM | PSPM | 1 | 681802 | WSCHD | EQUIP-ISOL | 2018-12-05 | 2019-05-05 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 42
2019-03-31 | 365264 | Work Order Description - 365264 - PM | PM | 4 | 656245 | WSCHD | PACK-ISOL | 2018-12-05 | 2019-05-29 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 365266 | Work Order Description - 365266 - PM | PM | 4 | 450481 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-05 | 2019-03-30 | 2019-03-30 | 2 | OPERATIONS | OPERATIONS | 1
2019-03-31 | 365268 | Work Order Description - 365268 - PM | PM | 2 | 312683 | SCHD | PACK-ISOL | 2018-12-24 | 2019-05-05 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 365272 | Work Order Description - 365272 - PM | PM | 3 | 309675 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-05 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 365274 | Work Order Description - 365274 - PM | PM | 3 | 309675 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-05 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 365276 | Work Order Description - 365276 - PSPM | PSPM | 1 | 555303 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-05 | 2019-04-13 | 2019-04-13 | 1 | OPERATIONS | SAFETY | 8
2019-03-31 | 365278 | Work Order Description - 365278 - PSPM | PSPM | 1 | 269368 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-05 | 2019-04-13 | 2019-04-13 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 365280 | Work Order Description - 365280 - PM | PM | 4 | 216612 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-05 | 2019-03-30 | 2019-03-30 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 365282 | Work Order Description - 365282 - PM | PM | 4 | 601923 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-05 | 2019-04-13 | 2019-04-13 | 2 | OPERATIONS | OPERATIONS | 60
2019-03-31 | 365294 | Work Order Description - 365294 - PSPM | PSPM | 1 | 123510 | SCHD | NORM-OPS | 2018-12-05 | 2019-05-05 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 365302 | Work Order Description - 365302 - PM | PM | 4 | 87424 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-10-02 | 2019-07-20 | 2019-07-20 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 365304 | Work Order Description - 365304 - PM | PM | 4 | 87423 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-10-02 | 2019-07-20 | 2019-07-20 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 365306 | Work Order Description - 365306 - PSPM | PSPM | 4 | 99434 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-05 | 2019-04-06 | 2019-04-07 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 365308 | Work Order Description - 365308 - PM | PM | 2 | 266139 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-05 | 2019-04-25 | 2019-04-25 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 365310 | Work Order Description - 365310 - PSPM | PSPM | 1 | 126920 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-05 | 2019-04-04 | 2019-04-04 | 1 | MAINTENANCE | ELECTRICAL | 0.5
2019-03-31 | 365312 | Work Order Description - 365312 - PM | PM | 4 | 126984 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-05 | 2019-04-04 | 2019-04-04 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 365314 | Work Order Description - 365314 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-05 | 2019-04-04 | 2019-04-04 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 365472 | Work Order Description - 365472 - CM | CM | 4 | 544183 | WMATL | NORM-OPS | 2018-12-10 | 2020-12-03 | 2019-12-04 | 2019-12-04 | 4 | MAINTENANCE | INSTRUMENTS | 32
2019-03-31 | 365473 | Work Order Description - 365473 - CM | CM | 1 | 451898 | WMATL | EQUIP-ISOL | 2018-12-10 | 2019-12-05 | 2019-06-05 | 2019-06-05 | 3 | INTEGRITY | ELECTRICAL | 28
2019-03-31 | 365475 | Work Order Description - 365475 - CM | CM | 4 | 124608 | SCHD | NORM-OPS | 2019-02-13 | 2020-12-03 | 2019-08-03 | 2019-08-06 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 365501 | Work Order Description - 365501 - BR | BR | 3 | 179788 | WPLAN | SYS-ISOL | 2018-12-06 | 2020-12-03 | 2019-12-04 | 2019-12-05 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 365537 | Work Order Description - 365537 - BR | BR | 3 | 359295 | SCHD | NORM-OPS | 2018-12-07 | 2020-12-03 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 365555 | Work Order Description - 365555 - PSPM | PSPM | 1 | 399692 | WSCHD | EQUIP-ISOL | 2019-01-14 | 2023-01-01 | 2021-04-24 | 2021-04-24 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 365557 | Work Order Description - 365557 - PSPM | PSPM | 1 | 248342 | WSCHD | EQUIP-ISOL | 2019-01-14 | 2019-12-01 | 2019-09-14 | 2019-09-14 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 365561 | Work Order Description - 365561 - PRJ | PRJ | 3 | 320026 | WPLAN | NORM-OPS | 2019-01-07 | 2019-04-08 | 2019-05-04 | 2019-05-04 | 4 | ENGINEERING | DRILLING | 48
2019-03-31 | 365582 | Work Order Description - 365582 - BR | BR | 4 | 451667 | SCHD | NORM-OPS | 2018-12-24 | 2019-12-20 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | FABRIC | 1
2019-03-31 | 365608 | Work Order Description - 365608 - BR | BR | 3 | 105207 | WPLAN | SUBSYS-ISOL | 2018-12-06 | 2019-12-05 | 2019-06-06 | 2019-06-11 | 3 | MAINTENANCE | MECHANICAL | 164
2019-03-31 | 365612 | Work Order Description - 365612 - PM | PM | 4 | 301660 | SCHD | NORM-OPS | 2019-02-21 | 2019-05-06 | 2019-04-02 | 2019-04-02 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 365614 | Work Order Description - 365614 - PM | PM | 4 | 308893 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-06 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 365616 | Work Order Description - 365616 - PM | PM | 4 | 51202 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-06 | 2019-04-05 | 2019-04-05 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 365618 | Work Order Description - 365618 - PSPM | PSPM | 1 | 671528 | WSCHD | NORM-OPS | 2018-12-06 | 2019-05-06 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 365620 | Work Order Description - 365620 - PSPM | PSPM | 1 | 137445 | WSCHD | NORM-OPS | 2018-12-06 | 2019-05-06 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 365622 | Work Order Description - 365622 - PSPM | PSPM | 1 | 671526 | WSCHD | NORM-OPS | 2018-12-06 | 2019-05-06 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 365624 | Work Order Description - 365624 - PM | PM | 2 | 305395 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-06 | 2019-04-02 | 2019-04-02 | 2 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 365627 | Work Order Description - 365627 - PSPM | PSPM | 1 | 308426 | WSCHD | NORM-OPS | 2018-12-06 | 2019-05-06 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 365629 | Work Order Description - 365629 - PSPM | PSPM | 1 | 471324 | WSCHD | NORM-OPS | 2018-12-06 | 2019-05-06 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 365631 | Work Order Description - 365631 - PSPM | PSPM | 1 | 261123 | WSCHD | EQUIP-ISOL | 2018-12-11 | 2019-05-06 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 365633 | Work Order Description - 365633 - PM | PM | 2 | 33427 | WSCHD | PACK-ISOL | 2018-12-11 | 2019-05-30 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 365637 | Work Order Description - 365637 - PSPM | PSPM | 1 | 357239 | WSCHD | NORM-OPS | 2018-12-06 | 2019-05-06 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 365639 | Work Order Description - 365639 - PSPM | PSPM | 1 | 267676 | WSCHD | NORM-OPS | 2018-12-06 | 2019-05-06 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 365643 | Work Order Description - 365643 - PSPM | PSPM | 1 | 310194 | SCHD | PACK-ISOL | 2018-12-24 | 2019-05-06 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 365645 | Work Order Description - 365645 - PSPM | PSPM | 1 | 310194 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-06 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 365647 | Work Order Description - 365647 - PSPM | PSPM | 1 | 499060 | SCHD | PACK-ISOL | 2018-12-24 | 2019-05-06 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 365649 | Work Order Description - 365649 - PSPM | PSPM | 1 | 499060 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-06 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 365651 | Work Order Description - 365651 - PSPM | PSPM | 1 | 310218 | SCHD | PACK-ISOL | 2018-12-24 | 2019-05-06 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 365653 | Work Order Description - 365653 - PSPM | PSPM | 1 | 310218 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-06 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 365655 | Work Order Description - 365655 - PSPM | PSPM | 1 | 189050 | SCHD | PACK-ISOL | 2018-12-24 | 2019-05-06 | 2019-03-16 | 2019-03-16 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 365659 | Work Order Description - 365659 - PSPM | PSPM | 1 | 262409 | SCHD | PACK-ISOL | 2018-12-24 | 2019-05-06 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 365667 | Work Order Description - 365667 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-06 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 365669 | Work Order Description - 365669 - PM | PM | 4 | 501105 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-06 | 2019-04-20 | 2019-04-20 | 3 | OPERATIONS | SAFETY | 4
2019-03-31 | 365671 | Work Order Description - 365671 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-06 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 365673 | Work Order Description - 365673 - PM | PM | 4 | 128236 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-06 | 2019-04-27 | 2019-04-27 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 365675 | Work Order Description - 365675 - PM | PM | 3 | 20477 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-06 | 2019-04-05 | 2019-04-05 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 365677 | Work Order Description - 365677 - PM | PM | 3 | 482752 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-06 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | MECHANICAL | 4.25
2019-03-31 | 365679 | Work Order Description - 365679 - PSPM | PSPM | 1 | 254238 | SCHD | PACK-ISOL | 2018-12-24 | 2019-05-06 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 365681 | Work Order Description - 365681 - PSPM | PSPM | 1 | 578830 | SCHD | PACK-ISOL | 2018-12-24 | 2019-05-06 | 2019-03-16 | 2019-03-16 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 365683 | Work Order Description - 365683 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-06 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 365685 | Work Order Description - 365685 - PM | PM | 4 | 262750 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-06 | 2020-02-08 | 2020-02-08 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 365687 | Work Order Description - 365687 - PM | PM | 4 | 450480 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-06 | 2019-04-05 | 2019-04-05 | 2 | MAINTENANCE | INSTRUMENTS | 50
2019-03-31 | 365697 | Work Order Description - 365697 - PSPM | PSPM | 1 | 375718 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-06 | 2019-04-05 | 2019-04-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 365699 | Work Order Description - 365699 - PSPM | PSPM | 1 | 110790 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-06 | 2019-04-05 | 2019-04-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 365701 | Work Order Description - 365701 - PSPM | PSPM | 1 | 670496 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-06 | 2019-04-05 | 2019-04-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 365703 | Work Order Description - 365703 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-06 | 2019-04-06 | 2019-04-08 | 3 | MAINTENANCE | MEDIC | 21
2019-03-31 | 365887 | Work Order Description - 365887 - CM | CM | 4 | 375636 | WPLAN | PACK-ISOL | 2018-12-06 | 2019-01-23 | 2020-07-28 | 2020-07-29 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 365921 | Work Order Description - 365921 - PSCM | PSCM | 1 | 567872 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-06-07 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | ELECTRICAL | 28
2019-03-31 | 365985 | Work Order Description - 365985 - BR | BR | 3 | 179788 | WPLAN | SYS-ISOL | 2018-12-11 | 2020-12-04 | 2019-12-05 | 2019-12-06 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 365988 | Work Order Description - 365988 - BR | BR | 3 | 377450 | SCHD | NORM-OPS | 2018-12-17 | 2020-12-04 | 2019-12-05 | 2019-12-06 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 366032 | Work Order Description - 366032 - PM | PM | 3 | 411326 | WSCHD | NORM-OPS | 2018-12-07 | 2019-05-07 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | INSPECTION | 30
2019-03-31 | 366034 | Work Order Description - 366034 - PM | PM | 3 | 411326 | WSCHD | NORM-OPS | 2018-12-07 | 2019-05-07 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | INSPECTION | 30
2019-03-31 | 366036 | Work Order Description - 366036 - PM | PM | 3 | 411326 | WSCHD | NORM-OPS | 2018-12-07 | 2019-05-07 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | INSPECTION | 30
2019-03-31 | 366038 | Work Order Description - 366038 - PM | PM | 4 | 411326 | WSCHD | NORM-OPS | 2018-12-07 | 2019-05-07 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | INSPECTION | 210
2019-03-31 | 366040 | Work Order Description - 366040 - PM | PM | 4 | 354350 | SCHD | NORM-OPS | 2019-02-21 | 2019-05-07 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 366042 | Work Order Description - 366042 - PM | PM | 4 | 481467 | WSCHD | EQUIP-ISOL | 2018-12-07 | 2019-05-07 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 366044 | Work Order Description - 366044 - PSPM | PSPM | 1 | 321203 | WSCHD | NORM-OPS | 2018-12-07 | 2019-05-07 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 366046 | Work Order Description - 366046 - PSPM | PSPM | 1 | 321218 | WSCHD | NORM-OPS | 2018-12-07 | 2019-05-07 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 366048 | Work Order Description - 366048 - PM | PM | 4 | 294918 | WSCHD | NORM-OPS | 2018-12-10 | 2019-05-07 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | MECHANICAL | 10.5
2019-03-31 | 366050 | Work Order Description - 366050 - PSPM | PSPM | 1 | 361110 | WSCHD | EQUIP-ISOL | 2018-12-10 | 2019-05-07 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 366052 | Work Order Description - 366052 - PM | PM | 4 | 666204 | SCHD | NORM-OPS | 2019-02-21 | 2019-05-07 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 366054 | Work Order Description - 366054 - PM | PM | 4 | 294916 | WSCHD | NORM-OPS | 2018-12-07 | 2019-05-07 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 366056 | Work Order Description - 366056 - PM | PM | 4 | 584012 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-07 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 366058 | Work Order Description - 366058 - PM | PM | 4 | 313319 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-07-24 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 366060 | Work Order Description - 366060 - PSPM | PSPM | 1 | 555234 | SCHD | NORM-OPS | 2018-12-13 | 2019-05-07 | 2019-04-13 | 2019-04-13 | 1 | OPERATIONS | OPERATIONS | 12
2019-03-31 | 366062 | Work Order Description - 366062 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-07 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 366104 | Work Order Description - 366104 - PM | PM | 3 | 78341 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-07-24 | 2019-04-09 | 2019-04-09 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 366106 | Work Order Description - 366106 - PM | PM | 3 | 99487 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-10-04 | 2019-05-05 | 2019-05-05 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 366112 | Work Order Description - 366112 - PM | PM | 3 | 105744 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-08-29 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 366124 | Work Order Description - 366124 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-07 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 366126 | Work Order Description - 366126 - PSPM | PSPM | 2 | 436046 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-07 | 2019-04-28 | 2019-05-13 | 1 | INTEGRITY | INSPECTION | 222
2019-03-31 | 366128 | Work Order Description - 366128 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-07 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 366130 | Work Order Description - 366130 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-07 | 2019-04-06 | 2019-04-06 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 366276 | Work Order Description - 366276 - CM | CM | 4 | 361655 | WPLAN | NORM-OPS | 2018-12-09 | 2019-06-08 | 2019-11-30 | 2019-11-30 | 3 | INTEGRITY | FABRIC | 16
2019-03-31 | 366425 | Work Order Description - 366425 - CM | CM | 1 | 403920 | WPLAN | NORM-OPS | 2018-12-09 | 2019-06-08 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | SERVICES | 1
2019-03-31 | 366431 | Work Order Description - 366431 - PM | PM | 2 | 572308 | WSCHD | NORM-OPS | 2018-12-08 | 2019-05-08 | 2019-04-07 | 2019-04-07 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 366433 | Work Order Description - 366433 - PM | PM | 4 | 248464 | WSCHD | EQUIP-ISOL | 2018-12-10 | 2019-05-08 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | CONSTRUCTION | 9
2019-03-31 | 366435 | Work Order Description - 366435 - PM | PM | 4 | 580762 | WSCHD | NORM-OPS | 2018-12-08 | 2019-05-08 | 2019-04-07 | 2019-04-07 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 366437 | Work Order Description - 366437 - PSPM | PSPM | 1 | 361193 | WSCHD | EQUIP-ISOL | 2018-12-10 | 2019-05-08 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 366439 | Work Order Description - 366439 - PM | PM | 4 | 324811 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366441 | Work Order Description - 366441 - PM | PM | 4 | 188857 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366443 | Work Order Description - 366443 - PM | PM | 4 | 498464 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366445 | Work Order Description - 366445 - PM | PM | 4 | 188855 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366447 | Work Order Description - 366447 - PM | PM | 4 | 188858 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366449 | Work Order Description - 366449 - PM | PM | 4 | 313220 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-08 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 366451 | Work Order Description - 366451 - PM | PM | 4 | 325184 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-08 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 366453 | Work Order Description - 366453 - PM | PM | 4 | 310069 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-08 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 366455 | Work Order Description - 366455 - PM | PM | 4 | 309712 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366457 | Work Order Description - 366457 - PM | PM | 4 | 498464 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366459 | Work Order Description - 366459 - PM | PM | 4 | 188855 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366461 | Work Order Description - 366461 - PM | PM | 4 | 188858 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366463 | Work Order Description - 366463 - PM | PM | 4 | 324811 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366465 | Work Order Description - 366465 - PM | PM | 4 | 188857 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366467 | Work Order Description - 366467 - PM | PM | 4 | 498464 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366469 | Work Order Description - 366469 - PM | PM | 4 | 188855 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366471 | Work Order Description - 366471 - PM | PM | 4 | 188858 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366473 | Work Order Description - 366473 - PM | PM | 4 | 324811 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366475 | Work Order Description - 366475 - PSPM | PSPM | 1 | 447441 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-08 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 366477 | Work Order Description - 366477 - PM | PM | 1 | 446516 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-08 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 366479 | Work Order Description - 366479 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-08 | 2019-04-07 | 2019-04-07 | 2 | MAINTENANCE | SAFETY | 7
2019-03-31 | 366481 | Work Order Description - 366481 - PM | PM | 4 | 78626 | SCHD | PACK-ISOL | 2018-12-17 | 2019-06-01 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 366485 | Work Order Description - 366485 - PSPM | PSPM | 1 | 669993 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-08 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 366487 | Work Order Description - 366487 - PM | PM | 4 | 106055 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-10-05 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 366489 | Work Order Description - 366489 - PSPM | PSPM | 1 | 99924 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-06-19 | 2019-04-08 | 2019-04-08 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366491 | Work Order Description - 366491 - PM | PM | 4 | 78463 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-10-05 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 366493 | Work Order Description - 366493 - PSPM | PSPM | 1 | 78457 | SCHD | PACK-ISOL | 2019-03-29 | 2019-07-08 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366501 | Work Order Description - 366501 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-08 | 2019-04-07 | 2019-04-07 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 366503 | Work Order Description - 366503 - PSPM | PSPM | 1 | 669726 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-08 | 2019-04-07 | 2019-04-07 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 366505 | Work Order Description - 366505 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-08 | 2019-04-07 | 2019-04-07 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 366507 | Work Order Description - 366507 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-08 | 2019-04-07 | 2019-04-07 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 366512 | Work Order Description - 366512 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-08 | 2019-04-07 | 2019-04-07 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 366634 | Work Order Description - 366634 - CM | CM | 3 | 464189 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-04-06 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 46
2019-03-31 | 366647 | Work Order Description - 366647 - BR | BR | 3 | 128568 | WPLAN | TPS | 2019-01-07 | 2019-06-09 | 2019-07-13 | 2019-07-14 | 3 | MAINTENANCE | CONSTRUCTION | 14
2019-03-31 | 366650 | Work Order Description - 366650 - BR | BR | 3 | 399042 | WPLAN | SYS-ISOL | 2018-12-11 | 2019-06-09 | 2019-07-13 | 2019-07-17 | 3 | MAINTENANCE | INSTRUMENTS | 79
2019-03-31 | 366738 | Work Order Description - 366738 - PM | PM | 4 | 51538 | WSCHD | NORM-OPS | 2018-12-09 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366740 | Work Order Description - 366740 - PM | PM | 4 | 51559 | WSCHD | NORM-OPS | 2018-12-09 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366742 | Work Order Description - 366742 - PM | PM | 4 | 18317 | WSCHD | EQUIP-ISOL | 2018-12-09 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366744 | Work Order Description - 366744 - PM | PM | 4 | 18316 | WSCHD | EQUIP-ISOL | 2018-12-09 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366746 | Work Order Description - 366746 - PM | PM | 4 | 666316 | WSCHD | EQUIP-ISOL | 2018-12-10 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366748 | Work Order Description - 366748 - PM | PM | 4 | 417521 | WSCHD | EQUIP-ISOL | 2018-12-10 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366750 | Work Order Description - 366750 - PM | PM | 4 | 50099 | WSCHD | EQUIP-ISOL | 2018-12-09 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 366752 | Work Order Description - 366752 - PM | PM | 4 | 50098 | WSCHD | EQUIP-ISOL | 2018-12-09 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 366754 | Work Order Description - 366754 - PM | PM | 4 | 411571 | WSCHD | NORM-OPS | 2018-12-09 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366756 | Work Order Description - 366756 - PM | PM | 4 | 358159 | WSCHD | NORM-OPS | 2018-12-09 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366758 | Work Order Description - 366758 - PM | PM | 4 | 540667 | WSCHD | NORM-OPS | 2018-12-09 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 366760 | Work Order Description - 366760 - PM | PM | 4 | 678551 | WSCHD | NORM-OPS | 2018-12-09 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 366762 | Work Order Description - 366762 - PM | PM | 4 | 595915 | WSCHD | EQUIP-ISOL | 2018-12-10 | 2019-05-09 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 366765 | Work Order Description - 366765 - PM | PM | 4 | 674306 | WSCHD | NORM-OPS | 2018-12-09 | 2019-05-09 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 366767 | Work Order Description - 366767 - PM | PM | 4 | 308006 | WSCHD | NORM-OPS | 2018-12-09 | 2019-05-09 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 366769 | Work Order Description - 366769 - PM | PM | 4 | 361470 | WSCHD | NORM-OPS | 2018-12-09 | 2019-05-09 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 366771 | Work Order Description - 366771 - PM | PM | 4 | 546054 | WSCHD | NORM-OPS | 2018-12-09 | 2019-05-09 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366773 | Work Order Description - 366773 - PM | PM | 4 | 541035 | WSCHD | NORM-OPS | 2018-12-09 | 2019-05-09 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 366781 | Work Order Description - 366781 - PM | PM | 4 | 246539 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-05-09 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 366785 | Work Order Description - 366785 - PM | PM | 4 | 323483 | WSCHD | PACK-ISOL | 2018-12-10 | 2019-05-09 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 366789 | Work Order Description - 366789 - PM | PM | 4 | 245880 | WSCHD | PACK-ISOL | 2018-12-10 | 2019-05-09 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 366793 | Work Order Description - 366793 - PM | PM | 4 | 245881 | WSCHD | PACK-ISOL | 2018-12-10 | 2019-05-09 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 366797 | Work Order Description - 366797 - PSPM | PSPM | 1 | 470877 | WSCHD | NORM-OPS | 2018-12-09 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 366799 | Work Order Description - 366799 - PM | PM | 4 | 361803 | WSCHD | PACK-ISOL | 2018-12-10 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 1 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 366801 | Work Order Description - 366801 - PM | PM | 4 | 360243 | WSCHD | NORM-OPS | 2018-12-09 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 366803 | Work Order Description - 366803 - PSPM | PSPM | 1 | 574963 | SCHD | EQUIP-ISOL | 2019-03-21 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 1 | MAINTENANCE | SERVICES | 4
2019-03-31 | 366805 | Work Order Description - 366805 - PM | PM | 4 | 555300 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-09 | 2019-04-13 | 2019-04-13 | 1 | OPERATIONS | SAFETY | 6
2019-03-31 | 366807 | Work Order Description - 366807 - PSPM | PSPM | 1 | 27342 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 366809 | Work Order Description - 366809 - PSPM | PSPM | 1 | 255834 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 366811 | Work Order Description - 366811 - PM | PM | 4 | 553208 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-09 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | DRILLING | 8
2019-03-31 | 366815 | Work Order Description - 366815 - PM | PM | 4 | 556260 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-09 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 366817 | Work Order Description - 366817 - PM | PM | 2 | 216011 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-09 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 366819 | Work Order Description - 366819 - PM | PM | 4 | 320026 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-09 | 2019-04-06 | 2019-04-06 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 366821 | Work Order Description - 366821 - PM | PM | 4 | 216158 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-09 | 2019-04-06 | 2019-04-06 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 366823 | Work Order Description - 366823 - PM | PM | 4 | 74216 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-09 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 366825 | Work Order Description - 366825 - PM | PM | 4 | 664897 | WPLAN | EQUIP-ISOL | 2018-12-09 | 2019-05-09 | 2019-04-29 | 2019-04-29 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 366827 | Work Order Description - 366827 - PSPM | PSPM | 1 | 659510 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 366829 | Work Order Description - 366829 - PSPM | PSPM | 1 | 659510 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 366831 | Work Order Description - 366831 - PSPM | PSPM | 1 | 659510 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-09 | 2019-04-12 | 2019-04-12 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 366833 | Work Order Description - 366833 - PSPM | PSPM | 1 | 659510 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 366835 | Work Order Description - 366835 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 366837 | Work Order Description - 366837 - PSPM | PSPM | 1 | 659510 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-09 | 2019-04-08 | 2019-04-08 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 366839 | Work Order Description - 366839 - PM | PM | 4 | 93189 | WPLAN | EQUIP-ISOL | 2018-12-09 | 2019-05-09 | 2019-04-29 | 2019-04-29 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 366841 | Work Order Description - 366841 - PM | PM | 4 | 393192 | WPLAN | EQUIP-ISOL | 2018-12-09 | 2019-05-09 | 2019-04-29 | 2019-04-29 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 367037 | Work Order Description - 367037 - CM | CM | 1 | 361657 | WPLAN | NORM-OPS | 2018-12-11 | 2019-12-09 | 2019-06-09 | 2019-06-09 | 3 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 367039 | Work Order Description - 367039 - BR | BR | 3 | 124183 | WPLAN | TPS | 2018-12-11 | 2019-06-10 | 2019-07-13 | 2019-07-21 | 3 | MAINTENANCE | INSTRUMENTS | 60
2019-03-31 | 367047 | Work Order Description - 367047 - PSCM | PSCM | 1 | 81240 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-12-09 | 2019-06-09 | 2019-06-09 | 3 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 367059 | Work Order Description - 367059 - PRJ | PRJ | 4 | 544931 | SCHD | NORM-OPS | 2018-12-24 | 2020-12-07 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | ELECTRICAL | 511.5
2019-03-31 | 367076 | Work Order Description - 367076 - CM | CM | 1 | 547588 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2020-12-07 | 2019-12-08 | 2019-12-08 | 4 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 367085 | Work Order Description - 367085 - CM | CM | 1 | 399437 | WPLAN | PACK-ISOL | 2018-12-11 | 2019-12-11 | 2019-06-11 | 2019-06-11 | 3 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 367193 | Work Order Description - 367193 - PM | PM | 4 | 314530 | WSCHD | EQUIP-ISOL | 2018-12-10 | 2019-05-10 | 2019-04-09 | 2019-04-09 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 367195 | Work Order Description - 367195 - PM | PM | 4 | 674224 | SCHD | EQUIP-ISOL | 2019-03-14 | 2019-05-10 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 367197 | Work Order Description - 367197 - PM | PM | 4 | 400439 | SCHD | EQUIP-ISOL | 2019-03-14 | 2019-05-10 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 367199 | Work Order Description - 367199 - PM | PM | 4 | 553700 | SCHD | NORM-OPS | 2019-03-14 | 2019-05-10 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 367201 | Work Order Description - 367201 - PM | PM | 4 | 243519 | WSCHD | NORM-OPS | 2018-12-10 | 2019-05-10 | 2019-04-09 | 2019-04-09 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 367205 | Work Order Description - 367205 - PM | PM | 4 | 356947 | WSCHD | NORM-OPS | 2018-12-10 | 2019-05-10 | 2019-04-09 | 2019-04-09 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 367207 | Work Order Description - 367207 - PM | PM | 4 | 314162 | WSCHD | NORM-OPS | 2018-12-10 | 2019-05-10 | 2019-04-09 | 2019-04-09 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 367209 | Work Order Description - 367209 - PM | PM | 4 | 314162 | WSCHD | NORM-OPS | 2018-12-10 | 2019-05-10 | 2019-04-09 | 2019-04-09 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 367211 | Work Order Description - 367211 - PM | PM | 4 | 356947 | WSCHD | NORM-OPS | 2018-12-10 | 2019-05-10 | 2019-04-09 | 2019-04-09 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 367213 | Work Order Description - 367213 - PSPM | PSPM | 1 | 575051 | WSCHD | PACK-ISOL | 2018-12-11 | 2019-05-10 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 367216 | Work Order Description - 367216 - PSPM | PSPM | 1 | 575051 | WSCHD | PACK-ISOL | 2018-12-11 | 2019-05-10 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 33
2019-03-31 | 367218 | Work Order Description - 367218 - PSPM | PSPM | 1 | 575051 | WSCHD | PACK-ISOL | 2018-12-11 | 2019-05-10 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 367220 | Work Order Description - 367220 - PSPM | PSPM | 1 | 575051 | WSCHD | PACK-ISOL | 2018-12-11 | 2019-05-10 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 25
2019-03-31 | 367222 | Work Order Description - 367222 - PSPM | PSPM | 1 | 575051 | WSCHD | PACK-ISOL | 2018-12-11 | 2019-05-10 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 367224 | Work Order Description - 367224 - PSPM | PSPM | 1 | 404664 | WSCHD | PACK-ISOL | 2018-12-11 | 2019-05-10 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 367226 | Work Order Description - 367226 - PSPM | PSPM | 1 | 404664 | WSCHD | PACK-ISOL | 2018-12-11 | 2019-05-10 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 367229 | Work Order Description - 367229 - PSPM | PSPM | 1 | 57146 | WSCHD | EQUIP-ISOL | 2018-12-10 | 2019-05-10 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 367231 | Work Order Description - 367231 - PSPM | PSPM | 1 | 54312 | WSCHD | EQUIP-ISOL | 2018-12-10 | 2019-05-10 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 367233 | Work Order Description - 367233 - PM | PM | 4 | 546030 | WSCHD | EQUIP-ISOL | 2018-12-10 | 2019-05-10 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 367235 | Work Order Description - 367235 - PSPM | PSPM | 1 | 361803 | WSCHD | NORM-OPS | 2018-12-10 | 2019-05-10 | 2019-04-09 | 2019-04-09 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 367237 | Work Order Description - 367237 - PSPM | PSPM | 1 | 653311 | WSCHD | NORM-OPS | 2018-12-10 | 2019-05-10 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 367239 | Work Order Description - 367239 - PSPM | PSPM | 1 | 399564 | WSCHD | NORM-OPS | 2018-12-10 | 2019-05-10 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 367243 | Work Order Description - 367243 - PSPM | PSPM | 1 | 653322 | WSCHD | PACK-ISOL | 2018-12-10 | 2019-05-10 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 367245 | Work Order Description - 367245 - PSPM | PSPM | 1 | 357619 | WSCHD | PACK-ISOL | 2018-12-10 | 2019-05-10 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 367247 | Work Order Description - 367247 - PSPM | PSPM | 1 | 653323 | WSCHD | PACK-ISOL | 2018-12-10 | 2019-05-10 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 367249 | Work Order Description - 367249 - PM | PM | 4 | 481609 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-10 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 367263 | Work Order Description - 367263 - PSPM | PSPM | 1 | 36117 | SCHD | PACK-ISOL | 2018-12-24 | 2019-04-25 | 2019-03-23 | 2019-03-23 | 1 | WELLS | WELLS | 1
2019-03-31 | 367271 | Work Order Description - 367271 - PSPM | PSPM | 1 | 462436 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-10 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 367281 | Work Order Description - 367281 - PSPM | PSPM | 1 | 465447 | SCHD | PACK-ISOL | 2018-12-24 | 2019-04-24 | 2019-03-23 | 2019-03-23 | 1 | WELLS | WELLS | 5
2019-03-31 | 367289 | Work Order Description - 367289 - PM | PM | 4 | 476154 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-10 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 367291 | Work Order Description - 367291 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-10 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 367295 | Work Order Description - 367295 - PM | PM | 4 | 632580 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-10 | 2019-04-20 | 2019-04-20 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 367297 | Work Order Description - 367297 - PM | PM | 4 | 583919 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-10 | 2019-04-20 | 2019-04-20 | 3 | OPERATIONS | SAFETY | 4
2019-03-31 | 367299 | Work Order Description - 367299 - PM | PM | 4 | 122683 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-10 | 2019-04-20 | 2019-04-20 | 3 | OPERATIONS | SAFETY | 15
2019-03-31 | 367301 | Work Order Description - 367301 - PM | PM | 4 | 583934 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-10 | 2019-04-20 | 2019-04-20 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 367303 | Work Order Description - 367303 - PM | PM | 4 | 583934 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-10 | 2019-04-20 | 2019-04-20 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 367305 | Work Order Description - 367305 - PSPM | PSPM | 1 | 254239 | SCHD | PACK-ISOL | 2018-12-24 | 2019-05-10 | 2019-04-09 | 2019-04-09 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 367307 | Work Order Description - 367307 - PSPM | PSPM | 4 | 403503 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-10 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 367324 | Work Order Description - 367324 - PM | PM | 4 | 74891 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-10 | 2019-04-09 | 2019-04-09 | 2 | OPERATIONS | OPERATIONS | 1
2019-03-31 | 367326 | Work Order Description - 367326 - PSPM | PSPM | 1 | 392215 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-10 | 2019-04-09 | 2019-04-09 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 367328 | Work Order Description - 367328 - PSPM | PSPM | 1 | 453251 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-10 | 2019-04-27 | 2019-04-28 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 367330 | Work Order Description - 367330 - PSPM | PSPM | 1 | 659510 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-10 | 2019-04-09 | 2019-04-09 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 367467 | Work Order Description - 367467 - BR | BR | 3 | 398935 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-11 | 2019-07-13 | 2019-07-14 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 367518 | Work Order Description - 367518 - PSPM | PSPM | 1 | 665053 | WPLAN | SYS-ISOL | 2018-12-10 | 2019-07-20 | 2019-07-13 | 2019-07-20 | 1 | INTEGRITY | MECHANICAL | 36
2019-03-31 | 367528 | Work Order Description - 367528 - CM | CM | 4 | 570144 | WPLAN | NORM-OPS | 2018-12-15 | 2020-03-01 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | CONSTRUCTION | 28
2019-03-31 | 367553 | Work Order Description - 367553 - CM | CM | 4 | 697913 | WSCHD | NORM-OPS | 2018-12-15 | 2020-03-01 | 2020-01-31 | 2020-01-31 | 3 | INTEGRITY | FABRIC | 168
2019-03-31 | 367586 | Work Order Description - 367586 - CM | CM | 4 | 570144 | WSCHD | NORM-OPS | 2018-12-15 | 2020-04-01 | 2019-06-10 | 2019-06-10 | 3 | INTEGRITY | FABRIC | 252
2019-03-31 | 367602 | Work Order Description - 367602 - CM | CM | 4 | 570144 | WSCHD | NORM-OPS | 2018-12-15 | 2020-12-08 | 2019-12-09 | 2019-12-09 | 4 | INTEGRITY | CONSTRUCTION | 20
2019-03-31 | 367606 | Work Order Description - 367606 - CM | CM | 4 | 570144 | WSCHD | NORM-OPS | 2018-12-15 | 2020-03-01 | 2019-06-10 | 2019-06-10 | 3 | INTEGRITY | CONSTRUCTION | 20
2019-03-31 | 367628 | Work Order Description - 367628 - PSCM | PSCM | 1 | 26860 | WMATL | EQUIP-ISOL | 2019-02-12 | 2021-02-03 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 367629 | Work Order Description - 367629 - PSPM | PSPM | 1 | 292677 | WSCHD | NORM-OPS | 2018-12-11 | 2019-05-11 | 2019-04-10 | 2019-04-10 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 367631 | Work Order Description - 367631 - PSPM | PSPM | 1 | 457573 | SCHD | NORM-OPS | 2019-03-21 | 2019-05-11 | 2019-04-02 | 2019-04-02 | 1 | OPERATIONS | SAFETY | 2
2019-03-31 | 367633 | Work Order Description - 367633 - PM | PM | 4 | 540691 | WSCHD | NORM-OPS | 2018-12-11 | 2019-05-11 | 2019-04-10 | 2019-04-10 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 367635 | Work Order Description - 367635 - PM | PM | 4 | 481470 | WSCHD | NORM-OPS | 2018-12-11 | 2019-05-11 | 2019-04-10 | 2019-04-10 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 367637 | Work Order Description - 367637 - PSPM | PSPM | 1 | 545260 | WSCHD | NORM-OPS | 2018-12-11 | 2019-05-11 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 367639 | Work Order Description - 367639 - PSPM | PSPM | 1 | 545261 | WSCHD | NORM-OPS | 2018-12-11 | 2019-05-11 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 367641 | Work Order Description - 367641 - PSPM | PSPM | 1 | 51662 | WSCHD | NORM-OPS | 2018-12-11 | 2020-02-21 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 367643 | Work Order Description - 367643 - PM | PM | 4 | 58419 | WSCHD | NORM-OPS | 2018-12-11 | 2019-05-11 | 2019-04-27 | 2019-04-27 | 1 | OPERATIONS | OPERATIONS | 4
2019-03-31 | 367645 | Work Order Description - 367645 - PSPM | PSPM | 1 | 137858 | WSCHD | NORM-OPS | 2018-12-11 | 2019-05-11 | 2019-04-10 | 2019-04-10 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 367647 | Work Order Description - 367647 - PSPM | PSPM | 1 | 547275 | WSCHD | NORM-OPS | 2018-12-11 | 2019-05-11 | 2019-04-10 | 2019-04-10 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 367649 | Work Order Description - 367649 - PSPM | PSPM | 1 | 652220 | WSCHD | NORM-OPS | 2018-12-11 | 2019-05-11 | 2019-04-10 | 2019-04-10 | 1 | MAINTENANCE | SERVICES | 10
2019-03-31 | 367651 | Work Order Description - 367651 - PM | PM | 4 | 469426 | WSCHD | NORM-OPS | 2018-12-11 | 2019-05-11 | 2019-04-13 | 2019-04-13 | 1 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 367653 | Work Order Description - 367653 - PM | PM | 4 | 315344 | WSCHD | EQUIP-ISOL | 2018-12-11 | 2020-04-05 | 2019-04-10 | 2019-04-10 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 367655 | Work Order Description - 367655 - PM | PM | 4 | 246173 | WSCHD | EQUIP-ISOL | 2018-12-11 | 2019-05-11 | 2019-04-10 | 2019-04-10 | 1 | INTEGRITY | SERVICES | 10
2019-03-31 | 367657 | Work Order Description - 367657 - PM | PM | 4 | 546030 | WSCHD | EQUIP-ISOL | 2018-12-11 | 2019-05-11 | 2019-04-10 | 2019-04-10 | 1 | INTEGRITY | SERVICES | 7
2019-03-31 | 367659 | Work Order Description - 367659 - PSPM | PSPM | 1 | 256496 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-11 | 2019-04-10 | 2019-04-10 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 367661 | Work Order Description - 367661 - PSPM | PSPM | 1 | 256425 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-11 | 2019-04-10 | 2019-04-10 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 367663 | Work Order Description - 367663 - PM | PM | 4 | 99579 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-11 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 367665 | Work Order Description - 367665 - PM | PM | 4 | 310224 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-07-28 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 367669 | Work Order Description - 367669 - PM | PM | 4 | 460846 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-11 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 367671 | Work Order Description - 367671 - PM | PM | 4 | 487367 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-11 | 2019-04-10 | 2019-04-10 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 367682 | Work Order Description - 367682 - PM | PM | 4 | 237629 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-11 | 2019-04-17 | 2019-04-17 | 1 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 367684 | Work Order Description - 367684 - PM | PM | 4 | 377675 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-11 | 2019-04-17 | 2019-04-17 | 1 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 367686 | Work Order Description - 367686 - PM | PM | 4 | 106045 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-09-20 | 2019-04-10 | 2019-04-10 | 2 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 367688 | Work Order Description - 367688 - PM | PM | 4 | 100153 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-05-11 | 2019-04-10 | 2019-04-10 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 367839 | Work Order Description - 367839 - CM | CM | 1 | 361655 | WSCHD | NORM-OPS | 2018-12-15 | 2020-12-09 | 2019-12-10 | 2019-12-10 | 4 | INTEGRITY | SERVICES | 8
2019-03-31 | 367855 | Work Order Description - 367855 - CM | CM | 1 | 361655 | WPLAN | EQUIP-ISOL | 2018-12-15 | 2020-12-09 | 2019-12-10 | 2019-12-10 | 4 | INTEGRITY | CONSTRUCTION | 7
2019-03-31 | 367856 | Work Order Description - 367856 - BR | BR | 1 | 527345 | SCHD | NORM-OPS | 2018-12-17 | 2020-12-09 | 2019-12-10 | 2019-12-10 | 4 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 367874 | Work Order Description - 367874 - PSPM | PSPM | 1 | 665052 | WPLAN | SYS-ISOL | 2018-12-11 | 2019-07-24 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 367876 | Work Order Description - 367876 - PSPM | PSPM | 1 | 436714 | WPLAN | SYS-ISOL | 2018-12-11 | 2019-07-28 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 367878 | Work Order Description - 367878 - PSPM | PSPM | 1 | 93294 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2019-07-20 | 2019-07-13 | 2019-07-14 | 1 | INTEGRITY | MECHANICAL | 16
2019-03-31 | 367880 | Work Order Description - 367880 - PSPM | PSPM | 1 | 436709 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2019-07-21 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 367882 | Work Order Description - 367882 - PSPM | PSPM | 1 | 664888 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2019-07-21 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 367884 | Work Order Description - 367884 - PSPM | PSPM | 1 | 89548 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2019-07-21 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 367886 | Work Order Description - 367886 - PSPM | PSPM | 1 | 396377 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2019-07-23 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 367888 | Work Order Description - 367888 - PSPM | PSPM | 1 | 396378 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2019-07-23 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 367891 | Work Order Description - 367891 - PSPM | PSPM | 1 | 388301 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2019-08-10 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 367893 | Work Order Description - 367893 - PSCM | PSCM | 1 | 361655 | WSCHD | NORM-OPS | 2018-12-15 | 2019-12-11 | 2019-06-11 | 2019-06-11 | 3 | INTEGRITY | SERVICES | 52
2019-03-31 | 367894 | Work Order Description - 367894 - PSPM | PSPM | 1 | 664928 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2019-09-19 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 367898 | Work Order Description - 367898 - PSPM | PSPM | 1 | 375653 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2019-10-04 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 367900 | Work Order Description - 367900 - PSPM | PSPM | 1 | 388107 | WPLAN | SYS-ISOL | 2018-12-11 | 2020-07-22 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 367902 | Work Order Description - 367902 - PSPM | PSPM | 1 | 436717 | WPLAN | SYS-ISOL | 2018-12-11 | 2020-07-22 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 367904 | Work Order Description - 367904 - PSPM | PSPM | 1 | 127999 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2020-07-21 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 367906 | Work Order Description - 367906 - PSPM | PSPM | 1 | 664890 | WPLAN | SYS-ISOL | 2018-12-11 | 2020-07-18 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 367908 | Work Order Description - 367908 - PSPM | PSPM | 1 | 664889 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2020-07-18 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 367911 | Work Order Description - 367911 - PSPM | PSPM | 1 | 396429 | WPLAN | SYS-ISOL | 2018-12-11 | 2020-07-10 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 367913 | Work Order Description - 367913 - PSPM | PSPM | 1 | 393229 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2020-07-07 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 367916 | Work Order Description - 367916 - PSPM | PSPM | 1 | 396425 | WPLAN | SYS-ISOL | 2018-12-11 | 2020-07-05 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 367918 | Work Order Description - 367918 - PSPM | PSPM | 1 | 436688 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2020-07-02 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 367920 | Work Order Description - 367920 - PSPM | PSPM | 1 | 93217 | WPLAN | SYS-ISOL | 2018-12-11 | 2020-05-11 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 8
2019-03-31 | 367924 | Work Order Description - 367924 - PSPM | PSPM | 1 | 436738 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2020-05-11 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 367927 | Work Order Description - 367927 - PSPM | PSPM | 1 | 93219 | WPLAN | SYS-ISOL | 2018-12-11 | 2020-05-05 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 367930 | Work Order Description - 367930 - PSPM | PSPM | 1 | 388274 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2020-04-16 | 2019-07-13 | 2019-07-14 | 1 | INTEGRITY | MECHANICAL | 28
2019-03-31 | 367937 | Work Order Description - 367937 - PSPM | PSPM | 1 | 93223 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2020-03-29 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 367939 | Work Order Description - 367939 - PSPM | PSPM | 1 | 93225 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2020-03-27 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 367941 | Work Order Description - 367941 - PSPM | PSPM | 1 | 89542 | WPLAN | SYS-ISOL | 2018-12-11 | 2020-03-07 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 367943 | Work Order Description - 367943 - PSPM | PSPM | 1 | 393198 | WPLAN | SYS-ISOL | 2018-12-11 | 2020-03-05 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 367945 | Work Order Description - 367945 - BR | BR | 2 | 357272 | WSCHD | EQUIP-ISOL | 2018-12-13 | 2020-12-11 | 2019-12-12 | 2019-12-12 | 4 | MAINTENANCE | MECHANICAL | 34
2019-03-31 | 367947 | Work Order Description - 367947 - PSPM | PSPM | 1 | 89713 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2020-01-05 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 367949 | Work Order Description - 367949 - PSPM | PSPM | 1 | 664896 | WPLAN | SYS-ISOL | 2018-12-11 | 2019-12-15 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 367952 | Work Order Description - 367952 - PSPM | PSPM | 1 | 396279 | WPLAN | SYS-ISOL | 2018-12-11 | 2019-11-28 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 11
2019-03-31 | 367957 | Work Order Description - 367957 - PSPM | PSPM | 1 | 664918 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2019-11-21 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 367959 | Work Order Description - 367959 - PSPM | PSPM | 1 | 664964 | WPLAN | SYS-ISOL | 2018-12-11 | 2019-11-19 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 367961 | Work Order Description - 367961 - PSPM | PSPM | 1 | 375652 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2019-10-26 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 367963 | Work Order Description - 367963 - PSPM | PSPM | 1 | 74940 | WPLAN | EQUIP-ISOL | 2018-12-11 | 2019-10-26 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 368019 | Work Order Description - 368019 - CM | CM | 1 | 411321 | WSCHD | TPS | 2018-12-22 | 2020-05-29 | 2019-08-31 | 2019-08-31 | 2 | INTEGRITY | CONSTRUCTION | 29
2019-03-31 | 368041 | Work Order Description - 368041 - CM | CM | 4 | 155742 | WSCHD | NORM-OPS | 2018-12-15 | 2020-12-09 | 2019-12-10 | 2019-12-10 | 4 | INTEGRITY | FABRIC | 112
2019-03-31 | 368063 | Work Order Description - 368063 - CM | CM | 2 | 262784 | WSCHD | NORM-OPS | 2019-03-25 | 2020-03-02 | 2019-06-11 | 2019-06-11 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 368072 | Work Order Description - 368072 - CM | CM | 1 | 472798 | WPLAN | NORM-OPS | 2018-12-12 | 2019-06-12 | 2019-06-01 | 2019-06-01 | 3 | INTEGRITY | FABRIC | 6
2019-03-31 | 368076 | Work Order Description - 368076 - PM | PM | 4 | 19020 | WSCHD | EQUIP-ISOL | 2018-12-12 | 2019-06-05 | 2019-04-11 | 2019-04-11 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 368078 | Work Order Description - 368078 - PM | PM | 4 | 660951 | WSCHD | NORM-OPS | 2018-12-12 | 2019-05-12 | 2019-04-11 | 2019-04-11 | 3 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 368082 | Work Order Description - 368082 - PM | PM | 4 | 446865 | SCHD | EQUIP-ISOL | 2018-12-24 | 2020-04-06 | 2019-10-12 | 2019-10-12 | 2 | MAINTENANCE | ELECTRICAL | 32
2019-03-31 | 368088 | Work Order Description - 368088 - PSPM | PSPM | 1 | 501444 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-12 | 2019-03-30 | 2019-03-30 | 1 | INTEGRITY | INSPECTION | 411
2019-03-31 | 368090 | Work Order Description - 368090 - PSPM | PSPM | 1 | 123510 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-12 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 368094 | Work Order Description - 368094 - PSPM | PSPM | 1 | 659510 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-12 | 2019-04-11 | 2019-04-11 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 368096 | Work Order Description - 368096 - PSPM | PSPM | 1 | 659056 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-12 | 2019-04-11 | 2019-04-11 | 1 | OPERATIONS | SAFETY | 6
2019-03-31 | 368098 | Work Order Description - 368098 - PSPM | PSPM | 1 | 42961 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-12 | 2019-04-11 | 2019-04-11 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 368100 | Work Order Description - 368100 - PSPM | PSPM | 4 | 99232 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-12 | 2019-04-13 | 2019-04-14 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 368102 | Work Order Description - 368102 - PSPM | PSPM | 1 | 659510 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-12 | 2019-04-11 | 2019-04-11 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 368104 | Work Order Description - 368104 - PSPM | PSPM | 1 | 126920 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-12 | 2019-04-11 | 2019-04-11 | 1 | MAINTENANCE | ELECTRICAL | 1.5
2019-03-31 | 368106 | Work Order Description - 368106 - PM | PM | 4 | 126984 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-12 | 2019-04-11 | 2019-04-11 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 368217 | Work Order Description - 368217 - BR | BR | 2 | 453254 | SCHD | NORM-OPS | 2019-03-06 | 2019-11-13 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 368226 | Work Order Description - 368226 - CM | CM | 1 | 155742 | WSCHD | NORM-OPS | 2018-12-15 | 2020-12-10 | 2019-12-11 | 2019-12-11 | 4 | INTEGRITY | CONSTRUCTION | 42
2019-03-31 | 368238 | Work Order Description - 368238 - CM | CM | 1 | 155742 | WSCHD | NORM-OPS | 2018-12-15 | 2019-06-13 | 2019-05-18 | 2019-05-18 | 3 | INTEGRITY | CONSTRUCTION | 196
2019-03-31 | 368241 | Work Order Description - 368241 - CM | CM | 1 | 155742 | WSCHD | NORM-OPS | 2018-12-15 | 2020-12-10 | 2019-12-11 | 2019-12-11 | 4 | INTEGRITY | CONSTRUCTION | 70
2019-03-31 | 368242 | Work Order Description - 368242 - CM | CM | 4 | 155742 | WPLAN | NORM-OPS | 2018-12-15 | 2020-12-10 | 2019-12-11 | 2019-12-11 | 4 | INTEGRITY | FABRIC | 280
2019-03-31 | 368245 | Work Order Description - 368245 - CM | CM | 4 | 570144 | WSCHD | NORM-OPS | 2018-12-15 | 2019-12-12 | 2019-06-12 | 2019-06-12 | 3 | INTEGRITY | FABRIC | 392
2019-03-31 | 368246 | Work Order Description - 368246 - PSCM | PSCM | 1 | 25950 | SCHD | SYS-ISOL | 2019-03-15 | 2019-04-19 | 2019-07-13 | 2019-07-18 | 4 | MAINTENANCE | OPERATIONS | 1
2019-03-31 | 368252 | Work Order Description - 368252 - PSCM | PSCM | 1 | 254572 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-13 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 368260 | Work Order Description - 368260 - BR | BR | 4 | 185355 | SCHD | NORM-OPS | 2018-12-24 | 2020-12-10 | 2019-12-11 | 2019-12-11 | 4 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 368350 | Work Order Description - 368350 - CM | CM | 1 | 254687 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-06-13 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 368377 | Work Order Description - 368377 - PSPM | PSPM | 1 | 595880 | WSCHD | EQUIP-ISOL | 2018-12-13 | 2019-05-13 | 2019-04-12 | 2019-04-12 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 368379 | Work Order Description - 368379 - PSPM | PSPM | 1 | 416377 | SCHD | NORM-OPS | 2019-03-21 | 2019-05-13 | 2019-03-30 | 2019-03-30 | 2 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 368381 | Work Order Description - 368381 - PM | PM | 4 | 51202 | WSCHD | NORM-OPS | 2018-12-13 | 2019-05-13 | 2019-04-12 | 2019-04-12 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 368383 | Work Order Description - 368383 - PM | PM | 4 | 246173 | WSCHD | NORM-OPS | 2018-12-13 | 2019-05-13 | 2019-04-12 | 2019-04-12 | 1 | INTEGRITY | SERVICES | 2
2019-03-31 | 368385 | Work Order Description - 368385 - PM | PM | 4 | 546030 | WSCHD | NORM-OPS | 2018-12-13 | 2019-05-13 | 2019-04-12 | 2019-04-12 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 368387 | Work Order Description - 368387 - PM | PM | 4 | 652482 | WSCHD | NORM-OPS | 2018-12-13 | 2019-05-13 | 2019-04-12 | 2019-04-12 | 1 | INTEGRITY | SERVICES | 2
2019-03-31 | 368389 | Work Order Description - 368389 - PSPM | PSPM | 1 | 675037 | WSCHD | NORM-OPS | 2018-12-13 | 2019-05-13 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 368391 | Work Order Description - 368391 - PSPM | PSPM | 1 | 671829 | WSCHD | NORM-OPS | 2018-12-13 | 2019-05-13 | 2019-04-12 | 2019-04-12 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 368393 | Work Order Description - 368393 - PSPM | PSPM | 1 | 519760 | WSCHD | NORM-OPS | 2018-12-13 | 2019-05-13 | 2019-04-12 | 2019-04-12 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 368395 | Work Order Description - 368395 - PM | PM | 4 | 138182 | WSCHD | EQUIP-ISOL | 2018-12-13 | 2019-09-22 | 2019-04-12 | 2019-04-12 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 368397 | Work Order Description - 368397 - PSPM | PSPM | 1 | 408823 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-13 | 2019-04-12 | 2019-04-12 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 368399 | Work Order Description - 368399 - PSPM | PSPM | 1 | 256497 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-13 | 2019-04-12 | 2019-04-12 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 368401 | Work Order Description - 368401 - PSPM | PSPM | 1 | 401659 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-13 | 2019-04-12 | 2019-04-12 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 368403 | Work Order Description - 368403 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-13 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 368405 | Work Order Description - 368405 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-13 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 368407 | Work Order Description - 368407 - PSPM | PSPM | 1 | 254096 | SCHD | PACK-ISOL | 2018-12-24 | 2019-05-13 | 2019-04-12 | 2019-04-12 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 368409 | Work Order Description - 368409 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-13 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 368411 | Work Order Description - 368411 - PSPM | PSPM | 1 | 528211 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-13 | 2019-04-12 | 2019-04-12 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 368413 | Work Order Description - 368413 - PSPM | PSPM | 1 | 663164 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-13 | 2019-04-12 | 2019-04-12 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 368415 | Work Order Description - 368415 - PM | PM | 4 | 78461 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-10-10 | 2019-04-12 | 2019-04-12 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 368417 | Work Order Description - 368417 - PM | PM | 4 | 78464 | SCHD | EQUIP-ISOL | 2018-12-17 | 2019-09-04 | 2019-04-12 | 2019-04-12 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 368421 | Work Order Description - 368421 - PSPM | PSPM | 1 | 238048 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-13 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 368423 | Work Order Description - 368423 - PM | PM | 4 | 450541 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-13 | 2019-04-12 | 2019-04-12 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 368425 | Work Order Description - 368425 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-13 | 2019-04-13 | 2019-04-15 | 3 | MAINTENANCE | MEDIC | 21
2019-03-31 | 368602 | Work Order Description - 368602 - PSCM | PSCM | 1 | 501209 | SCHD | NORM-OPS | 2019-01-31 | 2019-07-14 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 368608 | Work Order Description - 368608 - PSCM | PSCM | 1 | 568123 | SCHD | EQUIP-ISOL | 2019-01-25 | 2020-12-11 | 2019-12-12 | 2019-12-13 | 4 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 368611 | Work Order Description - 368611 - PSCM | PSCM | 3 | 107754 | WPLAN | EQUIP-ISOL | 2018-12-21 | 2019-10-09 | 2019-05-01 | 2019-05-01 | 4 | INTEGRITY | SUBSEA | 1
2019-03-31 | 368612 | Work Order Description - 368612 - PRJ | PRJ | 3 | 555932 | SCHD | NORM-OPS | 2019-03-15 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 4 | ENGINEERING | WELLS | 48
2019-03-31 | 368615 | Work Order Description - 368615 - PSCM | PSCM | 3 | 107756 | WPLAN | PACK-ISOL | 2018-12-21 | 2019-05-20 | 2019-05-01 | 2019-05-01 | 4 | INTEGRITY | SUBSEA | 1
2019-03-31 | 368623 | Work Order Description - 368623 - CM | CM | 3 | 312683 | WSCHD | EQUIP-ISOL | 2018-12-13 | 2020-12-11 |  |  | 4 | MAINTENANCE | MECHANICAL | 0
2019-03-31 | 368632 | Work Order Description - 368632 - PSCM | PSCM | 1 | 671828 | WPLAN | NORM-OPS | 2019-03-22 | 2020-03-21 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 72
2019-03-31 | 368655 | Work Order Description - 368655 - PSPM | PSPM | 1 | 321203 | WSCHD | NORM-OPS | 2018-12-14 | 2019-05-14 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 368657 | Work Order Description - 368657 - PSPM | PSPM | 1 | 321218 | WSCHD | NORM-OPS | 2018-12-14 | 2019-05-14 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 368659 | Work Order Description - 368659 - PSPM | PSPM | 1 | 546068 | WPLAN | NORM-OPS | 2018-12-14 | 2019-05-14 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 368661 | Work Order Description - 368661 - PM | PM | 4 | 294916 | WSCHD | NORM-OPS | 2018-12-14 | 2019-05-14 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 368663 | Work Order Description - 368663 - PM | PM | 4 | 51715 | WSCHD | EQUIP-ISOL | 2018-12-14 | 2019-05-14 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 368665 | Work Order Description - 368665 - PM | PM | 4 | 137805 | WSCHD | EQUIP-ISOL | 2018-12-14 | 2019-05-14 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 368667 | Work Order Description - 368667 - PM | PM | 4 | 475799 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-14 | 2019-04-13 | 2019-04-13 | 2 | DRILLING | DRILLING | 8
2019-03-31 | 368669 | Work Order Description - 368669 - PM | PM | 4 | 482054 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-14 | 2019-04-13 | 2019-04-13 | 2 | DRILLING | DRILLING | 8
2019-03-31 | 368671 | Work Order Description - 368671 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-14 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 368675 | Work Order Description - 368675 - PM | PM | 4 | 388198 | WPLAN | EQUIP-ISOL | 2018-12-14 | 2019-05-14 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 368677 | Work Order Description - 368677 - PM | PM | 3 | 668430 | WPLAN | EQUIP-ISOL | 2018-12-14 | 2019-06-07 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 368681 | Work Order Description - 368681 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-14 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 368683 | Work Order Description - 368683 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-14 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 368685 | Work Order Description - 368685 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-14 | 2019-04-13 | 2019-04-13 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 368860 | Work Order Description - 368860 - BR | BR | 1 | 500793 | WPLAN | EQUIP-ISOL | 2018-12-31 | 2020-12-12 | 2019-04-20 | 2019-04-23 | 4 | OPERATIONS | CONSTRUCTION | 77
2019-03-31 | 368879 | Work Order Description - 368879 - BR | BR | 3 | 544962 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-01-01 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 368889 | Work Order Description - 368889 - BR | BR | 4 | 383541 | SCHD | EQUIP-ISOL | 2019-01-31 | 2020-12-12 | 2019-05-25 | 2019-05-25 | 4 | INTEGRITY | OPERATIONS | 8
2019-03-31 | 368938 | Work Order Description - 368938 - PM | PM | 2 | 572308 | WSCHD | NORM-OPS | 2018-12-15 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 368940 | Work Order Description - 368940 - PM | PM | 3 | 57143 | WSCHD | EQUIP-ISOL | 2018-12-15 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 368942 | Work Order Description - 368942 - PM | PM | 3 | 653658 | WSCHD | PACK-ISOL | 2019-01-14 | 2019-08-01 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 368944 | Work Order Description - 368944 - PM | PM | 4 | 580762 | WSCHD | NORM-OPS | 2018-12-15 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 368946 | Work Order Description - 368946 - PSPM | PSPM | 1 | 547298 | WSCHD | NORM-OPS | 2018-12-15 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 368948 | Work Order Description - 368948 - PM | PM | 4 | 666204 | SCHD | NORM-OPS | 2019-02-21 | 2019-06-08 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 368950 | Work Order Description - 368950 - PM | PM | 4 | 463925 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 368952 | Work Order Description - 368952 - PM | PM | 4 | 254546 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 368954 | Work Order Description - 368954 - PM | PM | 4 | 27912 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 368956 | Work Order Description - 368956 - PM | PM | 4 | 309735 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-08 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 368958 | Work Order Description - 368958 - PM | PM | 4 | 324812 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-08 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 368960 | Work Order Description - 368960 - PM | PM | 4 | 188826 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-08 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 368962 | Work Order Description - 368962 - PM | PM | 4 | 324812 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-08 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 368964 | Work Order Description - 368964 - PM | PM | 3 | 309968 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 368966 | Work Order Description - 368966 - PM | PM | 4 | 464001 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 368968 | Work Order Description - 368968 - PM | PM | 4 | 533275 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 368970 | Work Order Description - 368970 - PSPM | PSPM | 1 | 30532 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-15 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 368972 | Work Order Description - 368972 - PSPM | PSPM | 1 | 304029 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-15 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 368974 | Work Order Description - 368974 - PSPM | PSPM | 1 | 408913 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 368976 | Work Order Description - 368976 - PSPM | PSPM | 1 | 30441 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-15 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 368978 | Work Order Description - 368978 - PSPM | PSPM | 1 | 256590 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 368980 | Work Order Description - 368980 - PSPM | PSPM | 1 | 320573 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-15 | 2019-04-20 | 2019-04-20 | 1 | OPERATIONS | OPERATIONS | 12
2019-03-31 | 368982 | Work Order Description - 368982 - PM | PM | 4 | 324812 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-08 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 368984 | Work Order Description - 368984 - PM | PM | 4 | 309735 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-08 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 368986 | Work Order Description - 368986 - PM | PM | 1 | 446516 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 368988 | Work Order Description - 368988 - PSPM | PSPM | 1 | 29041 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-15 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 368990 | Work Order Description - 368990 - PM | PM | 4 | 501387 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-08 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | SAFETY | 15
2019-03-31 | 368992 | Work Order Description - 368992 - PM | PM | 4 | 188834 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-15 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 368994 | Work Order Description - 368994 - PM | PM | 4 | 324746 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-15 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 368996 | Work Order Description - 368996 - PM | PM | 4 | 309669 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-15 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 369000 | Work Order Description - 369000 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | SAFETY | 7
2019-03-31 | 369002 | Work Order Description - 369002 - PM | PM | 4 | 663516 | WPLAN | PACK-ISOL | 2018-12-15 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 2 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 369004 | Work Order Description - 369004 - PM | PM | 4 | 450692 | SCHD | NORM-OPS | 2018-12-17 | 2019-06-08 | 2019-04-14 | 2019-04-15 | 2 | OPERATIONS | SAFETY | 9
2019-03-31 | 369006 | Work Order Description - 369006 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 369008 | Work Order Description - 369008 - PSPM | PSPM | 1 | 669726 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 369010 | Work Order Description - 369010 - PSPM | PSPM | 1 | 528118 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 1 | INTEGRITY | SERVICES | 4
2019-03-31 | 369012 | Work Order Description - 369012 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 369014 | Work Order Description - 369014 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 369017 | Work Order Description - 369017 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 3 | MAINTENANCE | ELECTRICAL | 0.5
2019-03-31 | 369173 | Work Order Description - 369173 - CM | CM | 3 | 189031 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-16 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 369190 | Work Order Description - 369190 - BR | BR | 3 | 126211 | SCHD | TPS | 2019-02-13 | 2019-06-16 | 2019-07-13 | 2019-07-17 | 3 | MAINTENANCE | INSTRUMENTS | 70
2019-03-31 | 369227 | Work Order Description - 369227 - CM | CM | 1 | 495145 | WPLAN | EQUIP-ISOL | 2018-12-17 | 2020-12-13 | 2019-12-14 | 2019-12-14 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 369246 | Work Order Description - 369246 - CM | CM | 1 | 247533 | WPLAN | EQUIP-ISOL | 2018-12-17 | 2020-12-13 | 2019-12-14 | 2019-12-14 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 369258 | Work Order Description - 369258 - PSPM | PSPM | 1 | 356340 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 369260 | Work Order Description - 369260 - PM | PM | 4 | 18317 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 369262 | Work Order Description - 369262 - PM | PM | 4 | 18316 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 369264 | Work Order Description - 369264 - PM | PM | 4 | 666316 | WSCHD | EQUIP-ISOL | 2019-01-07 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 369266 | Work Order Description - 369266 - PM | PM | 4 | 417521 | WSCHD | EQUIP-ISOL | 2019-01-07 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 369268 | Work Order Description - 369268 - PM | PM | 4 | 50099 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 369270 | Work Order Description - 369270 - PM | PM | 4 | 50098 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 369272 | Work Order Description - 369272 - PM | PM | 4 | 411571 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 369274 | Work Order Description - 369274 - PM | PM | 4 | 358159 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 369276 | Work Order Description - 369276 - PM | PM | 4 | 540667 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 369278 | Work Order Description - 369278 - PM | PM | 4 | 678551 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 369280 | Work Order Description - 369280 - PSPM | PSPM | 1 | 657680 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 369282 | Work Order Description - 369282 - PSPM | PSPM | 1 | 137779 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 369284 | Work Order Description - 369284 - PSPM | PSPM | 1 | 137779 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 369286 | Work Order Description - 369286 - PSPM | PSPM | 1 | 261979 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 369288 | Work Order Description - 369288 - PSPM | PSPM | 1 | 57142 | WSCHD | PACK-ISOL | 2019-01-14 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 369290 | Work Order Description - 369290 - PSPM | PSPM | 1 | 360508 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 369292 | Work Order Description - 369292 - PSPM | PSPM | 1 | 53170 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 369294 | Work Order Description - 369294 - PSPM | PSPM | 1 | 53174 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 369296 | Work Order Description - 369296 - PSPM | PSPM | 1 | 54465 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 369298 | Work Order Description - 369298 - PSPM | PSPM | 1 | 53175 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 369300 | Work Order Description - 369300 - PSPM | PSPM | 1 | 409626 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 369302 | Work Order Description - 369302 - PSPM | PSPM | 1 | 360513 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 369304 | Work Order Description - 369304 - PSPM | PSPM | 1 | 53176 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 369306 | Work Order Description - 369306 - PSPM | PSPM | 1 | 360514 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 369308 | Work Order Description - 369308 - PSPM | PSPM | 1 | 53566 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 369310 | Work Order Description - 369310 - PSPM | PSPM | 1 | 410053 | WSCHD | EQUIP-ISOL | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 369312 | Work Order Description - 369312 - PM | PM | 4 | 56615 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | INTEGRITY | INSPECTION | 3
2019-03-31 | 369314 | Work Order Description - 369314 - PM | PM | 4 | 56616 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | INTEGRITY | INSPECTION | 3
2019-03-31 | 369316 | Work Order Description - 369316 - PM | PM | 4 | 535861 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | INTEGRITY | INSPECTION | 3
2019-03-31 | 369318 | Work Order Description - 369318 - PM | PM | 4 | 676299 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | INTEGRITY | INSPECTION | 3
2019-03-31 | 369320 | Work Order Description - 369320 - PM | PM | 4 | 56620 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | INTEGRITY | INSPECTION | 3
2019-03-31 | 369322 | Work Order Description - 369322 - PM | PM | 4 | 535867 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | INTEGRITY | INSPECTION | 3
2019-03-31 | 369324 | Work Order Description - 369324 - PM | PM | 4 | 676323 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | INTEGRITY | INSPECTION | 3
2019-03-31 | 369326 | Work Order Description - 369326 - PM | PM | 4 | 547429 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 369328 | Work Order Description - 369328 - PSPM | PSPM | 1 | 470877 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 369330 | Work Order Description - 369330 - PSPM | PSPM | 1 | 671828 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 369332 | Work Order Description - 369332 - PM | PM | 4 | 51871 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 369334 | Work Order Description - 369334 - PM | PM | 4 | 416308 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 369336 | Work Order Description - 369336 - PSPM | PSPM | 1 | 357608 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 369338 | Work Order Description - 369338 - PM | PM | 4 | 360243 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 369340 | Work Order Description - 369340 - PSPM | PSPM | 1 | 546068 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | SERVICES | 6
2019-03-31 | 369342 | Work Order Description - 369342 - PSPM | PSPM | 1 | 652220 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | SERVICES | 6
2019-03-31 | 369344 | Work Order Description - 369344 - PSPM | PSPM | 1 | 54069 | WSCHD | PACK-ISOL | 2019-01-07 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 369346 | Work Order Description - 369346 - PSPM | PSPM | 1 | 399508 | WSCHD | PACK-ISOL | 2019-01-07 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 369348 | Work Order Description - 369348 - PSPM | PSPM | 1 | 399512 | WSCHD | NORM-OPS | 2018-12-16 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 369350 | Work Order Description - 369350 - PM | PM | 4 | 363674 | WSCHD | PACK-ISOL | 2019-01-14 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 369352 | Work Order Description - 369352 - PM | PM | 4 | 56429 | WSCHD | EQUIP-ISOL | 2019-01-14 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 15
2019-03-31 | 369354 | Work Order Description - 369354 - PM | PM | 4 | 363675 | WSCHD | PACK-ISOL | 2019-01-14 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 369356 | Work Order Description - 369356 - PSPM | PSPM | 1 | 216248 | SCHD | PACK-ISOL | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 369359 | Work Order Description - 369359 - PSPM | PSPM | 1 | 216248 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 369361 | Work Order Description - 369361 - PM | PM | 2 | 402622 | SCHD | SYS-ISOL | 2018-12-24 | 2019-06-09 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 369363 | Work Order Description - 369363 - PM | PM | 4 | 555977 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 369365 | Work Order Description - 369365 - PSPM | PSPM | 1 | 216927 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | OPERATIONS | MEDIC | 4
2019-03-31 | 369367 | Work Order Description - 369367 - PSPM | PSPM | 1 | 503330 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 369369 | Work Order Description - 369369 - PSPM | PSPM | 1 | 189054 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 369371 | Work Order Description - 369371 - PSPM | PSPM | 1 | 325633 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 369373 | Work Order Description - 369373 - PSPM | PSPM | 1 | 81212 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 369375 | Work Order Description - 369375 - PM | PM | 4 | 481636 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-27 | 2019-04-27 | 3 | OPERATIONS | SAFETY | 15
2019-03-31 | 369377 | Work Order Description - 369377 - PM | PM | 4 | 481637 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-27 | 2019-04-27 | 3 | OPERATIONS | SAFETY | 14
2019-03-31 | 369379 | Work Order Description - 369379 - PSPM | PSPM | 1 | 185355 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 369381 | Work Order Description - 369381 - PSPM | PSPM | 1 | 128338 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | OPERATIONS | OPERATIONS | 4
2019-03-31 | 369383 | Work Order Description - 369383 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 369385 | Work Order Description - 369385 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 369387 | Work Order Description - 369387 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 369389 | Work Order Description - 369389 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 369391 | Work Order Description - 369391 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 369393 | Work Order Description - 369393 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 369395 | Work Order Description - 369395 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 369397 | Work Order Description - 369397 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 369399 | Work Order Description - 369399 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 369401 | Work Order Description - 369401 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 369403 | Work Order Description - 369403 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 369405 | Work Order Description - 369405 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 369407 | Work Order Description - 369407 - PM | PM | 4 | 479919 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 369411 | Work Order Description - 369411 - PM | PM | 4 | 119613 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 369413 | Work Order Description - 369413 - PM | PM | 4 | 403056 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-09 | 2019-04-15 | 2019-04-15 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 369415 | Work Order Description - 369415 - PM | PM | 4 | 553212 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | DRILLING | DRILLING | 4
2019-03-31 | 369417 | Work Order Description - 369417 - PM | PM | 4 | 556583 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-06-09 | 2019-04-15 | 2019-04-15 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 369419 | Work Order Description - 369419 - PM | PM | 4 | 320685 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-06-09 | 2019-04-15 | 2019-04-15 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 369421 | Work Order Description - 369421 - PM | PM | 2 | 188988 | SCHD | SYS-ISOL | 2018-12-24 | 2019-06-09 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 369423 | Work Order Description - 369423 - PM | PM | 2 | 310082 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-06-09 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 369425 | Work Order Description - 369425 - PM | PM | 4 | 320686 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-06-09 | 2019-04-15 | 2019-04-15 | 2 | DRILLING | DRILLING | 5
2019-03-31 | 369427 | Work Order Description - 369427 - PM | PM | 4 | 216510 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-16 | 2019-04-20 | 2019-04-20 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 369431 | Work Order Description - 369431 - PM | PM | 4 | 552281 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-16 | 2019-03-30 | 2019-03-30 | 2 | DRILLING | DRILLING | 8
2019-03-31 | 369433 | Work Order Description - 369433 - PM | PM | 4 | 316530 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-16 | 2019-04-20 | 2019-04-20 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 369435 | Work Order Description - 369435 - PM | PM | 4 | 556509 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-16 | 2019-04-20 | 2019-04-20 | 2 | DRILLING | DRILLING | 48
2019-03-31 | 369441 | Work Order Description - 369441 - PM | PM | 4 | 556260 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 369443 | Work Order Description - 369443 - PM | PM | 2 | 216011 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 369445 | Work Order Description - 369445 - PM | PM | 4 | 320026 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 369447 | Work Order Description - 369447 - PSPM | PSPM | 1 | 478300 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 369449 | Work Order Description - 369449 - PM | PM | 4 | 216158 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 369451 | Work Order Description - 369451 - PM | PM | 4 | 567819 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 369453 | Work Order Description - 369453 - PM | PM | 4 | 74216 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 369462 | Work Order Description - 369462 - PSPM | PSPM | 1 | 435781 | SCHD | NORM-OPS | 2019-03-18 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 369464 | Work Order Description - 369464 - PM | PM | 3 | 266661 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-16 | 2019-04-15 | 2019-04-22 | 2 | MAINTENANCE | MECHANICAL | 54
2019-03-31 | 369466 | Work Order Description - 369466 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 369468 | Work Order Description - 369468 - PSPM | PSPM | 1 | 659055 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | OPERATIONS | SAFETY | 7
2019-03-31 | 369470 | Work Order Description - 369470 - PSPM | PSPM | 1 | 659511 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 369472 | Work Order Description - 369472 - PSPM | PSPM | 1 | 659511 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 369474 | Work Order Description - 369474 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 369476 | Work Order Description - 369476 - PSPM | PSPM | 1 | 127752 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 369478 | Work Order Description - 369478 - PM | PM | 4 | 112923 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 369480 | Work Order Description - 369480 - PSPM | PSPM | 1 | 450986 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 369482 | Work Order Description - 369482 - PM | PM | 4 | 670525 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 369484 | Work Order Description - 369484 - PM | PM | 4 | 375852 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 369486 | Work Order Description - 369486 - PSPM | PSPM | 1 | 99434 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-16 | 2019-04-15 | 2019-04-16 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 370045 | Work Order Description - 370045 - BR | BR | 1 | 481746 | WPLAN | NORM-OPS | 2018-12-21 | 2019-12-17 | 2019-06-18 | 2019-06-18 | 3 | INTEGRITY | CONSTRUCTION | 7
2019-03-31 | 370051 | Work Order Description - 370051 - BR | BR | 1 | 501211 | SCHD | TPS | 2018-12-24 | 2019-06-17 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 120
2019-03-31 | 370052 | Work Order Description - 370052 - BR | BR | 3 | 442930 | SCHD | TPS | 2018-12-21 | 2019-06-17 | 2019-07-13 | 2019-07-25 | 3 | INTEGRITY | CONSTRUCTION | 87
2019-03-31 | 370064 | Work Order Description - 370064 - CM | CM | 1 | 237448 | SCHD | NORM-OPS | 2018-12-21 | 2019-12-16 | 2019-04-15 | 2019-09-18 | 3 | INTEGRITY | ELECTRICAL | 36
2019-03-31 | 370142 | Work Order Description - 370142 - PSPM | PSPM | 1 | 356349 | WSCHD | EQUIP-ISOL | 2018-12-17 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 370144 | Work Order Description - 370144 - PSPM | PSPM | 1 | 356349 | WSCHD | EQUIP-ISOL | 2018-12-17 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 370146 | Work Order Description - 370146 - PM | PM | 4 | 671079 | WSCHD | EQUIP-ISOL | 2018-12-17 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 370148 | Work Order Description - 370148 - PSPM | PSPM | 1 | 293229 | WPLAN | PACK-ISOL | 2018-12-17 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 370151 | Work Order Description - 370151 - PSPM | PSPM | 1 | 293229 | WPLAN | PACK-ISOL | 2018-12-17 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | INSTRUMENTS | 33
2019-03-31 | 370153 | Work Order Description - 370153 - PSPM | PSPM | 1 | 293229 | WPLAN | PACK-ISOL | 2018-12-17 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 370155 | Work Order Description - 370155 - PSPM | PSPM | 1 | 293229 | WSCHD | PACK-ISOL | 2019-01-12 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | INSTRUMENTS | 25
2019-03-31 | 370157 | Work Order Description - 370157 - PSPM | PSPM | 1 | 293229 | WSCHD | PACK-ISOL | 2019-01-12 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 370159 | Work Order Description - 370159 - PSPM | PSPM | 1 | 545426 | WPLAN | PACK-ISOL | 2018-12-17 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 370161 | Work Order Description - 370161 - PSPM | PSPM | 1 | 545426 | WPLAN | PACK-ISOL | 2018-12-17 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 370164 | Work Order Description - 370164 - PM | PM | 4 | 651607 | WSCHD | NORM-OPS | 2018-12-17 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 370168 | Work Order Description - 370168 - PM | PM | 4 | 481609 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-17 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 370170 | Work Order Description - 370170 - PM | PM | 2 | 401261 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-17 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 370172 | Work Order Description - 370172 - PSPM | PSPM | 1 | 30393 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-17 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 370174 | Work Order Description - 370174 - PSPM | PSPM | 1 | 30396 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-17 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 370176 | Work Order Description - 370176 - PM | PM | 4 | 476154 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 370178 | Work Order Description - 370178 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 370182 | Work Order Description - 370182 - PSPM | PSPM | 1 | 256014 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 370184 | Work Order Description - 370184 - PSPM | PSPM | 1 | 255835 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 370186 | Work Order Description - 370186 - PSPM | PSPM | 1 | 255836 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 370188 | Work Order Description - 370188 - PSPM | PSPM | 1 | 256015 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 370190 | Work Order Description - 370190 - PM | PM | 4 | 482752 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 2 | MAINTENANCE | MECHANICAL | 35
2019-03-31 | 370192 | Work Order Description - 370192 - PSPM | PSPM | 4 | 403503 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-17 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 370198 | Work Order Description - 370198 - PM | PM | 4 | 89618 | WPLAN | EQUIP-ISOL | 2018-12-17 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 370200 | Work Order Description - 370200 - PSPM | PSPM | 1 | 659511 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 370202 | Work Order Description - 370202 - PSPM | PSPM | 1 | 392215 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 370204 | Work Order Description - 370204 - PSPM | PSPM | 1 | 127459 | SCHD | NORM-OPS | 2019-02-01 | 2019-05-17 | 2019-04-16 | 2019-05-09 | 2 | INTEGRITY | INSPECTION | 336
2019-03-31 | 370206 | Work Order Description - 370206 - PSPM | PSPM | 1 | 659511 | SCHD | NORM-OPS | 2018-12-17 | 2019-05-17 | 2019-04-16 | 2019-04-16 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 370307 | Work Order Description - 370307 - CM | CM | 4 | 481746 | WSCHD | NORM-OPS | 2019-03-25 | 2020-03-02 | 2019-06-18 | 2019-06-18 | 3 | INTEGRITY | CONSTRUCTION | 7
2019-03-31 | 370334 | Work Order Description - 370334 - PSPM | PSPM | 1 | 184992 | SCHD | SUBSYS-ISOL | 2018-12-24 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 370336 | Work Order Description - 370336 - PSPM | PSPM | 1 | 568622 | SCHD | SUBSYS-ISOL | 2018-12-24 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 370338 | Work Order Description - 370338 - PSPM | PSPM | 1 | 97765 | SCHD | SUBSYS-ISOL | 2018-12-24 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 370340 | Work Order Description - 370340 - PSPM | PSPM | 1 | 185277 | SCHD | SUBSYS-ISOL | 2018-12-24 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 370342 | Work Order Description - 370342 - PSPM | PSPM | 1 | 129067 | SCHD | SUBSYS-ISOL | 2018-12-24 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 370344 | Work Order Description - 370344 - PSPM | PSPM | 1 | 184961 | SCHD | SUBSYS-ISOL | 2018-12-24 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 370346 | Work Order Description - 370346 - PSPM | PSPM | 1 | 80857 | SCHD | SUBSYS-ISOL | 2018-12-24 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 370348 | Work Order Description - 370348 - PSPM | PSPM | 1 | 99614 | SCHD | SUBSYS-ISOL | 2018-12-24 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 370350 | Work Order Description - 370350 - PSPM | PSPM | 1 | 566793 | SCHD | SUBSYS-ISOL | 2018-12-24 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 370352 | Work Order Description - 370352 - PSPM | PSPM | 1 | 473010 | SCHD | SUBSYS-ISOL | 2018-12-24 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 370354 | Work Order Description - 370354 - PSPM | PSPM | 1 | 567094 | SCHD | SUBSYS-ISOL | 2018-12-24 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 370356 | Work Order Description - 370356 - PSPM | PSPM | 1 | 472998 | SCHD | SUBSYS-ISOL | 2018-12-24 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 370358 | Work Order Description - 370358 - PSPM | PSPM | 1 | 568622 | SCHD | SUBSYS-ISOL | 2018-12-24 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 370360 | Work Order Description - 370360 - PSPM | PSPM | 1 | 185239 | SCHD | SUBSYS-ISOL | 2018-12-24 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 370403 | Work Order Description - 370403 - PSCM | PSCM | 1 | 499149 | SCHD | PACK-ISOL | 2018-12-24 | 2020-12-15 | 2019-12-16 | 2019-12-17 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 370453 | Work Order Description - 370453 - PSCM | PSCM | 1 | 403578 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-18 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | ELECTRICAL | 30
2019-03-31 | 370464 | Work Order Description - 370464 - BR | BR | 4 | 323086 | WPLAN | EQUIP-ISOL | 2018-12-31 | 2020-12-16 | 2019-12-17 | 2019-12-18 | 4 | MAINTENANCE | MECHANICAL | 32
2019-03-31 | 370465 | Work Order Description - 370465 - PM | PM | 4 | 540691 | WSCHD | NORM-OPS | 2018-12-18 | 2019-05-18 | 2019-04-17 | 2019-04-17 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 370467 | Work Order Description - 370467 - PSPM | PSPM | 1 | 697891 | WSCHD | NORM-OPS | 2018-12-18 | 2019-05-18 | 2019-04-17 | 2019-04-17 | 1 | INTEGRITY | SERVICES | 4
2019-03-31 | 370469 | Work Order Description - 370469 - PM | PM | 4 | 595916 | WSCHD | EQUIP-ISOL | 2019-01-14 | 2019-05-18 | 2019-04-17 | 2019-04-17 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 370472 | Work Order Description - 370472 - PM | PM | 4 | 481470 | WSCHD | NORM-OPS | 2018-12-18 | 2019-05-18 | 2019-04-17 | 2019-04-17 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 370474 | Work Order Description - 370474 - PSPM | PSPM | 1 | 675036 | WSCHD | NORM-OPS | 2018-12-18 | 2019-05-18 | 2019-04-17 | 2019-04-17 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 370476 | Work Order Description - 370476 - PSPM | PSPM | 1 | 361799 | WSCHD | NORM-OPS | 2018-12-18 | 2019-05-18 | 2019-04-17 | 2019-04-17 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 370478 | Work Order Description - 370478 - PSPM | PSPM | 1 | 81146 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-18 | 2019-04-17 | 2019-04-17 | 1 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 370480 | Work Order Description - 370480 - PM | PM | 4 | 446862 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-18 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | SAFETY | 4
2019-03-31 | 370482 | Work Order Description - 370482 - PSPM | PSPM | 1 | 540269 | SCHD | PACK-ISOL | 2018-12-24 | 2019-05-18 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 370484 | Work Order Description - 370484 - PM | PM | 4 | 460846 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-18 | 2019-04-17 | 2019-04-17 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 370492 | Work Order Description - 370492 - PM | PM | 4 | 100430 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-11 | 2019-04-17 | 2019-04-17 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 370494 | Work Order Description - 370494 - PSPM | PSPM | 1 | 527317 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-18 | 2019-04-17 | 2019-04-17 | 1 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 370496 | Work Order Description - 370496 - PSPM | PSPM | 1 | 659551 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-18 | 2019-04-17 | 2019-04-17 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 370498 | Work Order Description - 370498 - PM | PM | 4 | 670154 | SCHD | EQUIP-ISOL | 2018-12-21 | 2019-09-27 | 2019-05-26 | 2019-05-26 | 2 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 370500 | Work Order Description - 370500 - PSPM | PSPM | 1 | 227941 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-18 | 2019-04-17 | 2019-04-17 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 370594 | Work Order Description - 370594 - BR | BR | 1 | 226530 | WPLAN | EQUIP-ISOL | 2018-12-31 | 2020-12-16 | 2019-12-17 | 2019-12-17 | 4 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 370651 | Work Order Description - 370651 - CM | CM | 1 | 451342 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-19 | 2019-04-14 | 2019-04-24 | 3 | INTEGRITY | CONSTRUCTION | 218.5
2019-03-31 | 370745 | Work Order Description - 370745 - BR | BR | 2 | 188441 | WPLAN | SYS-ISOL | 2018-12-24 | 2019-09-14 | 2019-10-19 | 2019-10-20 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 370792 | Work Order Description - 370792 - PSPM | PSPM | 1 | 200094 | INPRG | NORM-OPS | 2019-03-24 | 2019-11-01 | 2019-03-30 | 2019-04-05 | 1 | MAINTENANCE | ELECTRICAL | 166
2019-03-31 | 370794 | Work Order Description - 370794 - PSPM | PSPM | 1 | 269155 | SCHD | NORM-OPS | 2019-01-10 | 2019-11-01 | 2019-03-30 | 2019-04-05 | 1 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 370796 | Work Order Description - 370796 - PSPM | PSPM | 1 | 269156 | SCHD | NORM-OPS | 2019-01-10 | 2019-11-01 | 2019-03-30 | 2019-04-07 | 1 | MAINTENANCE | ELECTRICAL | 275
2019-03-31 | 370798 | Work Order Description - 370798 - PSPM | PSPM | 1 | 200095 | SCHD | NORM-OPS | 2019-01-10 | 2019-11-01 | 2019-03-30 | 2019-04-07 | 1 | MAINTENANCE | ELECTRICAL | 85
2019-03-31 | 370800 | Work Order Description - 370800 - PSPM | PSPM | 1 | 269157 | SCHD | NORM-OPS | 2019-01-10 | 2020-01-01 | 2019-11-12 | 2019-11-12 | 1 | MAINTENANCE | ELECTRICAL | 320
2019-03-31 | 370802 | Work Order Description - 370802 - PSPM | PSPM | 1 | 422379 | SCHD | NORM-OPS | 2019-01-10 | 2020-01-01 | 2019-11-12 | 2019-11-12 | 1 | MAINTENANCE | ELECTRICAL | 213
2019-03-31 | 370804 | Work Order Description - 370804 - PSPM | PSPM | 1 | 200096 | SCHD | NORM-OPS | 2019-01-10 | 2020-02-01 | 2019-11-12 | 2019-11-12 | 1 | MAINTENANCE | ELECTRICAL | 402
2019-03-31 | 370806 | Work Order Description - 370806 - PSPM | PSPM | 1 | 422380 | SCHD | NORM-OPS | 2019-01-10 | 2020-02-01 | 2019-11-12 | 2019-11-12 | 1 | MAINTENANCE | ELECTRICAL | 129
2019-03-31 | 370808 | Work Order Description - 370808 - PSPM | PSPM | 1 | 422381 | SCHD | NORM-OPS | 2019-01-10 | 2020-02-01 | 2019-11-16 | 2019-11-16 | 1 | MAINTENANCE | ELECTRICAL | 324
2019-03-31 | 370810 | Work Order Description - 370810 - PSPM | PSPM | 1 | 422382 | SCHD | NORM-OPS | 2019-01-10 | 2020-03-03 | 2019-11-23 | 2019-11-23 | 1 | MAINTENANCE | ELECTRICAL | 122
2019-03-31 | 370812 | Work Order Description - 370812 - PSPM | PSPM | 1 | 269158 | SCHD | NORM-OPS | 2019-01-10 | 2020-03-03 | 2019-11-16 | 2019-11-16 | 1 | MAINTENANCE | ELECTRICAL | 336
2019-03-31 | 370814 | Work Order Description - 370814 - PSPM | PSPM | 1 | 422383 | SCHD | NORM-OPS | 2019-01-10 | 2020-03-03 | 2019-11-23 | 2019-11-23 | 1 | MAINTENANCE | ELECTRICAL | 141
2019-03-31 | 370816 | Work Order Description - 370816 - PSPM | PSPM | 1 | 422377 | SCHD | NORM-OPS | 2019-01-10 | 2019-12-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 203
2019-03-31 | 370818 | Work Order Description - 370818 - PSPM | PSPM | 1 | 422378 | SCHD | NORM-OPS | 2019-01-10 | 2019-12-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 42
2019-03-31 | 370824 | Work Order Description - 370824 - BR | BR | 3 | 176921 | SCHD | PACK-ISOL | 2019-01-25 | 2019-05-25 | 2019-03-23 | 2019-03-23 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 370841 | Work Order Description - 370841 - BR | BR | 1 | 310986 | WSCHD | NORM-OPS | 2018-12-20 | 2020-12-16 | 2019-12-17 | 2019-12-17 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 370842 | Work Order Description - 370842 - BR | BR | 1 | 247360 | WPLAN | EQUIP-ISOL | 2018-12-20 | 2020-12-16 | 2019-12-17 | 2019-12-17 | 4 | INTEGRITY | CONSTRUCTION | 9
2019-03-31 | 370845 | Work Order Description - 370845 - BR | BR | 1 | 260863 | WSCHD | NORM-OPS | 2018-12-20 | 2020-12-16 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 370847 | Work Order Description - 370847 - BR | BR | 3 | 244138 | WSCHD | NORM-OPS | 2018-12-19 | 2019-06-19 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 370867 | Work Order Description - 370867 - PSPM | PSPM | 1 | 368215 | SCHD | NORM-OPS | 2019-03-14 | 2019-04-29 | 2019-03-30 | 2019-04-04 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 370869 | Work Order Description - 370869 - PSPM | PSPM | 1 | 531855 | WSCHD | NORM-OPS | 2018-12-19 | 2019-05-19 | 2019-04-18 | 2019-04-18 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 370871 | Work Order Description - 370871 - PSPM | PSPM | 1 | 363636 | WSCHD | NORM-OPS | 2018-12-19 | 2019-05-19 | 2019-04-18 | 2019-04-18 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 370873 | Work Order Description - 370873 - PM | PM | 4 | 601923 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-19 | 2019-04-18 | 2019-04-18 | 2 | OPERATIONS | OPERATIONS | 60
2019-03-31 | 370885 | Work Order Description - 370885 - PSPM | PSPM | 1 | 255837 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-19 | 2019-04-18 | 2019-04-18 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 370887 | Work Order Description - 370887 - PSPM | PSPM | 1 | 256016 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-19 | 2019-04-18 | 2019-04-18 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 370889 | Work Order Description - 370889 - PM | PM | 4 | 256187 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-19 | 2019-04-18 | 2019-04-18 | 1 | INTEGRITY | INSPECTION | 7
2019-03-31 | 370891 | Work Order Description - 370891 - PSPM | PSPM | 1 | 123510 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-19 | 2019-04-18 | 2019-04-18 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 370901 | Work Order Description - 370901 - PSPM | PSPM | 1 | 42961 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-19 | 2019-04-18 | 2019-04-18 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 370903 | Work Order Description - 370903 - PSPM | PSPM | 4 | 99434 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-19 | 2019-04-18 | 2019-04-19 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 370905 | Work Order Description - 370905 - PSPM | PSPM | 1 | 451439 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-19 | 2019-04-18 | 2019-04-21 | 1 | OPERATIONS | OPERATIONS | 28
2019-03-31 | 370907 | Work Order Description - 370907 - PSPM | PSPM | 1 | 126920 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-19 | 2019-04-18 | 2019-04-18 | 1 | MAINTENANCE | ELECTRICAL | 1.5
2019-03-31 | 370909 | Work Order Description - 370909 - PM | PM | 4 | 227823 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-28 | 2019-05-25 | 2019-05-26 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 370911 | Work Order Description - 370911 - PM | PM | 4 | 126984 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-19 | 2019-04-18 | 2019-04-18 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 370913 | Work Order Description - 370913 - PSPM | PSPM | 1 | 227957 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-19 | 2019-04-18 | 2019-04-19 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 370915 | Work Order Description - 370915 - PSPM | PSPM | 1 | 227957 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-19 | 2019-04-18 | 2019-04-19 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 370917 | Work Order Description - 370917 - PSPM | PSPM | 1 | 227957 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-19 | 2019-04-18 | 2019-04-19 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 371079 | Work Order Description - 371079 - CM | CM | 4 | 375820 | SCHD | EQUIP-ISOL | 2018-12-22 | 2020-12-17 | 2019-12-18 | 2019-12-18 | 4 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 371084 | Work Order Description - 371084 - BR | BR | 4 | 188421 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-12-19 | 2019-06-19 | 2019-06-19 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 371089 | Work Order Description - 371089 - BR | BR | 4 | 81146 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-12-19 | 2019-06-19 | 2019-06-19 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 371095 | Work Order Description - 371095 - BR | BR | 4 | 499149 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-12-19 | 2019-06-19 | 2019-06-19 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 371109 | Work Order Description - 371109 - BR | BR | 4 | 499149 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-12-19 | 2019-06-19 | 2019-06-19 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 371111 | Work Order Description - 371111 - BR | BR | 4 | 499149 | WSCHD | EQUIP-ISOL | 2018-12-19 | 2019-06-07 |  |  | 2 | MAINTENANCE | CONSTRUCTION | 2
2019-03-31 | 371113 | Work Order Description - 371113 - BR | BR | 1 | 125754 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-20 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 371117 | Work Order Description - 371117 - BR | BR | 4 | 499149 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-12-19 | 2019-06-19 | 2019-06-19 | 3 | MAINTENANCE | ELECTRICAL | 48
2019-03-31 | 371121 | Work Order Description - 371121 - BR | BR | 4 | 499149 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-12-19 | 2019-06-19 | 2019-06-19 | 3 | MAINTENANCE | CONSTRUCTION | 42
2019-03-31 | 371127 | Work Order Description - 371127 - PSCM | PSCM | 2 | 396057 | SCHD | NORM-OPS | 2018-12-24 | 2019-03-21 | 2019-04-27 | 2019-04-27 | 4 | INTEGRITY | SUBSEA | 168
2019-03-31 | 371159 | Work Order Description - 371159 - PSCM | PSCM | 1 | 81648 | SCHD | EQUIP-ISOL | 2018-12-24 | 2020-12-17 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 371160 | Work Order Description - 371160 - CM | CM | 4 | 501444 | WPLAN | NORM-OPS | 2018-12-21 | 2019-12-19 | 2020-02-29 | 2020-03-21 | 3 | INTEGRITY | FABRIC | 150
2019-03-31 | 371173 | Work Order Description - 371173 - BR | BR | 1 | 185245 | SCHD | EQUIP-ISOL | 2018-12-22 | 2019-12-19 | 2019-06-19 | 2019-06-21 | 3 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 371177 | Work Order Description - 371177 - CM | CM | 1 | 528181 | SCHD | NORM-OPS | 2019-01-07 | 2019-12-19 | 2019-06-19 | 2019-07-15 | 3 | INTEGRITY | CONSTRUCTION | 448.5
2019-03-31 | 371196 | Work Order Description - 371196 - CM | CM | 1 | 528181 | SCHD | NORM-OPS | 2019-01-07 | 2019-06-21 | 2019-06-15 | 2019-07-09 | 3 | INTEGRITY | CONSTRUCTION | 476.5
2019-03-31 | 371238 | Work Order Description - 371238 - BR | BR | 1 | 402591 | SCHD | EQUIP-ISOL | 2018-12-24 | 2020-12-17 | 2019-12-18 | 2019-12-18 | 4 | INTEGRITY | INSTRUMENTS | 10
2019-03-31 | 371255 | Work Order Description - 371255 - PSPM | PSPM | 1 | 356351 | WSCHD | EQUIP-ISOL | 2018-12-20 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 371257 | Work Order Description - 371257 - PM | PM | 4 | 51202 | WSCHD | NORM-OPS | 2018-12-20 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 371261 | Work Order Description - 371261 - PSPM | PSPM | 1 | 657975 | SCHD | NORM-OPS | 2019-02-21 | 2019-05-07 | 2019-03-30 | 2019-04-09 | 1 | INTEGRITY | MECHANICAL | 1
2019-03-31 | 371263 | Work Order Description - 371263 - PSPM | PSPM | 1 | 53575 | WPLAN | PACK-ISOL | 2018-12-20 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | INTEGRITY | MECHANICAL | 30
2019-03-31 | 371265 | Work Order Description - 371265 - PSPM | PSPM | 1 | 294959 | SCHD | NORM-OPS | 2019-02-21 | 2019-05-20 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371267 | Work Order Description - 371267 - PSPM | PSPM | 1 | 547275 | WSCHD | NORM-OPS | 2019-01-07 | 2019-05-20 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 371269 | Work Order Description - 371269 - PSPM | PSPM | 1 | 547276 | SCHD | NORM-OPS | 2019-03-29 | 2019-05-20 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 371271 | Work Order Description - 371271 - PSPM | PSPM | 1 | 519760 | WSCHD | NORM-OPS | 2019-01-07 | 2019-05-20 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 371273 | Work Order Description - 371273 - PSPM | PSPM | 1 | 410324 | WSCHD | NORM-OPS | 2019-01-07 | 2019-05-20 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 371275 | Work Order Description - 371275 - PSPM | PSPM | 1 | 361798 | WSCHD | NORM-OPS | 2019-01-07 | 2019-05-20 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 371277 | Work Order Description - 371277 - PM | PM | 4 | 292836 | WSCHD | NORM-OPS | 2018-12-20 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 371279 | Work Order Description - 371279 - PSPM | PSPM | 1 | 546068 | WSCHD | PACK-ISOL | 2019-01-07 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | MECHANICAL | 72
2019-03-31 | 371281 | Work Order Description - 371281 - PSPM | PSPM | 1 | 578791 | SCHD | PACK-ISOL | 2018-12-24 | 2019-05-08 | 2019-03-23 | 2019-03-23 | 1 | WELLS | WELLS | 1
2019-03-31 | 371285 | Work Order Description - 371285 - PSPM | PSPM | 1 | 578829 | SCHD | PACK-ISOL | 2018-12-24 | 2019-04-30 | 2019-03-23 | 2019-03-23 | 1 | WELLS | WELLS | 1
2019-03-31 | 371287 | Work Order Description - 371287 - PSPM | PSPM | 1 | 36124 | SCHD | PACK-ISOL | 2018-12-24 | 2019-05-08 | 2019-03-23 | 2019-03-23 | 1 | WELLS | WELLS | 1
2019-03-31 | 371291 | Work Order Description - 371291 - PSPM | PSPM | 1 | 403503 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | INSTRUMENTS | 5.5
2019-03-31 | 371293 | Work Order Description - 371293 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371295 | Work Order Description - 371295 - PSPM | PSPM | 1 | 27535 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 371297 | Work Order Description - 371297 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 371299 | Work Order Description - 371299 - PSPM | PSPM | 1 | 567452 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 371301 | Work Order Description - 371301 - PSPM | PSPM | 1 | 184667 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 371303 | Work Order Description - 371303 - PSPM | PSPM | 1 | 567562 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 371305 | Work Order Description - 371305 - PSPM | PSPM | 1 | 584883 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 371307 | Work Order Description - 371307 - PSPM | PSPM | 1 | 567646 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 371309 | Work Order Description - 371309 - PSPM | PSPM | 1 | 255604 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 371311 | Work Order Description - 371311 - PSPM | PSPM | 1 | 534909 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 371313 | Work Order Description - 371313 - PM | PM | 4 | 316451 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-20 | 2019-04-20 | 2019-04-20 | 2 | DRILLING | DRILLING | 24
2019-03-31 | 371315 | Work Order Description - 371315 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-20 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 371317 | Work Order Description - 371317 - PM | PM | 4 | 555790 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-06-13 | 2019-04-19 | 2019-04-19 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 371319 | Work Order Description - 371319 - PM | PM | 4 | 499149 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 371321 | Work Order Description - 371321 - PM | PM | 4 | 325633 | SCHD | PACK-ISOL | 2018-12-24 | 2019-06-04 | 2019-04-19 | 2019-04-19 | 4 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 371327 | Work Order Description - 371327 - PM | PM | 4 | 228835 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 371329 | Work Order Description - 371329 - PSPM | PSPM | 1 | 663164 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 371333 | Work Order Description - 371333 - PSPM | PSPM | 1 | 392100 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-20 | 2019-04-19 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 371335 | Work Order Description - 371335 - PSPM | PSPM | 1 | 179515 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-20 | 2019-04-19 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 371337 | Work Order Description - 371337 - PSPM | PSPM | 1 | 527315 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 371341 | Work Order Description - 371341 - PM | PM | 4 | 443412 | SCHD | PACK-ISOL | 2019-03-22 | 2020-04-14 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 371343 | Work Order Description - 371343 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-20 | 2019-04-20 | 2019-04-22 | 3 | MAINTENANCE | MEDIC | 21
2019-03-31 | 371510 | Work Order Description - 371510 - BR | BR | 4 | 419556 | WSCHD | EQUIP-ISOL | 2019-02-07 | 2020-12-18 | 2019-12-19 | 2019-12-19 | 4 | DRILLING | DRILLING | 32
2019-03-31 | 371512 | Work Order Description - 371512 - BR | BR | 4 | 419556 | SCHD | EQUIP-ISOL | 2019-02-07 | 2020-12-18 | 2019-04-06 | 2019-04-15 | 4 | DRILLING | DRILLING | 8
2019-03-31 | 371515 | Work Order Description - 371515 - BR | BR | 4 | 66522 | WSCHD | EQUIP-ISOL | 2019-02-07 | 2020-12-18 | 2019-12-19 | 2019-12-19 | 4 | DRILLING | DRILLING | 14
2019-03-31 | 371524 | Work Order Description - 371524 - BR | BR | 4 | 18495 | SCHD | NORM-OPS | 2019-03-22 | 2020-12-18 | 2019-03-30 | 2019-03-30 | 4 | DRILLING | DRILLING | 1
2019-03-31 | 371538 | Work Order Description - 371538 - PSCM | PSCM | 4 | 411189 | SCHD | EQUIP-ISOL | 2019-03-29 | 2020-12-18 | 2019-03-30 | 2019-04-24 | 4 | DRILLING | DRILLING | 349
2019-03-31 | 371545 | Work Order Description - 371545 - BR | BR | 4 | 73300 | SCHD | SYS-ISOL | 2019-03-29 | 2019-12-20 | 2019-06-20 | 2019-06-20 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 371546 | Work Order Description - 371546 - PM | PM | 4 | 324741 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371556 | Work Order Description - 371556 - BR | BR | 4 | 419555 | WSCHD | EQUIP-ISOL | 2019-01-18 | 2020-12-18 | 2019-12-19 | 2019-12-19 | 4 | MAINTENANCE | DRILLING | 1
2019-03-31 | 371563 | Work Order Description - 371563 - BR | BR | 3 | 477561 | WSCHD | SYS-ISOL | 2019-02-06 | 2019-07-23 | 2019-02-09 | 2019-02-10 | 1 | MAINTENANCE | INSTRUMENTS | 44
2019-03-31 | 371572 | Work Order Description - 371572 - BR | BR | 2 | 262409 | WMATL | EQUIP-ISOL | 2019-01-25 | 2019-09-28 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | MECHANICAL | 92
2019-03-31 | 371583 | Work Order Description - 371583 - PM | PM | 4 | 188855 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371585 | Work Order Description - 371585 - PM | PM | 4 | 188858 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371587 | Work Order Description - 371587 - PM | PM | 4 | 309678 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371589 | Work Order Description - 371589 - PSPM | PSPM | 1 | 502744 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | SAFETY | 10
2019-03-31 | 371591 | Work Order Description - 371591 - PM | PM | 4 | 309671 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371593 | Work Order Description - 371593 - PM | PM | 4 | 498446 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371595 | Work Order Description - 371595 - PM | PM | 4 | 188835 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371597 | Work Order Description - 371597 - PM | PM | 4 | 188836 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371599 | Work Order Description - 371599 - PM | PM | 4 | 498447 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371603 | Work Order Description - 371603 - PM | PM | 4 | 188840 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371605 | Work Order Description - 371605 - PM | PM | 4 | 188839 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371607 | Work Order Description - 371607 - PM | PM | 4 | 498448 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371609 | Work Order Description - 371609 - PM | PM | 4 | 188841 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371611 | Work Order Description - 371611 - PM | PM | 4 | 188842 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371613 | Work Order Description - 371613 - PM | PM | 4 | 324747 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371615 | Work Order Description - 371615 - PM | PM | 4 | 324748 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371617 | Work Order Description - 371617 - PM | PM | 4 | 498445 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371619 | Work Order Description - 371619 - PM | PM | 4 | 188837 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371621 | Work Order Description - 371621 - PM | PM | 4 | 324782 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371623 | Work Order Description - 371623 - PM | PM | 4 | 498461 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371625 | Work Order Description - 371625 - PM | PM | 4 | 324783 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371627 | Work Order Description - 371627 - PM | PM | 4 | 498462 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371629 | Work Order Description - 371629 - PM | PM | 4 | 309706 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371631 | Work Order Description - 371631 - PM | PM | 4 | 309707 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371633 | Work Order Description - 371633 - PM | PM | 4 | 324784 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371635 | Work Order Description - 371635 - PM | PM | 4 | 324805 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371637 | Work Order Description - 371637 - PM | PM | 4 | 498466 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371639 | Work Order Description - 371639 - PM | PM | 4 | 309736 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371641 | Work Order Description - 371641 - PM | PM | 4 | 324806 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371643 | Work Order Description - 371643 - PM | PM | 4 | 309708 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371645 | Work Order Description - 371645 - PM | PM | 4 | 188856 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371647 | Work Order Description - 371647 - PM | PM | 4 | 309709 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371649 | Work Order Description - 371649 - PM | PM | 4 | 188853 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371651 | Work Order Description - 371651 - PM | PM | 4 | 324807 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371653 | Work Order Description - 371653 - PM | PM | 4 | 498463 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371655 | Work Order Description - 371655 - PM | PM | 4 | 309711 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371657 | Work Order Description - 371657 - PM | PM | 4 | 324808 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371659 | Work Order Description - 371659 - PM | PM | 4 | 324809 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371661 | Work Order Description - 371661 - PM | PM | 4 | 324810 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371663 | Work Order Description - 371663 - PM | PM | 4 | 498465 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371665 | Work Order Description - 371665 - PM | PM | 4 | 309712 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371667 | Work Order Description - 371667 - PM | PM | 4 | 309713 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371669 | Work Order Description - 371669 - PM | PM | 4 | 188857 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371671 | Work Order Description - 371671 - PM | PM | 4 | 498464 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371673 | Work Order Description - 371673 - PM | PM | 4 | 188855 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371675 | Work Order Description - 371675 - PM | PM | 4 | 324811 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371677 | Work Order Description - 371677 - PM | PM | 4 | 324812 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371679 | Work Order Description - 371679 - PM | PM | 4 | 309735 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371681 | Work Order Description - 371681 - PM | PM | 4 | 309637 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371683 | Work Order Description - 371683 - PM | PM | 4 | 188826 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371691 | Work Order Description - 371691 - PM | PM | 4 | 262537 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 371693 | Work Order Description - 371693 - PM | PM | 4 | 25182 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 371695 | Work Order Description - 371695 - PM | PM | 4 | 310099 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 371697 | Work Order Description - 371697 - PM | PM | 4 | 188825 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371699 | Work Order Description - 371699 - PM | PM | 4 | 309636 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371701 | Work Order Description - 371701 - PM | PM | 4 | 324721 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371703 | Work Order Description - 371703 - PM | PM | 4 | 324749 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371705 | Work Order Description - 371705 - PM | PM | 4 | 498449 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371711 | Work Order Description - 371711 - PM | PM | 2 | 324834 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371715 | Work Order Description - 371715 - PM | PM | 4 | 309638 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371717 | Work Order Description - 371717 - PM | PM | 4 | 309639 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371719 | Work Order Description - 371719 - PM | PM | 4 | 188843 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-01 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 371721 | Work Order Description - 371721 - PSPM | PSPM | 1 | 170113 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-05 | 2019-04-04 | 2019-04-04 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 371726 | Work Order Description - 371726 - PSPM | PSPM | 1 | 122684 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-14 | 2019-04-13 | 2019-04-13 | 1 | OPERATIONS | SAFETY | 5
2019-03-31 | 371728 | Work Order Description - 371728 - PM | PM | 2 | 482752 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | MECHANICAL | 0.75
2019-03-31 | 371738 | Work Order Description - 371738 - PSCM | PSCM | 4 | 476275 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-08-14 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 372368 | Work Order Description - 372368 - PSPM | PSPM | 1 | 51688 | WSCHD | NORM-OPS | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 372370 | Work Order Description - 372370 - PSPM | PSPM | 1 | 441401 | WSCHD | NORM-OPS | 2018-12-21 | 2019-05-21 | 2019-04-12 | 2019-04-12 | 1 | WELLS | WELLS | 3
2019-03-31 | 372377 | Work Order Description - 372377 - PM | PM | 4 | 361293 | WSCHD | EQUIP-ISOL | 2019-01-12 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | CONSTRUCTION | 10
2019-03-31 | 372380 | Work Order Description - 372380 - PSPM | PSPM | 1 | 678344 | WSCHD | EQUIP-ISOL | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 372382 | Work Order Description - 372382 - PSPM | PSPM | 1 | 545266 | WSCHD | NORM-OPS | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 372384 | Work Order Description - 372384 - PSPM | PSPM | 1 | 321203 | WSCHD | NORM-OPS | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 372386 | Work Order Description - 372386 - PSPM | PSPM | 1 | 321218 | WSCHD | NORM-OPS | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 372388 | Work Order Description - 372388 - PM | PM | 4 | 547276 | WSCHD | NORM-OPS | 2019-01-07 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 372390 | Work Order Description - 372390 - PSPM | PSPM | 1 | 547276 | WSCHD | NORM-OPS | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 372392 | Work Order Description - 372392 - PM | PM | 4 | 293029 | SCHD | NORM-OPS | 2019-03-21 | 2019-05-21 | 2019-04-06 | 2019-04-06 | 1 | OPERATIONS | SAFETY | 13
2019-03-31 | 372394 | Work Order Description - 372394 - PM | PM | 4 | 666204 | SCHD | NORM-OPS | 2019-02-21 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 372396 | Work Order Description - 372396 - PM | PM | 4 | 294916 | WSCHD | NORM-OPS | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 372398 | Work Order Description - 372398 - PSPM | PSPM | 1 | 128192 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 372400 | Work Order Description - 372400 - PM | PM | 4 | 81212 | SCHD | PACK-ISOL | 2018-12-24 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | ELECTRICAL | 18
2019-03-31 | 372404 | Work Order Description - 372404 - PSPM | PSPM | 1 | 216946 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-21 | 2019-04-13 | 2019-04-13 | 1 | OPERATIONS | SAFETY | 4
2019-03-31 | 372406 | Work Order Description - 372406 - PSPM | PSPM | 1 | 29041 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 372408 | Work Order Description - 372408 - PSPM | PSPM | 1 | 462436 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 372410 | Work Order Description - 372410 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 372412 | Work Order Description - 372412 - PSPM | PSPM | 1 | 122617 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-21 | 2019-04-13 | 2019-04-13 | 1 | OPERATIONS | SAFETY | 7
2019-03-31 | 372414 | Work Order Description - 372414 - PSPM | PSPM | 1 | 27341 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 372416 | Work Order Description - 372416 - PM | PM | 4 | 256412 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-07-02 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 372418 | Work Order Description - 372418 - PSPM | PSPM | 1 | 303827 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 372420 | Work Order Description - 372420 - PSPM | PSPM | 1 | 256565 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-21 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 372426 | Work Order Description - 372426 - PM | PM | 4 | 527603 | WPLAN | PACK-ISOL | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-28 | 2 | INTEGRITY | MECHANICAL | 60
2019-03-31 | 372428 | Work Order Description - 372428 - PM | PM | 4 | 527375 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 372430 | Work Order Description - 372430 - PM | PM | 4 | 659575 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | SAFETY | 7
2019-03-31 | 372432 | Work Order Description - 372432 - PM | PM | 4 | 659576 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | SAFETY | 7
2019-03-31 | 372434 | Work Order Description - 372434 - PM | PM | 4 | 527399 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 372436 | Work Order Description - 372436 - PM | PM | 4 | 450998 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | OPERATIONS | SAFETY | 1
2019-03-31 | 372438 | Work Order Description - 372438 - PM | PM | 4 | 450999 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | OPERATIONS | SAFETY | 1
2019-03-31 | 372440 | Work Order Description - 372440 - PSPM | PSPM | 1 | 378467 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-21 | 1 | MAINTENANCE | ELECTRICAL | 16
2019-03-31 | 372442 | Work Order Description - 372442 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 372444 | Work Order Description - 372444 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 372446 | Work Order Description - 372446 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2018-12-21 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 372607 | Work Order Description - 372607 - BR | BR | 2 | 411110 | WPLAN | TPS | 2018-12-25 | 2019-06-22 | 2020-05-02 | 2020-05-02 | 3 | MAINTENANCE | MECHANICAL | 68
2019-03-31 | 372618 | Work Order Description - 372618 - BR | BR | 4 | 411324 | WSCHD | PACK-ISOL | 2018-12-22 | 2019-12-21 | 2019-06-21 | 2019-06-21 | 3 | INTEGRITY | CONSTRUCTION | 3.5
2019-03-31 | 372621 | Work Order Description - 372621 - BR | BR | 2 | 238033 | SCHD | EQUIP-ISOL | 2018-12-21 | 2019-01-26 | 2019-04-27 | 2019-04-29 | 2 | MAINTENANCE | MECHANICAL | 17
2019-03-31 | 372638 | Work Order Description - 372638 - BR | BR | 4 | 484467 | WSCHD | EQUIP-ISOL | 2019-02-07 | 2020-12-19 | 2019-12-20 | 2019-12-20 | 4 | MAINTENANCE | DRILLING | 22
2019-03-31 | 372650 | Work Order Description - 372650 - BR | BR | 4 | 136757 | WSCHD | EQUIP-ISOL | 2019-02-07 | 2020-12-19 | 2019-12-20 | 2019-12-20 | 4 | MAINTENANCE | DRILLING | 40
2019-03-31 | 372659 | Work Order Description - 372659 - BR | BR | 4 | 246196 | WSCHD | NORM-OPS | 2019-02-07 | 2020-12-19 | 2019-12-20 | 2019-12-20 | 4 | DRILLING | DRILLING | 80
2019-03-31 | 372661 | Work Order Description - 372661 - CM | CM | 4 | 546035 | SCHD | NORM-OPS | 2018-12-22 | 2020-12-19 | 2019-04-27 | 2019-04-27 | 4 | INTEGRITY | CONSTRUCTION | 49
2019-03-31 | 372668 | Work Order Description - 372668 - PSPM | PSPM | 1 | 448768 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-18 | 2019-04-17 | 2019-04-17 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 372676 | Work Order Description - 372676 - PSPM | PSPM | 1 | 127843 | SCHD | NORM-OPS | 2018-12-22 | 2019-04-28 | 2019-04-10 | 2019-04-10 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 372678 | Work Order Description - 372678 - PSPM | PSPM | 1 | 123391 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-05-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 372680 | Work Order Description - 372680 - PSPM | PSPM | 1 | 80727 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 1 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 372690 | Work Order Description - 372690 - CM | CM | 1 | 361657 | WSCHD | NORM-OPS | 2018-12-25 | 2020-12-19 | 2019-12-20 | 2019-12-20 | 4 | INTEGRITY | SERVICES | 48
2019-03-31 | 372703 | Work Order Description - 372703 - CM | CM | 3 | 499126 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-08-06 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 372718 | Work Order Description - 372718 - PM | PM | 4 | 659514 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-03 | 2019-04-07 | 2019-04-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 372720 | Work Order Description - 372720 - PM | PM | 4 | 80369 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-04 | 2019-04-03 | 2019-04-03 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 372722 | Work Order Description - 372722 - PM | PM | 4 | 450692 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-14 | 2019-04-13 | 2019-04-13 | 1 | OPERATIONS | SAFETY | 1
2019-03-31 | 372724 | Work Order Description - 372724 - PM | PM | 4 | 378688 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 372726 | Work Order Description - 372726 - PM | PM | 4 | 659554 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 372728 | Work Order Description - 372728 - PM | PM | 4 | 450989 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 372730 | Work Order Description - 372730 - PM | PM | 4 | 450988 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 372734 | Work Order Description - 372734 - PSPM | PSPM | 1 | 450957 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-06 | 2019-04-05 | 2019-04-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 372736 | Work Order Description - 372736 - PSPM | PSPM | 1 | 450957 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-06 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 372738 | Work Order Description - 372738 - PM | PM | 4 | 266218 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-06 | 2019-04-05 | 2019-04-05 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 372740 | Work Order Description - 372740 - PM | PM | 4 | 185339 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-08 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 372742 | Work Order Description - 372742 - PM | PM | 4 | 185344 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-08 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 372744 | Work Order Description - 372744 - PM | PM | 4 | 669981 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-08 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 372746 | Work Order Description - 372746 - PM | PM | 4 | 185367 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-08 | 2019-04-16 | 2019-04-16 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 372748 | Work Order Description - 372748 - PM | PM | 4 | 436674 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-08 | 2019-04-16 | 2019-04-16 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 372750 | Work Order Description - 372750 - PM | PM | 4 | 659501 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-01 | 2019-04-07 | 2019-04-09 | 1 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 372752 | Work Order Description - 372752 - PM | PM | 4 | 450974 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-01 | 2019-04-07 | 2019-04-09 | 1 | MAINTENANCE | ELECTRICAL | 16
2019-03-31 | 372754 | Work Order Description - 372754 - PSPM | PSPM | 1 | 227935 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 372756 | Work Order Description - 372756 - PSPM | PSPM | 1 | 227935 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 372758 | Work Order Description - 372758 - PSPM | PSPM | 1 | 527367 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-03 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 372760 | Work Order Description - 372760 - PSPM | PSPM | 1 | 659514 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-03 | 2019-04-02 | 2019-04-02 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 372762 | Work Order Description - 372762 - PSPM | PSPM | 1 | 659514 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-03 | 2019-04-02 | 2019-04-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 372764 | Work Order Description - 372764 - PSPM | PSPM | 1 | 450984 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-10 | 2019-04-24 | 2019-04-24 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 372766 | Work Order Description - 372766 - PSPM | PSPM | 1 | 450984 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-10 | 2019-04-24 | 2019-04-24 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 372768 | Work Order Description - 372768 - PSPM | PSPM | 1 | 450984 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-10 | 2019-04-24 | 2019-04-24 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 372770 | Work Order Description - 372770 - PSPM | PSPM | 1 | 450984 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-10 | 2019-04-24 | 2019-04-24 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 372774 | Work Order Description - 372774 - PSPM | PSPM | 1 | 227935 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 372776 | Work Order Description - 372776 - PSPM | PSPM | 1 | 659560 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-03 | 2019-04-02 | 2019-04-03 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 372778 | Work Order Description - 372778 - PSPM | PSPM | 1 | 527367 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-03 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 372780 | Work Order Description - 372780 - PSPM | PSPM | 1 | 378468 | SCHD | EQUIP-ISOL | 2018-12-22 | 2019-05-08 | 2019-04-07 | 2019-04-07 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 372783 | Work Order Description - 372783 - PSPM | PSPM | 1 | 528118 | SCHD | PACK-ISOL | 2019-03-18 | 2019-04-30 | 2019-04-10 | 2019-04-13 | 1 | OPERATIONS | SERVICES | 32
2019-03-31 | 372785 | Work Order Description - 372785 - PSPM | PSPM | 1 | 375803 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 372787 | Work Order Description - 372787 - PSPM | PSPM | 1 | 375805 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 372789 | Work Order Description - 372789 - PSPM | PSPM | 1 | 449175 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 372791 | Work Order Description - 372791 - PSPM | PSPM | 1 | 669725 | SCHD | NORM-OPS | 2019-03-06 | 2019-05-01 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 372793 | Work Order Description - 372793 - PSPM | PSPM | 1 | 128836 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 372795 | Work Order Description - 372795 - PSPM | PSPM | 1 | 227935 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 1 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 372797 | Work Order Description - 372797 - PSPM | PSPM | 1 | 527367 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-03 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 372799 | Work Order Description - 372799 - PSPM | PSPM | 1 | 659514 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-03 | 2019-04-02 | 2019-04-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 372801 | Work Order Description - 372801 - PSPM | PSPM | 1 | 527367 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-03 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 372803 | Work Order Description - 372803 - PM | PM | 4 | 95325 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-01 | 2019-03-31 | 2019-03-31 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 372845 | Work Order Description - 372845 - PRJ | PRJ | 1 | 207744 | WPLAN | NORM-OPS | 2018-12-24 | 2019-07-20 | 2019-09-07 | 2019-09-07 | 3 | ENGINEERING | CONSTRUCTION | 14
2019-03-31 | 372878 | Work Order Description - 372878 - CM | CM | 4 | 411321 | WPLAN | NORM-OPS | 2019-01-14 | 2020-12-19 | 2019-12-20 | 2019-12-20 | 4 | INTEGRITY | SERVICES | 4
2019-03-31 | 372891 | Work Order Description - 372891 - PM | PM | 2 | 376546 | SCHD | SYS-ISOL | 2019-03-18 | 2019-08-01 | 2019-07-13 | 2019-07-19 | 1 | INTEGRITY | INSPECTION | 144
2019-03-31 | 372915 | Work Order Description - 372915 - PSCM | PSCM | 4 | 177563 | SCHD | SYS-ISOL | 2019-01-25 | 2019-06-18 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 7
2019-03-31 | 372924 | Work Order Description - 372924 - PM | PM | 4 | 51662 | WSCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 372926 | Work Order Description - 372926 - PM | PM | 2 | 572308 | WSCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 372928 | Work Order Description - 372928 - PM | PM | 4 | 18972 | WSCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 372930 | Work Order Description - 372930 - PM | PM | 4 | 355546 | WSCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 372932 | Work Order Description - 372932 - PM | PM | 4 | 18973 | WSCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 372934 | Work Order Description - 372934 - PM | PM | 4 | 355547 | WSCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 372936 | Work Order Description - 372936 - PM | PM | 4 | 18985 | WSCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 372938 | Work Order Description - 372938 - PM | PM | 4 | 355548 | WSCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 372940 | Work Order Description - 372940 - PM | PM | 4 | 267676 | WSCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 2 | OPERATIONS | SAFETY | 2
2019-03-31 | 372942 | Work Order Description - 372942 - PM | PM | 4 | 580762 | WSCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 372944 | Work Order Description - 372944 - PM | PM | 4 | 363762 | WSCHD | NORM-OPS | 2019-01-07 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | MECHANICAL | 65
2019-03-31 | 372946 | Work Order Description - 372946 - PSPM | PSPM | 1 | 481467 | WSCHD | NORM-OPS | 2019-01-07 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 1 | OPERATIONS | OPERATIONS | 15
2019-03-31 | 372948 | Work Order Description - 372948 - PM | PM | 3 | 56321 | WSCHD | PACK-ISOL | 2019-01-07 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 372950 | Work Order Description - 372950 - PM | PM | 4 | 309637 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-15 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 372952 | Work Order Description - 372952 - PM | PM | 4 | 309637 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-15 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 372954 | Work Order Description - 372954 - PM | PM | 4 | 309637 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-15 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 372956 | Work Order Description - 372956 - PM | PM | 4 | 309637 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-15 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 372958 | Work Order Description - 372958 - PM | PM | 4 | 188826 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-15 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 372960 | Work Order Description - 372960 - PM | PM | 4 | 188826 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-15 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 372962 | Work Order Description - 372962 - PM | PM | 4 | 533248 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 372964 | Work Order Description - 372964 - PM | PM | 4 | 310166 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 372966 | Work Order Description - 372966 - PM | PM | 4 | 188496 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-22 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 23.5
2019-03-31 | 372970 | Work Order Description - 372970 - PM | PM | 4 | 324915 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-22 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 7.5
2019-03-31 | 372972 | Work Order Description - 372972 - PM | PM | 4 | 188499 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-22 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 7.5
2019-03-31 | 372974 | Work Order Description - 372974 - PSPM | PSPM | 1 | 320573 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-22 | 2019-04-27 | 2019-04-27 | 1 | OPERATIONS | OPERATIONS | 12
2019-03-31 | 372976 | Work Order Description - 372976 - PM | PM | 4 | 188826 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-15 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 372978 | Work Order Description - 372978 - PM | PM | 4 | 188826 | SCHD | NORM-OPS | 2018-12-24 | 2019-06-15 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 372980 | Work Order Description - 372980 - PSPM | PSPM | 1 | 97870 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 372982 | Work Order Description - 372982 - PSPM | PSPM | 1 | 569012 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 372984 | Work Order Description - 372984 - PSPM | PSPM | 1 | 457812 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 372986 | Work Order Description - 372986 - PSPM | PSPM | 4 | 457813 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 372988 | Work Order Description - 372988 - PSPM | PSPM | 1 | 447441 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 372990 | Work Order Description - 372990 - PM | PM | 1 | 446516 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 372992 | Work Order Description - 372992 - PSPM | PSPM | 1 | 534908 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 373000 | Work Order Description - 373000 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | SAFETY | 7
2019-03-31 | 373002 | Work Order Description - 373002 - PM | PM | 4 | 659870 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 373004 | Work Order Description - 373004 - PM | PM | 3 | 387964 | WPLAN | EQUIP-ISOL | 2018-12-22 | 2019-06-15 | 2019-04-21 | 2019-04-21 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 373008 | Work Order Description - 373008 - PM | PM | 4 | 440672 | SCHD | EQUIP-ISOL | 2018-12-22 | 2019-09-13 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 373010 | Work Order Description - 373010 - PM | PM | 4 | 659501 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-22 | 4 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 373012 | Work Order Description - 373012 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 373014 | Work Order Description - 373014 - PSPM | PSPM | 1 | 669726 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 373016 | Work Order Description - 373016 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 373018 | Work Order Description - 373018 - PSPM | PSPM | 1 | 527371 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 373020 | Work Order Description - 373020 - PSPM | PSPM | 1 | 527371 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 373022 | Work Order Description - 373022 - PSPM | PSPM | 1 | 227956 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 373024 | Work Order Description - 373024 - PSPM | PSPM | 1 | 450993 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 373026 | Work Order Description - 373026 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2018-12-22 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 373201 | Work Order Description - 373201 - CM | CM | 4 | 435782 | SCHD | PACK-ISOL | 2019-01-07 | 2020-12-20 | 2019-12-21 | 2019-12-25 | 4 | MAINTENANCE | MECHANICAL | 74
2019-03-31 | 373221 | Work Order Description - 373221 - CM | CM | 4 | 204614 | WSCHD | NORM-OPS | 2018-12-25 | 2020-12-20 | 2019-12-21 | 2019-12-21 | 4 | INTEGRITY | CONSTRUCTION | 26
2019-03-31 | 373231 | Work Order Description - 373231 - CM | CM | 4 | 204614 | WSCHD | NORM-OPS | 2018-12-25 | 2020-12-20 | 2019-12-21 | 2019-12-21 | 4 | INTEGRITY | CONSTRUCTION | 4
2019-03-31 | 373234 | Work Order Description - 373234 - CM | CM | 1 | 451342 | INPRG | NORM-OPS | 2019-01-06 | 2020-12-20 | 2019-04-15 | 2020-02-05 | 4 | INTEGRITY | CONSTRUCTION | 43
2019-03-31 | 373310 | Work Order Description - 373310 - BR | BR | 3 | 555483 | SCHD | SYS-ISOL | 2019-01-25 | 2019-06-23 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 373316 | Work Order Description - 373316 - CM | CM | 4 | 237448 | WPLAN | NORM-OPS | 2019-01-07 | 2020-12-20 | 2019-12-22 | 2019-12-25 | 4 | INTEGRITY | CONSTRUCTION | 28
2019-03-31 | 373328 | Work Order Description - 373328 - PM | PM | 4 | 18317 | WSCHD | EQUIP-ISOL | 2018-12-23 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 373330 | Work Order Description - 373330 - PM | PM | 4 | 18316 | WSCHD | EQUIP-ISOL | 2018-12-23 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 373332 | Work Order Description - 373332 - PM | PM | 4 | 666316 | WSCHD | EQUIP-ISOL | 2019-01-07 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 373334 | Work Order Description - 373334 - PM | PM | 4 | 417521 | WSCHD | EQUIP-ISOL | 2019-01-07 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 373336 | Work Order Description - 373336 - PM | PM | 4 | 50099 | WSCHD | EQUIP-ISOL | 2018-12-23 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 373338 | Work Order Description - 373338 - PM | PM | 4 | 50098 | WSCHD | EQUIP-ISOL | 2018-12-23 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 373340 | Work Order Description - 373340 - PM | PM | 4 | 411571 | WSCHD | NORM-OPS | 2018-12-23 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 373342 | Work Order Description - 373342 - PM | PM | 4 | 358159 | WSCHD | NORM-OPS | 2018-12-23 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 373344 | Work Order Description - 373344 - PM | PM | 4 | 540667 | WSCHD | NORM-OPS | 2018-12-23 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 373346 | Work Order Description - 373346 - PM | PM | 4 | 678551 | WSCHD | NORM-OPS | 2018-12-23 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 373348 | Work Order Description - 373348 - PSPM | PSPM | 1 | 470877 | WSCHD | NORM-OPS | 2018-12-23 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 373350 | Work Order Description - 373350 - PM | PM | 4 | 360243 | WSCHD | NORM-OPS | 2018-12-23 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 373352 | Work Order Description - 373352 - PSPM | PSPM | 1 | 361118 | WSCHD | EQUIP-ISOL | 2019-01-12 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 373354 | Work Order Description - 373354 - PSPM | PSPM | 1 | 447441 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 373356 | Work Order Description - 373356 - PSPM | PSPM | 1 | 632455 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 373358 | Work Order Description - 373358 - PM | PM | 4 | 556260 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 373362 | Work Order Description - 373362 - PM | PM | 4 | 320026 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 373364 | Work Order Description - 373364 - PM | PM | 4 | 216158 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 373366 | Work Order Description - 373366 - PM | PM | 4 | 74216 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 373370 | Work Order Description - 373370 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 373372 | Work Order Description - 373372 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 373374 | Work Order Description - 373374 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 373376 | Work Order Description - 373376 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 373378 | Work Order Description - 373378 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 373380 | Work Order Description - 373380 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 373382 | Work Order Description - 373382 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 373384 | Work Order Description - 373384 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 373386 | Work Order Description - 373386 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 373388 | Work Order Description - 373388 - PSPM | PSPM | 1 | 378695 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-07 | 2019-04-07 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 373390 | Work Order Description - 373390 - PSPM | PSPM | 1 | 378816 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-07 | 2019-04-07 | 3 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 373392 | Work Order Description - 373392 - PSPM | PSPM | 1 | 451327 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-07 | 2019-04-07 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 373394 | Work Order Description - 373394 - PSPM | PSPM | 1 | 528139 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-07 | 2019-04-07 | 3 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 373396 | Work Order Description - 373396 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 373398 | Work Order Description - 373398 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 373400 | Work Order Description - 373400 - PSPM | PSPM | 1 | 99232 | SCHD | NORM-OPS | 2019-01-07 | 2019-05-23 | 2019-04-22 | 2019-04-23 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 373402 | Work Order Description - 373402 - PSPM | PSPM | 1 | 442313 | SCHD | EQUIP-ISOL | 2018-12-24 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 373571 | Work Order Description - 373571 - PSCM | PSCM | 4 | 247357 | WSCHD | NORM-OPS | 2018-12-25 | 2020-12-21 | 2019-12-22 | 2019-12-22 | 4 | INTEGRITY | FABRIC | 2
2019-03-31 | 373573 | Work Order Description - 373573 - BR | BR | 3 | 55288 | WMATL | NORM-OPS | 2019-02-27 | 2019-07-21 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 50
2019-03-31 | 373612 | Work Order Description - 373612 - CM | CM | 2 | 128823 | SCHD | PACK-ISOL | 2019-01-21 | 2019-06-24 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 373620 | Work Order Description - 373620 - CM | CM | 3 | 578791 | SCHD | PACK-ISOL | 2019-01-25 | 2019-12-23 | 2019-06-23 | 2019-06-23 | 3 | WELLS | INSTRUMENTS | 2
2019-03-31 | 373648 | Work Order Description - 373648 - BR | BR | 3 | 226660 | WPLAN | TPS | 2018-12-25 | 2019-12-24 | 2019-06-24 | 2019-06-24 | 3 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 373659 | Work Order Description - 373659 - PSCM | PSCM | 1 | 25403 | WMATL | EQUIP-ISOL | 2019-01-21 | 2020-12-22 | 2019-04-20 | 2019-04-22 | 4 | INTEGRITY | CONSTRUCTION | 16
2019-03-31 | 373730 | Work Order Description - 373730 - CM | CM | 3 | 36124 | SCHD | PACK-ISOL | 2019-01-25 | 2020-12-22 | 2019-12-23 | 2019-12-23 | 4 | WELLS | INSTRUMENTS | 1
2019-03-31 | 373736 | Work Order Description - 373736 - BR | BR | 1 | 538956 | WSCHD | NORM-OPS | 2018-12-31 | 2020-12-23 | 2019-12-24 | 2019-12-24 | 4 | MAINTENANCE | SAFETY | 1
2019-03-31 | 373876 | Work Order Description - 373876 - BR | BR | 4 | 447444 | SCHD | EQUIP-ISOL | 2019-01-25 | 2020-12-25 | 2019-12-26 | 2019-12-26 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 373892 | Work Order Description - 373892 - CM | CM | 4 | 482372 | INPRG | EQUIP-ISOL | 2019-03-25 | 2020-12-25 | 2019-03-30 | 2019-03-30 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 373942 | Work Order Description - 373942 - BR | BR | 4 | 568472 | WMATL | PACK-ISOL | 2019-03-14 | 2021-02-16 | 2020-02-17 | 2020-02-17 | 4 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 373994 | Work Order Description - 373994 - CM | CM | 3 | 36122 | SCHD | PACK-ISOL | 2019-01-25 | 2020-12-25 | 2019-12-26 | 2019-12-26 | 4 | WELLS | INSTRUMENTS | 4
2019-03-31 | 374021 | Work Order Description - 374021 - CM | CM | 3 | 375789 | WPLAN | EQUIP-ISOL | 2018-12-31 | 2019-06-28 | 2019-03-23 | 2019-03-24 | 3 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 374022 | Work Order Description - 374022 - CM | CM | 3 | 375789 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-12-27 | 2019-06-28 | 2019-06-28 | 3 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 374032 | Work Order Description - 374032 - PSCM | PSCM | 1 | 670525 | SCHD | EQUIP-ISOL | 2019-02-08 | 2019-08-06 | 2019-04-14 | 2019-04-16 | 3 | MAINTENANCE | MECHANICAL | 47
2019-03-31 | 374037 | Work Order Description - 374037 - CM | CM | 3 | 671641 | WSCHD | EQUIP-ISOL | 2018-12-31 | 2019-06-29 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 374078 | Work Order Description - 374078 - BR | BR | 1 | 447577 | SCHD | EQUIP-ISOL | 2019-01-31 | 2020-12-26 | 2019-12-27 | 2019-12-27 | 4 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 374108 | Work Order Description - 374108 - BR | BR | 3 | 126211 | SCHD | NORM-OPS | 2019-02-04 | 2019-03-23 | 2019-03-09 | 2019-03-09 | 2 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 374110 | Work Order Description - 374110 - BR | BR | 3 | 126211 | SCHD | NORM-OPS | 2019-02-04 | 2019-03-23 | 2019-03-09 | 2019-03-09 | 2 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 374172 | Work Order Description - 374172 - CM | CM | 3 | 375761 | SCHD | EQUIP-ISOL | 2019-01-07 | 2019-06-30 | 2019-03-30 | 2019-04-08 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 374190 | Work Order Description - 374190 - CM | CM | 4 | 185355 | WPLAN | EQUIP-ISOL | 2019-01-02 | 2020-12-27 | 2019-12-28 | 2019-12-28 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 374193 | Work Order Description - 374193 - PRJ | PRJ | 4 | 584491 | SCHD | NORM-OPS | 2019-02-13 | 2021-02-10 | 2020-04-04 | 2020-04-04 | 4 | ENGINEERING | MECHANICAL | 12
2019-03-31 | 374212 | Work Order Description - 374212 - PSCM | PSCM | 1 | 59361 | WMATL | NORM-OPS | 2019-01-03 | 2019-06-30 | 2019-05-04 | 2019-05-04 | 3 | INTEGRITY | INSTRUMENTS | 2
2019-03-31 | 374213 | Work Order Description - 374213 - BR | BR | 4 | 260246 | SCHD | EQUIP-ISOL | 2019-01-14 | 2020-12-28 | 2019-12-29 | 2019-12-29 | 4 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 374218 | Work Order Description - 374218 - BR | BR | 3 | 51132 | WSCHD | EQUIP-ISOL | 2019-01-17 | 2019-04-02 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 374297 | Work Order Description - 374297 - BR | BR | 4 | 99434 | SCHD | NORM-OPS | 2019-01-07 | 2020-12-28 | 2019-12-30 | 2019-12-30 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 374299 | Work Order Description - 374299 - BR | BR | 4 | 403972 | SCHD | NORM-OPS | 2019-01-25 | 2019-03-31 | 2019-08-24 | 2019-08-24 | 4 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 374338 | Work Order Description - 374338 - CM | CM | 3 | 21418 | WMATL | EQUIP-ISOL | 2019-01-17 | 2019-12-31 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 374366 | Work Order Description - 374366 - PRJ | PRJ | 1 | 490533 | SCHD | EQUIP-ISOL | 2019-03-12 | 2019-04-10 | 2019-03-23 | 2019-03-23 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 374413 | Work Order Description - 374413 - BR | BR | 1 | 546068 | WRISKQ | EQUIP-ISOL | 2019-01-19 | 2020-12-29 |  |  | 4 | MAINTENANCE | SERVICES | 1
2019-03-31 | 374416 | Work Order Description - 374416 - BR | BR | 3 | 556432 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 62
2019-03-31 | 374488 | Work Order Description - 374488 - PSCM | PSCM | 1 | 325633 | SCHD | EQUIP-ISOL | 2019-01-25 | 2020-12-31 | 2019-12-07 | 2019-12-07 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 374495 | Work Order Description - 374495 - BR | BR | 3 | 189042 | WMATL | EQUIP-ISOL | 2019-02-27 | 2020-12-31 | 2020-01-01 | 2020-01-01 | 4 | MAINTENANCE | MECHANICAL | 68
2019-03-31 | 374500 | Work Order Description - 374500 - BR | BR | 4 | 460235 | SCHD | EQUIP-ISOL | 2019-03-25 | 2020-01-02 | 2019-03-30 | 2019-03-30 | 3 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 374505 | Work Order Description - 374505 - BR | BR | 4 | 313512 | SCHD | EQUIP-ISOL | 2019-03-29 | 2020-01-02 | 2019-03-30 | 2019-03-30 | 3 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 374543 | Work Order Description - 374543 - CM | CM | 4 | 447441 | SCHD | NORM-OPS | 2019-01-31 | 2020-12-31 | 2020-01-01 | 2020-01-01 | 4 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 374560 | Work Order Description - 374560 - CM | CM | 3 | 409262 | WPLAN | PACK-ISOL | 2019-01-08 | 2020-01-08 | 2019-07-09 | 2019-07-09 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 374756 | Work Order Description - 374756 - PSCM | PSCM | 3 | 308255 | WSCHD | SUBSYS-ISOL | 2019-03-21 | 2019-09-03 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | INSTRUMENTS | 84
2019-03-31 | 374769 | Work Order Description - 374769 - BR | BR | 1 | 547389 | WPLAN | PACK-ISOL | 2019-01-14 | 2020-01-14 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 374841 | Work Order Description - 374841 - BR | BR | 4 | 216084 | WPLAN | EQUIP-ISOL | 2019-01-15 | 2021-01-02 | 2020-01-03 | 2020-01-03 | 4 | MAINTENANCE | DRILLING | 100
2019-03-31 | 374915 | Work Order Description - 374915 - CM | CM | 1 | 528181 | SCHD | NORM-OPS | 2019-01-21 | 2019-07-07 | 2019-04-13 | 2019-04-17 | 3 | INTEGRITY | CONSTRUCTION | 68
2019-03-31 | 374923 | Work Order Description - 374923 - CM | CM | 4 | 685304 | SCHD | NORM-OPS | 2019-01-11 | 2020-01-05 | 2019-03-30 | 2020-01-04 | 3 | MAINTENANCE | INSPECTION | 697.5
2019-03-31 | 374929 | Work Order Description - 374929 - CM | CM | 4 | 655512 | SCHD | NORM-OPS | 2019-01-07 | 2021-01-03 | 2020-01-04 | 2020-01-08 | 4 | INTEGRITY | SERVICES | 105
2019-03-31 | 374946 | Work Order Description - 374946 - CM | CM | 3 | 262786 | WSCHD | EQUIP-ISOL | 2019-03-25 | 2020-07-30 | 2019-05-04 | 2019-05-04 | 2 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 374994 | Work Order Description - 374994 - BR | BR | 3 | 544960 | SCHD | PACK-ISOL | 2019-01-25 | 2019-01-19 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | MECHANICAL | 80
2019-03-31 | 375032 | Work Order Description - 375032 - BR | BR | 4 | 664847 | SCHD | EQUIP-ISOL | 2019-01-11 | 2020-01-06 | 2019-07-07 | 2019-07-07 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 375049 | Work Order Description - 375049 - BR | BR | 4 | 100389 | SCHD | EQUIP-ISOL | 2019-01-11 | 2021-01-04 | 2020-01-05 | 2020-01-07 | 4 | MAINTENANCE | ELECTRICAL | 44
2019-03-31 | 375081 | Work Order Description - 375081 - CM | CM | 4 | 29041 | WPLAN | EQUIP-ISOL | 2019-01-09 | 2021-01-04 | 2020-01-05 | 2020-01-05 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 375149 | Work Order Description - 375149 - BR | BR | 3 | 184428 | SCHD | TPS | 2019-01-31 | 2019-04-02 | 2019-07-13 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 375177 | Work Order Description - 375177 - CM | CM | 3 | 320440 | WPLAN | TPS | 2019-01-16 | 2020-01-07 | 2019-07-08 | 2019-07-08 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 375191 | Work Order Description - 375191 - BR | BR | 3 | 138640 | SCHD | NORM-OPS | 2019-01-09 | 2019-04-02 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 375211 | Work Order Description - 375211 - PM | PM | 4 | 383541 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-07-03 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 375218 | Work Order Description - 375218 - PSCM | PSCM | 1 | 361973 | WSCHD | EQUIP-ISOL | 2019-01-12 | 2021-01-05 | 2020-01-06 | 2020-01-06 | 4 | MAINTENANCE | INSTRUMENTS | 9
2019-03-31 | 375229 | Work Order Description - 375229 - BR | BR | 3 | 446864 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-07-09 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | ELECTRICAL | 120
2019-03-31 | 375235 | Work Order Description - 375235 - CM | CM | 3 | 411322 | WPLAN | SYS-ISOL | 2019-01-14 | 2021-01-05 | 2020-01-06 | 2020-01-06 | 4 | INTEGRITY | CONSTRUCTION | 29
2019-03-31 | 375270 | Work Order Description - 375270 - BR | BR | 3 | 499154 | WSCHD | EQUIP-ISOL | 2019-01-07 | 2018-12-07 |  |  | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 375272 | Work Order Description - 375272 - BR | BR | 3 | 176573 | SCHD | TPS | 2019-01-31 | 2019-07-15 | 2019-07-13 | 2019-07-14 | 3 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 375286 | Work Order Description - 375286 - CM | CM | 3 | 403920 | WSCHD | NORM-OPS | 2019-03-25 | 2020-01-31 | 2019-08-24 | 2019-08-24 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 375302 | Work Order Description - 375302 - PSPM | PSPM | 1 | 260939 | WSCHD | EQUIP-ISOL | 2019-01-12 | 2019-04-19 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 375310 | Work Order Description - 375310 - BR | BR | 4 | 136887 | WSCHD | NORM-OPS | 2019-01-18 | 2021-01-06 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | ELECTRICAL | 16
2019-03-31 | 375347 | Work Order Description - 375347 - BR | BR | 1 | 304042 | WMATL | EQUIP-ISOL | 2019-01-17 | 2021-01-07 | 2020-01-08 | 2020-01-08 | 4 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 375358 | Work Order Description - 375358 - BR | BR | 3 | 29074 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-07-19 | 2019-07-13 | 2019-07-14 | 3 | INTEGRITY | INSTRUMENTS | 12
2019-03-31 | 375368 | Work Order Description - 375368 - BR | BR | 3 | 388194 | SCHD | EQUIP-ISOL | 2019-01-21 | 2019-07-10 | 2019-04-16 | 2019-04-17 | 3 | INTEGRITY | MECHANICAL | 6
2019-03-31 | 375375 | Work Order Description - 375375 - BR | BR | 3 | 534320 | INPRG | EQUIP-ISOL | 2019-02-18 | 2019-04-03 | 2019-02-19 | 2019-02-21 | 2 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 375380 | Work Order Description - 375380 - PM | PM | 4 | 248531 | WSCHD | EQUIP-ISOL | 2019-01-12 | 2019-05-30 | 2019-08-24 | 2019-08-24 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 375435 | Work Order Description - 375435 - CM | CM | 2 | 409872 | WPLAN | NORM-OPS | 2019-01-14 | 2019-07-11 | 2019-05-11 | 2019-05-11 | 3 | INTEGRITY | SERVICES | 6
2019-03-31 | 375521 | Work Order Description - 375521 - BR | BR | 1 | 95213 | SCHD | NORM-OPS | 2019-01-25 | 2019-07-11 | 2019-04-10 | 2019-04-10 | 3 | MAINTENANCE | ELECTRICAL | 64
2019-03-31 | 375532 | Work Order Description - 375532 - BR | BR | 4 | 273508 | WSCHD | NORM-OPS | 2019-02-22 | 2021-01-07 | 2019-04-20 | 2019-04-21 | 4 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 375541 | Work Order Description - 375541 - CM | CM | 4 | 262344 | WSCHD | SYS-ISOL | 2019-03-16 | 2021-01-07 | 2020-01-08 | 2020-01-08 | 4 | MAINTENANCE | CONSTRUCTION | 24
2019-03-31 | 375611 | Work Order Description - 375611 - PRJ | PRJ | 3 | 247357 | SCHD | NORM-OPS | 2019-01-30 | 2019-05-04 | 2019-03-30 | 2019-04-27 | 3 | INTEGRITY | INSTRUMENTS | 1
2019-03-31 | 375680 | Work Order Description - 375680 - PM | PM | 2 | 484754 | SCHD | NORM-OPS | 2019-02-22 | 2019-06-01 | 2019-04-27 | 2019-04-28 | 2 | INTEGRITY | INSPECTION | 302
2019-03-31 | 375695 | Work Order Description - 375695 - BR | BR | 1 | 99579 | SCHD | NORM-OPS | 2019-01-25 | 2021-01-12 | 2020-01-13 | 2020-01-13 | 4 | MAINTENANCE | INSTRUMENTS | 82
2019-03-31 | 375699 | Work Order Description - 375699 - PSPM | PSPM | 1 | 447441 | SCHD | PACK-ISOL | 2019-01-25 | 2019-05-25 | 2019-04-24 | 2019-04-24 | 1 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 375711 | Work Order Description - 375711 - PSPM | PSPM | 1 | 528193 | SCHD | NORM-OPS | 2019-02-01 | 2019-12-02 | 2019-11-01 | 2019-11-15 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 375717 | Work Order Description - 375717 - PSCM | PSCM | 1 | 491870 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-11 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 375722 | Work Order Description - 375722 - CM | CM | 1 | 528178 | SCHD | NORM-OPS | 2019-01-21 | 2020-01-09 | 2019-06-10 | 2019-06-11 | 3 | INTEGRITY | INSPECTION | 42
2019-03-31 | 375751 | Work Order Description - 375751 - BR | BR | 3 | 324418 | WSCHD | PACK-ISOL | 2019-01-12 | 2019-07-11 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 375776 | Work Order Description - 375776 - BR | BR | 1 | 501363 | WPLAN | NORM-OPS | 2019-01-16 | 2020-01-10 | 2019-07-11 | 2019-07-12 | 3 | INTEGRITY | FABRIC | 12
2019-03-31 | 375784 | Work Order Description - 375784 - CM | CM | 3 | 128609 | SCHD | TPS | 2019-01-21 | 2019-07-12 | 2019-07-13 | 2019-07-23 | 3 | MAINTENANCE | CONSTRUCTION | 137
2019-03-31 | 375796 | Work Order Description - 375796 - CM | CM | 1 | 528178 | SCHD | NORM-OPS | 2019-02-13 | 2020-01-10 | 2019-07-11 | 2019-07-15 | 3 | INTEGRITY | CONSTRUCTION | 112
2019-03-31 | 375806 | Work Order Description - 375806 - BR | BR | 3 | 663477 | SCHD | TPS | 2019-03-15 | 2019-07-12 | 2019-07-13 | 2019-07-31 | 3 | INTEGRITY | CONSTRUCTION | 480.5
2019-03-31 | 375810 | Work Order Description - 375810 - PRJ | PRJ | 3 | 320026 | SCHD | NORM-OPS | 2019-01-25 | 2021-01-13 | 2019-05-04 | 2019-05-04 | 4 | ENGINEERING | DRILLING | 212
2019-03-31 | 375811 | Work Order Description - 375811 - CM | CM | 3 | 254687 | SCHD | SYS-ISOL | 2019-01-31 | 2019-07-12 | 2019-06-08 | 2019-06-08 | 3 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 375814 | Work Order Description - 375814 - CM | CM | 1 | 528178 | SCHD | NORM-OPS | 2019-02-13 | 2020-01-10 | 2019-07-11 | 2019-07-19 | 3 | INTEGRITY | FABRIC | 224
2019-03-31 | 375827 | Work Order Description - 375827 - CM | CM | 1 | 671270 | WSCHD | EQUIP-ISOL | 2019-01-22 | 2020-01-10 | 2019-05-04 | 2019-05-05 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 375846 | Work Order Description - 375846 - CM | CM | 1 | 602978 | WPLAN | SUBSYS-ISOL | 2019-01-15 | 2020-01-10 | 2019-07-11 | 2019-07-11 | 3 | INTEGRITY | WELLS | 1
2019-03-31 | 375848 | Work Order Description - 375848 - CM | CM | 1 | 306818 | WPLAN | EQUIP-ISOL | 2019-02-20 | 2021-02-18 | 2021-01-06 | 2021-01-07 | 4 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 375861 | Work Order Description - 375861 - PSCM | PSCM | 1 | 78920 | WPLAN | SUBSYS-ISOL | 2019-01-15 | 2019-08-25 | 2019-08-03 | 2019-08-03 | 3 | INTEGRITY | WELLS | 1
2019-03-31 | 375869 | Work Order Description - 375869 - PSCM | PSCM | 1 | 602980 | WRISKQ | SUBSYS-ISOL | 2019-03-09 | 2021-02-23 | 2020-08-07 |  | 4 | INTEGRITY | SUBSEA | 1
2019-03-31 | 375917 | Work Order Description - 375917 - CM | CM | 4 | 180458 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-04-05 | 2019-02-21 | 2019-02-21 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 375927 | Work Order Description - 375927 - CM | CM | 3 | 20477 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-04-05 | 2019-02-23 | 2019-02-23 | 2 | INTEGRITY | INSTRUMENTS | 21
2019-03-31 | 375935 | Work Order Description - 375935 - CM | CM | 4 | 310156 | WSCHD | EQUIP-ISOL | 2019-01-11 | 2021-01-09 |  |  | 4 | MAINTENANCE | ELECTRICAL | 0
2019-03-31 | 375946 | Work Order Description - 375946 - BR | BR | 1 | 668310 | SCHD | NORM-OPS | 2019-02-13 | 2021-01-09 | 2020-01-10 | 2020-01-11 | 4 | MAINTENANCE | ELECTRICAL | 7
2019-03-31 | 375987 | Work Order Description - 375987 - PSCM | PSCM | 1 | 602979 | WPLAN | SUBSYS-ISOL | 2019-01-15 | 2021-01-09 | 2020-01-10 | 2020-01-10 | 4 | INTEGRITY | WELLS | 1
2019-03-31 | 376041 | Work Order Description - 376041 - CM | CM | 1 | 378844 | SCHD | NORM-OPS | 2019-01-21 | 2019-07-13 | 2019-04-12 | 2019-04-22 | 3 | INTEGRITY | FABRIC | 252
2019-03-31 | 376086 | Work Order Description - 376086 - CM | CM | 3 | 514559 | WPLAN | NORM-OPS | 2019-01-12 | 2020-01-12 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 376100 | Work Order Description - 376100 - CM | CM | 3 | 354360 | WSCHD | EQUIP-ISOL | 2019-01-14 | 2020-01-11 | 2019-04-16 | 2019-04-16 | 3 | WELLS | WELLS | 156
2019-03-31 | 376104 | Work Order Description - 376104 - CM | CM | 3 | 318579 | WSCHD | EQUIP-ISOL | 2019-01-14 | 2020-01-11 | 2019-04-16 | 2019-04-16 | 3 | WELLS | WELLS | 144
2019-03-31 | 376107 | Work Order Description - 376107 - CM | CM | 3 | 354363 | WSCHD | EQUIP-ISOL | 2019-01-14 | 2020-01-11 | 2019-04-21 | 2019-04-21 | 3 | WELLS | WELLS | 144
2019-03-31 | 376158 | Work Order Description - 376158 - BR | BR | 4 | 403492 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-07-13 | 2019-05-18 | 2019-05-18 | 3 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 376176 | Work Order Description - 376176 - BR | BR | 3 | 493617 | SCHD | NORM-OPS | 2019-02-13 | 2021-01-17 | 2020-01-18 | 2020-01-18 | 4 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 376229 | Work Order Description - 376229 - CM | CM | 1 | 501209 | WPLAN | NORM-OPS | 2019-02-11 | 2019-07-14 | 2019-06-22 | 2019-06-22 | 3 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 376259 | Work Order Description - 376259 - CM | CM | 3 | 74945 | SCHD | EQUIP-ISOL | 2019-03-06 | 2021-01-10 | 2020-11-29 | 2020-11-30 | 4 | WELLS | MECHANICAL | 28
2019-03-31 | 376262 | Work Order Description - 376262 - BR | BR | 3 | 465837 | SCHD | NORM-OPS | 2019-01-31 | 2021-01-11 | 2020-01-12 | 2020-01-12 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 376295 | Work Order Description - 376295 - BR | BR | 4 | 18946 | SCHD | NORM-OPS | 2019-01-17 | 2021-01-11 | 2019-04-20 | 2019-04-20 | 4 | INTEGRITY | CONSTRUCTION | 110
2019-03-31 | 376399 | Work Order Description - 376399 - BR | BR | 2 | 493618 | SCHD | EQUIP-ISOL | 2019-02-13 | 2021-01-18 | 2020-01-19 | 2020-01-19 | 4 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 376418 | Work Order Description - 376418 - PSCM | PSCM | 1 | 72943 | SCHD | PACK-ISOL | 2019-01-31 | 2020-01-14 | 2019-07-15 | 2019-07-15 | 3 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 376441 | Work Order Description - 376441 - PSCM | PSCM | 1 | 403920 | SCHD | NORM-OPS | 2019-03-20 | 2019-07-16 | 2019-04-13 | 2019-04-13 | 3 | INTEGRITY | INSPECTION | 200
2019-03-31 | 376452 | Work Order Description - 376452 - BR | BR | 4 | 669364 | SCHD | EQUIP-ISOL | 2019-01-21 | 2021-01-12 | 2019-04-10 | 2019-04-11 | 4 | MAINTENANCE | DRILLING | 8
2019-03-31 | 376456 | Work Order Description - 376456 - BR | BR | 4 | 123346 | SCHD | EQUIP-ISOL | 2019-01-21 | 2021-01-12 | 2019-04-06 | 2019-04-07 | 4 | MAINTENANCE | DRILLING | 8
2019-03-31 | 376459 | Work Order Description - 376459 - BR | BR | 4 | 669366 | SCHD | EQUIP-ISOL | 2019-01-21 | 2021-01-12 | 2019-04-08 | 2019-04-09 | 4 | MAINTENANCE | DRILLING | 8
2019-03-31 | 376462 | Work Order Description - 376462 - BR | BR | 4 | 124797 | SCHD | EQUIP-ISOL | 2019-01-21 | 2021-01-12 | 2019-04-13 | 2019-04-14 | 4 | MAINTENANCE | DRILLING | 8
2019-03-31 | 376464 | Work Order Description - 376464 - CM | CM | 4 | 237446 | SCHD | NORM-OPS | 2019-01-21 | 2019-07-16 | 2019-05-01 | 2019-05-11 | 3 | INTEGRITY | INSPECTION | 154
2019-03-31 | 376465 | Work Order Description - 376465 - BR | BR | 4 | 124982 | SCHD | EQUIP-ISOL | 2019-01-21 | 2021-01-12 | 2019-04-06 | 2019-04-07 | 4 | DRILLING | DRILLING | 12
2019-03-31 | 376469 | Work Order Description - 376469 - BR | BR | 4 | 124982 | SCHD | EQUIP-ISOL | 2019-01-21 | 2021-01-12 | 2019-04-06 | 2019-04-07 | 4 | DRILLING | DRILLING | 12
2019-03-31 | 376480 | Work Order Description - 376480 - BR | BR | 4 | 669325 | SCHD | EQUIP-ISOL | 2019-01-21 | 2021-01-12 | 2019-04-08 | 2019-04-09 | 4 | MAINTENANCE | DRILLING | 12
2019-03-31 | 376489 | Work Order Description - 376489 - BR | BR | 4 | 276633 | SCHD | EQUIP-ISOL | 2019-01-21 | 2021-01-12 | 2019-04-06 | 2019-04-08 | 4 | MAINTENANCE | DRILLING | 16
2019-03-31 | 376499 | Work Order Description - 376499 - BR | BR | 4 | 276633 | SCHD | EQUIP-ISOL | 2019-01-21 | 2021-01-12 | 2019-04-08 | 2019-04-09 | 4 | MAINTENANCE | DRILLING | 8
2019-03-31 | 376501 | Work Order Description - 376501 - BR | BR | 4 | 655155 | SCHD | EQUIP-ISOL | 2019-01-21 | 2021-01-12 | 2019-04-06 | 2019-04-07 | 4 | MAINTENANCE | DRILLING | 12
2019-03-31 | 376512 | Work Order Description - 376512 - BR | BR | 4 | 475467 | SCHD | NORM-OPS | 2019-01-25 | 2021-01-12 | 2020-01-13 | 2020-01-13 | 4 | MAINTENANCE | FABRIC | 40
2019-03-31 | 376515 | Work Order Description - 376515 - CM | CM | 4 | 128959 | SCHD | NORM-OPS | 2019-01-22 | 2021-01-12 | 2019-02-16 | 2019-02-16 | 4 | INTEGRITY | SERVICES | 251
2019-03-31 | 376722 | Work Order Description - 376722 - BR | BR | 3 | 554763 | SCHD | TPS | 2019-01-31 | 2019-07-17 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 376756 | Work Order Description - 376756 - CM | CM | 4 | 685304 | SCHD | NORM-OPS | 2019-03-08 | 2021-01-14 | 2019-07-20 | 2019-07-20 | 4 | MAINTENANCE | CONSTRUCTION | 134
2019-03-31 | 376767 | Work Order Description - 376767 - BR | BR | 1 | 556337 | WPLAN | NORM-OPS | 2019-01-16 | 2019-07-17 | 2019-06-22 | 2019-06-22 | 3 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 376770 | Work Order Description - 376770 - CM | CM | 1 | 368322 | WSCHD | NORM-OPS | 2019-01-16 | 2019-12-01 | 2019-04-16 | 2019-04-16 | 3 | INTEGRITY | INSPECTION | 105
2019-03-31 | 376797 | Work Order Description - 376797 - CM | CM | 4 | 383066 | SCHD | PACK-ISOL | 2019-03-06 | 2019-07-17 | 2019-05-07 | 2019-05-08 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 376812 | Work Order Description - 376812 - CM | CM | 4 | 325633 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2021-01-13 |  |  | 4 | MAINTENANCE | MECHANICAL | 0
2019-03-31 | 376833 | Work Order Description - 376833 - CM | CM | 3 | 491879 | WMATL | EQUIP-ISOL | 2019-03-29 | 2020-01-15 | 2019-07-16 | 2019-07-16 | 3 | MAINTENANCE | INSTRUMENTS | 56
2019-03-31 | 376847 | Work Order Description - 376847 - CM | CM | 3 | 188972 | WMATL | TPS | 2019-03-29 | 2019-07-17 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 105
2019-03-31 | 376862 | Work Order Description - 376862 - CM | CM | 2 | 492146 | WMATL | SYS-ISOL | 2019-03-29 | 2020-01-16 | 2019-07-17 | 2019-07-17 | 3 | MAINTENANCE | INSTRUMENTS | 92
2019-03-31 | 376866 | Work Order Description - 376866 - CM | CM | 4 | 368279 | SCHD | NORM-OPS | 2019-01-22 | 2020-01-15 | 2019-04-13 | 2019-04-13 | 3 | INTEGRITY | INSPECTION | 6
2019-03-31 | 376870 | Work Order Description - 376870 - PSPM | PSPM | 1 | 657125 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 376872 | Work Order Description - 376872 - PSPM | PSPM | 1 | 657125 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 376874 | Work Order Description - 376874 - PSPM | PSPM | 1 | 657125 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 376876 | Work Order Description - 376876 - PSPM | PSPM | 1 | 657125 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 376878 | Work Order Description - 376878 - PSPM | PSPM | 1 | 657125 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 376880 | Work Order Description - 376880 - PSPM | PSPM | 1 | 657125 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 376882 | Work Order Description - 376882 - PSPM | PSPM | 1 | 657126 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 376884 | Work Order Description - 376884 - PSPM | PSPM | 1 | 540547 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 376890 | Work Order Description - 376890 - PSPM | PSPM | 1 | 51164 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 376892 | Work Order Description - 376892 - PSPM | PSPM | 1 | 656067 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376894 | Work Order Description - 376894 - PSPM | PSPM | 1 | 408377 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-05-31 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 376896 | Work Order Description - 376896 - PSPM | PSPM | 1 | 408410 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 376898 | Work Order Description - 376898 - PSPM | PSPM | 1 | 489653 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 376900 | Work Order Description - 376900 - PSPM | PSPM | 1 | 480139 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-11 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 376902 | Work Order Description - 376902 - PSPM | PSPM | 1 | 33417 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 376904 | Work Order Description - 376904 - PSPM | PSPM | 1 | 480139 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 376906 | Work Order Description - 376906 - PSPM | PSPM | 1 | 267677 | SCHD | EQUIP-ISOL | 2019-03-21 | 2019-06-03 | 2019-04-02 | 2019-04-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 376908 | Work Order Description - 376908 - PSPM | PSPM | 1 | 53985 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376910 | Work Order Description - 376910 - PSPM | PSPM | 1 | 357622 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376912 | Work Order Description - 376912 - PSPM | PSPM | 1 | 656136 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376914 | Work Order Description - 376914 - PSPM | PSPM | 1 | 679184 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-01 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 376917 | Work Order Description - 376917 - PSPM | PSPM | 1 | 679184 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-01 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 376919 | Work Order Description - 376919 - PSPM | PSPM | 1 | 679184 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-01 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 376921 | Work Order Description - 376921 - PSPM | PSPM | 1 | 314269 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 376923 | Work Order Description - 376923 - PSPM | PSPM | 1 | 520075 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376925 | Work Order Description - 376925 - PSPM | PSPM | 1 | 679204 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 376927 | Work Order Description - 376927 - PM | PM | 4 | 318813 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-16 | 2019-05-01 | 2019-05-01 | 4 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 376932 | Work Order Description - 376932 - PSPM | PSPM | 1 | 661008 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 1 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 376934 | Work Order Description - 376934 - PM | PM | 4 | 650444 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 3 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 376936 | Work Order Description - 376936 - PM | PM | 4 | 356949 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376938 | Work Order Description - 376938 - PM | PM | 4 | 356950 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376940 | Work Order Description - 376940 - PM | PM | 4 | 541015 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376942 | Work Order Description - 376942 - PM | PM | 4 | 680978 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376944 | Work Order Description - 376944 - PM | PM | 4 | 541013 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376946 | Work Order Description - 376946 - PM | PM | 4 | 356948 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376948 | Work Order Description - 376948 - PM | PM | 4 | 356950 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376950 | Work Order Description - 376950 - PM | PM | 4 | 541015 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376952 | Work Order Description - 376952 - PM | PM | 4 | 361418 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 376954 | Work Order Description - 376954 - PM | PM | 4 | 541013 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376956 | Work Order Description - 376956 - PM | PM | 4 | 356948 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376958 | Work Order Description - 376958 - PM | PM | 4 | 356950 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376960 | Work Order Description - 376960 - PM | PM | 4 | 541015 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376962 | Work Order Description - 376962 - PM | PM | 4 | 545577 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 376964 | Work Order Description - 376964 - PM | PM | 4 | 674222 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-06-26 | 2019-05-02 | 2019-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 376969 | Work Order Description - 376969 - PM | PM | 4 | 137550 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-21 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 376971 | Work Order Description - 376971 - PM | PM | 4 | 471679 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-21 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 376973 | Work Order Description - 376973 - PM | PM | 4 | 356946 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376975 | Work Order Description - 376975 - PM | PM | 4 | 356949 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376977 | Work Order Description - 376977 - PM | PM | 4 | 356949 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376979 | Work Order Description - 376979 - PM | PM | 4 | 308894 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376983 | Work Order Description - 376983 - PM | PM | 4 | 51531 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376985 | Work Order Description - 376985 - PM | PM | 4 | 357358 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-03 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 376987 | Work Order Description - 376987 - PSPM | PSPM | 1 | 292677 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 376989 | Work Order Description - 376989 - PSPM | PSPM | 1 | 457573 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | OPERATIONS | SAFETY | 2
2019-03-31 | 376991 | Work Order Description - 376991 - PM | PM | 4 | 356949 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376993 | Work Order Description - 376993 - PM | PM | 4 | 356949 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376995 | Work Order Description - 376995 - PM | PM | 4 | 356949 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 376997 | Work Order Description - 376997 - PM | PM | 4 | 356949 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 376999 | Work Order Description - 376999 - PM | PM | 4 | 308919 | SCHD | NORM-OPS | 2019-03-20 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377001 | Work Order Description - 377001 - PM | PM | 4 | 671294 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377003 | Work Order Description - 377003 - PM | PM | 4 | 308898 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377005 | Work Order Description - 377005 - PM | PM | 4 | 18317 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377007 | Work Order Description - 377007 - PM | PM | 4 | 18317 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377009 | Work Order Description - 377009 - PM | PM | 4 | 18317 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377011 | Work Order Description - 377011 - PM | PM | 4 | 18316 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377013 | Work Order Description - 377013 - PM | PM | 4 | 18316 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377015 | Work Order Description - 377015 - PM | PM | 4 | 18316 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377017 | Work Order Description - 377017 - PM | PM | 4 | 666316 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377019 | Work Order Description - 377019 - PM | PM | 4 | 666316 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377021 | Work Order Description - 377021 - PM | PM | 4 | 666316 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377023 | Work Order Description - 377023 - PM | PM | 4 | 417521 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377025 | Work Order Description - 377025 - PM | PM | 4 | 417521 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377027 | Work Order Description - 377027 - PM | PM | 4 | 417521 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377029 | Work Order Description - 377029 - PM | PM | 4 | 50099 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377031 | Work Order Description - 377031 - PM | PM | 4 | 50099 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377033 | Work Order Description - 377033 - PM | PM | 4 | 50099 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377035 | Work Order Description - 377035 - PM | PM | 4 | 50098 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377037 | Work Order Description - 377037 - PM | PM | 4 | 50098 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377039 | Work Order Description - 377039 - PM | PM | 4 | 50098 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377041 | Work Order Description - 377041 - PM | PM | 4 | 411571 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377043 | Work Order Description - 377043 - PM | PM | 4 | 411571 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377045 | Work Order Description - 377045 - PM | PM | 4 | 411571 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377047 | Work Order Description - 377047 - PM | PM | 4 | 358159 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377049 | Work Order Description - 377049 - PM | PM | 4 | 358159 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377051 | Work Order Description - 377051 - PM | PM | 4 | 358159 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377053 | Work Order Description - 377053 - PSPM | PSPM | 1 | 273469 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 377055 | Work Order Description - 377055 - PM | PM | 4 | 490234 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-07-01 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377057 | Work Order Description - 377057 - PM | PM | 4 | 540667 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377059 | Work Order Description - 377059 - PM | PM | 4 | 540667 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377061 | Work Order Description - 377061 - PM | PM | 4 | 540667 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377063 | Work Order Description - 377063 - PM | PM | 4 | 51202 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377065 | Work Order Description - 377065 - PM | PM | 4 | 51202 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-03 | 2019-05-03 | 2019-05-03 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377067 | Work Order Description - 377067 - PM | PM | 4 | 51202 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377069 | Work Order Description - 377069 - PM | PM | 4 | 678551 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377071 | Work Order Description - 377071 - PM | PM | 4 | 678551 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377073 | Work Order Description - 377073 - PM | PM | 4 | 678551 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377075 | Work Order Description - 377075 - PM | PM | 4 | 540691 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-25 | 2019-04-24 | 2019-04-24 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377077 | Work Order Description - 377077 - PM | PM | 4 | 540691 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377079 | Work Order Description - 377079 - PM | PM | 4 | 540691 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-08 | 2019-05-08 | 2019-05-08 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377081 | Work Order Description - 377081 - PM | PM | 4 | 540691 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377083 | Work Order Description - 377083 - PSPM | PSPM | 1 | 697891 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | INTEGRITY | SERVICES | 4
2019-03-31 | 377085 | Work Order Description - 377085 - PM | PM | 2 | 580380 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 377087 | Work Order Description - 377087 - PM | PM | 2 | 572308 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 377089 | Work Order Description - 377089 - PM | PM | 2 | 572308 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 377091 | Work Order Description - 377091 - PM | PM | 2 | 572308 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 377093 | Work Order Description - 377093 - PSPM | PSPM | 1 | 19090 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 377095 | Work Order Description - 377095 - PM | PM | 4 | 51214 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-06-24 | 2019-04-30 | 2019-04-30 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 377098 | Work Order Description - 377098 - PM | PM | 4 | 51215 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-07-01 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 26
2019-03-31 | 377101 | Work Order Description - 377101 - PM | PM | 4 | 678552 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-07-08 | 2019-05-14 | 2019-05-14 | 2 | MAINTENANCE | INSTRUMENTS | 26
2019-03-31 | 377104 | Work Order Description - 377104 - PM | PM | 4 | 674225 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377106 | Work Order Description - 377106 - PM | PM | 4 | 357077 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377108 | Work Order Description - 377108 - PM | PM | 4 | 314532 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377110 | Work Order Description - 377110 - PM | PM | 4 | 357078 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377112 | Work Order Description - 377112 - PM | PM | 4 | 674226 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377114 | Work Order Description - 377114 - PSPM | PSPM | 1 | 296636 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 377117 | Work Order Description - 377117 - PSPM | PSPM | 1 | 457538 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 377119 | Work Order Description - 377119 - PSPM | PSPM | 1 | 657680 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 377121 | Work Order Description - 377121 - PM | PM | 4 | 361415 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377123 | Work Order Description - 377123 - PM | PM | 4 | 361417 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377125 | Work Order Description - 377125 - PM | PM | 3 | 361420 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377127 | Work Order Description - 377127 - PM | PM | 4 | 541013 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377129 | Work Order Description - 377129 - PM | PM | 4 | 243523 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377131 | Work Order Description - 377131 - PM | PM | 4 | 541013 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377133 | Work Order Description - 377133 - PM | PM | 4 | 356948 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377135 | Work Order Description - 377135 - PM | PM | 4 | 356950 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377137 | Work Order Description - 377137 - PM | PM | 4 | 541015 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377139 | Work Order Description - 377139 - PM | PM | 4 | 680978 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377141 | Work Order Description - 377141 - PM | PM | 4 | 354350 | SCHD | NORM-OPS | 2019-02-21 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 377143 | Work Order Description - 377143 - PM | PM | 4 | 481470 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-25 | 2019-04-24 | 2019-04-24 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 377145 | Work Order Description - 377145 - PM | PM | 4 | 481470 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 377147 | Work Order Description - 377147 - PM | PM | 4 | 481470 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-08 | 2019-05-08 | 2019-05-08 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 377149 | Work Order Description - 377149 - PM | PM | 4 | 481470 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 377151 | Work Order Description - 377151 - PM | PM | 4 | 541013 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377153 | Work Order Description - 377153 - PM | PM | 4 | 356948 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377155 | Work Order Description - 377155 - PSPM | PSPM | 1 | 308460 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377157 | Work Order Description - 377157 - PSPM | PSPM | 1 | 308461 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377159 | Work Order Description - 377159 - PSPM | PSPM | 1 | 308461 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 377161 | Work Order Description - 377161 - PSPM | PSPM | 1 | 308460 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 377163 | Work Order Description - 377163 - PSPM | PSPM | 1 | 545222 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 377165 | Work Order Description - 377165 - PSPM | PSPM | 1 | 674740 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 377167 | Work Order Description - 377167 - PM | PM | 2 | 305395 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 2 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 377170 | Work Order Description - 377170 - PSPM | PSPM | 1 | 671539 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 377172 | Work Order Description - 377172 - PM | PM | 2 | 321199 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-07-04 | 2019-05-10 | 2019-05-10 | 2 | MAINTENANCE | INSTRUMENTS | 35
2019-03-31 | 377174 | Work Order Description - 377174 - PM | PM | 4 | 314269 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 377176 | Work Order Description - 377176 - PM | PM | 3 | 363614 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377178 | Work Order Description - 377178 - PM | PM | 4 | 531789 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-08-21 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 377180 | Work Order Description - 377180 - PM | PM | 4 | 595820 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 377182 | Work Order Description - 377182 - PM | PM | 2 | 33427 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-21 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 377186 | Work Order Description - 377186 - PM | PM | 4 | 249534 | SCHD | NORM-OPS | 2019-02-21 | 2019-06-19 | 2019-04-25 | 2019-04-25 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 377190 | Work Order Description - 377190 - PM | PM | 4 | 261768 | WSCHD | NORM-OPS | 2019-01-17 | 2019-06-08 | 2019-05-08 | 2019-05-08 | 2 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 377192 | Work Order Description - 377192 - PM | PM | 1 | 540396 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 377194 | Work Order Description - 377194 - PM | PM | 4 | 361285 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-03 | 2019-05-03 | 2019-05-03 | 1 | INTEGRITY | CONSTRUCTION | 6
2019-03-31 | 377203 | Work Order Description - 377203 - PM | PM | 4 | 33430 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 377205 | Work Order Description - 377205 - PSPM | PSPM | 1 | 57930 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-25 | 2019-04-24 | 2019-04-24 | 1 | MAINTENANCE | INSTRUMENTS | 47
2019-03-31 | 377209 | Work Order Description - 377209 - PSPM | PSPM | 1 | 595630 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-03 | 2019-05-03 | 2019-05-03 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 377211 | Work Order Description - 377211 - PM | PM | 4 | 547429 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-08-12 | 2019-04-25 | 2019-04-25 | 2 | MAINTENANCE | ELECTRICAL | 45
2019-03-31 | 377220 | Work Order Description - 377220 - PSPM | PSPM | 1 | 357244 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 377222 | Work Order Description - 377222 - PSPM | PSPM | 1 | 137779 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 377224 | Work Order Description - 377224 - PSPM | PSPM | 1 | 399721 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-06-14 | 2019-05-14 | 2019-05-14 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 377226 | Work Order Description - 377226 - PM | PM | 3 | 54832 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-09-01 | 2019-05-15 | 2019-05-15 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 377228 | Work Order Description - 377228 - PM | PM | 3 | 409967 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-09-01 | 2019-05-15 | 2019-05-15 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 377230 | Work Order Description - 377230 - PM | PM | 3 | 54419 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-10-07 | 2019-05-15 | 2019-05-15 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377232 | Work Order Description - 377232 - PM | PM | 3 | 409596 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-08-27 | 2019-05-10 | 2019-05-10 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377234 | Work Order Description - 377234 - PSPM | PSPM | 1 | 57130 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377236 | Work Order Description - 377236 - PSPM | PSPM | 1 | 54276 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377238 | Work Order Description - 377238 - PSPM | PSPM | 1 | 261813 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377240 | Work Order Description - 377240 - PM | PM | 3 | 54212 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377242 | Work Order Description - 377242 - PM | PM | 3 | 54224 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377244 | Work Order Description - 377244 - PM | PM | 3 | 360298 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377246 | Work Order Description - 377246 - PSPM | PSPM | 1 | 360357 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377248 | Work Order Description - 377248 - PSPM | PSPM | 1 | 57148 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377250 | Work Order Description - 377250 - PSPM | PSPM | 1 | 54324 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377252 | Work Order Description - 377252 - PSPM | PSPM | 1 | 262031 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377254 | Work Order Description - 377254 - PM | PM | 3 | 54289 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377256 | Work Order Description - 377256 - PM | PM | 3 | 360351 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377258 | Work Order Description - 377258 - PM | PM | 3 | 360356 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377260 | Work Order Description - 377260 - PM | PM | 4 | 54323 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377262 | Work Order Description - 377262 - PM | PM | 4 | 248459 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 377264 | Work Order Description - 377264 - PSPM | PSPM | 1 | 650444 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | OPERATIONS | OPERATIONS | 15
2019-03-31 | 377266 | Work Order Description - 377266 - PSPM | PSPM | 1 | 409597 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377268 | Work Order Description - 377268 - PSPM | PSPM | 1 | 360518 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377270 | Work Order Description - 377270 - PM | PM | 3 | 357395 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-10-28 | 2019-04-30 | 2019-04-30 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377272 | Work Order Description - 377272 - PM | PM | 4 | 361228 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 377274 | Work Order Description - 377274 - PM | PM | 4 | 248493 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 377276 | Work Order Description - 377276 - PM | PM | 3 | 53569 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-10-28 | 2019-04-30 | 2019-04-30 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377278 | Work Order Description - 377278 - PSPM | PSPM | 1 | 53304 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377280 | Work Order Description - 377280 - PSPM | PSPM | 1 | 53305 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377282 | Work Order Description - 377282 - PSPM | PSPM | 1 | 357391 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377284 | Work Order Description - 377284 - PM | PM | 3 | 410055 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-10-28 | 2019-04-30 | 2019-04-30 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377286 | Work Order Description - 377286 - PM | PM | 3 | 409760 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377288 | Work Order Description - 377288 - PM | PM | 3 | 409761 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377290 | Work Order Description - 377290 - PM | PM | 3 | 360591 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377292 | Work Order Description - 377292 - PSPM | PSPM | 1 | 54623 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377294 | Work Order Description - 377294 - PSPM | PSPM | 1 | 53368 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377296 | Work Order Description - 377296 - PSPM | PSPM | 1 | 409789 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377298 | Work Order Description - 377298 - PSPM | PSPM | 1 | 53370 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377300 | Work Order Description - 377300 - PSPM | PSPM | 1 | 409788 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377302 | Work Order Description - 377302 - PM | PM | 3 | 54607 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377304 | Work Order Description - 377304 - PM | PM | 3 | 53372 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377314 | Work Order Description - 377314 - PSPM | PSPM | 1 | 54831 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-15 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377316 | Work Order Description - 377316 - PM | PM | 4 | 262352 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-08-18 | 2019-05-01 | 2019-05-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377318 | Work Order Description - 377318 - PM | PM | 3 | 409689 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-09-01 | 2019-05-15 | 2019-05-15 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377320 | Work Order Description - 377320 - PM | PM | 3 | 410213 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-10-24 | 2019-04-26 | 2019-04-26 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 377322 | Work Order Description - 377322 - PM | PM | 3 | 410214 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-11-06 | 2019-05-09 | 2019-05-09 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377324 | Work Order Description - 377324 - PSPM | PSPM | 1 | 410249 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377326 | Work Order Description - 377326 - PM | PM | 3 | 409790 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-08-26 | 2019-05-09 | 2019-05-09 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377332 | Work Order Description - 377332 - PSPM | PSPM | 1 | 53499 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377334 | Work Order Description - 377334 - PSPM | PSPM | 1 | 361162 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 377336 | Work Order Description - 377336 - PM | PM | 3 | 357392 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-09-22 | 2019-04-30 | 2019-04-30 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377338 | Work Order Description - 377338 - PM | PM | 3 | 357393 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-09-22 | 2019-04-30 | 2019-04-30 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377340 | Work Order Description - 377340 - PM | PM | 3 | 357394 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-09-22 | 2019-04-30 | 2019-04-30 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377342 | Work Order Description - 377342 - PM | PM | 3 | 55065 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-09-18 | 2019-04-26 | 2019-04-26 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377344 | Work Order Description - 377344 - PM | PM | 4 | 368329 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 2 | INTEGRITY | INSPECTION | 6
2019-03-31 | 377348 | Work Order Description - 377348 - PM | PM | 4 | 580762 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 377350 | Work Order Description - 377350 - PM | PM | 4 | 580762 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 377352 | Work Order Description - 377352 - PM | PM | 4 | 580762 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 377354 | Work Order Description - 377354 - PM | PM | 2 | 480203 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-07-04 | 2019-05-10 | 2019-05-10 | 2 | MAINTENANCE | INSTRUMENTS | 69
2019-03-31 | 377356 | Work Order Description - 377356 - PM | PM | 4 | 672771 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-08-14 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | ELECTRICAL | 9
2019-03-31 | 377358 | Work Order Description - 377358 - PM | PM | 4 | 680754 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-08-14 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | ELECTRICAL | 9
2019-03-31 | 377360 | Work Order Description - 377360 - PM | PM | 4 | 246173 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | INTEGRITY | SERVICES | 2
2019-03-31 | 377362 | Work Order Description - 377362 - PM | PM | 4 | 246173 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | INTEGRITY | SERVICES | 2
2019-03-31 | 377364 | Work Order Description - 377364 - PM | PM | 4 | 546030 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 377366 | Work Order Description - 377366 - PM | PM | 4 | 546030 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 377368 | Work Order Description - 377368 - PM | PM | 4 | 547429 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 377370 | Work Order Description - 377370 - PM | PM | 4 | 547429 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 377372 | Work Order Description - 377372 - PM | PM | 4 | 652482 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | INTEGRITY | SERVICES | 2
2019-03-31 | 377374 | Work Order Description - 377374 - PM | PM | 4 | 652482 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | INTEGRITY | SERVICES | 2
2019-03-31 | 377376 | Work Order Description - 377376 - PM | PM | 4 | 54771 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 377378 | Work Order Description - 377378 - PM | PM | 4 | 545346 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 377382 | Work Order Description - 377382 - PSPM | PSPM | 1 | 679717 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 377386 | Work Order Description - 377386 - PM | PM | 4 | 408315 | WSCHD | NORM-OPS | 2019-01-15 | 2019-07-08 | 2019-05-14 | 2019-05-14 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 377388 | Work Order Description - 377388 - PM | PM | 4 | 408315 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2020-05-09 | 2019-05-14 | 2019-05-14 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 377390 | Work Order Description - 377390 - PM | PM | 4 | 660951 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-26 | 2019-04-25 | 2019-04-25 | 3 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 377394 | Work Order Description - 377394 - PM | PM | 4 | 660951 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 3 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 377398 | Work Order Description - 377398 - PSPM | PSPM | 1 | 308462 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 377400 | Work Order Description - 377400 - PSPM | PSPM | 1 | 674739 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 377402 | Work Order Description - 377402 - PSPM | PSPM | 1 | 51659 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 377404 | Work Order Description - 377404 - PSPM | PSPM | 1 | 318577 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | WELLS | WELLS | 24
2019-03-31 | 377408 | Work Order Description - 377408 - PSPM | PSPM | 1 | 498622 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | WELLS | WELLS | 19
2019-03-31 | 377412 | Work Order Description - 377412 - PSPM | PSPM | 1 | 318578 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 1 | WELLS | WELLS | 24
2019-03-31 | 377416 | Work Order Description - 377416 - PSPM | PSPM | 1 | 354362 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-03 | 2019-05-03 | 2019-05-03 | 1 | WELLS | WELLS | 19
2019-03-31 | 377420 | Work Order Description - 377420 - PSPM | PSPM | 1 | 520395 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 1 | WELLS | WELLS | 19
2019-03-31 | 377424 | Work Order Description - 377424 - PSPM | PSPM | 1 | 520393 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | WELLS | WELLS | 19
2019-03-31 | 377428 | Work Order Description - 377428 - PSPM | PSPM | 1 | 498623 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | WELLS | WELLS | 19
2019-03-31 | 377432 | Work Order Description - 377432 - PM | PM | 4 | 538880 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 377434 | Work Order Description - 377434 - PSPM | PSPM | 1 | 520388 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | WELLS | WELLS | 19
2019-03-31 | 377438 | Work Order Description - 377438 - PM | PM | 4 | 138073 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 377441 | Work Order Description - 377441 - PSPM | PSPM | 1 | 470877 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 377443 | Work Order Description - 377443 - PSPM | PSPM | 1 | 470877 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 377445 | Work Order Description - 377445 - PSPM | PSPM | 1 | 470877 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 377447 | Work Order Description - 377447 - PSPM | PSPM | 1 | 273468 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 377449 | Work Order Description - 377449 - PSPM | PSPM | 1 | 470878 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 377451 | Work Order Description - 377451 - PSPM | PSPM | 1 | 480207 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 377453 | Work Order Description - 377453 - PSPM | PSPM | 1 | 321203 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 377455 | Work Order Description - 377455 - PSPM | PSPM | 1 | 321203 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 377457 | Work Order Description - 377457 - PSPM | PSPM | 1 | 321203 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 377459 | Work Order Description - 377459 - PSPM | PSPM | 1 | 321218 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 377461 | Work Order Description - 377461 - PSPM | PSPM | 1 | 321218 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 377463 | Work Order Description - 377463 - PSPM | PSPM | 1 | 321218 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 377465 | Work Order Description - 377465 - PM | PM | 4 | 457525 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | SAFETY | 3
2019-03-31 | 377467 | Work Order Description - 377467 - PSPM | PSPM | 1 | 538631 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 377469 | Work Order Description - 377469 - PSPM | PSPM | 1 | 273470 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 377471 | Work Order Description - 377471 - PSPM | PSPM | 1 | 538632 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 377473 | Work Order Description - 377473 - PSPM | PSPM | 1 | 671828 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 377475 | Work Order Description - 377475 - PSPM | PSPM | 1 | 671828 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 377477 | Work Order Description - 377477 - PSPM | PSPM | 1 | 675036 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 377479 | Work Order Description - 377479 - PSPM | PSPM | 1 | 675036 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 377481 | Work Order Description - 377481 - PSPM | PSPM | 1 | 675037 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 377483 | Work Order Description - 377483 - PSPM | PSPM | 1 | 675037 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 377485 | Work Order Description - 377485 - PSPM | PSPM | 1 | 671829 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 377487 | Work Order Description - 377487 - PSPM | PSPM | 1 | 671829 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 377489 | Work Order Description - 377489 - PM | PM | 4 | 535884 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | OPERATIONS | MEDIC | 3
2019-03-31 | 377491 | Work Order Description - 377491 - PM | PM | 4 | 676326 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | OPERATIONS | MEDIC | 2
2019-03-31 | 377493 | Work Order Description - 377493 - PM | PM | 4 | 545401 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 377495 | Work Order Description - 377495 - PM | PM | 4 | 51882 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 377497 | Work Order Description - 377497 - PM | PM | 4 | 137858 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 377499 | Work Order Description - 377499 - PM | PM | 4 | 54970 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 377501 | Work Order Description - 377501 - PM | PM | 4 | 545347 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 377503 | Work Order Description - 377503 - PSPM | PSPM | 1 | 136833 | SCHD | NORM-OPS | 2019-03-29 | 2019-06-01 | 2019-03-30 | 2019-04-07 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 377505 | Work Order Description - 377505 - PM | PM | 4 | 137962 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 377507 | Work Order Description - 377507 - PM | PM | 4 | 137923 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 377509 | Work Order Description - 377509 - PM | PM | 4 | 545892 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 377511 | Work Order Description - 377511 - PM | PM | 4 | 657598 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 377513 | Work Order Description - 377513 - PM | PM | 4 | 545676 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 377515 | Work Order Description - 377515 - PM | PM | 4 | 641288 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 377517 | Work Order Description - 377517 - PM | PM | 4 | 652076 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 377519 | Work Order Description - 377519 - PM | PM | 4 | 653559 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 377521 | Work Order Description - 377521 - PM | PM | 4 | 138083 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 377523 | Work Order Description - 377523 - PM | PM | 4 | 138088 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 377525 | Work Order Description - 377525 - PSPM | PSPM | 1 | 545401 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 377527 | Work Order Description - 377527 - PM | PM | 4 | 410324 | WSCHD | NORM-OPS | 2019-01-19 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 377529 | Work Order Description - 377529 - PM | PM | 4 | 361799 | WSCHD | NORM-OPS | 2019-01-19 | 2019-06-14 | 2019-05-14 | 2019-05-14 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 377531 | Work Order Description - 377531 - PM | PM | 4 | 519759 | WSCHD | NORM-OPS | 2019-01-19 | 2019-06-14 | 2019-05-14 | 2019-05-14 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 377535 | Work Order Description - 377535 - PSPM | PSPM | 1 | 519760 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 377537 | Work Order Description - 377537 - PSPM | PSPM | 1 | 547275 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 377539 | Work Order Description - 377539 - PSPM | PSPM | 1 | 547298 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-14 | 2019-05-14 | 2019-05-14 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 377541 | Work Order Description - 377541 - PSPM | PSPM | 1 | 410324 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 377543 | Work Order Description - 377543 - PSPM | PSPM | 1 | 361798 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-03 | 2019-05-03 | 2019-05-03 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 377545 | Work Order Description - 377545 - PSPM | PSPM | 1 | 361803 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 377547 | Work Order Description - 377547 - PSPM | PSPM | 1 | 519759 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-25 | 2019-04-24 | 2019-04-24 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 377549 | Work Order Description - 377549 - PSPM | PSPM | 1 | 137954 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 377551 | Work Order Description - 377551 - PSPM | PSPM | 1 | 361803 | WSCHD | NORM-OPS | 2019-01-17 | 2019-05-27 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 377553 | Work Order Description - 377553 - PSPM | PSPM | 1 | 519759 | WSCHD | NORM-OPS | 2019-01-17 | 2019-05-31 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 377555 | Work Order Description - 377555 - PSPM | PSPM | 1 | 546105 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 377557 | Work Order Description - 377557 - PSPM | PSPM | 1 | 657598 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 377559 | Work Order Description - 377559 - PM | PM | 4 | 653699 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-10-25 | 2019-05-15 | 2019-05-15 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 377561 | Work Order Description - 377561 - PM | PM | 4 | 657869 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-10-10 | 2019-04-30 | 2019-04-30 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 377563 | Work Order Description - 377563 - PM | PM | 4 | 267676 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | SAFETY | 4
2019-03-31 | 377565 | Work Order Description - 377565 - PM | PM | 4 | 294918 | WSCHD | NORM-OPS | 2019-01-19 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 2 | MAINTENANCE | MECHANICAL | 10.5
2019-03-31 | 377567 | Work Order Description - 377567 - PM | PM | 4 | 545668 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 377569 | Work Order Description - 377569 - PM | PM | 4 | 55096 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 377571 | Work Order Description - 377571 - PSPM | PSPM | 1 | 357612 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377573 | Work Order Description - 377573 - PM | PM | 2 | 321115 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 377577 | Work Order Description - 377577 - PM | PM | 2 | 480203 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 377581 | Work Order Description - 377581 - PM | PM | 4 | 361917 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 377583 | Work Order Description - 377583 - PM | PM | 4 | 520071 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 377585 | Work Order Description - 377585 - PSPM | PSPM | 1 | 357651 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377587 | Work Order Description - 377587 - PSPM | PSPM | 1 | 399675 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377589 | Work Order Description - 377589 - PSPM | PSPM | 1 | 653341 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377591 | Work Order Description - 377591 - PM | PM | 4 | 360243 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 377593 | Work Order Description - 377593 - PM | PM | 4 | 360243 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 377595 | Work Order Description - 377595 - PM | PM | 4 | 360243 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 377597 | Work Order Description - 377597 - PM | PM | 3 | 361921 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 377599 | Work Order Description - 377599 - PM | PM | 3 | 399406 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 377601 | Work Order Description - 377601 - PM | PM | 3 | 361889 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 377603 | Work Order Description - 377603 - PM | PM | 4 | 361916 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 377605 | Work Order Description - 377605 - PM | PM | 4 | 361881 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 377607 | Work Order Description - 377607 - PM | PM | 3 | 547543 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-08 | 2019-05-08 | 2019-05-08 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 377609 | Work Order Description - 377609 - PM | PM | 4 | 481344 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | SAFETY | 10
2019-03-31 | 377611 | Work Order Description - 377611 - PM | PM | 1 | 267779 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 377613 | Work Order Description - 377613 - PM | PM | 4 | 292678 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-08 | 2019-05-08 | 2019-05-08 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 377615 | Work Order Description - 377615 - PM | PM | 4 | 292678 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-08 | 2019-05-08 | 2019-05-08 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 377617 | Work Order Description - 377617 - PM | PM | 4 | 292678 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 377619 | Work Order Description - 377619 - PM | PM | 4 | 292678 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 377629 | Work Order Description - 377629 - PSPM | PSPM | 1 | 292668 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | SAFETY | 6
2019-03-31 | 377631 | Work Order Description - 377631 - PM | PM | 3 | 57067 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377633 | Work Order Description - 377633 - PM | PM | 3 | 571865 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-06-25 | 2019-05-01 | 2019-05-01 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 377638 | Work Order Description - 377638 - PM | PM | 4 | 212354 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-25 | 2019-04-24 | 2019-04-24 | 2 | INTEGRITY | INSPECTION | 2
2019-03-31 | 377640 | Work Order Description - 377640 - PM | PM | 4 | 267676 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 377642 | Work Order Description - 377642 - PSPM | PSPM | 1 | 457527 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | OPERATIONS | SAFETY | 6
2019-03-31 | 377644 | Work Order Description - 377644 - PSPM | PSPM | 1 | 267870 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | OPERATIONS | SAFETY | 6
2019-03-31 | 377646 | Work Order Description - 377646 - PSPM | PSPM | 1 | 292659 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | OPERATIONS | SAFETY | 6
2019-03-31 | 377648 | Work Order Description - 377648 - PSPM | PSPM | 1 | 546068 | WSCHD | NORM-OPS | 2019-01-19 | 2019-06-03 | 2019-05-03 | 2019-05-03 | 1 | MAINTENANCE | SERVICES | 10
2019-03-31 | 377650 | Work Order Description - 377650 - PSPM | PSPM | 1 | 652220 | WSCHD | NORM-OPS | 2019-01-19 | 2019-05-25 | 2019-04-24 | 2019-04-24 | 1 | MAINTENANCE | SERVICES | 12
2019-03-31 | 377652 | Work Order Description - 377652 - PSPM | PSPM | 1 | 652220 | WSCHD | NORM-OPS | 2019-01-19 | 2019-06-08 | 2019-05-08 | 2019-05-08 | 1 | MAINTENANCE | SERVICES | 10
2019-03-31 | 377654 | Work Order Description - 377654 - PSPM | PSPM | 1 | 546068 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | SERVICES | 6
2019-03-31 | 377656 | Work Order Description - 377656 - PSPM | PSPM | 1 | 652220 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | SERVICES | 6
2019-03-31 | 377658 | Work Order Description - 377658 - PSPM | PSPM | 1 | 652220 | WSCHD | NORM-OPS | 2019-01-19 | 2019-05-25 | 2019-04-24 | 2019-04-24 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 377660 | Work Order Description - 377660 - PSPM | PSPM | 1 | 546068 | WPLAN | PACK-ISOL | 2019-01-15 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | MECHANICAL | 336
2019-03-31 | 377665 | Work Order Description - 377665 - PSPM | PSPM | 1 | 574963 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2019-06-08 | 2019-05-08 | 2019-05-08 | 1 | MAINTENANCE | SERVICES | 4
2019-03-31 | 377667 | Work Order Description - 377667 - PM | PM | 3 | 656110 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 377669 | Work Order Description - 377669 - PM | PM | 3 | 656111 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 377671 | Work Order Description - 377671 - PM | PM | 4 | 653342 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 377673 | Work Order Description - 377673 - PSPM | PSPM | 1 | 399456 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377675 | Work Order Description - 377675 - PM | PM | 4 | 361227 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 377677 | Work Order Description - 377677 - PSPM | PSPM | 1 | 54036 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377679 | Work Order Description - 377679 - PSPM | PSPM | 1 | 399457 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377681 | Work Order Description - 377681 - PSPM | PSPM | 1 | 54038 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377683 | Work Order Description - 377683 - PSPM | PSPM | 1 | 357597 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377685 | Work Order Description - 377685 - PSPM | PSPM | 1 | 248096 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 377687 | Work Order Description - 377687 - PSPM | PSPM | 1 | 357578 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377689 | Work Order Description - 377689 - PSPM | PSPM | 1 | 653285 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377691 | Work Order Description - 377691 - PSPM | PSPM | 1 | 399418 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377693 | Work Order Description - 377693 - PSPM | PSPM | 1 | 399419 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377695 | Work Order Description - 377695 - PSPM | PSPM | 1 | 53987 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377697 | Work Order Description - 377697 - PSPM | PSPM | 1 | 53988 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377699 | Work Order Description - 377699 - PSPM | PSPM | 1 | 653286 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377701 | Work Order Description - 377701 - PSPM | PSPM | 1 | 357582 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377703 | Work Order Description - 377703 - PSPM | PSPM | 1 | 399416 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377705 | Work Order Description - 377705 - PSPM | PSPM | 1 | 399572 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 377707 | Work Order Description - 377707 - PM | PM | 4 | 666204 | SCHD | NORM-OPS | 2019-02-21 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377709 | Work Order Description - 377709 - PSPM | PSPM | 1 | 653308 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377711 | Work Order Description - 377711 - PSPM | PSPM | 1 | 399556 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377713 | Work Order Description - 377713 - PSPM | PSPM | 1 | 54105 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377715 | Work Order Description - 377715 - PSPM | PSPM | 1 | 653309 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377717 | Work Order Description - 377717 - PSPM | PSPM | 1 | 261210 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 377719 | Work Order Description - 377719 - PSPM | PSPM | 1 | 399587 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377721 | Work Order Description - 377721 - PSPM | PSPM | 1 | 399588 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377723 | Work Order Description - 377723 - PSPM | PSPM | 1 | 656068 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377725 | Work Order Description - 377725 - PSPM | PSPM | 1 | 357621 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377727 | Work Order Description - 377727 - PSPM | PSPM | 1 | 399589 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377729 | Work Order Description - 377729 - PSPM | PSPM | 1 | 357620 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377731 | Work Order Description - 377731 - PSPM | PSPM | 1 | 656066 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377733 | Work Order Description - 377733 - PSPM | PSPM | 1 | 653325 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377735 | Work Order Description - 377735 - PSPM | PSPM | 1 | 653346 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377737 | Work Order Description - 377737 - PSPM | PSPM | 1 | 399674 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377739 | Work Order Description - 377739 - PSPM | PSPM | 1 | 357652 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377741 | Work Order Description - 377741 - PSPM | PSPM | 1 | 653344 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377743 | Work Order Description - 377743 - PSPM | PSPM | 1 | 656114 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377745 | Work Order Description - 377745 - PSPM | PSPM | 1 | 656135 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377747 | Work Order Description - 377747 - PSPM | PSPM | 1 | 653345 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377749 | Work Order Description - 377749 - PSPM | PSPM | 1 | 54037 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377751 | Work Order Description - 377751 - PM | PM | 2 | 363762 | WSCHD | NORM-OPS | 2019-01-19 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | MECHANICAL | 3.5
2019-03-31 | 377753 | Work Order Description - 377753 - PSPM | PSPM | 1 | 19090 | WPLAN | EQUIP-ISOL | 2019-01-15 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 377755 | Work Order Description - 377755 - PSPM | PSPM | 1 | 697913 | SCHD | NORM-OPS | 2019-03-13 | 2019-06-02 | 2019-03-30 | 2019-04-08 | 1 | INTEGRITY | INSPECTION | 239
2019-03-31 | 377757 | Work Order Description - 377757 - PSPM | PSPM | 1 | 155742 | WSCHD | NORM-OPS | 2019-01-15 | 2019-10-01 | 2019-04-24 | 2019-04-24 | 1 | INTEGRITY | INSPECTION | 294
2019-03-31 | 377759 | Work Order Description - 377759 - PM | PM | 3 | 531859 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-05-29 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 377761 | Work Order Description - 377761 - PM | PM | 3 | 363639 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 377763 | Work Order Description - 377763 - PM | PM | 3 | 531879 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 377765 | Work Order Description - 377765 - PM | PM | 4 | 294916 | WSCHD | NORM-OPS | 2019-01-15 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 377767 | Work Order Description - 377767 - PM | PM | 4 | 294916 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 377769 | Work Order Description - 377769 - PM | PM | 4 | 294916 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 377771 | Work Order Description - 377771 - PM | PM | 4 | 308517 | WSCHD | EQUIP-ISOL | 2019-01-15 | 2020-04-19 | 2019-04-24 | 2019-04-24 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 377773 | Work Order Description - 377773 - PM | PM | 4 | 676836 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 377775 | Work Order Description - 377775 - PM | PM | 4 | 356992 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 377777 | Work Order Description - 377777 - PM | PM | 4 | 481408 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 4 | MAINTENANCE | MEDIC | 25
2019-03-31 | 377779 | Work Order Description - 377779 - PM | PM | 4 | 295994 | WSCHD | NORM-OPS | 2019-01-15 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 2 | MAINTENANCE | MEDIC | 20
2019-03-31 | 377781 | Work Order Description - 377781 - PM | PM | 4 | 295994 | WSCHD | NORM-OPS | 2019-01-15 | 2020-04-26 | 2019-05-01 | 2019-05-01 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 377783 | Work Order Description - 377783 - PM | PM | 4 | 450481 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 2 | OPERATIONS | OPERATIONS | 5
2019-03-31 | 377785 | Work Order Description - 377785 - PM | PM | 4 | 451997 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-20 | 2019-04-26 | 2019-04-26 | 2 | MAINTENANCE | ELECTRICAL | 24
2019-03-31 | 377787 | Work Order Description - 377787 - PM | PM | 4 | 584012 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377789 | Work Order Description - 377789 - PM | PM | 4 | 679283 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 377791 | Work Order Description - 377791 - PSPM | PSPM | 1 | 633441 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 377793 | Work Order Description - 377793 - PSPM | PSPM | 1 | 95502 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 377795 | Work Order Description - 377795 - PSPM | PSPM | 1 | 81182 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 377797 | Work Order Description - 377797 - PSPM | PSPM | 1 | 180996 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 33
2019-03-31 | 377805 | Work Order Description - 377805 - PSPM | PSPM | 1 | 309212 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 377809 | Work Order Description - 377809 - PSPM | PSPM | 1 | 309605 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 377811 | Work Order Description - 377811 - PSPM | PSPM | 1 | 325359 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 377813 | Work Order Description - 377813 - PSPM | PSPM | 1 | 189100 | SCHD | PACK-ISOL | 2019-01-31 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377815 | Work Order Description - 377815 - PSPM | PSPM | 1 | 189100 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 377817 | Work Order Description - 377817 - PSPM | PSPM | 1 | 189101 | SCHD | PACK-ISOL | 2019-01-31 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377819 | Work Order Description - 377819 - PSPM | PSPM | 1 | 189101 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 377821 | Work Order Description - 377821 - PSPM | PSPM | 1 | 325575 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-05 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 377823 | Work Order Description - 377823 - PSPM | PSPM | 1 | 499274 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 377825 | Work Order Description - 377825 - PSPM | PSPM | 4 | 99563 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 2 | MAINTENANCE | INSTRUMENTS | 50
2019-03-31 | 377827 | Work Order Description - 377827 - PSPM | PSPM | 4 | 450480 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 2 | MAINTENANCE | INSTRUMENTS | 50
2019-03-31 | 377829 | Work Order Description - 377829 - PSPM | PSPM | 1 | 472605 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 377831 | Work Order Description - 377831 - PSPM | PSPM | 1 | 584921 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 377833 | Work Order Description - 377833 - PSPM | PSPM | 1 | 29816 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 377835 | Work Order Description - 377835 - PSPM | PSPM | 1 | 304040 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 377837 | Work Order Description - 377837 - PSPM | PSPM | 1 | 303774 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 377839 | Work Order Description - 377839 - PSPM | PSPM | 1 | 535485 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 377841 | Work Order Description - 377841 - PM | PM | 4 | 323665 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 377843 | Work Order Description - 377843 - PM | PM | 3 | 180987 | SCHD | PACK-ISOL | 2019-01-31 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | INTEGRITY | MECHANICAL | 18
2019-03-31 | 377849 | Work Order Description - 377849 - PM | PM | 2 | 402622 | SCHD | SYS-ISOL | 2019-01-31 | 2019-10-05 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 377851 | Work Order Description - 377851 - PM | PM | 4 | 81511 | SCHD | PACK-ISOL | 2019-01-31 | 2019-06-24 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 377853 | Work Order Description - 377853 - PM | PM | 4 | 98009 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 377855 | Work Order Description - 377855 - PM | PM | 2 | 312683 | SCHD | PACK-ISOL | 2019-01-31 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 377859 | Work Order Description - 377859 - PM | PM | 2 | 312718 | SCHD | PACK-ISOL | 2019-01-31 | 2019-05-26 | 2019-04-25 | 2019-04-25 | 2 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 377863 | Work Order Description - 377863 - PM | PM | 4 | 555977 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-15 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 377865 | Work Order Description - 377865 - PM | PM | 4 | 450393 | SCHD | PACK-ISOL | 2019-01-31 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | INTEGRITY | MECHANICAL | 16
2019-03-31 | 377871 | Work Order Description - 377871 - PM | PM | 4 | 450355 | SCHD | PACK-ISOL | 2019-01-31 | 2019-06-08 | 2019-05-08 | 2019-05-08 | 3 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 377875 | Work Order Description - 377875 - PSPM | PSPM | 1 | 59015 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 1 | MAINTENANCE | MECHANICAL | 33
2019-03-31 | 377883 | Work Order Description - 377883 - PM | PM | 4 | 498445 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-18 | 2019-04-24 | 2019-04-24 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377885 | Work Order Description - 377885 - PSPM | PSPM | 1 | 491403 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 377887 | Work Order Description - 377887 - PM | PM | 4 | 481609 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 377889 | Work Order Description - 377889 - PM | PM | 4 | 481609 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 377891 | Work Order Description - 377891 - PM | PM | 4 | 481609 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 377893 | Work Order Description - 377893 - PM | PM | 4 | 481609 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-14 | 2019-05-14 | 2019-05-14 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 377895 | Work Order Description - 377895 - PSPM | PSPM | 1 | 74216 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-08-24 | 2019-08-24 | 1 | MAINTENANCE | MECHANICAL | 60
2019-03-31 | 377897 | Work Order Description - 377897 - PSPM | PSPM | 1 | 320057 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-03 | 2019-05-03 | 2019-05-03 | 1 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 377907 | Work Order Description - 377907 - PM | PM | 4 | 475799 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 2 | DRILLING | DRILLING | 8
2019-03-31 | 377909 | Work Order Description - 377909 - PM | PM | 4 | 482054 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 2 | DRILLING | DRILLING | 8
2019-03-31 | 377911 | Work Order Description - 377911 - PSPM | PSPM | 1 | 216927 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | OPERATIONS | MEDIC | 4
2019-03-31 | 377913 | Work Order Description - 377913 - PM | PM | 4 | 259533 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 377915 | Work Order Description - 377915 - PM | PM | 4 | 259529 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 377917 | Work Order Description - 377917 - PM | PM | 4 | 477563 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 377919 | Work Order Description - 377919 - PM | PM | 4 | 477561 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 377921 | Work Order Description - 377921 - PM | PM | 4 | 477562 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 377923 | Work Order Description - 377923 - PM | PM | 4 | 477566 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 377937 | Work Order Description - 377937 - PM | PM | 4 | 313220 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 377939 | Work Order Description - 377939 - PSPM | PSPM | 1 | 462436 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 1 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 377941 | Work Order Description - 377941 - PSPM | PSPM | 1 | 462436 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 377943 | Work Order Description - 377943 - PSPM | PSPM | 1 | 578835 | SCHD | PACK-ISOL | 2019-01-25 | 2019-05-26 | 2019-03-23 | 2019-03-23 | 1 | WELLS | WELLS | 1
2019-03-31 | 377947 | Work Order Description - 377947 - PM | PM | 2 | 475264 | SCHD | NORM-OPS | 2019-01-31 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | INSPECTION | 600
2019-03-31 | 377949 | Work Order Description - 377949 - PM | PM | 2 | 501753 | SCHD | NORM-OPS | 2019-01-31 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | INSPECTION | 600
2019-03-31 | 377951 | Work Order Description - 377951 - PM | PM | 4 | 309635 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377953 | Work Order Description - 377953 - PM | PM | 2 | 325104 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377955 | Work Order Description - 377955 - PSPM | PSPM | 1 | 555235 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | OPERATIONS | OPERATIONS | 12
2019-03-31 | 377957 | Work Order Description - 377957 - PM | PM | 2 | 481850 | SCHD | NORM-OPS | 2019-01-31 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | INSPECTION | 600
2019-03-31 | 377959 | Work Order Description - 377959 - PM | PM | 4 | 403468 | SCHD | NORM-OPS | 2019-01-31 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 377961 | Work Order Description - 377961 - PM | PM | 4 | 476154 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377963 | Work Order Description - 377963 - PM | PM | 4 | 476154 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377965 | Work Order Description - 377965 - PM | PM | 4 | 476154 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377967 | Work Order Description - 377967 - PM | PM | 4 | 476154 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-14 | 2019-05-14 | 2019-05-14 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377969 | Work Order Description - 377969 - PM | PM | 4 | 254753 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377971 | Work Order Description - 377971 - PM | PM | 4 | 403849 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 377973 | Work Order Description - 377973 - PM | PM | 4 | 501022 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-24 | 2019-04-30 | 2019-04-30 | 2 | MAINTENANCE | MECHANICAL | 60
2019-03-31 | 377975 | Work Order Description - 377975 - PM | PM | 4 | 253422 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-10-11 | 2019-05-01 | 2019-05-01 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 377977 | Work Order Description - 377977 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377979 | Work Order Description - 377979 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-03 | 2019-05-03 | 2019-05-03 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377981 | Work Order Description - 377981 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377983 | Work Order Description - 377983 - PM | PM | 4 | 28831 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377985 | Work Order Description - 377985 - PM | PM | 3 | 309675 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 377989 | Work Order Description - 377989 - PSPM | PSPM | 1 | 479265 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-08 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | SAFETY | 6
2019-03-31 | 377991 | Work Order Description - 377991 - PM | PM | 4 | 479266 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-25 | 2019-05-25 | 1 | OPERATIONS | SAFETY | 15
2019-03-31 | 377993 | Work Order Description - 377993 - PM | PM | 4 | 183835 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-10-25 | 2019-05-15 | 2019-05-15 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 377995 | Work Order Description - 377995 - PM | PM | 4 | 462750 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 377997 | Work Order Description - 377997 - PM | PM | 3 | 309675 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 377999 | Work Order Description - 377999 - PSPM | PSPM | 1 | 462750 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 378001 | Work Order Description - 378001 - PSPM | PSPM | 1 | 256887 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 378003 | Work Order Description - 378003 - PSPM | PSPM | 1 | 189054 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-03 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378005 | Work Order Description - 378005 - PSPM | PSPM | 1 | 499149 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-03 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378007 | Work Order Description - 378007 - PSPM | PSPM | 1 | 325633 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-03 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378009 | Work Order Description - 378009 - PSPM | PSPM | 1 | 81212 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-03 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | OPERATIONS | 4
2019-03-31 | 378011 | Work Order Description - 378011 - PSPM | PSPM | 1 | 189054 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 378014 | Work Order Description - 378014 - PSPM | PSPM | 1 | 189054 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 378016 | Work Order Description - 378016 - PSPM | PSPM | 1 | 325633 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-30 | 2019-04-27 | 2019-04-27 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 378018 | Work Order Description - 378018 - PSPM | PSPM | 1 | 325633 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 378020 | Work Order Description - 378020 - PSPM | PSPM | 1 | 81212 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378022 | Work Order Description - 378022 - PSPM | PSPM | 1 | 81212 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | OPERATIONS | OPERATIONS | 1
2019-03-31 | 378024 | Work Order Description - 378024 - PSPM | PSPM | 1 | 555303 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-04 | 2019-05-25 | 2019-05-25 | 1 | OPERATIONS | SAFETY | 8
2019-03-31 | 378026 | Work Order Description - 378026 - PSPM | PSPM | 1 | 269368 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-04 | 2019-05-25 | 2019-05-25 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 378028 | Work Order Description - 378028 - PM | PM | 4 | 555305 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-03 | 2019-05-25 | 2019-05-25 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 378030 | Work Order Description - 378030 - PM | PM | 4 | 479286 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | SAFETY | 3
2019-03-31 | 378032 | Work Order Description - 378032 - PM | PM | 4 | 479287 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | SAFETY | 3
2019-03-31 | 378034 | Work Order Description - 378034 - PM | PM | 4 | 481636 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-15 | 2019-06-01 | 2019-06-01 | 3 | OPERATIONS | SAFETY | 15
2019-03-31 | 378036 | Work Order Description - 378036 - PM | PM | 4 | 481637 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-15 | 2019-05-25 | 2019-05-25 | 3 | OPERATIONS | SAFETY | 14
2019-03-31 | 378038 | Work Order Description - 378038 - PM | PM | 4 | 501105 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-05 | 2019-05-25 | 2019-05-25 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 378040 | Work Order Description - 378040 - PM | PM | 4 | 481631 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-25 | 2019-05-25 | 1 | OPERATIONS | SAFETY | 8
2019-03-31 | 378042 | Work Order Description - 378042 - PSPM | PSPM | 1 | 265465 | SCHD | NORM-OPS | 2019-01-31 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 1 | INTEGRITY | INSPECTION | 8
2019-03-31 | 378044 | Work Order Description - 378044 - PSPM | PSPM | 1 | 320574 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | OPERATIONS | OPERATIONS | 12
2019-03-31 | 378046 | Work Order Description - 378046 - PSPM | PSPM | 1 | 555235 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | OPERATIONS | OPERATIONS | 12
2019-03-31 | 378048 | Work Order Description - 378048 - PSPM | PSPM | 1 | 460846 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 378050 | Work Order Description - 378050 - PSPM | PSPM | 1 | 259529 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378052 | Work Order Description - 378052 - PSPM | PSPM | 1 | 631926 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 378054 | Work Order Description - 378054 - PSPM | PSPM | 4 | 383657 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 378056 | Work Order Description - 378056 - PM | PM | 4 | 99579 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-25 | 2019-04-24 | 2019-04-24 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 378058 | Work Order Description - 378058 - PM | PM | 4 | 99579 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-08 | 2019-05-08 | 2019-05-08 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 378060 | Work Order Description - 378060 - PM | PM | 4 | 99579 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-26 | 2019-04-25 | 2019-04-25 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 378062 | Work Order Description - 378062 - PSPM | PSPM | 1 | 447441 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-05 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 378064 | Work Order Description - 378064 - PM | PM | 4 | 128192 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 378066 | Work Order Description - 378066 - PM | PM | 1 | 632649 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-04-27 | 2019-04-27 | 1 | OPERATIONS | SAFETY | 10
2019-03-31 | 378068 | Work Order Description - 378068 - PSPM | PSPM | 1 | 632581 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-26 | 2019-05-18 | 2019-05-18 | 1 | OPERATIONS | SAFETY | 5
2019-03-31 | 378070 | Work Order Description - 378070 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 378074 | Work Order Description - 378074 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 378078 | Work Order Description - 378078 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 378082 | Work Order Description - 378082 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-14 | 2019-05-14 | 2019-05-14 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 378086 | Work Order Description - 378086 - PM | PM | 4 | 472553 | SCHD | NORM-OPS | 2019-01-31 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378088 | Work Order Description - 378088 - PM | PM | 4 | 81255 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 378090 | Work Order Description - 378090 - PM | PM | 4 | 568915 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-07-19 | 2019-05-07 | 2019-05-07 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378092 | Work Order Description - 378092 - PM | PM | 4 | 72943 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 1 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 378094 | Work Order Description - 378094 - PM | PM | 4 | 72943 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 378096 | Work Order Description - 378096 - PM | PM | 4 | 74447 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-01 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 378098 | Work Order Description - 378098 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 378100 | Work Order Description - 378100 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-03 | 2019-05-03 | 2019-05-03 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 378102 | Work Order Description - 378102 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 378104 | Work Order Description - 378104 - PM | PM | 4 | 184916 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378106 | Work Order Description - 378106 - PM | PM | 4 | 217593 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378108 | Work Order Description - 378108 - PM | PM | 4 | 217594 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378110 | Work Order Description - 378110 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 378112 | Work Order Description - 378112 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 378114 | Work Order Description - 378114 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 378116 | Work Order Description - 378116 - PM | PM | 4 | 74694 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378118 | Work Order Description - 378118 - PM | PM | 4 | 127287 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378120 | Work Order Description - 378120 - PSPM | PSPM | 1 | 583857 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-29 | 2019-05-18 | 2019-05-18 | 1 | OPERATIONS | SAFETY | 7
2019-03-31 | 378122 | Work Order Description - 378122 - PSPM | PSPM | 1 | 128338 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | MAINTENANCE | SAFETY | 8
2019-03-31 | 378126 | Work Order Description - 378126 - PSPM | PSPM | 1 | 128338 | SCHD | PACK-ISOL | 2019-01-25 | 2019-06-06 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 378128 | Work Order Description - 378128 - PSPM | PSPM | 1 | 128338 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-15 | 2019-05-11 | 2019-05-11 | 1 | OPERATIONS | OPERATIONS | 4
2019-03-31 | 378130 | Work Order Description - 378130 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-26 | 2019-04-25 | 2019-04-25 | 1 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 378132 | Work Order Description - 378132 - PSPM | PSPM | 1 | 81194 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378134 | Work Order Description - 378134 - PM | PM | 4 | 451898 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378136 | Work Order Description - 378136 - PM | PM | 4 | 448862 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378138 | Work Order Description - 378138 - PM | PM | 4 | 568555 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378140 | Work Order Description - 378140 - PM | PM | 4 | 128236 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-05 | 2019-05-25 | 2019-05-25 | 3 | OPERATIONS | SAFETY | 14
2019-03-31 | 378142 | Work Order Description - 378142 - PM | PM | 4 | 632580 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-09 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 378144 | Work Order Description - 378144 - PM | PM | 4 | 583919 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-09 | 2019-06-01 | 2019-06-01 | 3 | OPERATIONS | SAFETY | 14
2019-03-31 | 378146 | Work Order Description - 378146 - PM | PM | 4 | 122683 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-09 | 2019-06-01 | 2019-06-01 | 3 | OPERATIONS | SAFETY | 4
2019-03-31 | 378148 | Work Order Description - 378148 - PM | PM | 4 | 122684 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-29 | 2019-05-25 | 2019-05-25 | 3 | OPERATIONS | SAFETY | 2
2019-03-31 | 378150 | Work Order Description - 378150 - PM | PM | 4 | 583934 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-09 | 2019-06-01 | 2019-06-01 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 378152 | Work Order Description - 378152 - PM | PM | 4 | 583934 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-09 | 2019-06-01 | 2019-06-01 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 378156 | Work Order Description - 378156 - PM | PM | 4 | 632577 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-05 | 2019-05-25 | 2019-05-25 | 2 | OPERATIONS | SAFETY | 2
2019-03-31 | 378158 | Work Order Description - 378158 - PM | PM | 1 | 446516 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378160 | Work Order Description - 378160 - PM | PM | 1 | 446516 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378162 | Work Order Description - 378162 - PM | PM | 1 | 446516 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378164 | Work Order Description - 378164 - PM | PM | 3 | 499060 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-10-18 | 2019-05-08 | 2019-05-08 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 378166 | Work Order Description - 378166 - PM | PM | 3 | 499060 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-10-18 | 2019-05-08 | 2019-05-08 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 378172 | Work Order Description - 378172 - PM | PM | 4 | 408811 | SCHD | PACK-ISOL | 2019-01-31 | 2019-08-14 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378174 | Work Order Description - 378174 - PM | PM | 4 | 475670 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-10-11 | 2019-05-01 | 2019-05-01 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 378176 | Work Order Description - 378176 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 378178 | Work Order Description - 378178 - PM | PM | 3 | 20477 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 378180 | Work Order Description - 378180 - PM | PM | 4 | 601923 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 2 | OPERATIONS | OPERATIONS | 60
2019-03-31 | 378192 | Work Order Description - 378192 - PSPM | PSPM | 1 | 29041 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 378194 | Work Order Description - 378194 - PSPM | PSPM | 1 | 29041 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 378196 | Work Order Description - 378196 - PM | PM | 1 | 583832 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 378199 | Work Order Description - 378199 - PSPM | PSPM | 1 | 555932 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | ELECTRICAL | 84
2019-03-31 | 378201 | Work Order Description - 378201 - PSPM | PSPM | 1 | 534910 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378203 | Work Order Description - 378203 - PSPM | PSPM | 1 | 73725 | SCHD | PACK-ISOL | 2019-01-25 | 2019-05-27 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378205 | Work Order Description - 378205 - PSPM | PSPM | 1 | 403506 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 378207 | Work Order Description - 378207 - PSPM | PSPM | 1 | 303849 | SCHD | SYS-ISOL | 2019-01-31 | 2019-06-13 | 2019-03-30 | 2019-03-30 | 1 | INTEGRITY | INSPECTION | 14
2019-03-31 | 378209 | Work Order Description - 378209 - PSPM | PSPM | 1 | 482583 | SCHD | SYS-ISOL | 2019-01-31 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | INTEGRITY | INSPECTION | 20
2019-03-31 | 378211 | Work Order Description - 378211 - PM | PM | 1 | 501092 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-02 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | SAFETY | 6
2019-03-31 | 378213 | Work Order Description - 378213 - PM | PM | 4 | 555734 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-12-02 | 2019-04-29 | 2019-04-29 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 378215 | Work Order Description - 378215 - PM | PM | 4 | 479920 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 378219 | Work Order Description - 378219 - PM | PM | 4 | 320850 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-25 | 2019-05-01 | 2019-05-01 | 2 | DRILLING | DRILLING | 5
2019-03-31 | 378225 | Work Order Description - 378225 - PM | PM | 4 | 552014 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 2 | DRILLING | DRILLING | 8
2019-03-31 | 378229 | Work Order Description - 378229 - PM | PM | 4 | 216069 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 2 | DRILLING | DRILLING | 4.5
2019-03-31 | 378231 | Work Order Description - 378231 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 378233 | Work Order Description - 378233 - PM | PM | 4 | 243160 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 378235 | Work Order Description - 378235 - PM | PM | 4 | 502361 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 378239 | Work Order Description - 378239 - PM | PM | 4 | 479949 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 378241 | Work Order Description - 378241 - PM | PM | 4 | 479641 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-08-18 | 2019-05-01 | 2019-05-01 | 2 | DRILLING | ELECTRICAL | 4
2019-03-31 | 378243 | Work Order Description - 378243 - PM | PM | 4 | 243841 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-08-18 | 2019-05-01 | 2019-05-01 | 2 | DRILLING | ELECTRICAL | 4
2019-03-31 | 378245 | Work Order Description - 378245 - PM | PM | 4 | 216927 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-25 | 2019-04-24 | 2019-04-24 | 3 | OPERATIONS | MEDIC | 11
2019-03-31 | 378247 | Work Order Description - 378247 - PM | PM | 4 | 320752 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 2 | DRILLING | DRILLING | 4
2019-03-31 | 378249 | Work Order Description - 378249 - PM | PM | 4 | 556633 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 2 | DRILLING | DRILLING | 4
2019-03-31 | 378251 | Work Order Description - 378251 - PM | PM | 4 | 320336 | SCHD | NORM-OPS | 2019-01-25 | 2019-07-09 | 2019-05-15 | 2019-05-15 | 2 | DRILLING | DRILLING | 11
2019-03-31 | 378255 | Work Order Description - 378255 - PM | PM | 4 | 216249 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 2 | DRILLING | DRILLING | 8
2019-03-31 | 378257 | Work Order Description - 378257 - PM | PM | 4 | 552241 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 2 | DRILLING | DRILLING | 4
2019-03-31 | 378259 | Work Order Description - 378259 - PM | PM | 4 | 316323 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 2 | DRILLING | DRILLING | 5
2019-03-31 | 378263 | Work Order Description - 378263 - PM | PM | 2 | 216248 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 2 | DRILLING | DRILLING | 18
2019-03-31 | 378267 | Work Order Description - 378267 - PM | PM | 4 | 479949 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 2 | DRILLING | DRILLING | 8
2019-03-31 | 378271 | Work Order Description - 378271 - PM | PM | 4 | 316226 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 378275 | Work Order Description - 378275 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-27 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 378277 | Work Order Description - 378277 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-03 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 378279 | Work Order Description - 378279 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-10 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 378283 | Work Order Description - 378283 - PM | PM | 4 | 189042 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-08-27 | 2019-05-10 | 2019-05-10 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 378285 | Work Order Description - 378285 - PM | PM | 2 | 502749 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-25 | 2019-05-25 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 378287 | Work Order Description - 378287 - PM | PM | 2 | 20523 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-08-18 | 2019-05-01 | 2019-05-01 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 378289 | Work Order Description - 378289 - PM | PM | 3 | 478664 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-25 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 378291 | Work Order Description - 378291 - PM | PM | 3 | 258358 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-25 | 2019-05-01 | 2019-05-01 | 2 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 378293 | Work Order Description - 378293 - PSPM | PSPM | 4 | 403503 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-24 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 378295 | Work Order Description - 378295 - PSPM | PSPM | 4 | 403503 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-31 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 378297 | Work Order Description - 378297 - PSPM | PSPM | 4 | 403503 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-07 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 378299 | Work Order Description - 378299 - PSPM | PSPM | 4 | 403503 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-14 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 378301 | Work Order Description - 378301 - PSPM | PSPM | 1 | 555932 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | OPERATIONS | OPERATIONS | 16
2019-03-31 | 378303 | Work Order Description - 378303 - PSPM | PSPM | 1 | 478533 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 378305 | Work Order Description - 378305 - PSPM | PSPM | 1 | 482706 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 378307 | Work Order Description - 378307 - PM | PM | 4 | 556260 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 378309 | Work Order Description - 378309 - PM | PM | 4 | 556260 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 378311 | Work Order Description - 378311 - PM | PM | 4 | 556260 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 378313 | Work Order Description - 378313 - PSPM | PSPM | 1 | 555385 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-14 | 2019-05-14 | 2019-05-14 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 378315 | Work Order Description - 378315 - PSPM | PSPM | 1 | 176747 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-14 | 2019-05-14 | 2019-05-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378319 | Work Order Description - 378319 - PM | PM | 2 | 216011 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378321 | Work Order Description - 378321 - PM | PM | 2 | 216011 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378323 | Work Order Description - 378323 - PM | PM | 2 | 216011 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378325 | Work Order Description - 378325 - PM | PM | 3 | 490777 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378327 | Work Order Description - 378327 - PM | PM | 4 | 464230 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378329 | Work Order Description - 378329 - PM | PM | 2 | 216248 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 2 | DRILLING | DRILLING | 12
2019-03-31 | 378331 | Work Order Description - 378331 - PM | PM | 4 | 554809 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 378333 | Work Order Description - 378333 - PM | PM | 4 | 502421 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-08 | 2019-05-08 | 2019-05-08 | 1 | MAINTENANCE | MECHANICAL | 15
2019-03-31 | 378335 | Work Order Description - 378335 - PSPM | PSPM | 1 | 479579 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | INTEGRITY | INSPECTION | 675
2019-03-31 | 378337 | Work Order Description - 378337 - PM | PM | 4 | 320150 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-27 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 378339 | Work Order Description - 378339 - PSPM | PSPM | 1 | 303784 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378341 | Work Order Description - 378341 - PM | PM | 4 | 460846 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-25 | 2019-04-24 | 2019-04-24 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 378343 | Work Order Description - 378343 - PM | PM | 4 | 460846 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 378345 | Work Order Description - 378345 - PM | PM | 4 | 460846 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-08 | 2019-05-08 | 2019-05-08 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 378347 | Work Order Description - 378347 - PM | PM | 4 | 460846 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 378349 | Work Order Description - 378349 - PM | PM | 4 | 320026 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 378351 | Work Order Description - 378351 - PM | PM | 4 | 320026 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 378353 | Work Order Description - 378353 - PM | PM | 4 | 320026 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 378355 | Work Order Description - 378355 - PSPM | PSPM | 1 | 34240 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 48
2019-03-31 | 378357 | Work Order Description - 378357 - PSPM | PSPM | 1 | 34240 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 48
2019-03-31 | 378359 | Work Order Description - 378359 - PSPM | PSPM | 1 | 34240 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-14 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 378361 | Work Order Description - 378361 - PSPM | PSPM | 1 | 34240 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-07 | 2019-05-11 | 2019-05-11 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 378365 | Work Order Description - 378365 - PM | PM | 4 | 180449 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-03 | 2019-05-03 | 2019-05-03 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378367 | Work Order Description - 378367 - PM | PM | 4 | 180450 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-03 | 2019-05-03 | 2019-05-03 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378369 | Work Order Description - 378369 - PM | PM | 4 | 216158 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 378371 | Work Order Description - 378371 - PM | PM | 4 | 216158 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-08 | 2019-05-08 | 2019-05-08 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 378373 | Work Order Description - 378373 - PM | PM | 4 | 216158 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 378375 | Work Order Description - 378375 - PM | PM | 3 | 464260 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2020-04-04 | 2020-04-04 | 3 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378377 | Work Order Description - 378377 - PM | PM | 1 | 464259 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-04-13 | 2019-04-13 | 3 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378379 | Work Order Description - 378379 - PM | PM | 1 | 464260 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2020-04-04 | 2020-04-04 | 3 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378381 | Work Order Description - 378381 - PM | PM | 3 | 464260 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2020-04-04 | 2020-04-04 | 3 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378383 | Work Order Description - 378383 - PM | PM | 3 | 464260 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2020-04-04 | 2020-04-04 | 3 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378385 | Work Order Description - 378385 - PM | PM | 3 | 464260 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2020-04-04 | 2020-04-04 | 3 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378387 | Work Order Description - 378387 - PM | PM | 4 | 567819 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378389 | Work Order Description - 378389 - PM | PM | 4 | 74216 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378391 | Work Order Description - 378391 - PM | PM | 4 | 74216 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378393 | Work Order Description - 378393 - PM | PM | 4 | 74216 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378395 | Work Order Description - 378395 - PM | PM | 4 | 259282 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378397 | Work Order Description - 378397 - PM | PM | 4 | 325096 | SCHD | EQUIP-ISOL | 2019-03-18 | 2019-06-26 | 2019-05-02 | 2019-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 378399 | Work Order Description - 378399 - PM | PM | 4 | 257361 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378401 | Work Order Description - 378401 - PM | PM | 1 | 464260 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2020-04-04 | 2020-04-04 | 3 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378403 | Work Order Description - 378403 - PM | PM | 1 | 464260 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2020-04-04 | 2020-04-04 | 3 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378405 | Work Order Description - 378405 - PM | PM | 1 | 464259 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2020-04-04 | 2020-04-04 | 3 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378407 | Work Order Description - 378407 - PM | PM | 3 | 464260 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2020-04-04 | 2020-04-04 | 3 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378409 | Work Order Description - 378409 - PM | PM | 4 | 309966 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 378411 | Work Order Description - 378411 - PM | PM | 4 | 325097 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 378413 | Work Order Description - 378413 - PM | PM | 4 | 180379 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378415 | Work Order Description - 378415 - PM | PM | 1 | 464260 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2020-04-04 | 2020-04-04 | 3 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378417 | Work Order Description - 378417 - PM | PM | 4 | 95502 | SCHD | PACK-ISOL | 2019-01-31 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378419 | Work Order Description - 378419 - PSPM | PSPM | 1 | 81186 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 378421 | Work Order Description - 378421 - PSPM | PSPM | 1 | 128959 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | INTEGRITY | INSPECTION | 294
2019-03-31 | 378423 | Work Order Description - 378423 - PM | PM | 4 | 325097 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378425 | Work Order Description - 378425 - PSPM | PSPM | 1 | 123510 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-26 | 2019-04-25 | 2019-04-25 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 378427 | Work Order Description - 378427 - PSPM | PSPM | 1 | 123510 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 378429 | Work Order Description - 378429 - PSPM | PSPM | 1 | 123510 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 378431 | Work Order Description - 378431 - PM | PM | 3 | 123510 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 378433 | Work Order Description - 378433 - PM | PM | 4 | 487367 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378435 | Work Order Description - 378435 - PM | PM | 4 | 555301 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 4 | MAINTENANCE | MEDIC | 21
2019-03-31 | 378437 | Work Order Description - 378437 - PM | PM | 4 | 491877 | SCHD | NORM-OPS | 2019-01-25 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 378439 | Work Order Description - 378439 - PM | PM | 4 | 383750 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-29 | 2019-05-05 | 2019-05-05 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378441 | Work Order Description - 378441 - PM | PM | 4 | 309966 | SCHD | EQUIP-ISOL | 2019-03-18 | 2019-06-26 | 2019-05-02 | 2019-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 378443 | Work Order Description - 378443 - PM | PM | 4 | 325096 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 378445 | Work Order Description - 378445 - PM | PM | 4 | 325097 | SCHD | EQUIP-ISOL | 2019-03-18 | 2019-06-26 | 2019-05-02 | 2019-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 378447 | Work Order Description - 378447 - PM | PM | 4 | 259936 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378449 | Work Order Description - 378449 - PM | PM | 4 | 28508 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 378451 | Work Order Description - 378451 - PM | PM | 4 | 19641 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 378653 | Work Order Description - 378653 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | SAFETY | 7
2019-03-31 | 378655 | Work Order Description - 378655 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 2 | MAINTENANCE | SAFETY | 7
2019-03-31 | 378657 | Work Order Description - 378657 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 2 | MAINTENANCE | SAFETY | 7
2019-03-31 | 378659 | Work Order Description - 378659 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-26 | 2019-04-25 | 2019-04-25 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 378661 | Work Order Description - 378661 - PM | PM | 4 | 74891 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-03 | 2019-05-09 | 2019-05-11 | 2 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 378663 | Work Order Description - 378663 - PM | PM | 4 | 527315 | SCHD | NORM-OPS | 2019-01-21 | 2019-07-01 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 378665 | Work Order Description - 378665 - PM | PM | 4 | 527315 | SCHD | NORM-OPS | 2019-01-21 | 2019-07-01 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 378667 | Work Order Description - 378667 - PM | PM | 4 | 527315 | SCHD | NORM-OPS | 2019-01-21 | 2019-07-01 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 378669 | Work Order Description - 378669 - PM | PM | 4 | 659434 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 378671 | Work Order Description - 378671 - PM | PM | 4 | 659434 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 2 | MAINTENANCE | ELECTRICAL | 7
2019-03-31 | 378673 | Work Order Description - 378673 - PM | PM | 4 | 659434 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-15 | 2019-05-10 | 2019-05-10 | 2 | MAINTENANCE | ELECTRICAL | 7
2019-03-31 | 378675 | Work Order Description - 378675 - PM | PM | 4 | 659434 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-15 | 2019-05-10 | 2019-05-10 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 378677 | Work Order Description - 378677 - PM | PM | 4 | 659434 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 378679 | Work Order Description - 378679 - PM | PM | 4 | 659434 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 2 | MAINTENANCE | ELECTRICAL | 7
2019-03-31 | 378681 | Work Order Description - 378681 - PM | PM | 4 | 383151 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-01 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 378685 | Work Order Description - 378685 - PM | PM | 4 | 78558 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-01 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 378687 | Work Order Description - 378687 - PM | PM | 4 | 383144 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-01 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 378689 | Work Order Description - 378689 - PM | PM | 4 | 450692 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 378691 | Work Order Description - 378691 - PM | PM | 3 | 449150 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378693 | Work Order Description - 378693 - PSPM | PSPM | 1 | 74959 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-08 | 2019-05-08 | 2019-05-08 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378695 | Work Order Description - 378695 - PSPM | PSPM | 1 | 669626 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378697 | Work Order Description - 378697 - PM | PM | 3 | 375909 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 378699 | Work Order Description - 378699 - PSPM | PSPM | 1 | 451271 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 378701 | Work Order Description - 378701 - PM | PM | 4 | 448718 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378703 | Work Order Description - 378703 - PM | PM | 4 | 127778 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378705 | Work Order Description - 378705 - PM | PM | 4 | 448757 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378707 | Work Order Description - 378707 - PM | PM | 4 | 448753 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378709 | Work Order Description - 378709 - PM | PM | 4 | 127779 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378711 | Work Order Description - 378711 - PM | PM | 4 | 218109 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378713 | Work Order Description - 378713 - PM | PM | 4 | 448754 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378715 | Work Order Description - 378715 - PM | PM | 4 | 375727 | SCHD | EQUIP-ISOL | 2019-01-21 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378717 | Work Order Description - 378717 - PM | PM | 4 | 74891 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 2 | OPERATIONS | OPERATIONS | 1
2019-03-31 | 378719 | Work Order Description - 378719 - PM | PM | 4 | 127873 | SCHD | EQUIP-ISOL | 2019-01-21 | 2019-07-01 | 2019-05-24 | 2019-05-24 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 378721 | Work Order Description - 378721 - PM | PM | 4 | 670583 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 378723 | Work Order Description - 378723 - PM | PM | 4 | 450692 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 1 | OPERATIONS | SAFETY | 2
2019-03-31 | 378725 | Work Order Description - 378725 - PSPM | PSPM | 1 | 383476 | SCHD | EQUIP-ISOL | 2019-01-21 | 2019-07-27 | 2019-06-22 | 2019-06-22 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 378727 | Work Order Description - 378727 - PM | PM | 4 | 105130 | SCHD | EQUIP-ISOL | 2019-01-21 | 2019-10-25 | 2019-06-22 | 2019-06-22 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 378731 | Work Order Description - 378731 - PSPM | PSPM | 1 | 127843 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 378733 | Work Order Description - 378733 - PM | PM | 4 | 80734 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-25 | 2019-05-01 | 2019-05-01 | 2 | OPERATIONS | SAFETY | 1
2019-03-31 | 378735 | Work Order Description - 378735 - PM | PM | 3 | 266661 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-15 | 2019-05-15 | 2019-05-22 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 378737 | Work Order Description - 378737 - PSPM | PSPM | 1 | 105915 | SCHD | PACK-ISOL | 2019-02-13 | 2019-05-26 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 378739 | Work Order Description - 378739 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378741 | Work Order Description - 378741 - PM | PM | 4 | 237629 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 378743 | Work Order Description - 378743 - PM | PM | 4 | 377675 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 378745 | Work Order Description - 378745 - PSPM | PSPM | 1 | 127760 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | OPERATIONS | SAFETY | 2
2019-03-31 | 378747 | Work Order Description - 378747 - PSPM | PSPM | 1 | 659251 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 378749 | Work Order Description - 378749 - PSPM | PSPM | 1 | 659086 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | SAFETY | 6
2019-03-31 | 378751 | Work Order Description - 378751 - PSPM | PSPM | 1 | 127761 | SCHD | NORM-OPS | 2019-03-22 | 2019-06-09 | 2019-05-09 | 2019-05-10 | 1 | MAINTENANCE | SAFETY | 14
2019-03-31 | 378753 | Work Order Description - 378753 - PSPM | PSPM | 1 | 659055 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | OPERATIONS | SAFETY | 7
2019-03-31 | 378755 | Work Order Description - 378755 - PSPM | PSPM | 1 | 659056 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | OPERATIONS | SAFETY | 6
2019-03-31 | 378757 | Work Order Description - 378757 - PSPM | PSPM | 1 | 528211 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 378759 | Work Order Description - 378759 - PSPM | PSPM | 1 | 659058 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | OPERATIONS | SAFETY | 1
2019-03-31 | 378761 | Work Order Description - 378761 - PSPM | PSPM | 1 | 450992 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | SAFETY | 4
2019-03-31 | 378763 | Work Order Description - 378763 - PSPM | PSPM | 1 | 663164 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378765 | Work Order Description - 378765 - PSPM | PSPM | 1 | 663164 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-03 | 2019-05-03 | 2019-05-03 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378767 | Work Order Description - 378767 - PSPM | PSPM | 1 | 663164 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378769 | Work Order Description - 378769 - PSPM | PSPM | 1 | 42961 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-26 | 2019-04-25 | 2019-04-25 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378771 | Work Order Description - 378771 - PSPM | PSPM | 1 | 42961 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378773 | Work Order Description - 378773 - PSPM | PSPM | 1 | 42961 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378775 | Work Order Description - 378775 - PM | PM | 4 | 528193 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-01 | 2019-05-01 | 2019-05-04 | 1 | INTEGRITY | INSPECTION | 34
2019-03-31 | 378777 | Work Order Description - 378777 - PM | PM | 4 | 440671 | SCHD | EQUIP-ISOL | 2019-01-21 | 2019-11-03 | 2019-05-06 | 2019-05-06 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378779 | Work Order Description - 378779 - PSPM | PSPM | 1 | 106053 | SCHD | PACK-ISOL | 2019-02-13 | 2019-05-26 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 378781 | Work Order Description - 378781 - PM | PM | 4 | 186635 | SCHD | EQUIP-ISOL | 2019-01-21 | 2019-07-18 | 2019-05-06 | 2019-05-06 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378783 | Work Order Description - 378783 - PM | PM | 4 | 186634 | SCHD | EQUIP-ISOL | 2019-01-21 | 2019-07-18 | 2019-05-06 | 2019-05-06 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378785 | Work Order Description - 378785 - PSPM | PSPM | 1 | 92712 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378787 | Work Order Description - 378787 - PSPM | PSPM | 1 | 277246 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378789 | Work Order Description - 378789 - PSPM | PSPM | 1 | 396754 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 378791 | Work Order Description - 378791 - PSPM | PSPM | 1 | 277349 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378793 | Work Order Description - 378793 - PM | PM | 4 | 527339 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 378795 | Work Order Description - 378795 - PM | PM | 4 | 93182 | WPLAN | EQUIP-ISOL | 2019-01-15 | 2019-06-14 | 2019-05-14 | 2019-05-14 | 1 | INTEGRITY | DRILLING | 4
2019-03-31 | 378799 | Work Order Description - 378799 - PSPM | PSPM | 4 | 99232 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-26 | 2019-04-25 | 2019-04-26 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 378801 | Work Order Description - 378801 - PSPM | PSPM | 4 | 99232 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-09 | 2019-05-09 | 2019-05-10 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 378803 | Work Order Description - 378803 - PSPM | PSPM | 4 | 99434 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-02 | 2019-05-02 | 2019-05-03 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 378805 | Work Order Description - 378805 - PSPM | PSPM | 1 | 99232 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | SERVICES | 4
2019-03-31 | 378807 | Work Order Description - 378807 - PSPM | PSPM | 1 | 99434 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | SERVICES | 4
2019-03-31 | 378809 | Work Order Description - 378809 - PM | PM | 4 | 266557 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-01 | 2019-05-01 | 2019-05-02 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 378811 | Work Order Description - 378811 - PM | PM | 4 | 126130 | SCHD | EQUIP-ISOL | 2019-01-21 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378813 | Work Order Description - 378813 - PSPM | PSPM | 1 | 392310 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 378815 | Work Order Description - 378815 - PM | PM | 2 | 80160 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-05-26 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 378817 | Work Order Description - 378817 - PM | PM | 4 | 527749 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 378819 | Work Order Description - 378819 - PM | PM | 4 | 123579 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378821 | Work Order Description - 378821 - PM | PM | 4 | 123592 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378823 | Work Order Description - 378823 - PSPM | PSPM | 1 | 527364 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 378825 | Work Order Description - 378825 - PSPM | PSPM | 1 | 527364 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378827 | Work Order Description - 378827 - PSPM | PSPM | 1 | 450982 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378829 | Work Order Description - 378829 - PSPM | PSPM | 1 | 450982 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378831 | Work Order Description - 378831 - PSPM | PSPM | 1 | 527364 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378833 | Work Order Description - 378833 - PSPM | PSPM | 1 | 450982 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378835 | Work Order Description - 378835 - PSPM | PSPM | 1 | 450982 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378837 | Work Order Description - 378837 - PSPM | PSPM | 1 | 659512 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 378839 | Work Order Description - 378839 - PSPM | PSPM | 1 | 659512 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378841 | Work Order Description - 378841 - PSPM | PSPM | 1 | 659512 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378843 | Work Order Description - 378843 - PSPM | PSPM | 1 | 659512 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378845 | Work Order Description - 378845 - PSPM | PSPM | 1 | 659512 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378847 | Work Order Description - 378847 - PSPM | PSPM | 1 | 527364 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378849 | Work Order Description - 378849 - PSPM | PSPM | 1 | 227906 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378851 | Work Order Description - 378851 - PSPM | PSPM | 1 | 227906 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 378853 | Work Order Description - 378853 - PSPM | PSPM | 1 | 659514 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-14 | 2019-05-14 | 2019-05-15 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 378855 | Work Order Description - 378855 - PSPM | PSPM | 1 | 392215 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 378857 | Work Order Description - 378857 - PSPM | PSPM | 1 | 392215 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 378859 | Work Order Description - 378859 - PSPM | PSPM | 1 | 392215 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 378861 | Work Order Description - 378861 - PSPM | PSPM | 1 | 392215 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-14 | 2019-05-14 | 2019-05-14 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 378863 | Work Order Description - 378863 - PSPM | PSPM | 1 | 451126 | SCHD | NORM-OPS | 2019-03-18 | 2019-06-08 | 2019-04-06 | 2019-04-17 | 1 | MAINTENANCE | MECHANICAL | 80
2019-03-31 | 378865 | Work Order Description - 378865 - PSPM | PSPM | 1 | 227869 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 378867 | Work Order Description - 378867 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378869 | Work Order Description - 378869 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-06 | 2019-05-06 | 2019-05-06 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378871 | Work Order Description - 378871 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378873 | Work Order Description - 378873 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378875 | Work Order Description - 378875 - PSPM | PSPM | 1 | 227906 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378877 | Work Order Description - 378877 - PSPM | PSPM | 1 | 227906 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378879 | Work Order Description - 378879 - PSPM | PSPM | 1 | 450982 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378881 | Work Order Description - 378881 - PSPM | PSPM | 1 | 127636 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 378883 | Work Order Description - 378883 - PSPM | PSPM | 1 | 453251 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-09 | 2019-05-09 | 2019-05-10 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 378885 | Work Order Description - 378885 - PSPM | PSPM | 1 | 238048 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378887 | Work Order Description - 378887 - PSPM | PSPM | 1 | 127752 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 378889 | Work Order Description - 378889 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 378891 | Work Order Description - 378891 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 378893 | Work Order Description - 378893 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 378895 | Work Order Description - 378895 - PSPM | PSPM | 1 | 669726 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 378897 | Work Order Description - 378897 - PSPM | PSPM | 1 | 669726 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 378899 | Work Order Description - 378899 - PSPM | PSPM | 1 | 669726 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 378901 | Work Order Description - 378901 - PM | PM | 4 | 528189 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 378903 | Work Order Description - 378903 - PM | PM | 4 | 659496 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-03 | 2019-05-03 | 2019-05-03 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 378905 | Work Order Description - 378905 - PSPM | PSPM | 1 | 528213 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-25 | 2019-04-24 | 2019-04-24 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 378907 | Work Order Description - 378907 - PSPM | PSPM | 1 | 451126 | WPLAN | NORM-OPS | 2019-01-15 | 2019-06-07 | 2019-04-20 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 80
2019-03-31 | 378909 | Work Order Description - 378909 - PSPM | PSPM | 1 | 228306 | SCHD | NORM-OPS | 2019-03-18 | 2019-06-08 | 2019-04-18 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 120
2019-03-31 | 378911 | Work Order Description - 378911 - PM | PM | 4 | 444792 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 378913 | Work Order Description - 378913 - PM | PM | 4 | 266422 | SCHD | EQUIP-ISOL | 2019-01-24 | 2019-10-22 | 2019-05-12 | 2019-05-12 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 378915 | Work Order Description - 378915 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378917 | Work Order Description - 378917 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378919 | Work Order Description - 378919 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378921 | Work Order Description - 378921 - PSPM | PSPM | 1 | 378444 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-28 | 2019-04-20 | 2019-04-21 | 1 | MAINTENANCE | ELECTRICAL | 52
2019-03-31 | 378923 | Work Order Description - 378923 - PSPM | PSPM | 1 | 451162 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-28 | 2019-04-20 | 2019-05-02 | 1 | MAINTENANCE | ELECTRICAL | 267
2019-03-31 | 378925 | Work Order Description - 378925 - PM | PM | 4 | 126786 | SCHD | EQUIP-ISOL | 2019-01-21 | 2019-07-13 | 2019-05-01 | 2019-05-01 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378929 | Work Order Description - 378929 - PSPM | PSPM | 1 | 450687 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-11 | 2019-03-31 | 2019-03-31 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 378931 | Work Order Description - 378931 - PSPM | PSPM | 1 | 528118 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | INTEGRITY | SERVICES | 4
2019-03-31 | 378933 | Work Order Description - 378933 - PM | PM | 4 | 126787 | SCHD | EQUIP-ISOL | 2019-01-21 | 2019-07-13 | 2019-05-01 | 2019-05-01 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378937 | Work Order Description - 378937 - PSPM | PSPM | 1 | 659551 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378939 | Work Order Description - 378939 - PSPM | PSPM | 1 | 659551 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 378941 | Work Order Description - 378941 - PM | PM | 4 | 110954 | SCHD | EQUIP-ISOL | 2019-01-21 | 2019-06-25 | 2019-05-01 | 2019-05-01 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 378943 | Work Order Description - 378943 - PSPM | PSPM | 1 | 126920 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-26 | 2019-04-25 | 2019-04-25 | 1 | MAINTENANCE | ELECTRICAL | 1.5
2019-03-31 | 378945 | Work Order Description - 378945 - PSPM | PSPM | 1 | 126920 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | MAINTENANCE | ELECTRICAL | 1.5
2019-03-31 | 378947 | Work Order Description - 378947 - PSPM | PSPM | 1 | 126920 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 1 | MAINTENANCE | ELECTRICAL | 1.5
2019-03-31 | 378949 | Work Order Description - 378949 - PSPM | PSPM | 1 | 450926 | SCHD | PACK-ISOL | 2019-02-13 | 2019-05-26 | 2019-04-25 | 2019-04-25 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378951 | Work Order Description - 378951 - PSPM | PSPM | 1 | 450926 | SCHD | PACK-ISOL | 2019-02-13 | 2019-05-26 | 2019-04-25 | 2019-04-25 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378953 | Work Order Description - 378953 - PSPM | PSPM | 1 | 670506 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378955 | Work Order Description - 378955 - PSPM | PSPM | 1 | 670511 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378957 | Work Order Description - 378957 - PSPM | PSPM | 1 | 375789 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 378959 | Work Order Description - 378959 - PSPM | PSPM | 1 | 450926 | SCHD | PACK-ISOL | 2019-02-13 | 2019-05-26 | 2019-04-25 | 2019-04-25 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378961 | Work Order Description - 378961 - PSPM | PSPM | 1 | 450926 | SCHD | PACK-ISOL | 2019-02-13 | 2019-05-26 | 2019-04-25 | 2019-04-25 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378963 | Work Order Description - 378963 - PSPM | PSPM | 1 | 227791 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-25 | 2019-03-17 | 2019-03-17 | 1 | MAINTENANCE | MECHANICAL | 0
2019-03-31 | 378965 | Work Order Description - 378965 - PSPM | PSPM | 1 | 659338 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-25 | 2019-04-24 | 2019-04-24 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 378967 | Work Order Description - 378967 - PSPM | PSPM | 1 | 659339 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-25 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 378969 | Work Order Description - 378969 - PSPM | PSPM | 1 | 450926 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-25 | 2019-04-24 | 2019-04-24 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 378971 | Work Order Description - 378971 - PSPM | PSPM | 1 | 450926 | SCHD | PACK-ISOL | 2019-02-13 | 2019-05-26 | 2019-04-25 | 2019-04-25 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 378978 | Work Order Description - 378978 - PSPM | PSPM | 1 | 228343 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-09 | 2019-04-27 | 2019-04-28 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 378980 | Work Order Description - 378980 - PSPM | PSPM | 1 | 228343 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-08 | 2019-05-08 | 2019-05-09 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 378988 | Work Order Description - 378988 - PSPM | PSPM | 1 | 668570 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-25 | 2019-04-24 | 2019-04-25 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 378990 | Work Order Description - 378990 - PM | PM | 4 | 227826 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-25 | 2019-04-24 | 2019-05-08 | 2 | MAINTENANCE | ELECTRICAL | 100
2019-03-31 | 378992 | Work Order Description - 378992 - PSPM | PSPM | 1 | 450681 | SCHD | NORM-OPS | 2019-03-18 | 2019-05-31 | 2019-04-30 | 2019-05-04 | 2 | INTEGRITY | INSPECTION | 70
2019-03-31 | 378994 | Work Order Description - 378994 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 378996 | Work Order Description - 378996 - PSPM | PSPM | 1 | 450982 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 378998 | Work Order Description - 378998 - PSPM | PSPM | 1 | 659512 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 379000 | Work Order Description - 379000 - PSPM | PSPM | 1 | 227906 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-14 | 2019-05-14 | 2019-05-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 379002 | Work Order Description - 379002 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 379004 | Work Order Description - 379004 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 379006 | Work Order Description - 379006 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 379008 | Work Order Description - 379008 - PSPM | PSPM | 1 | 527370 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-08 | 2019-05-02 | 2019-05-03 | 1 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 379012 | Work Order Description - 379012 - PSPM | PSPM | 1 | 237941 | SCHD | PACK-ISOL | 2019-02-13 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 379014 | Work Order Description - 379014 - PSPM | PSPM | 1 | 80094 | SCHD | PACK-ISOL | 2019-02-13 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 379016 | Work Order Description - 379016 - PSPM | PSPM | 1 | 237943 | SCHD | PACK-ISOL | 2019-02-13 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 379018 | Work Order Description - 379018 - PM | PM | 3 | 375585 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 379020 | Work Order Description - 379020 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 379022 | Work Order Description - 379022 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 379024 | Work Order Description - 379024 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 379026 | Work Order Description - 379026 - PM | PM | 4 | 126984 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-26 | 2019-04-25 | 2019-04-25 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 379028 | Work Order Description - 379028 - PM | PM | 4 | 126984 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 379030 | Work Order Description - 379030 - PM | PM | 4 | 126984 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-09 | 2019-05-09 | 2019-05-09 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 379032 | Work Order Description - 379032 - PSPM | PSPM | 1 | 527370 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-08 | 2019-05-02 | 2019-05-03 | 1 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 379034 | Work Order Description - 379034 - PM | PM | 2 | 450548 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 3 | OPERATIONS | OPERATIONS | 4
2019-03-31 | 379036 | Work Order Description - 379036 - PM | PM | 4 | 238227 | SCHD | EQUIP-ISOL | 2019-03-18 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 2 | INTEGRITY | SERVICES | 8
2019-03-31 | 379038 | Work Order Description - 379038 - PSPM | PSPM | 1 | 227941 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 379040 | Work Order Description - 379040 - PSPM | PSPM | 1 | 227941 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 379042 | Work Order Description - 379042 - PSPM | PSPM | 1 | 450986 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 379044 | Work Order Description - 379044 - PSPM | PSPM | 1 | 450986 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-13 | 2019-05-13 | 2019-05-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 379046 | Work Order Description - 379046 - PSPM | PSPM | 1 | 659559 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-24 | 2019-04-23 | 2019-04-24 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 379048 | Work Order Description - 379048 - PSPM | PSPM | 1 | 659558 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-24 | 2019-04-23 | 2019-04-24 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 379050 | Work Order Description - 379050 - PSPM | PSPM | 1 | 450994 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 379052 | Work Order Description - 379052 - PSPM | PSPM | 1 | 450994 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-24 | 2019-04-23 | 2019-04-23 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 379054 | Work Order Description - 379054 - PM | PM | 4 | 670525 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 379056 | Work Order Description - 379056 - PM | PM | 4 | 375852 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-15 | 2019-05-15 | 2019-05-15 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 379058 | Work Order Description - 379058 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 379063 | Work Order Description - 379063 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 379068 | Work Order Description - 379068 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 379076 | Work Order Description - 379076 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-14 | 2019-05-14 | 2019-05-14 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 379079 | Work Order Description - 379079 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 3 | MAINTENANCE | INSTRUMENTS | 0.5
2019-03-31 | 379082 | Work Order Description - 379082 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-14 | 2019-05-14 | 2019-05-14 | 3 | MAINTENANCE | ELECTRICAL | 0.5
2019-03-31 | 379084 | Work Order Description - 379084 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 379087 | Work Order Description - 379087 - PM | PM | 4 | 124535 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-19 | 2019-04-25 | 2019-04-25 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 379089 | Work Order Description - 379089 - PM | PM | 4 | 398470 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-27 | 2019-04-26 | 2019-05-02 | 2 | MAINTENANCE | INSTRUMENTS | 49
2019-03-31 | 379091 | Work Order Description - 379091 - PSPM | PSPM | 1 | 99434 | SCHD | PACK-ISOL | 2019-01-21 | 2019-06-15 | 2019-05-15 | 2019-05-20 | 1 | MAINTENANCE | SERVICES | 36
2019-03-31 | 379093 | Work Order Description - 379093 - PM | PM | 4 | 450541 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-12 | 2019-05-12 | 2019-05-12 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 379095 | Work Order Description - 379095 - PM | PM | 4 | 98664 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-14 | 2019-05-14 | 2019-05-15 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 379097 | Work Order Description - 379097 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 379099 | Work Order Description - 379099 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 379101 | Work Order Description - 379101 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 379103 | Work Order Description - 379103 - PM | PM | 3 | 392215 | SCHD | PACK-ISOL | 2019-03-22 | 2019-06-25 | 2019-05-01 | 2019-05-02 | 2 | MAINTENANCE | ELECTRICAL | 28
2019-03-31 | 379105 | Work Order Description - 379105 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-27 | 2019-04-27 | 2019-04-29 | 3 | MAINTENANCE | MEDIC | 21
2019-03-31 | 379107 | Work Order Description - 379107 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-03 | 2019-05-03 | 2019-05-05 | 3 | MAINTENANCE | MEDIC | 21
2019-03-31 | 379109 | Work Order Description - 379109 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-10 | 2019-05-10 | 2019-05-12 | 3 | MAINTENANCE | MEDIC | 21
2019-03-31 | 379111 | Work Order Description - 379111 - PSPM | PSPM | 1 | 392053 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-15 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 379113 | Work Order Description - 379113 - PM | PM | 4 | 227935 | SCHD | NORM-OPS | 2019-01-21 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 379115 | Work Order Description - 379115 - PSPM | PSPM | 1 | 670509 | SCHD | EQUIP-ISOL | 2019-01-21 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 379117 | Work Order Description - 379117 - PSPM | PSPM | 1 | 110847 | SCHD | EQUIP-ISOL | 2019-01-21 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 384113 | Work Order Description - 384113 - BR | BR | 3 | 321719 | WPLAN | TPS | 2019-01-19 | 2020-01-15 | 2019-07-16 | 2019-07-16 | 3 | MAINTENANCE | MECHANICAL | 44
2019-03-31 | 384119 | Work Order Description - 384119 - BR | BR | 3 | 502629 | WPLAN | TPS | 2019-01-19 | 2020-01-16 | 2019-07-17 | 2019-07-17 | 3 | MAINTENANCE | MECHANICAL | 53
2019-03-31 | 384126 | Work Order Description - 384126 - BR | BR | 3 | 490205 | WPLAN | TPS | 2019-01-19 | 2020-01-16 | 2019-07-17 | 2019-07-17 | 3 | MAINTENANCE | MECHANICAL | 53
2019-03-31 | 384132 | Work Order Description - 384132 - BR | BR | 3 | 33635 | WPLAN | TPS | 2019-01-19 | 2020-01-16 | 2019-07-17 | 2019-07-17 | 3 | MAINTENANCE | MECHANICAL | 53
2019-03-31 | 384140 | Work Order Description - 384140 - BR | BR | 3 | 33634 | WPLAN | TPS | 2019-01-19 | 2020-01-16 | 2019-07-17 | 2019-07-17 | 3 | MAINTENANCE | MECHANICAL | 53
2019-03-31 | 384149 | Work Order Description - 384149 - PM | PM | 4 | 651607 | WSCHD | NORM-OPS | 2019-01-16 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 384151 | Work Order Description - 384151 - PSPM | PSPM | 1 | 360560 | WSCHD | EQUIP-ISOL | 2019-01-16 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 384153 | Work Order Description - 384153 - PSPM | PSPM | 1 | 410145 | WSCHD | EQUIP-ISOL | 2019-01-16 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 384155 | Work Order Description - 384155 - PSPM | PSPM | 1 | 55010 | WSCHD | EQUIP-ISOL | 2019-01-16 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 384157 | Work Order Description - 384157 - PM | PM | 3 | 53302 | WSCHD | EQUIP-ISOL | 2019-01-16 | 2019-09-02 | 2019-05-16 | 2019-05-16 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 384159 | Work Order Description - 384159 - PM | PM | 4 | 53332 | WSCHD | EQUIP-ISOL | 2019-01-16 | 2019-09-02 | 2019-05-16 | 2019-05-16 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 384161 | Work Order Description - 384161 - PM | PM | 4 | 357429 | WSCHD | EQUIP-ISOL | 2019-01-16 | 2019-10-08 | 2019-05-16 | 2019-05-16 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 384163 | Work Order Description - 384163 - PSPM | PSPM | 1 | 656071 | WSCHD | NORM-OPS | 2019-01-16 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 384165 | Work Order Description - 384165 - PSPM | PSPM | 1 | 357624 | WSCHD | NORM-OPS | 2019-01-16 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 384167 | Work Order Description - 384167 - PSPM | PSPM | 1 | 656072 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 384169 | Work Order Description - 384169 - PSPM | PSPM | 1 | 653327 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 384171 | Work Order Description - 384171 - PSPM | PSPM | 1 | 357626 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 384173 | Work Order Description - 384173 - PSPM | PSPM | 1 | 656070 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 384175 | Work Order Description - 384175 - PM | PM | 4 | 552838 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-22 | 2019-05-16 | 2019-05-16 | 3 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 384177 | Work Order Description - 384177 - PM | PM | 4 | 601923 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 2 | OPERATIONS | OPERATIONS | 60
2019-03-31 | 384189 | Work Order Description - 384189 - PM | PM | 4 | 482752 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-16 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | MECHANICAL | 35
2019-03-31 | 384191 | Work Order Description - 384191 - PSPM | PSPM | 1 | 312455 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 384193 | Work Order Description - 384193 - PSPM | PSPM | 1 | 312479 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 384195 | Work Order Description - 384195 - PSPM | PSPM | 1 | 123510 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 384205 | Work Order Description - 384205 - PSPM | PSPM | 1 | 42961 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 384207 | Work Order Description - 384207 - PSPM | PSPM | 4 | 99434 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-16 | 2019-05-16 | 2019-05-17 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 384209 | Work Order Description - 384209 - PM | PM | 3 | 266661 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-16 | 2019-05-16 | 2019-05-22 | 2 | MAINTENANCE | ELECTRICAL | 98
2019-03-31 | 384211 | Work Order Description - 384211 - PSPM | PSPM | 1 | 126920 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 1 | MAINTENANCE | ELECTRICAL | 1.5
2019-03-31 | 384213 | Work Order Description - 384213 - PSPM | PSPM | 1 | 127700 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 1 | MAINTENANCE | SAFETY | 3
2019-03-31 | 384215 | Work Order Description - 384215 - PM | PM | 4 | 126984 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-16 | 2019-05-16 | 2019-05-16 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 384288 | Work Order Description - 384288 - CM | CM | 3 | 249642 | WSCHD | EQUIP-ISOL | 2019-01-17 | 2020-01-16 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 384295 | Work Order Description - 384295 - BR | BR | 1 | 494032 | WPLAN | EQUIP-ISOL | 2019-01-16 | 2021-01-14 | 2020-01-15 | 2020-01-15 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 384298 | Work Order Description - 384298 - CM | CM | 2 | 324950 | WMATL | SYS-ISOL | 2019-03-29 | 2020-01-16 | 2019-07-17 | 2019-07-17 | 3 | MAINTENANCE | INSTRUMENTS | 75
2019-03-31 | 384299 | Work Order Description - 384299 - CM | CM | 2 | 492147 | WMATL | SYS-ISOL | 2019-03-29 | 2020-01-16 | 2019-07-17 | 2019-07-17 | 3 | MAINTENANCE | INSTRUMENTS | 110
2019-03-31 | 384301 | Work Order Description - 384301 - CM | CM | 1 | 29722 | WPLAN | EQUIP-ISOL | 2019-01-16 | 2020-01-16 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 384313 | Work Order Description - 384313 - CM | CM | 2 | 188509 | WMATL | SYS-ISOL | 2019-03-29 | 2020-03-17 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 66
2019-03-31 | 384332 | Work Order Description - 384332 - CM | CM | 4 | 451342 | SCHD | NORM-OPS | 2019-01-21 | 2020-01-16 | 2019-07-17 | 2019-07-24 | 3 | INTEGRITY | FABRIC | 50
2019-03-31 | 384371 | Work Order Description - 384371 - CM | CM | 4 | 260757 | WSCHD | NORM-OPS | 2019-01-16 | 2020-01-16 | 2019-04-13 | 2019-04-13 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 384375 | Work Order Description - 384375 - CM | CM | 4 | 260937 | WSCHD | NORM-OPS | 2019-01-16 | 2020-01-16 | 2019-04-06 | 2019-04-06 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 384380 | Work Order Description - 384380 - CM | CM | 4 | 361110 | SCHD | NORM-OPS | 2019-03-24 | 2020-01-16 | 2019-04-06 | 2019-04-06 | 3 | INTEGRITY | OPERATIONS | 2
2019-03-31 | 384388 | Work Order Description - 384388 - CM | CM | 3 | 110975 | SCHD | EQUIP-ISOL | 2019-01-21 | 2021-01-14 | 2019-07-06 | 2019-07-08 | 4 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 384430 | Work Order Description - 384430 - CM | CM | 3 | 318257 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-04-11 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 384445 | Work Order Description - 384445 - BR | BR | 3 | 262570 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-07-19 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 384446 | Work Order Description - 384446 - PSPM | PSPM | 1 | 356358 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 384448 | Work Order Description - 384448 - PSPM | PSPM | 1 | 356358 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 384450 | Work Order Description - 384450 - PSPM | PSPM | 1 | 356358 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 384452 | Work Order Description - 384452 - PSPM | PSPM | 1 | 57932 | WSCHD | EQUIP-ISOL | 2019-01-17 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | INSTRUMENTS | 92
2019-03-31 | 384456 | Work Order Description - 384456 - PM | PM | 3 | 409823 | WSCHD | EQUIP-ISOL | 2019-01-17 | 2019-09-03 | 2019-05-17 | 2019-05-17 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 384458 | Work Order Description - 384458 - PM | PM | 3 | 409824 | WSCHD | EQUIP-ISOL | 2019-01-17 | 2019-09-03 | 2019-05-17 | 2019-05-17 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 384462 | Work Order Description - 384462 - PM | PM | 3 | 54325 | WSCHD | EQUIP-ISOL | 2019-01-17 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 384472 | Work Order Description - 384472 - PM | PM | 3 | 360608 | WSCHD | EQUIP-ISOL | 2019-01-17 | 2019-09-03 | 2019-05-17 | 2019-05-17 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 384474 | Work Order Description - 384474 - PM | PM | 3 | 54656 | WSCHD | EQUIP-ISOL | 2019-01-17 | 2019-09-03 | 2019-05-17 | 2019-05-17 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 384478 | Work Order Description - 384478 - PSPM | PSPM | 1 | 361799 | WSCHD | NORM-OPS | 2019-01-17 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 384480 | Work Order Description - 384480 - PSPM | PSPM | 1 | 656140 | WSCHD | NORM-OPS | 2019-01-17 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 384482 | Work Order Description - 384482 - PSPM | PSPM | 1 | 546068 | WSCHD | NORM-OPS | 2019-01-19 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | SERVICES | 19
2019-03-31 | 384484 | Work Order Description - 384484 - PSPM | PSPM | 1 | 361105 | WSCHD | PACK-ISOL | 2019-01-19 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 384486 | Work Order Description - 384486 - PSPM | PSPM | 1 | 399678 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 384488 | Work Order Description - 384488 - PSPM | PSPM | 1 | 54031 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 384490 | Work Order Description - 384490 - PSPM | PSPM | 1 | 357658 | WSCHD | SUBSYS-ISOL | 2019-01-19 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 384492 | Work Order Description - 384492 - PM | PM | 4 | 293251 | WSCHD | NORM-OPS | 2019-01-19 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | ELECTRICAL | 138
2019-03-31 | 384494 | Work Order Description - 384494 - PSPM | PSPM | 1 | 567820 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | INSTRUMENTS | 38
2019-03-31 | 384496 | Work Order Description - 384496 - PSPM | PSPM | 1 | 479363 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | ELECTRICAL | 191
2019-03-31 | 384498 | Work Order Description - 384498 - PSPM | PSPM | 1 | 479364 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | ELECTRICAL | 153
2019-03-31 | 384500 | Work Order Description - 384500 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 384502 | Work Order Description - 384502 - PSPM | PSPM | 1 | 540304 | SCHD | PACK-ISOL | 2019-01-25 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 384504 | Work Order Description - 384504 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-17 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 384512 | Work Order Description - 384512 - PM | PM | 4 | 663545 | SCHD | PACK-ISOL | 2019-03-18 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 384514 | Work Order Description - 384514 - PM | PM | 4 | 441824 | SCHD | PACK-ISOL | 2019-03-18 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 384516 | Work Order Description - 384516 - PSPM | PSPM | 1 | 527317 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 384518 | Work Order Description - 384518 - PSPM | PSPM | 1 | 663164 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 384520 | Work Order Description - 384520 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-17 | 2019-05-17 | 2019-05-19 | 3 | MAINTENANCE | MEDIC | 21
2019-03-31 | 384611 | Work Order Description - 384611 - CM | CM | 1 | 247360 | WPLAN | PACK-ISOL | 2019-01-19 | 2020-01-17 | 2019-07-18 | 2019-07-18 | 3 | INTEGRITY | CONSTRUCTION | 7
2019-03-31 | 384618 | Work Order Description - 384618 - BR | BR | 4 | 307227 | SCHD | EQUIP-ISOL | 2019-01-17 | 2021-01-15 | 2019-05-17 | 2019-05-18 | 4 | MAINTENANCE | ELECTRICAL | 30
2019-03-31 | 384790 | Work Order Description - 384790 - PSPM | PSPM | 1 | 356354 | WSCHD | EQUIP-ISOL | 2019-01-18 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 384792 | Work Order Description - 384792 - PSPM | PSPM | 1 | 356354 | WSCHD | EQUIP-ISOL | 2019-01-18 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 384799 | Work Order Description - 384799 - PSPM | PSPM | 1 | 356354 | WSCHD | EQUIP-ISOL | 2019-01-18 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 384801 | Work Order Description - 384801 - PSPM | PSPM | 1 | 657130 | WSCHD | EQUIP-ISOL | 2019-01-18 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 384803 | Work Order Description - 384803 - PSPM | PSPM | 1 | 657130 | WSCHD | EQUIP-ISOL | 2019-01-18 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 384805 | Work Order Description - 384805 - PSPM | PSPM | 1 | 422375 | WSCHD | NORM-OPS | 2019-01-18 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | ELECTRICAL | 189
2019-03-31 | 384807 | Work Order Description - 384807 - PSPM | PSPM | 1 | 418083 | WSCHD | NORM-OPS | 2019-01-18 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 384809 | Work Order Description - 384809 - PSPM | PSPM | 1 | 680808 | WSCHD | NORM-OPS | 2019-01-18 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 384811 | Work Order Description - 384811 - PM | PM | 4 | 18978 | WSCHD | EQUIP-ISOL | 2019-01-18 | 2019-09-04 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | INSTRUMENTS | 31
2019-03-31 | 384815 | Work Order Description - 384815 - PSPM | PSPM | 1 | 680809 | WSCHD | NORM-OPS | 2019-01-18 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 384817 | Work Order Description - 384817 - PSPM | PSPM | 1 | 418084 | WSCHD | NORM-OPS | 2019-01-18 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 384819 | Work Order Description - 384819 - PSPM | PSPM | 1 | 321203 | WSCHD | NORM-OPS | 2019-01-18 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 384821 | Work Order Description - 384821 - PSPM | PSPM | 1 | 321218 | WSCHD | NORM-OPS | 2019-01-18 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 384823 | Work Order Description - 384823 - PM | PM | 4 | 666204 | SCHD | NORM-OPS | 2019-02-21 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 384825 | Work Order Description - 384825 - PSPM | PSPM | 1 | 248355 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 384827 | Work Order Description - 384827 - PM | PM | 4 | 294916 | WSCHD | NORM-OPS | 2019-01-18 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 384829 | Work Order Description - 384829 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 384831 | Work Order Description - 384831 - PSPM | PSPM | 1 | 458184 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | ELECTRICAL | 92
2019-03-31 | 384833 | Work Order Description - 384833 - PM | PM | 4 | 256187 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | INTEGRITY | INSPECTION | 7
2019-03-31 | 384835 | Work Order Description - 384835 - PSPM | PSPM | 1 | 491141 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 384837 | Work Order Description - 384837 - PSPM | PSPM | 1 | 626120 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 384841 | Work Order Description - 384841 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 384843 | Work Order Description - 384843 - PM | PM | 4 | 655878 | SCHD | EQUIP-ISOL | 2019-01-21 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 384845 | Work Order Description - 384845 - PSPM | PSPM | 1 | 448826 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 384847 | Work Order Description - 384847 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 385072 | Work Order Description - 385072 - PSCM | PSCM | 1 | 396618 | SCHD | NORM-OPS | 2019-01-21 | 2020-01-18 | 2019-07-19 | 2019-07-20 | 3 | MAINTENANCE | ELECTRICAL | 7
2019-03-31 | 385103 | Work Order Description - 385103 - PM | PM | 4 | 51202 | WSCHD | NORM-OPS | 2019-01-18 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 385107 | Work Order Description - 385107 - PM | PM | 4 | 324749 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 385109 | Work Order Description - 385109 - PM | PM | 4 | 312388 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 385111 | Work Order Description - 385111 - PM | PM | 4 | 257365 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 385113 | Work Order Description - 385113 - PM | PM | 4 | 498449 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 385115 | Work Order Description - 385115 - PM | PM | 4 | 257270 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 385117 | Work Order Description - 385117 - PM | PM | 4 | 312412 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 385119 | Work Order Description - 385119 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 385121 | Work Order Description - 385121 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 385238 | Work Order Description - 385238 - BR | BR | 3 | 499277 | WPLAN | PACK-ISOL | 2019-01-19 | 2019-07-20 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 385249 | Work Order Description - 385249 - CM | CM | 1 | 65475 | WPLAN | NORM-OPS | 2019-01-19 | 2019-07-20 | 2019-04-19 | 2019-04-19 | 3 | INTEGRITY | FABRIC | 280
2019-03-31 | 385270 | Work Order Description - 385270 - CM | CM | 4 | 243872 | WRISKQ | EQUIP-ISOL | 2019-01-22 | 2021-01-20 |  |  | 4 | MAINTENANCE | DRILLING | 8
2019-03-31 | 385282 | Work Order Description - 385282 - CM | CM | 4 | 409872 | SCHD | EQUIP-ISOL | 2019-02-22 | 2019-07-21 | 2019-06-01 | 2019-06-01 | 3 | INTEGRITY | CONSTRUCTION | 32
2019-03-31 | 385305 | Work Order Description - 385305 - PSPM | PSPM | 1 | 681829 | WSCHD | EQUIP-ISOL | 2019-01-19 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | INSTRUMENTS | 50
2019-03-31 | 385307 | Work Order Description - 385307 - PM | PM | 2 | 572308 | WSCHD | NORM-OPS | 2019-01-19 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 385309 | Work Order Description - 385309 - PSPM | PSPM | 4 | 411264 | WSCHD | NORM-OPS | 2019-01-19 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | INTEGRITY | INSPECTION | 210
2019-03-31 | 385311 | Work Order Description - 385311 - PSPM | PSPM | 4 | 411264 | WSCHD | NORM-OPS | 2019-01-19 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | INTEGRITY | INSPECTION | 210
2019-03-31 | 385313 | Work Order Description - 385313 - PM | PM | 4 | 580762 | WSCHD | NORM-OPS | 2019-01-19 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 385315 | Work Order Description - 385315 - PSPM | PSPM | 1 | 294959 | SCHD | NORM-OPS | 2019-02-21 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 385317 | Work Order Description - 385317 - PM | PM | 4 | 481371 | WSCHD | NORM-OPS | 2019-01-19 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 385319 | Work Order Description - 385319 - PM | PM | 4 | 267786 | WSCHD | NORM-OPS | 2019-01-19 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 385323 | Work Order Description - 385323 - PSPM | PSPM | 1 | 29639 | SCHD | PACK-ISOL | 2019-01-31 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 385325 | Work Order Description - 385325 - PSPM | PSPM | 1 | 403503 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | INSTRUMENTS | 5.5
2019-03-31 | 385327 | Work Order Description - 385327 - PSPM | PSPM | 1 | 27535 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 385329 | Work Order Description - 385329 - PSPM | PSPM | 1 | 447441 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 385331 | Work Order Description - 385331 - PSPM | PSPM | 1 | 567452 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 385333 | Work Order Description - 385333 - PSPM | PSPM | 1 | 184667 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 385335 | Work Order Description - 385335 - PSPM | PSPM | 1 | 567562 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 385337 | Work Order Description - 385337 - PSPM | PSPM | 1 | 584883 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 385339 | Work Order Description - 385339 - PSPM | PSPM | 1 | 567646 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 385341 | Work Order Description - 385341 - PM | PM | 1 | 446516 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 385343 | Work Order Description - 385343 - PM | PM | 4 | 316451 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 2 | DRILLING | DRILLING | 4
2019-03-31 | 385345 | Work Order Description - 385345 - PM | PM | 4 | 216143 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 2 | DRILLING | DRILLING | 4
2019-03-31 | 385347 | Work Order Description - 385347 - PSPM | PSPM | 1 | 539543 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 385349 | Work Order Description - 385349 - PSPM | PSPM | 1 | 25683 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 385351 | Work Order Description - 385351 - PM | PM | 4 | 499149 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | MECHANICAL | 72
2019-03-31 | 385355 | Work Order Description - 385355 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 2 | MAINTENANCE | SAFETY | 7
2019-03-31 | 385357 | Work Order Description - 385357 - PSPM | PSPM | 1 | 179514 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-19 | 2019-05-19 | 2019-05-20 | 1 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 385359 | Work Order Description - 385359 - PSPM | PSPM | 1 | 659513 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 385361 | Work Order Description - 385361 - PSPM | PSPM | 1 | 659513 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 385363 | Work Order Description - 385363 - PSPM | PSPM | 1 | 392100 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-19 | 2019-05-19 | 2019-05-20 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 385365 | Work Order Description - 385365 - PSPM | PSPM | 1 | 179515 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-19 | 2019-05-19 | 2019-05-20 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 385367 | Work Order Description - 385367 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 385369 | Work Order Description - 385369 - PSPM | PSPM | 1 | 527315 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 385371 | Work Order Description - 385371 - PSPM | PSPM | 1 | 669726 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 385373 | Work Order Description - 385373 - PSPM | PSPM | 1 | 436549 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 385375 | Work Order Description - 385375 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-19 | 2019-05-19 | 2019-05-19 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 385515 | Work Order Description - 385515 - CM | CM | 4 | 409872 | WPLAN | NORM-OPS | 2019-01-19 | 2021-01-17 | 2020-01-18 | 2020-01-18 | 4 | INTEGRITY | FABRIC | 16
2019-03-31 | 385527 | Work Order Description - 385527 - BR | BR | 3 | 460386 | WPLAN | TPS | 2019-01-22 | 2020-01-19 | 2019-07-20 | 2019-07-20 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 385529 | Work Order Description - 385529 - CM | CM | 4 | 409872 | WPLAN | EQUIP-ISOL | 2019-01-21 | 2020-01-19 | 2019-05-25 | 2019-05-25 | 3 | INTEGRITY | CONSTRUCTION | 6
2019-03-31 | 385533 | Work Order Description - 385533 - CM | CM | 4 | 409872 | WPLAN | NORM-OPS | 2019-01-21 | 2021-01-17 | 2019-05-18 | 2019-05-18 | 4 | INTEGRITY | FABRIC | 12
2019-03-31 | 385551 | Work Order Description - 385551 - BR | BR | 3 | 319246 | WSCHD | PACK-ISOL | 2019-01-21 | 2020-01-19 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 385571 | Work Order Description - 385571 - CM | CM | 3 | 409872 | WPLAN | EQUIP-ISOL | 2019-01-22 | 2021-01-17 | 2020-01-18 | 2020-01-18 | 4 | INTEGRITY | CONSTRUCTION | 19
2019-03-31 | 385588 | Work Order Description - 385588 - CM | CM | 4 | 409872 | WPLAN | NORM-OPS | 2019-01-21 | 2020-01-19 | 2019-07-20 | 2019-07-20 | 3 | INTEGRITY | FABRIC | 12
2019-03-31 | 385607 | Work Order Description - 385607 - BR | BR | 3 | 324363 | WPLAN | SYS-ISOL | 2019-01-21 | 2021-01-17 | 2019-05-11 | 2019-05-11 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 385637 | Work Order Description - 385637 - PSPM | PSPM | 1 | 677715 | WSCHD | EQUIP-ISOL | 2019-01-20 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 385639 | Work Order Description - 385639 - PSPM | PSPM | 1 | 541313 | WSCHD | EQUIP-ISOL | 2019-01-20 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 385641 | Work Order Description - 385641 - PM | PM | 4 | 595921 | WSCHD | EQUIP-ISOL | 2019-01-21 | 2019-07-14 | 2019-05-20 | 2019-05-20 | 2 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 385646 | Work Order Description - 385646 - PM | PM | 4 | 540746 | WSCHD | EQUIP-ISOL | 2019-01-21 | 2019-07-14 | 2019-05-20 | 2019-05-20 | 2 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 385651 | Work Order Description - 385651 - PM | PM | 4 | 18317 | WSCHD | EQUIP-ISOL | 2019-01-20 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 385653 | Work Order Description - 385653 - PM | PM | 4 | 18316 | WSCHD | EQUIP-ISOL | 2019-01-20 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 385655 | Work Order Description - 385655 - PM | PM | 4 | 666316 | WSCHD | EQUIP-ISOL | 2019-01-21 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 385657 | Work Order Description - 385657 - PM | PM | 4 | 417521 | WSCHD | EQUIP-ISOL | 2019-01-21 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 385659 | Work Order Description - 385659 - PM | PM | 4 | 50099 | WSCHD | EQUIP-ISOL | 2019-01-20 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 385661 | Work Order Description - 385661 - PM | PM | 4 | 50098 | WSCHD | EQUIP-ISOL | 2019-01-20 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 385663 | Work Order Description - 385663 - PM | PM | 4 | 411571 | WSCHD | NORM-OPS | 2019-01-20 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 385665 | Work Order Description - 385665 - PM | PM | 4 | 358159 | WSCHD | NORM-OPS | 2019-01-20 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 385667 | Work Order Description - 385667 - PM | PM | 4 | 540667 | WSCHD | NORM-OPS | 2019-01-20 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 385669 | Work Order Description - 385669 - PM | PM | 4 | 678551 | WSCHD | NORM-OPS | 2019-01-20 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 385671 | Work Order Description - 385671 - PM | PM | 4 | 314191 | WSCHD | NORM-OPS | 2019-01-20 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 385673 | Work Order Description - 385673 - PM | PM | 4 | 314193 | WSCHD | NORM-OPS | 2019-01-20 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 385675 | Work Order Description - 385675 - PSPM | PSPM | 1 | 520389 | WSCHD | PACK-ISOL | 2019-01-21 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 1 | WELLS | WELLS | 19
2019-03-31 | 385679 | Work Order Description - 385679 - PSPM | PSPM | 1 | 354363 | WSCHD | PACK-ISOL | 2019-01-21 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | WELLS | WELLS | 19
2019-03-31 | 385683 | Work Order Description - 385683 - PSPM | PSPM | 1 | 498646 | WSCHD | PACK-ISOL | 2019-01-21 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | WELLS | WELLS | 19
2019-03-31 | 385687 | Work Order Description - 385687 - PSPM | PSPM | 1 | 498643 | WSCHD | PACK-ISOL | 2019-01-21 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 1 | WELLS | WELLS | 19
2019-03-31 | 385691 | Work Order Description - 385691 - PSPM | PSPM | 1 | 354360 | WSCHD | PACK-ISOL | 2019-01-21 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | WELLS | WELLS | 19
2019-03-31 | 385695 | Work Order Description - 385695 - PSPM | PSPM | 1 | 318579 | WSCHD | PACK-ISOL | 2019-01-21 | 2019-06-02 | 2019-05-02 | 2019-05-02 | 1 | WELLS | WELLS | 19
2019-03-31 | 385699 | Work Order Description - 385699 - PSPM | PSPM | 1 | 520391 | WSCHD | PACK-ISOL | 2019-01-21 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | WELLS | WELLS | 19
2019-03-31 | 385703 | Work Order Description - 385703 - PSPM | PSPM | 1 | 520390 | WSCHD | PACK-ISOL | 2019-01-21 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 1 | WELLS | WELLS | 19
2019-03-31 | 385707 | Work Order Description - 385707 - PSPM | PSPM | 1 | 470877 | WSCHD | NORM-OPS | 2019-01-20 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 385709 | Work Order Description - 385709 - PSPM | PSPM | 1 | 547276 | WSCHD | NORM-OPS | 2019-01-20 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 385711 | Work Order Description - 385711 - PM | PM | 4 | 360243 | WSCHD | NORM-OPS | 2019-01-20 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 385713 | Work Order Description - 385713 - PM | PM | 4 | 183627 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 2 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 385715 | Work Order Description - 385715 - PM | PM | 4 | 183627 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 2 | OPERATIONS | OPERATIONS | 7
2019-03-31 | 385717 | Work Order Description - 385717 - PSPM | PSPM | 1 | 216946 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | OPERATIONS | SAFETY | 4
2019-03-31 | 385719 | Work Order Description - 385719 - PSPM | PSPM | 1 | 29041 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 385721 | Work Order Description - 385721 - PSPM | PSPM | 1 | 462436 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 385723 | Work Order Description - 385723 - PM | PM | 4 | 567654 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-09-06 | 2019-05-20 | 2019-05-20 | 2 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 385725 | Work Order Description - 385725 - PSPM | PSPM | 1 | 632646 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | MAINTENANCE | SAFETY | 6
2019-03-31 | 385727 | Work Order Description - 385727 - PSPM | PSPM | 1 | 122617 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-20 | 2019-06-01 | 2019-06-01 | 1 | OPERATIONS | SAFETY | 7
2019-03-31 | 385729 | Work Order Description - 385729 - PM | PM | 4 | 556260 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 385731 | Work Order Description - 385731 - PM | PM | 4 | 320336 | SCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 385733 | Work Order Description - 385733 - PM | PM | 2 | 216011 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 385735 | Work Order Description - 385735 - PM | PM | 4 | 320026 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 385737 | Work Order Description - 385737 - PM | PM | 4 | 74216 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 385791 | Work Order Description - 385791 - PM | PM | 4 | 100270 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-06 | 2019-05-20 | 2019-05-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 385793 | Work Order Description - 385793 - PM | PM | 4 | 78549 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-14 | 2019-05-20 | 2019-05-20 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 385795 | Work Order Description - 385795 - PM | PM | 4 | 440934 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-06 | 2019-05-20 | 2019-05-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 385797 | Work Order Description - 385797 - PM | PM | 4 | 100131 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-14 | 2019-05-20 | 2019-05-20 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 385799 | Work Order Description - 385799 - PM | PM | 4 | 527375 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | MAINTENANCE | SAFETY | 4
2019-03-31 | 385801 | Work Order Description - 385801 - PM | PM | 4 | 659575 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-20 | 2019-05-20 | 2019-05-21 | 1 | MAINTENANCE | SAFETY | 14
2019-03-31 | 385803 | Work Order Description - 385803 - PM | PM | 4 | 659576 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-20 | 2019-05-20 | 2019-05-21 | 1 | MAINTENANCE | SAFETY | 14
2019-03-31 | 385805 | Work Order Description - 385805 - PM | PM | 4 | 527399 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 385807 | Work Order Description - 385807 - PM | PM | 4 | 450998 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 385809 | Work Order Description - 385809 - PM | PM | 4 | 450999 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 385811 | Work Order Description - 385811 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-20 | 2019-05-20 | 2019-05-20 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 386069 | Work Order Description - 386069 - BR | BR | 1 | 244144 | WSCHD | NORM-OPS | 2019-01-22 | 2021-01-18 | 2020-01-19 | 2020-01-19 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 386074 | Work Order Description - 386074 - BR | BR | 1 | 321537 | SCHD | NORM-OPS | 2019-03-29 | 2021-01-18 | 2019-03-30 | 2019-03-30 | 4 | MAINTENANCE | INSTRUMENTS | 19
2019-03-31 | 386083 | Work Order Description - 386083 - CM | CM | 3 | 254687 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-22 | 2019-06-08 | 2019-06-08 | 3 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 386099 | Work Order Description - 386099 - BR | BR | 3 | 548510 | WPLAN | EQUIP-ISOL | 2019-01-22 | 2019-01-14 | 2019-07-13 | 2019-07-27 | 2 | MAINTENANCE | INSTRUMENTS | 100
2019-03-31 | 386147 | Work Order Description - 386147 - CM | CM | 4 | 409872 | WPLAN | NORM-OPS | 2019-01-21 | 2020-01-20 | 2019-04-06 | 2019-04-06 | 3 | INTEGRITY | FABRIC | 8
2019-03-31 | 386165 | Work Order Description - 386165 - CM | CM | 3 | 409872 | WPLAN | EQUIP-ISOL | 2019-01-22 | 2020-01-20 | 2019-07-21 | 2019-07-21 | 3 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 386179 | Work Order Description - 386179 - BR | BR | 4 | 326871 | WPLAN | EQUIP-ISOL | 2019-01-21 | 2021-01-18 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 386182 | Work Order Description - 386182 - BR | BR | 4 | 326867 | WPLAN | EQUIP-ISOL | 2019-01-21 | 2021-01-18 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 386183 | Work Order Description - 386183 - CM | CM | 3 | 409872 | WSCHD | NORM-OPS | 2019-01-21 | 2019-07-22 | 2019-04-13 | 2019-04-13 | 3 | INTEGRITY | INSPECTION | 24
2019-03-31 | 386186 | Work Order Description - 386186 - BR | BR | 4 | 326868 | WPLAN | EQUIP-ISOL | 2019-01-21 | 2021-01-18 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 386214 | Work Order Description - 386214 - PSPM | PSPM | 1 | 356346 | WSCHD | EQUIP-ISOL | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 386216 | Work Order Description - 386216 - PM | PM | 4 | 51662 | WSCHD | NORM-OPS | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 386218 | Work Order Description - 386218 - PM | PM | 4 | 18972 | WSCHD | NORM-OPS | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 386220 | Work Order Description - 386220 - PM | PM | 4 | 355546 | WSCHD | NORM-OPS | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 386222 | Work Order Description - 386222 - PM | PM | 4 | 18973 | WSCHD | NORM-OPS | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 386224 | Work Order Description - 386224 - PM | PM | 4 | 355547 | WSCHD | NORM-OPS | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 386226 | Work Order Description - 386226 - PM | PM | 4 | 18985 | WSCHD | NORM-OPS | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 386228 | Work Order Description - 386228 - PM | PM | 4 | 355548 | WSCHD | NORM-OPS | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 386230 | Work Order Description - 386230 - PM | PM | 4 | 357081 | WSCHD | EQUIP-ISOL | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 386232 | Work Order Description - 386232 - PM | PM | 4 | 246512 | WSCHD | EQUIP-ISOL | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 386234 | Work Order Description - 386234 - PM | PM | 4 | 553703 | WSCHD | NORM-OPS | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 386236 | Work Order Description - 386236 - PM | PM | 2 | 33427 | WSCHD | NORM-OPS | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 386238 | Work Order Description - 386238 - PM | PM | 4 | 554265 | WSCHD | NORM-OPS | 2019-01-21 | 2019-07-15 | 2019-05-21 | 2019-05-21 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 386240 | Work Order Description - 386240 - PM | PM | 4 | 248494 | WSCHD | EQUIP-ISOL | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 386242 | Work Order Description - 386242 - PM | PM | 4 | 267676 | WSCHD | NORM-OPS | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 2 | OPERATIONS | SAFETY | 2
2019-03-31 | 386244 | Work Order Description - 386244 - PM | PM | 4 | 363762 | WSCHD | NORM-OPS | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 2 | MAINTENANCE | MECHANICAL | 65
2019-03-31 | 386246 | Work Order Description - 386246 - PSPM | PSPM | 1 | 481467 | WSCHD | NORM-OPS | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 1 | OPERATIONS | OPERATIONS | 15
2019-03-31 | 386250 | Work Order Description - 386250 - PSPM | PSPM | 1 | 510291 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 386252 | Work Order Description - 386252 - PM | PM | 4 | 481609 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 386254 | Work Order Description - 386254 - PSPM | PSPM | 1 | 462436 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 1 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 386256 | Work Order Description - 386256 - PM | PM | 4 | 476154 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 386258 | Work Order Description - 386258 - PSPM | PSPM | 1 | 265465 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 1 | INTEGRITY | INSPECTION | 8
2019-03-31 | 386260 | Work Order Description - 386260 - PM | PM | 4 | 491256 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-21 | 2019-06-15 | 2019-06-15 | 2 | INTEGRITY | INSPECTION | 72
2019-03-31 | 386262 | Work Order Description - 386262 - PM | PM | 4 | 482736 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-21 | 2019-06-15 | 2019-06-15 | 2 | INTEGRITY | INSPECTION | 72
2019-03-31 | 386264 | Work Order Description - 386264 - PM | PM | 4 | 548378 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 2 | INTEGRITY | INSPECTION | 72
2019-03-31 | 386266 | Work Order Description - 386266 - PM | PM | 4 | 462585 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-21 | 2019-06-15 | 2019-06-15 | 2 | INTEGRITY | INSPECTION | 72
2019-03-31 | 386268 | Work Order Description - 386268 - PM | PM | 4 | 29071 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-21 | 2019-06-15 | 2019-06-15 | 2 | INTEGRITY | INSPECTION | 72
2019-03-31 | 386270 | Work Order Description - 386270 - PM | PM | 4 | 462586 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-21 | 2019-06-15 | 2019-06-15 | 2 | INTEGRITY | INSPECTION | 72
2019-03-31 | 386272 | Work Order Description - 386272 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 386276 | Work Order Description - 386276 - PSPM | PSPM | 4 | 403503 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 386278 | Work Order Description - 386278 - PSPM | PSPM | 1 | 34240 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-21 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 386280 | Work Order Description - 386280 - PM | PM | 4 | 446929 | SCHD | NORM-OPS | 2019-01-25 | 2019-08-02 | 2019-05-21 | 2019-05-21 | 3 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 386282 | Work Order Description - 386282 - PSPM | PSPM | 1 | 481742 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-21 | 2019-06-15 | 2019-06-15 | 1 | INTEGRITY | INSPECTION | 72
2019-03-31 | 386284 | Work Order Description - 386284 - PSPM | PSPM | 1 | 392215 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 386286 | Work Order Description - 386286 - PSPM | PSPM | 1 | 659513 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 386288 | Work Order Description - 386288 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-01-21 | 2019-06-21 | 2019-05-21 | 2019-05-21 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 386459 | Work Order Description - 386459 - BR | BR | 2 | 552143 | WPLAN | NORM-OPS | 2019-01-22 | 2019-07-23 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 386470 | Work Order Description - 386470 - CM | CM | 3 | 53520 | WPLAN | EQUIP-ISOL | 2019-01-22 | 2019-07-23 | 2019-04-22 | 2019-04-22 | 3 | INTEGRITY | CONSTRUCTION | 216
2019-03-31 | 386499 | Work Order Description - 386499 - CM | CM | 4 | 79812 | SCHD | EQUIP-ISOL | 2019-03-06 | 2021-01-19 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 386539 | Work Order Description - 386539 - CM | CM | 4 | 368322 | WSCHD | NORM-OPS | 2019-01-24 | 2020-01-21 | 2019-07-22 | 2019-07-22 | 3 | INTEGRITY | FABRIC | 168
2019-03-31 | 386541 | Work Order Description - 386541 - CM | CM | 4 | 65475 | WSCHD | NORM-OPS | 2019-01-24 | 2020-01-21 | 2019-07-22 | 2019-07-22 | 3 | INTEGRITY | FABRIC | 280
2019-03-31 | 386550 | Work Order Description - 386550 - BR | BR | 3 | 185381 | WPLAN | TPS | 2019-02-04 | 2021-02-02 | 2019-07-13 | 2019-07-21 | 4 | MAINTENANCE | INSTRUMENTS | 60
2019-03-31 | 386551 | Work Order Description - 386551 - BR | BR | 4 | 584912 | WPLAN | NORM-OPS | 2019-01-22 | 2019-04-16 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 386558 | Work Order Description - 386558 - BR | BR | 3 | 377777 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-04-16 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 386562 | Work Order Description - 386562 - PSCM | PSCM | 1 | 65475 | WSCHD | NORM-OPS | 2019-01-24 | 2020-01-21 | 2019-07-22 | 2019-07-22 | 3 | INTEGRITY | FABRIC | 84
2019-03-31 | 386572 | Work Order Description - 386572 - PSCM | PSCM | 1 | 65475 | WSCHD | NORM-OPS | 2019-01-24 | 2020-01-21 | 2019-07-22 | 2019-07-22 | 3 | INTEGRITY | FABRIC | 224
2019-03-31 | 386574 | Work Order Description - 386574 - CM | CM | 1 | 65475 | WPLAN | NORM-OPS | 2019-01-22 | 2020-01-21 | 2019-07-22 | 2019-07-22 | 3 | INTEGRITY | FABRIC | 84
2019-03-31 | 386584 | Work Order Description - 386584 - BR | BR | 3 | 137798 | WSCHD | EQUIP-ISOL | 2019-01-22 | 2019-07-24 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 386587 | Work Order Description - 386587 - BR | BR | 3 | 55289 | WMATL | NORM-OPS | 2019-02-27 | 2019-04-17 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 386594 | Work Order Description - 386594 - CM | CM | 1 | 292440 | WPLAN | NORM-OPS | 2019-01-22 | 2020-01-21 | 2019-07-22 | 2019-07-22 | 3 | INTEGRITY | CONSTRUCTION | 350
2019-03-31 | 386595 | Work Order Description - 386595 - BR | BR | 1 | 555483 | WMATL | TPS | 2019-01-25 | 2019-04-16 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 386597 | Work Order Description - 386597 - BR | BR | 1 | 545299 | WSCHD | EQUIP-ISOL | 2019-01-22 | 2019-07-24 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 386602 | Work Order Description - 386602 - BR | BR | 1 | 554851 | WMATL | TPS | 2019-01-28 | 2019-04-16 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 386618 | Work Order Description - 386618 - CM | CM | 4 | 462436 | WPLAN | NORM-OPS | 2019-01-22 | 2021-01-19 | 2020-01-20 | 2020-01-20 | 4 | MAINTENANCE | SERVICES | 24
2019-03-31 | 386632 | Work Order Description - 386632 - PSCM | PSCM | 1 | 482372 | INPRG | EQUIP-ISOL | 2019-03-17 | 2019-04-16 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 386635 | Work Order Description - 386635 - CM | CM | 1 | 482373 | INPRG | NORM-OPS | 2019-03-17 | 2019-04-16 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 386639 | Work Order Description - 386639 - CM | CM | 4 | 292839 | WPLAN | NORM-OPS | 2019-01-22 | 2020-01-21 | 2019-11-30 | 2019-11-30 | 3 | OPERATIONS | FABRIC | 32
2019-03-31 | 386643 | Work Order Description - 386643 - CM | CM | 3 | 312683 | SCHD | NORM-OPS | 2019-01-31 | 2019-07-23 | 2019-04-22 | 2019-04-22 | 3 | MAINTENANCE | ELECTRICAL | 56
2019-03-31 | 386657 | Work Order Description - 386657 - PM | PM | 4 | 540691 | WSCHD | NORM-OPS | 2019-01-22 | 2019-06-22 | 2019-05-22 | 2019-05-22 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 386659 | Work Order Description - 386659 - PM | PM | 4 | 481470 | WSCHD | NORM-OPS | 2019-01-22 | 2019-06-22 | 2019-05-22 | 2019-05-22 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 386661 | Work Order Description - 386661 - PSPM | PSPM | 1 | 318580 | WSCHD | PACK-ISOL | 2019-01-22 | 2019-06-07 | 2019-05-07 | 2019-05-07 | 1 | WELLS | WELLS | 13
2019-03-31 | 386665 | Work Order Description - 386665 - PSPM | PSPM | 1 | 652220 | WSCHD | NORM-OPS | 2019-01-22 | 2019-06-22 | 2019-05-22 | 2019-05-22 | 1 | MAINTENANCE | SERVICES | 30
2019-03-31 | 386667 | Work Order Description - 386667 - PSPM | PSPM | 1 | 487829 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-22 | 2019-05-22 | 2019-05-22 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 386671 | Work Order Description - 386671 - PSPM | PSPM | 1 | 59212 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-22 | 2019-05-22 | 2019-05-22 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 386675 | Work Order Description - 386675 - PSPM | PSPM | 1 | 315750 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-22 | 2019-05-22 | 2019-05-22 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 386677 | Work Order Description - 386677 - PM | PM | 4 | 99579 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-22 | 2019-05-22 | 2019-05-22 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 386679 | Work Order Description - 386679 - PSPM | PSPM | 1 | 447441 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-22 | 2019-05-22 | 2019-05-22 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 386681 | Work Order Description - 386681 - PSPM | PSPM | 1 | 632455 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-22 | 2019-05-22 | 2019-05-22 | 1 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 386683 | Work Order Description - 386683 - PM | PM | 4 | 482752 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-22 | 2019-05-22 | 2019-05-22 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 386685 | Work Order Description - 386685 - PM | PM | 4 | 460846 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-22 | 2019-05-22 | 2019-05-22 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 386687 | Work Order Description - 386687 - PM | PM | 4 | 216158 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-22 | 2019-05-22 | 2019-05-22 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 386695 | Work Order Description - 386695 - PM | PM | 4 | 238227 | SCHD | EQUIP-ISOL | 2019-03-18 | 2019-06-22 | 2019-05-22 | 2019-05-22 | 2 | INTEGRITY | INSPECTION | 8
2019-03-31 | 386697 | Work Order Description - 386697 - PSPM | PSPM | 1 | 99232 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-22 | 2019-05-22 | 2019-05-23 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 386854 | Work Order Description - 386854 - PRJ | PRJ | 4 | 447441 | SCHD | NORM-OPS | 2019-03-03 | 2021-01-20 | 2019-03-30 | 2019-03-30 | 4 | MAINTENANCE | SERVICES | 1
2019-03-31 | 386882 | Work Order Description - 386882 - BR | BR | 4 | 538343 | WPLAN | EQUIP-ISOL | 2019-01-22 | 2021-01-20 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | ELECTRICAL | 32
2019-03-31 | 387048 | Work Order Description - 387048 - BR | BR | 2 | 25369 | WPLAN | EQUIP-ISOL | 2019-03-06 | 2020-01-22 | 2019-07-23 | 2019-07-23 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 387049 | Work Order Description - 387049 - PSPM | PSPM | 1 | 457538 | WSCHD | NORM-OPS | 2019-01-23 | 2019-06-23 | 2019-05-23 | 2019-05-23 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 387051 | Work Order Description - 387051 - PM | PM | 4 | 660951 | WSCHD | NORM-OPS | 2019-01-23 | 2019-06-23 | 2019-05-23 | 2019-05-23 | 3 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 387055 | Work Order Description - 387055 - PM | PM | 4 | 292678 | WSCHD | NORM-OPS | 2019-01-23 | 2019-06-23 | 2019-05-23 | 2019-05-23 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 387057 | Work Order Description - 387057 - PSPM | PSPM | 1 | 34240 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-23 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 387059 | Work Order Description - 387059 - PSPM | PSPM | 1 | 123510 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-23 | 2019-05-23 | 2019-05-23 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 387063 | Work Order Description - 387063 - PM | PM | 4 | 664573 | SCHD | EQUIP-ISOL | 2019-01-24 | 2019-06-23 | 2019-05-23 | 2019-05-23 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 387065 | Work Order Description - 387065 - PM | PM | 4 | 686619 | WPLAN | PACK-ISOL | 2019-01-23 | 2019-06-23 | 2019-05-23 | 2019-05-23 | 2 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 387067 | Work Order Description - 387067 - PM | PM | 4 | 450692 | SCHD | NORM-OPS | 2019-01-24 | 2019-06-23 | 2019-05-23 | 2019-05-23 | 1 | OPERATIONS | SAFETY | 2
2019-03-31 | 387069 | Work Order Description - 387069 - PSPM | PSPM | 1 | 42961 | SCHD | NORM-OPS | 2019-01-24 | 2019-06-23 | 2019-05-23 | 2019-05-23 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 387071 | Work Order Description - 387071 - PM | PM | 4 | 277287 | SCHD | PACK-ISOL | 2019-03-22 | 2019-07-17 | 2019-05-23 | 2019-05-23 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 387073 | Work Order Description - 387073 - PM | PM | 4 | 396753 | SCHD | PACK-ISOL | 2019-03-22 | 2019-07-17 | 2019-05-23 | 2019-05-23 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 387075 | Work Order Description - 387075 - PM | PM | 4 | 396802 | SCHD | PACK-ISOL | 2019-03-22 | 2019-07-17 | 2019-05-23 | 2019-05-23 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 387077 | Work Order Description - 387077 - PSPM | PSPM | 4 | 99232 | SCHD | NORM-OPS | 2019-01-24 | 2019-06-23 | 2019-05-23 | 2019-05-24 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 387079 | Work Order Description - 387079 - PSPM | PSPM | 1 | 126920 | SCHD | NORM-OPS | 2019-01-24 | 2019-06-23 | 2019-05-23 | 2019-05-23 | 1 | MAINTENANCE | ELECTRICAL | 1.5
2019-03-31 | 387081 | Work Order Description - 387081 - PSPM | PSPM | 1 | 396489 | SCHD | NORM-OPS | 2019-01-24 | 2019-06-23 | 2019-05-23 | 2019-05-23 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 387083 | Work Order Description - 387083 - PM | PM | 4 | 126984 | SCHD | NORM-OPS | 2019-01-24 | 2019-06-23 | 2019-05-23 | 2019-05-23 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 387085 | Work Order Description - 387085 - PM | PM | 2 | 450548 | SCHD | NORM-OPS | 2019-01-24 | 2019-06-23 | 2019-05-23 | 2019-05-23 | 3 | OPERATIONS | OPERATIONS | 4
2019-03-31 | 387087 | Work Order Description - 387087 - PSPM | PSPM | 1 | 396488 | SCHD | NORM-OPS | 2019-01-24 | 2019-06-23 | 2019-05-23 | 2019-05-23 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 387089 | Work Order Description - 387089 - PM | PM | 3 | 440885 | SCHD | EQUIP-ISOL | 2019-01-24 | 2019-09-09 | 2019-05-23 | 2019-05-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 387199 | Work Order Description - 387199 - CM | CM | 3 | 96012 | WPLAN | PACK-ISOL | 2019-03-09 | 2020-01-23 | 2020-01-22 | 2020-01-23 | 3 | MAINTENANCE | FABRIC | 11
2019-03-31 | 387200 | Work Order Description - 387200 - BR | BR | 1 | 272042 | WSCHD | NORM-OPS | 2019-01-25 | 2020-01-23 | 2019-07-24 | 2019-07-24 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 387201 | Work Order Description - 387201 - BR | BR | 1 | 417838 | WSCHD | NORM-OPS | 2019-01-25 | 2020-01-23 | 2019-07-24 | 2019-07-24 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 387224 | Work Order Description - 387224 - BR | BR | 1 | 680544 | WSCHD | NORM-OPS | 2019-01-25 | 2020-01-23 | 2019-07-24 | 2019-07-24 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 387314 | Work Order Description - 387314 - CM | CM | 4 | 204611 | WPLAN | NORM-OPS | 2019-01-26 | 2020-01-23 | 2019-07-24 | 2019-07-24 | 3 | INTEGRITY | CONSTRUCTION | 238
2019-03-31 | 387330 | Work Order Description - 387330 - CM | CM | 4 | 73634 | SCHD | NORM-OPS | 2019-01-25 | 2021-01-21 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 48
2019-03-31 | 387331 | Work Order Description - 387331 - CM | CM | 1 | 155742 | WPLAN | NORM-OPS | 2019-01-26 | 2021-01-21 | 2020-01-22 | 2020-01-22 | 4 | INTEGRITY | CONSTRUCTION | 56
2019-03-31 | 387342 | Work Order Description - 387342 - CM | CM | 1 | 204611 | WPLAN | NORM-OPS | 2019-01-26 | 2020-01-23 | 2019-07-24 | 2019-07-24 | 3 | INTEGRITY | CONSTRUCTION | 196
2019-03-31 | 387347 | Work Order Description - 387347 - BR | BR | 4 | 99664 | SCHD | NORM-OPS | 2019-02-13 | 2021-01-21 | 2020-01-23 | 2020-01-24 | 4 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 387352 | Work Order Description - 387352 - CM | CM | 4 | 292440 | WPLAN | NORM-OPS | 2019-01-26 | 2021-01-21 | 2020-01-22 | 2020-01-22 | 4 | INTEGRITY | CONSTRUCTION | 210
2019-03-31 | 387357 | Work Order Description - 387357 - CM | CM | 1 | 155742 | WPLAN | NORM-OPS | 2019-01-26 | 2020-01-23 | 2019-07-24 | 2019-07-24 | 3 | INTEGRITY | CONSTRUCTION | 196
2019-03-31 | 387360 | Work Order Description - 387360 - CM | CM | 4 | 547275 | WSCHD | NORM-OPS | 2019-02-06 | 2021-01-22 | 2020-01-23 | 2020-01-23 | 4 | OPERATIONS | MECHANICAL | 6
2019-03-31 | 387363 | Work Order Description - 387363 - CM | CM | 4 | 570144 | WPLAN | NORM-OPS | 2019-01-26 | 2021-01-21 | 2020-01-22 | 2020-01-22 | 4 | INTEGRITY | CONSTRUCTION | 56
2019-03-31 | 387373 | Work Order Description - 387373 - PM | PM | 4 | 51202 | WSCHD | NORM-OPS | 2019-01-24 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 387375 | Work Order Description - 387375 - PM | PM | 4 | 246173 | WSCHD | NORM-OPS | 2019-01-24 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | INTEGRITY | SERVICES | 2
2019-03-31 | 387377 | Work Order Description - 387377 - PM | PM | 4 | 546030 | WSCHD | NORM-OPS | 2019-01-24 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 387379 | Work Order Description - 387379 - PM | PM | 4 | 652482 | WSCHD | NORM-OPS | 2019-01-24 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | INTEGRITY | SERVICES | 2
2019-03-31 | 387381 | Work Order Description - 387381 - PSPM | PSPM | 1 | 675037 | WSCHD | NORM-OPS | 2019-01-24 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 387383 | Work Order Description - 387383 - PSPM | PSPM | 1 | 671829 | WSCHD | NORM-OPS | 2019-01-24 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 387385 | Work Order Description - 387385 - PSPM | PSPM | 1 | 519759 | WSCHD | NORM-OPS | 2019-01-24 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 387387 | Work Order Description - 387387 - PM | PM | 4 | 212354 | WSCHD | NORM-OPS | 2019-01-24 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 2 | INTEGRITY | INSPECTION | 2
2019-03-31 | 387389 | Work Order Description - 387389 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 387391 | Work Order Description - 387391 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 387393 | Work Order Description - 387393 - PM | PM | 4 | 476739 | SCHD | PACK-ISOL | 2019-01-31 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 387395 | Work Order Description - 387395 - PM | PM | 4 | 320715 | SCHD | PACK-ISOL | 2019-01-31 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 2 | DRILLING | DRILLING | 4
2019-03-31 | 387397 | Work Order Description - 387397 - PM | PM | 4 | 552599 | SCHD | PACK-ISOL | 2019-01-31 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 387399 | Work Order Description - 387399 - PM | PM | 4 | 216594 | SCHD | PACK-ISOL | 2019-01-31 | 2019-06-24 | 2019-08-17 | 2019-08-17 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 387401 | Work Order Description - 387401 - PM | PM | 4 | 502362 | SCHD | PACK-ISOL | 2019-01-31 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 387403 | Work Order Description - 387403 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 387405 | Work Order Description - 387405 - PSPM | PSPM | 1 | 663164 | SCHD | NORM-OPS | 2019-01-24 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 387407 | Work Order Description - 387407 - PM | PM | 4 | 441911 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-09-10 | 2019-05-24 | 2019-05-24 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 387409 | Work Order Description - 387409 - PM | PM | 4 | 436477 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-09-10 | 2019-05-24 | 2019-05-24 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 387411 | Work Order Description - 387411 - PSPM | PSPM | 1 | 528213 | SCHD | NORM-OPS | 2019-01-24 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 387413 | Work Order Description - 387413 - PM | PM | 4 | 393381 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 387415 | Work Order Description - 387415 - PM | PM | 4 | 185332 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 387417 | Work Order Description - 387417 - PSPM | PSPM | 1 | 668570 | SCHD | NORM-OPS | 2019-01-24 | 2019-06-24 | 2019-05-24 | 2019-05-25 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 387419 | Work Order Description - 387419 - PSPM | PSPM | 1 | 127775 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 387421 | Work Order Description - 387421 - PSPM | PSPM | 1 | 375483 | SCHD | EQUIP-ISOL | 2019-01-24 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 387423 | Work Order Description - 387423 - PSPM | PSPM | 1 | 127738 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 387425 | Work Order Description - 387425 - PSPM | PSPM | 1 | 128022 | SCHD | EQUIP-ISOL | 2019-01-24 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 387427 | Work Order Description - 387427 - PSPM | PSPM | 1 | 127779 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 387429 | Work Order Description - 387429 - PSPM | PSPM | 1 | 448753 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 387431 | Work Order Description - 387431 - PSPM | PSPM | 1 | 218108 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 387433 | Work Order Description - 387433 - PSPM | PSPM | 1 | 74947 | SCHD | EQUIP-ISOL | 2019-01-24 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 387435 | Work Order Description - 387435 - PSPM | PSPM | 1 | 74874 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 387437 | Work Order Description - 387437 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2019-01-24 | 2019-06-24 | 2019-05-24 | 2019-05-26 | 3 | MAINTENANCE | MEDIC | 21
2019-03-31 | 387546 | Work Order Description - 387546 - CM | CM | 1 | 501333 | WPLAN | NORM-OPS | 2019-01-25 | 2021-01-23 | 2020-01-24 | 2020-01-26 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 387583 | Work Order Description - 387583 - PSCM | PSCM | 1 | 547298 | WSCHD | SYS-ISOL | 2019-01-26 | 2020-01-24 | 2019-07-25 | 2019-07-25 | 3 | OPERATIONS | ELECTRICAL | 20
2019-03-31 | 387609 | Work Order Description - 387609 - CM | CM | 1 | 106117 | WPLAN | PACK-ISOL | 2019-02-13 | 2021-01-22 | 2020-01-23 | 2020-01-24 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 387666 | Work Order Description - 387666 - PSPM | PSPM | 1 | 477571 | SCHD | NORM-OPS | 2019-01-31 | 2019-05-15 | 2019-04-14 | 2019-04-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 387710 | Work Order Description - 387710 - BR | BR | 3 | 514559 | WPLAN | SYS-ISOL | 2019-02-20 | 2020-02-20 | 2020-02-19 | 2020-02-19 | 3 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 387734 | Work Order Description - 387734 - CM | CM | 1 | 327996 | WPLAN | NORM-OPS | 2019-01-26 | 2021-01-22 | 2020-01-24 | 2020-01-27 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 387757 | Work Order Description - 387757 - BR | BR | 3 | 357114 | WPLAN | EQUIP-ISOL | 2019-01-25 | 2021-01-22 | 2020-01-23 | 2020-01-23 | 4 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 387797 | Work Order Description - 387797 - BR | BR | 3 | 674314 | WPLAN | EQUIP-ISOL | 2019-01-26 | 2021-01-22 | 2020-01-23 | 2020-01-23 | 4 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 387819 | Work Order Description - 387819 - CM | CM | 1 | 189054 | WMATL | EQUIP-ISOL | 2019-02-06 | 2020-01-24 | 2019-07-25 | 2019-07-25 | 3 | MAINTENANCE | MECHANICAL | 56
2019-03-31 | 387849 | Work Order Description - 387849 - PM | PM | 4 | 249226 | WSCHD | NORM-OPS | 2019-01-25 | 2019-06-25 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 387851 | Work Order Description - 387851 - PM | PM | 3 | 54298 | WSCHD | EQUIP-ISOL | 2019-01-25 | 2019-06-25 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 387853 | Work Order Description - 387853 - PM | PM | 4 | 318579 | WSCHD | EQUIP-ISOL | 2019-01-25 | 2019-09-11 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 387855 | Work Order Description - 387855 - PM | PM | 4 | 352197 | WSCHD | EQUIP-ISOL | 2019-01-25 | 2019-09-11 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 387857 | Work Order Description - 387857 - PSPM | PSPM | 1 | 321203 | WSCHD | NORM-OPS | 2019-01-25 | 2019-06-25 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 387859 | Work Order Description - 387859 - PSPM | PSPM | 1 | 321218 | WSCHD | NORM-OPS | 2019-01-25 | 2019-06-25 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 387861 | Work Order Description - 387861 - PSPM | PSPM | 1 | 357607 | WSCHD | NORM-OPS | 2019-01-25 | 2019-06-25 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 387863 | Work Order Description - 387863 - PSPM | PSPM | 1 | 547448 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-06-25 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 387865 | Work Order Description - 387865 - PSPM | PSPM | 1 | 653301 | WSCHD | NORM-OPS | 2019-01-25 | 2019-06-25 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 387867 | Work Order Description - 387867 - PM | PM | 4 | 294916 | WSCHD | NORM-OPS | 2019-01-25 | 2019-06-25 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 387869 | Work Order Description - 387869 - PM | PM | 2 | 312718 | SCHD | PACK-ISOL | 2019-01-31 | 2019-06-25 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 387875 | Work Order Description - 387875 - PM | PM | 4 | 257240 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-25 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 387877 | Work Order Description - 387877 - PM | PM | 4 | 99579 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-25 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 387879 | Work Order Description - 387879 - PSPM | PSPM | 1 | 632581 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-25 | 2019-05-18 | 2019-05-18 | 1 | OPERATIONS | SAFETY | 5
2019-03-31 | 387881 | Work Order Description - 387881 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-25 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 387885 | Work Order Description - 387885 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-25 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 387887 | Work Order Description - 387887 - PM | PM | 4 | 668715 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-25 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 387889 | Work Order Description - 387889 - PM | PM | 4 | 98044 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-25 | 2019-05-25 | 2019-05-25 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 387891 | Work Order Description - 387891 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-25 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 387893 | Work Order Description - 387893 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2019-01-25 | 2019-06-25 | 2019-05-25 | 2019-05-25 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 388187 | Work Order Description - 388187 - BR | BR | 4 | 216510 | SCHD | EQUIP-ISOL | 2019-01-31 | 2021-01-23 | 2020-01-24 | 2020-01-24 | 4 | MAINTENANCE | DRILLING | 48
2019-03-31 | 388276 | Work Order Description - 388276 - PSPM | PSPM | 1 | 580769 | SCHD | NORM-OPS | 2019-03-26 | 2019-04-29 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 388278 | Work Order Description - 388278 - PSPM | PSPM | 1 | 580769 | WSCHD | NORM-OPS | 2019-01-25 | 2019-05-06 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 388280 | Work Order Description - 388280 - PSPM | PSPM | 1 | 580769 | WSCHD | NORM-OPS | 2019-01-25 | 2019-05-13 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 388282 | Work Order Description - 388282 - PSPM | PSPM | 1 | 580769 | WSCHD | NORM-OPS | 2019-01-25 | 2019-05-20 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 388284 | Work Order Description - 388284 - PSPM | PSPM | 1 | 580769 | WSCHD | NORM-OPS | 2019-01-25 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 388286 | Work Order Description - 388286 - PSPM | PSPM | 1 | 580769 | WSCHD | NORM-OPS | 2019-01-25 | 2019-06-03 | 2019-05-03 | 2019-05-03 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 388288 | Work Order Description - 388288 - PSPM | PSPM | 1 | 580769 | WSCHD | NORM-OPS | 2019-01-25 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 388290 | Work Order Description - 388290 - PSPM | PSPM | 1 | 580769 | WSCHD | NORM-OPS | 2019-01-25 | 2019-06-17 | 2019-05-17 | 2019-05-17 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 388292 | Work Order Description - 388292 - PSPM | PSPM | 1 | 580769 | WSCHD | NORM-OPS | 2019-01-25 | 2019-06-24 | 2019-05-24 | 2019-05-24 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 388362 | Work Order Description - 388362 - PSPM | PSPM | 1 | 25401 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 388375 | Work Order Description - 388375 - PSPM | PSPM | 1 | 356364 | WSCHD | EQUIP-ISOL | 2019-01-26 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 388377 | Work Order Description - 388377 - PM | PM | 4 | 650444 | WSCHD | NORM-OPS | 2019-01-26 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 3 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 388379 | Work Order Description - 388379 - PM | PM | 2 | 572308 | WSCHD | NORM-OPS | 2019-01-26 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 388381 | Work Order Description - 388381 - PM | PM | 4 | 308032 | WSCHD | EQUIP-ISOL | 2019-01-26 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 388383 | Work Order Description - 388383 - PM | PM | 4 | 357113 | WSCHD | EQUIP-ISOL | 2019-01-26 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 388385 | Work Order Description - 388385 - PM | PM | 4 | 580762 | WSCHD | NORM-OPS | 2019-01-26 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 388387 | Work Order Description - 388387 - PSPM | PSPM | 1 | 399422 | WSCHD | NORM-OPS | 2019-01-26 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 388389 | Work Order Description - 388389 - PSPM | PSPM | 1 | 248303 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | INTEGRITY | CONSTRUCTION | 2.3
2019-03-31 | 388391 | Work Order Description - 388391 - PSPM | PSPM | 1 | 216926 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | OPERATIONS | OPERATIONS | 12
2019-03-31 | 388393 | Work Order Description - 388393 - PSPM | PSPM | 1 | 460846 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 388395 | Work Order Description - 388395 - PM | PM | 1 | 446516 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 388397 | Work Order Description - 388397 - PSPM | PSPM | 1 | 29041 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 388399 | Work Order Description - 388399 - PM | PM | 4 | 320150 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 388403 | Work Order Description - 388403 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 2 | MAINTENANCE | SAFETY | 7
2019-03-31 | 388405 | Work Order Description - 388405 - PSPM | PSPM | 1 | 451271 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 388407 | Work Order Description - 388407 - PSPM | PSPM | 4 | 375482 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 388409 | Work Order Description - 388409 - PSPM | PSPM | 4 | 375482 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 388411 | Work Order Description - 388411 - PSPM | PSPM | 4 | 375482 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 388413 | Work Order Description - 388413 - PM | PM | 3 | 445190 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 388415 | Work Order Description - 388415 - PM | PM | 3 | 453817 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 388417 | Work Order Description - 388417 - PM | PM | 4 | 527339 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 388419 | Work Order Description - 388419 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 388421 | Work Order Description - 388421 - PSPM | PSPM | 1 | 669726 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 388425 | Work Order Description - 388425 - PSPM | PSPM | 1 | 663379 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 388427 | Work Order Description - 388427 - PSPM | PSPM | 1 | 445513 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 388429 | Work Order Description - 388429 - PSPM | PSPM | 1 | 392054 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 388431 | Work Order Description - 388431 - PSPM | PSPM | 1 | 663380 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 388433 | Work Order Description - 388433 - PSPM | PSPM | 1 | 445514 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 388435 | Work Order Description - 388435 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-26 | 2019-05-26 | 2019-05-26 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 388520 | Work Order Description - 388520 - BR | BR | 3 | 176537 | WSCHD | PACK-ISOL | 2019-01-26 | 2021-01-24 |  |  | 4 | MAINTENANCE | CONSTRUCTION | 0
2019-03-31 | 388522 | Work Order Description - 388522 - BR | BR | 4 | 405152 | WSCHD | NORM-OPS | 2019-03-28 | 2019-08-07 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 388523 | Work Order Description - 388523 - CM | CM | 3 | 358159 | WPLAN | NORM-OPS | 2019-01-26 | 2021-01-24 | 2020-01-25 | 2020-01-27 | 4 | MAINTENANCE | ELECTRICAL | 120
2019-03-31 | 388541 | Work Order Description - 388541 - CM | CM | 1 | 259477 | WPLAN | EQUIP-ISOL | 2019-02-28 | 2021-01-24 | 2020-12-12 | 2020-12-12 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 388604 | Work Order Description - 388604 - CM | CM | 1 | 80471 | SCHD | NORM-OPS | 2019-02-13 | 2021-01-24 | 2020-01-26 | 2020-01-29 | 4 | INTEGRITY | FABRIC | 56
2019-03-31 | 388625 | Work Order Description - 388625 - PSPM | PSPM | 1 | 657122 | WSCHD | EQUIP-ISOL | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 388627 | Work Order Description - 388627 - PM | PM | 4 | 595814 | WSCHD | EQUIP-ISOL | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 388629 | Work Order Description - 388629 - PSPM | PSPM | 1 | 661008 | WSCHD | NORM-OPS | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 388631 | Work Order Description - 388631 - PM | PM | 4 | 18317 | WSCHD | EQUIP-ISOL | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 388633 | Work Order Description - 388633 - PM | PM | 4 | 18316 | WSCHD | EQUIP-ISOL | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 388635 | Work Order Description - 388635 - PM | PM | 4 | 666316 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 388637 | Work Order Description - 388637 - PM | PM | 4 | 417521 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 388639 | Work Order Description - 388639 - PM | PM | 4 | 50099 | WSCHD | EQUIP-ISOL | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 388641 | Work Order Description - 388641 - PM | PM | 4 | 50098 | WSCHD | EQUIP-ISOL | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 388643 | Work Order Description - 388643 - PM | PM | 4 | 411571 | WSCHD | NORM-OPS | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 388645 | Work Order Description - 388645 - PM | PM | 4 | 358159 | WSCHD | NORM-OPS | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 388647 | Work Order Description - 388647 - PM | PM | 4 | 540667 | WSCHD | NORM-OPS | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 388649 | Work Order Description - 388649 - PM | PM | 4 | 678551 | WSCHD | NORM-OPS | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 388651 | Work Order Description - 388651 - PM | PM | 4 | 595820 | WSCHD | EQUIP-ISOL | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 388653 | Work Order Description - 388653 - PM | PM | 4 | 404414 | WSCHD | NORM-OPS | 2019-01-27 | 2019-07-21 | 2019-05-27 | 2019-05-27 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 388655 | Work Order Description - 388655 - PM | PM | 4 | 547429 | WSCHD | NORM-OPS | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 388657 | Work Order Description - 388657 - PSPM | PSPM | 1 | 470877 | WSCHD | NORM-OPS | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 388659 | Work Order Description - 388659 - PSPM | PSPM | 1 | 671828 | WSCHD | NORM-OPS | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 388661 | Work Order Description - 388661 - PM | PM | 4 | 267676 | WSCHD | NORM-OPS | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 2 | MAINTENANCE | SAFETY | 4
2019-03-31 | 388663 | Work Order Description - 388663 - PM | PM | 4 | 360243 | WSCHD | NORM-OPS | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 388665 | Work Order Description - 388665 - PM | PM | 4 | 98009 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 388667 | Work Order Description - 388667 - PSPM | PSPM | 1 | 189054 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 388670 | Work Order Description - 388670 - PSPM | PSPM | 1 | 325633 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 388672 | Work Order Description - 388672 - PSPM | PSPM | 1 | 81212 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 388674 | Work Order Description - 388674 - PSPM | PSPM | 1 | 457948 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 388676 | Work Order Description - 388676 - PM | PM | 4 | 556260 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 388678 | Work Order Description - 388678 - PM | PM | 2 | 216011 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 388680 | Work Order Description - 388680 - PM | PM | 4 | 320026 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 388682 | Work Order Description - 388682 - PM | PM | 4 | 74216 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 388688 | Work Order Description - 388688 - PM | PM | 4 | 388104 | WPLAN | EQUIP-ISOL | 2019-01-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 388690 | Work Order Description - 388690 - PM | PM | 4 | 377978 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-07-21 | 2019-05-27 | 2019-05-27 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 388692 | Work Order Description - 388692 - PM | PM | 4 | 80141 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-07-21 | 2019-05-27 | 2019-05-27 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 388694 | Work Order Description - 388694 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 388696 | Work Order Description - 388696 - PSPM | PSPM | 1 | 659494 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-27 | 2019-05-27 | 2019-05-29 | 1 | MAINTENANCE | ELECTRICAL | 16
2019-03-31 | 388698 | Work Order Description - 388698 - PSPM | PSPM | 1 | 450986 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 388880 | Work Order Description - 388880 - CM | CM | 4 | 481746 | WPLAN | NORM-OPS | 2019-01-31 | 2021-01-25 | 2020-01-26 | 2020-01-26 | 4 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 388918 | Work Order Description - 388918 - CM | CM | 4 | 481746 | WPLAN | NORM-OPS | 2019-01-31 | 2021-01-25 | 2020-01-26 | 2020-01-27 | 4 | INTEGRITY | CONSTRUCTION | 7
2019-03-31 | 388936 | Work Order Description - 388936 - CM | CM | 3 | 482567 | WPLAN | NORM-OPS | 2019-01-30 | 2021-01-25 | 2020-01-27 | 2020-01-28 | 4 | INTEGRITY | SERVICES | 12
2019-03-31 | 388957 | Work Order Description - 388957 - CM | CM | 3 | 411326 | WPLAN | TPS | 2019-01-29 | 2021-01-25 | 2020-01-26 | 2020-01-26 | 4 | INTEGRITY | CONSTRUCTION | 56
2019-03-31 | 388966 | Work Order Description - 388966 - BR | BR | 2 | 312708 | SCHD | SYS-ISOL | 2019-02-04 | 2021-01-25 | 2020-01-26 | 2020-01-26 | 4 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 388983 | Work Order Description - 388983 - PM | PM | 4 | 489712 | SCHD | PACK-ISOL | 2019-02-17 | 2019-06-28 | 2019-05-27 | 2019-05-27 | 2 | INTEGRITY | MECHANICAL | 5
2019-03-31 | 388985 | Work Order Description - 388985 - PM | PM | 2 | 363762 | WSCHD | NORM-OPS | 2019-02-20 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 2 | MAINTENANCE | MECHANICAL | 3.5
2019-03-31 | 388987 | Work Order Description - 388987 - PSPM | PSPM | 1 | 459098 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 388989 | Work Order Description - 388989 - PSPM | PSPM | 1 | 633441 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 388991 | Work Order Description - 388991 - PSPM | PSPM | 1 | 81182 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 388993 | Work Order Description - 388993 - PM | PM | 4 | 481609 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 388995 | Work Order Description - 388995 - PM | PM | 4 | 476154 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 388997 | Work Order Description - 388997 - PM | PM | 4 | 309638 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 388999 | Work Order Description - 388999 - PSPM | PSPM | 1 | 122620 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-28 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | SAFETY | 3
2019-03-31 | 389001 | Work Order Description - 389001 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 389005 | Work Order Description - 389005 - PSPM | PSPM | 1 | 583857 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-28 | 2019-05-25 | 2019-05-25 | 1 | OPERATIONS | SAFETY | 7
2019-03-31 | 389007 | Work Order Description - 389007 - PM | PM | 4 | 122684 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-28 | 2019-05-25 | 2019-05-25 | 3 | OPERATIONS | SAFETY | 2
2019-03-31 | 389009 | Work Order Description - 389009 - PM | PM | 4 | 449384 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 389011 | Work Order Description - 389011 - PSPM | PSPM | 4 | 403503 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-28 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 389013 | Work Order Description - 389013 - PSPM | PSPM | 1 | 555932 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 1 | OPERATIONS | OPERATIONS | 16
2019-03-31 | 389015 | Work Order Description - 389015 - PM | PM | 4 | 491877 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 389023 | Work Order Description - 389023 - PM | PM | 4 | 237410 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-28 | 2019-05-28 | 2019-05-29 | 2 | INTEGRITY | INSPECTION | 8
2019-03-31 | 389025 | Work Order Description - 389025 - PM | PM | 4 | 451323 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 2 | INTEGRITY | INSPECTION | 2
2019-03-31 | 389027 | Work Order Description - 389027 - PSPM | PSPM | 1 | 375476 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 389029 | Work Order Description - 389029 - PSPM | PSPM | 1 | 127843 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 389031 | Work Order Description - 389031 - PSPM | PSPM | 1 | 127594 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 389033 | Work Order Description - 389033 - PM | PM | 4 | 527749 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 389035 | Work Order Description - 389035 - PSPM | PSPM | 1 | 392215 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 389037 | Work Order Description - 389037 - PM | PM | 3 | 375585 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 389039 | Work Order Description - 389039 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 389044 | Work Order Description - 389044 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 3 | MAINTENANCE | INSTRUMENTS | 0.5
2019-03-31 | 389049 | Work Order Description - 389049 - PM | PM | 4 | 393597 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-28 | 2019-05-26 | 2019-05-27 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 389051 | Work Order Description - 389051 - PM | PM | 4 | 98775 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-28 | 2019-05-28 | 2019-05-31 | 2 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 389053 | Work Order Description - 389053 - PM | PM | 4 | 377283 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-28 | 2019-05-28 | 2019-05-29 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 389055 | Work Order Description - 389055 - PM | PM | 4 | 668959 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-28 | 2019-05-18 | 2019-05-19 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 389057 | Work Order Description - 389057 - PM | PM | 4 | 398918 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 389059 | Work Order Description - 389059 - PM | PM | 4 | 96050 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 389061 | Work Order Description - 389061 - PM | PM | 4 | 98689 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-28 | 2019-05-28 | 2019-05-29 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 389065 | Work Order Description - 389065 - PM | PM | 4 | 373565 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 389370 | Work Order Description - 389370 - BR | BR | 3 | 98005 | WPLAN | TPS | 2019-02-04 | 2020-01-17 | 2019-07-13 | 2019-07-14 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 389396 | Work Order Description - 389396 - CM | CM | 2 | 361657 | WPLAN | NORM-OPS | 2019-01-29 | 2020-01-28 | 2019-07-29 | 2019-07-29 | 3 | INTEGRITY | SERVICES | 16
2019-03-31 | 389432 | Work Order Description - 389432 - BR | BR | 1 | 186615 | SCHD | NORM-OPS | 2019-02-13 | 2020-02-03 | 2019-08-04 | 2019-08-04 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 389446 | Work Order Description - 389446 - PRJ | PRJ | 4 | 544931 | SCHD | EQUIP-ISOL | 2019-01-31 | 2021-01-26 | 2020-01-27 | 2020-01-27 | 4 | MAINTENANCE | ELECTRICAL | 130
2019-03-31 | 389485 | Work Order Description - 389485 - PSCM | PSCM | 1 | 217952 | WMATL | NORM-OPS | 2019-03-25 | 2020-01-28 | 2019-07-29 | 2019-07-29 | 3 | MAINTENANCE | MECHANICAL | 94
2019-03-31 | 389487 | Work Order Description - 389487 - PSCM | PSCM | 1 | 541344 | WSCHD | EQUIP-ISOL | 2019-01-29 | 2020-01-28 | 2019-07-29 | 2019-07-29 | 3 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 389522 | Work Order Description - 389522 - BR | BR | 3 | 312585 | SCHD | NORM-OPS | 2019-01-31 | 2020-01-28 | 2019-07-29 | 2019-07-29 | 3 | MAINTENANCE | OPERATIONS | 1
2019-03-31 | 389527 | Work Order Description - 389527 - BR | BR | 4 | 312585 | SCHD | NORM-OPS | 2019-01-31 | 2021-01-26 | 2020-01-27 | 2020-01-27 | 4 | MAINTENANCE | OPERATIONS | 1
2019-03-31 | 389568 | Work Order Description - 389568 - BR | BR | 3 | 105356 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-04-23 | 2019-04-21 | 2019-04-22 | 2 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 389595 | Work Order Description - 389595 - PSPM | PSPM | 1 | 679151 | WSCHD | EQUIP-ISOL | 2019-01-29 | 2019-06-29 | 2019-05-29 | 2019-05-29 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 389597 | Work Order Description - 389597 - PM | PM | 4 | 540691 | WSCHD | NORM-OPS | 2019-01-29 | 2019-06-29 | 2019-05-29 | 2019-05-29 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 389599 | Work Order Description - 389599 - PM | PM | 4 | 481470 | WSCHD | NORM-OPS | 2019-01-29 | 2019-06-29 | 2019-05-29 | 2019-05-29 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 389601 | Work Order Description - 389601 - PM | PM | 2 | 321218 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-06-29 | 2019-05-29 | 2019-05-29 | 1 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 389603 | Work Order Description - 389603 - PSPM | PSPM | 1 | 650444 | WSCHD | NORM-OPS | 2019-01-29 | 2019-06-29 | 2019-05-29 | 2019-05-29 | 1 | OPERATIONS | OPERATIONS | 15
2019-03-31 | 389605 | Work Order Description - 389605 - PSPM | PSPM | 1 | 675036 | WSCHD | NORM-OPS | 2019-01-29 | 2019-06-29 | 2019-05-29 | 2019-05-29 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 389607 | Work Order Description - 389607 - PM | PM | 3 | 188962 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-29 | 2019-05-29 | 2019-05-29 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 389609 | Work Order Description - 389609 - PM | PM | 3 | 325138 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-29 | 2019-05-29 | 2019-05-29 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 389611 | Work Order Description - 389611 - PM | PM | 3 | 188963 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-29 | 2019-05-29 | 2019-05-29 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 389613 | Work Order Description - 389613 - PM | PM | 3 | 188964 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-29 | 2019-05-29 | 2019-05-29 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 389615 | Work Order Description - 389615 - PSPM | PSPM | 1 | 449294 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-29 | 2019-05-29 | 2019-05-29 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 389617 | Work Order Description - 389617 - PSPM | PSPM | 1 | 449296 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-29 | 2019-05-29 | 2019-05-29 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 389619 | Work Order Description - 389619 - PM | PM | 4 | 460846 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-29 | 2019-05-29 | 2019-05-29 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 389621 | Work Order Description - 389621 - PSPM | PSPM | 1 | 659551 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-29 | 2019-05-29 | 2019-05-29 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 389623 | Work Order Description - 389623 - PSPM | PSPM | 1 | 227941 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-29 | 2019-05-29 | 2019-05-29 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 389727 | Work Order Description - 389727 - CM | CM | 2 | 409872 | WSCHD | NORM-OPS | 2019-01-29 | 2020-01-29 | 2019-07-30 | 2019-07-30 | 3 | INTEGRITY | SERVICES | 63
2019-03-31 | 389766 | Work Order Description - 389766 - PSCM | PSCM | 1 | 652578 | WSCHD | NORM-OPS | 2019-01-30 | 2021-01-27 | 2020-01-28 | 2020-01-28 | 4 | MAINTENANCE | MECHANICAL | 38
2019-03-31 | 389827 | Work Order Description - 389827 - CM | CM | 3 | 436046 | SCHD | SUBSYS-ISOL | 2019-03-06 | 2020-01-29 | 2019-07-30 | 2019-07-31 | 3 | INTEGRITY | CONSTRUCTION | 12
2019-03-31 | 389831 | Work Order Description - 389831 - CM | CM | 4 | 442893 | WPLAN | NORM-OPS | 2019-02-18 | 2019-07-31 | 2019-04-30 | 2019-05-01 | 3 | INTEGRITY | FABRIC | 4
2019-03-31 | 389833 | Work Order Description - 389833 - BR | BR | 3 | 357332 | WPLAN | NORM-OPS | 2019-01-30 | 2019-04-24 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 46
2019-03-31 | 389849 | Work Order Description - 389849 - BR | BR | 3 | 671728 | WSCHD | PACK-ISOL | 2019-01-31 | 2019-07-31 | 2019-04-30 | 2019-04-30 | 3 | MAINTENANCE | MECHANICAL | 46
2019-03-31 | 389959 | Work Order Description - 389959 - BR | BR | 4 | 481864 | INPRG | NORM-OPS | 2019-02-13 | 2021-01-27 | 2020-01-28 | 2020-01-28 | 4 | INTEGRITY | SERVICES | 256
2019-03-31 | 389976 | Work Order Description - 389976 - PM | PM | 4 | 228839 | SCHD | NORM-OPS | 2019-03-18 | 2019-10-28 | 2019-09-27 | 2019-09-27 | 2 | INTEGRITY | INSPECTION | 21
2019-03-31 | 389979 | Work Order Description - 389979 - PM | PM | 4 | 228839 | SCHD | NORM-OPS | 2019-03-18 | 2019-10-20 | 2019-09-19 | 2019-09-19 | 2 | INTEGRITY | INSPECTION | 21
2019-03-31 | 389981 | Work Order Description - 389981 - PM | PM | 4 | 228839 | SCHD | NORM-OPS | 2019-03-18 | 2019-10-20 | 2019-09-19 | 2019-09-19 | 2 | INTEGRITY | INSPECTION | 21
2019-03-31 | 389983 | Work Order Description - 389983 - PM | PM | 4 | 228839 | SCHD | NORM-OPS | 2019-03-18 | 2019-10-20 | 2019-09-19 | 2019-09-19 | 2 | INTEGRITY | INSPECTION | 21
2019-03-31 | 389985 | Work Order Description - 389985 - PM | PM | 4 | 228839 | SCHD | NORM-OPS | 2019-03-18 | 2019-10-27 | 2019-09-26 | 2019-09-26 | 2 | INTEGRITY | INSPECTION | 21
2019-03-31 | 389987 | Work Order Description - 389987 - PM | PM | 4 | 228839 | SCHD | NORM-OPS | 2019-03-18 | 2019-10-12 | 2019-09-11 | 2019-09-11 | 2 | INTEGRITY | INSPECTION | 21
2019-03-31 | 389989 | Work Order Description - 389989 - PM | PM | 4 | 228839 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-31 | 2019-07-31 | 2019-07-31 | 2 | INTEGRITY | INSPECTION | 21
2019-03-31 | 389991 | Work Order Description - 389991 - PM | PM | 4 | 228839 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-31 | 2019-07-31 | 2019-08-01 | 2 | INTEGRITY | INSPECTION | 30
2019-03-31 | 389993 | Work Order Description - 389993 - PM | PM | 4 | 228839 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-28 | 2019-07-28 | 2019-07-29 | 2 | INTEGRITY | INSPECTION | 30
2019-03-31 | 389995 | Work Order Description - 389995 - PM | PM | 4 | 228839 | SCHD | NORM-OPS | 2019-03-18 | 2020-08-31 | 2020-07-31 | 2020-08-01 | 2 | INTEGRITY | INSPECTION | 30
2019-03-31 | 390005 | Work Order Description - 390005 - PSPM | PSPM | 1 | 499149 | SCHD | NORM-OPS | 2019-01-31 | 2019-05-07 | 2019-04-06 | 2019-04-06 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 390007 | Work Order Description - 390007 - PSPM | PSPM | 1 | 499149 | SCHD | NORM-OPS | 2019-01-31 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 390009 | Work Order Description - 390009 - PSPM | PSPM | 1 | 499149 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 390011 | Work Order Description - 390011 - PSPM | PSPM | 1 | 499149 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-18 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 390032 | Work Order Description - 390032 - PSPM | PSPM | 1 | 358850 | WSCHD | EQUIP-ISOL | 2019-01-30 | 2019-06-30 | 2019-05-30 | 2019-05-30 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 390034 | Work Order Description - 390034 - PM | PM | 4 | 294918 | WSCHD | NORM-OPS | 2019-01-30 | 2019-06-30 | 2019-05-30 | 2019-05-30 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 390036 | Work Order Description - 390036 - PM | PM | 4 | 294918 | WSCHD | NORM-OPS | 2019-02-20 | 2019-06-30 | 2019-05-30 | 2019-05-30 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 390038 | Work Order Description - 390038 - PM | PM | 4 | 478755 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-07-24 | 2019-05-30 | 2019-05-30 | 2 | DRILLING | DRILLING | 3
2019-03-31 | 390040 | Work Order Description - 390040 - PM | PM | 4 | 258567 | SCHD | EQUIP-ISOL | 2019-01-31 | 2019-07-24 | 2019-05-30 | 2019-05-30 | 2 | DRILLING | DRILLING | 3
2019-03-31 | 390042 | Work Order Description - 390042 - PM | PM | 4 | 601923 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-30 | 2019-05-30 | 2019-05-30 | 2 | OPERATIONS | OPERATIONS | 60
2019-03-31 | 390054 | Work Order Description - 390054 - PSPM | PSPM | 1 | 462782 | SCHD | PACK-ISOL | 2019-02-04 | 2019-06-30 | 2019-05-30 | 2019-05-30 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 390056 | Work Order Description - 390056 - PM | PM | 4 | 25401 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-30 | 2019-05-30 | 2019-05-30 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 390058 | Work Order Description - 390058 - PSPM | PSPM | 1 | 123510 | SCHD | NORM-OPS | 2019-01-31 | 2019-06-30 | 2019-05-30 | 2019-05-30 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 390066 | Work Order Description - 390066 - PSPM | PSPM | 1 | 42961 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-30 | 2019-05-30 | 2019-05-30 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 390068 | Work Order Description - 390068 - PSPM | PSPM | 4 | 99434 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-30 | 2019-05-30 | 2019-05-31 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 390070 | Work Order Description - 390070 - PSPM | PSPM | 1 | 126920 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-30 | 2019-05-30 | 2019-05-30 | 1 | MAINTENANCE | ELECTRICAL | 1.5
2019-03-31 | 390072 | Work Order Description - 390072 - PSPM | PSPM | 1 | 659338 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-30 | 2019-05-30 | 2019-05-30 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 390074 | Work Order Description - 390074 - PSPM | PSPM | 1 | 659338 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-30 | 2019-05-30 | 2019-05-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390076 | Work Order Description - 390076 - PSPM | PSPM | 1 | 659338 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-30 | 2019-05-30 | 2019-05-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390078 | Work Order Description - 390078 - PSPM | PSPM | 1 | 659338 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-30 | 2019-05-30 | 2019-05-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390080 | Work Order Description - 390080 - PSPM | PSPM | 1 | 659338 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-30 | 2019-05-30 | 2019-05-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390083 | Work Order Description - 390083 - PM | PM | 4 | 126984 | SCHD | NORM-OPS | 2019-02-04 | 2019-06-30 | 2019-05-30 | 2019-05-30 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 390091 | Work Order Description - 390091 - PM | PM | 4 | 78550 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-16 | 2019-05-30 | 2019-05-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390093 | Work Order Description - 390093 - PM | PM | 4 | 100210 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-16 | 2019-05-30 | 2019-05-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390095 | Work Order Description - 390095 - PM | PM | 4 | 383118 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-16 | 2019-05-30 | 2019-05-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390097 | Work Order Description - 390097 - PM | PM | 4 | 383117 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-16 | 2019-05-30 | 2019-05-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390099 | Work Order Description - 390099 - PM | PM | 4 | 383116 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-16 | 2019-05-30 | 2019-05-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390101 | Work Order Description - 390101 - PM | PM | 4 | 78551 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-16 | 2019-05-30 | 2019-05-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 390103 | Work Order Description - 390103 - PM | PM | 4 | 440927 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-16 | 2019-05-30 | 2019-05-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 390105 | Work Order Description - 390105 - PM | PM | 4 | 100064 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-07-24 | 2019-05-30 | 2019-05-30 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 390107 | Work Order Description - 390107 - PM | PM | 4 | 78508 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-24 | 2019-05-30 | 2019-05-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 390109 | Work Order Description - 390109 - PM | PM | 4 | 383009 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-24 | 2019-05-30 | 2019-05-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 390205 | Work Order Description - 390205 - PM | PM | 4 | 228839 | WPLAN | EQUIP-ISOL | 2019-01-30 | 2019-05-02 | 2019-05-22 | 2019-05-22 | 1 | INTEGRITY | INSPECTION | 8
2019-03-31 | 390208 | Work Order Description - 390208 - PRJ | PRJ | 3 | 578834 | SCHD | NORM-OPS | 2019-01-30 | 2019-08-01 | 2019-05-01 | 2019-05-01 | 3 | WELLS | DRILLING | 142.5
2019-03-31 | 390210 | Work Order Description - 390210 - BR | BR | 2 | 471137 | WRISKQ | SUBSYS-ISOL | 2019-02-11 | 2019-08-01 |  |  | 3 | MAINTENANCE | MARINE | 12
2019-03-31 | 390213 | Work Order Description - 390213 - PRJ | PRJ | 4 | 29137 | SCHD | NORM-OPS | 2019-02-04 | 2021-01-28 | 2019-03-30 | 2019-03-30 | 4 | MAINTENANCE | SERVICES | 561.5
2019-03-31 | 390250 | Work Order Description - 390250 - CM | CM | 4 | 260939 | SCHD | NORM-OPS | 2019-02-22 | 2021-01-28 | 2019-03-30 | 2019-03-31 | 4 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 390267 | Work Order Description - 390267 - PM | PM | 4 | 97504 | SCHD | PACK-ISOL | 2019-02-04 | 2019-05-19 | 2019-03-09 | 2019-03-09 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390269 | Work Order Description - 390269 - PM | PM | 4 | 568746 | SCHD | PACK-ISOL | 2019-02-04 | 2019-05-19 | 2019-03-09 | 2019-03-09 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390271 | Work Order Description - 390271 - PM | PM | 4 | 568686 | SCHD | PACK-ISOL | 2019-02-04 | 2019-05-19 | 2019-03-09 | 2019-03-09 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390273 | Work Order Description - 390273 - PM | PM | 4 | 81439 | SCHD | PACK-ISOL | 2019-02-04 | 2019-05-19 | 2019-03-09 | 2019-03-09 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390275 | Work Order Description - 390275 - PM | PM | 4 | 97536 | SCHD | PACK-ISOL | 2019-02-04 | 2019-05-19 | 2019-03-09 | 2019-03-09 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390277 | Work Order Description - 390277 - PM | PM | 4 | 568783 | SCHD | PACK-ISOL | 2019-02-04 | 2019-05-19 | 2019-03-09 | 2019-03-09 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390279 | Work Order Description - 390279 - PM | PM | 4 | 97539 | SCHD | PACK-ISOL | 2019-02-04 | 2019-05-19 | 2019-03-23 | 2019-03-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 390281 | Work Order Description - 390281 - PM | PM | 4 | 97542 | SCHD | PACK-ISOL | 2019-02-04 | 2019-05-19 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390283 | Work Order Description - 390283 - PM | PM | 4 | 567338 | SCHD | PACK-ISOL | 2019-02-04 | 2019-11-05 | 2019-05-26 | 2019-05-26 | 2 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 390285 | Work Order Description - 390285 - PM | PM | 4 | 74701 | SCHD | PACK-ISOL | 2019-02-04 | 2019-11-05 | 2019-05-26 | 2019-05-26 | 2 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 390287 | Work Order Description - 390287 - PM | PM | 4 | 81430 | SCHD | PACK-ISOL | 2019-02-04 | 2019-05-19 | 2019-01-30 | 2019-01-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390289 | Work Order Description - 390289 - PM | PM | 4 | 97465 | SCHD | PACK-ISOL | 2019-02-04 | 2019-05-19 | 2019-01-30 | 2019-01-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390291 | Work Order Description - 390291 - PM | PM | 4 | 81431 | SCHD | PACK-ISOL | 2019-02-04 | 2019-05-19 | 2019-01-30 | 2019-01-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390293 | Work Order Description - 390293 - PM | PM | 4 | 81216 | SCHD | PACK-ISOL | 2019-02-04 | 2019-12-29 | 2019-05-26 | 2019-05-26 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 390295 | Work Order Description - 390295 - PM | PM | 4 | 568023 | SCHD | PACK-ISOL | 2019-02-04 | 2019-12-29 | 2019-05-26 | 2019-05-26 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 390297 | Work Order Description - 390297 - PM | PM | 4 | 568025 | SCHD | PACK-ISOL | 2019-02-04 | 2019-12-29 | 2019-05-26 | 2019-05-26 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 390299 | Work Order Description - 390299 - PM | PM | 4 | 81406 | SCHD | PACK-ISOL | 2019-02-04 | 2019-03-26 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 390301 | Work Order Description - 390301 - PM | PM | 4 | 448109 | SCHD | PACK-ISOL | 2019-02-04 | 2019-02-17 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | ELECTRICAL | 24
2019-03-31 | 390303 | Work Order Description - 390303 - PSPM | PSPM | 1 | 95502 | SCHD | PACK-ISOL | 2019-03-15 | 2019-05-31 | 2019-04-27 | 2019-04-27 | 1 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 390305 | Work Order Description - 390305 - PM | PM | 4 | 446587 | SCHD | PACK-ISOL | 2019-02-04 | 2019-06-24 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390307 | Work Order Description - 390307 - PM | PM | 4 | 567743 | SCHD | PACK-ISOL | 2019-02-04 | 2019-12-29 | 2019-05-26 | 2019-05-26 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 390309 | Work Order Description - 390309 - PM | PM | 4 | 568848 | SCHD | PACK-ISOL | 2019-02-04 | 2019-12-29 | 2019-05-26 | 2019-05-26 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 390311 | Work Order Description - 390311 - PM | PM | 4 | 81625 | SCHD | PACK-ISOL | 2019-02-04 | 2019-11-05 | 2019-05-26 | 2019-05-26 | 2 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 390314 | Work Order Description - 390314 - BR | BR | 3 | 51659 | WSCHD | EQUIP-ISOL | 2019-02-03 | 2021-01-28 | 2020-01-29 | 2020-01-29 | 4 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 390324 | Work Order Description - 390324 - BR | BR | 4 | 544494 | SCHD | EQUIP-ISOL | 2019-01-31 | 2021-01-28 | 2020-01-29 | 2020-01-29 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 390340 | Work Order Description - 390340 - BR | BR | 4 | 653659 | WSCHD | SYS-ISOL | 2019-03-17 | 2021-01-28 | 2019-07-20 | 2019-07-20 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390352 | Work Order Description - 390352 - CM | CM | 4 | 310224 | SCHD | NORM-OPS | 2019-01-31 | 2021-01-28 | 2020-01-30 | 2020-01-30 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 390353 | Work Order Description - 390353 - CM | CM | 4 | 310224 | WPLAN | SYS-ISOL | 2019-01-31 | 2021-01-28 | 2019-05-18 | 2019-05-18 | 4 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 390391 | Work Order Description - 390391 - PM | PM | 4 | 51202 | WSCHD | NORM-OPS | 2019-01-31 | 2019-07-01 | 2019-05-31 | 2019-05-31 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390393 | Work Order Description - 390393 - PSPM | PSPM | 1 | 580769 | WSCHD | NORM-OPS | 2019-01-31 | 2019-07-01 | 2019-05-31 | 2019-05-31 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 390395 | Work Order Description - 390395 - PSPM | PSPM | 1 | 546068 | WSCHD | NORM-OPS | 2019-02-20 | 2019-07-01 | 2019-05-31 | 2019-05-31 | 1 | MAINTENANCE | SERVICES | 10
2019-03-31 | 390397 | Work Order Description - 390397 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2019-01-31 | 2019-07-01 | 2019-05-31 | 2019-05-31 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 390399 | Work Order Description - 390399 - PM | PM | 4 | 309874 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-07-01 | 2019-05-31 | 2019-05-31 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 390401 | Work Order Description - 390401 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2019-01-31 | 2019-07-01 | 2019-05-31 | 2019-05-31 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 390403 | Work Order Description - 390403 - PSPM | PSPM | 1 | 128957 | SCHD | NORM-OPS | 2019-01-31 | 2019-07-01 | 2019-06-15 | 2019-06-15 | 1 | INTEGRITY | INSPECTION | 675
2019-03-31 | 390405 | Work Order Description - 390405 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2019-01-31 | 2019-07-01 | 2019-05-31 | 2019-05-31 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 390407 | Work Order Description - 390407 - PM | PM | 3 | 128615 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-25 | 2019-07-13 | 2019-07-14 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 390409 | Work Order Description - 390409 - PSPM | PSPM | 1 | 663164 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 390411 | Work Order Description - 390411 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-01 | 2019-07-13 | 2019-07-15 | 3 | MAINTENANCE | MEDIC | 21
2019-03-31 | 390530 | Work Order Description - 390530 - PSCM | PSCM | 3 | 671798 | WSCHD | PACK-ISOL | 2019-02-01 | 2021-01-29 | 2020-01-30 | 2020-01-30 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 390531 | Work Order Description - 390531 - CM | CM | 4 | 313971 | WPLAN | EQUIP-ISOL | 2019-03-16 | 2020-01-31 | 2020-01-30 | 2020-01-30 | 3 | MAINTENANCE | CONSTRUCTION | 15
2019-03-31 | 390536 | Work Order Description - 390536 - CM | CM | 3 | 500040 | WSCHD | PACK-ISOL | 2019-02-01 | 2021-01-29 | 2020-01-30 | 2020-01-30 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 390644 | Work Order Description - 390644 - PSCM | PSCM | 3 | 259501 | WMATL | EQUIP-ISOL | 2019-02-06 | 2019-04-26 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 390655 | Work Order Description - 390655 - CM | CM | 4 | 375820 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-08-02 | 2019-05-02 | 2019-05-06 | 3 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 390688 | Work Order Description - 390688 - CM | CM | 4 | 74225 | SCHD | EQUIP-ISOL | 2019-02-13 | 2021-01-29 | 2020-01-30 | 2020-01-30 | 4 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 390693 | Work Order Description - 390693 - BR | BR | 4 | 468955 | WSCHD | EQUIP-ISOL | 2019-02-01 | 2020-01-31 | 2019-08-01 | 2019-08-01 | 3 | MAINTENANCE | CONSTRUCTION | 200
2019-03-31 | 390696 | Work Order Description - 390696 - BR | BR | 3 | 248034 | WPLAN | SYS-ISOL | 2019-02-25 | 2021-01-29 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | MECHANICAL | 214
2019-03-31 | 390703 | Work Order Description - 390703 - PSCM | PSCM | 1 | 315249 | WSCHD | TPS | 2019-03-07 | 2021-01-29 | 2020-12-17 | 2020-12-17 | 4 | MAINTENANCE | FABRIC | 200
2019-03-31 | 390708 | Work Order Description - 390708 - BR | BR | 4 | 75619 | WPLAN | NORM-OPS | 2019-02-04 | 2021-01-29 | 2020-01-31 | 2020-02-01 | 4 | MAINTENANCE | INSTRUMENTS | 13
2019-03-31 | 390767 | Work Order Description - 390767 - CM | CM | 3 | 403920 | WPLAN | NORM-OPS | 2019-02-04 | 2020-01-31 | 2019-05-11 | 2019-05-11 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 390770 | Work Order Description - 390770 - PM | PM | 3 | 215998 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 390773 | Work Order Description - 390773 - PSPM | PSPM | 1 | 480749 | WSCHD | TPS | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 390775 | Work Order Description - 390775 - PSPM | PSPM | 1 | 18946 | WPLAN | PACK-ISOL | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 390777 | Work Order Description - 390777 - PSPM | PSPM | 1 | 355568 | WPLAN | SYS-ISOL | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 390779 | Work Order Description - 390779 - PSPM | PSPM | 1 | 273469 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 390781 | Work Order Description - 390781 - PM | PM | 2 | 580380 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 390783 | Work Order Description - 390783 - PSPM | PSPM | 4 | 19030 | WPLAN | SYS-ISOL | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | MECHANICAL | 12
2019-03-31 | 390785 | Work Order Description - 390785 - PSPM | PSPM | 4 | 355569 | WPLAN | SYS-ISOL | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | MECHANICAL | 12
2019-03-31 | 390787 | Work Order Description - 390787 - PSPM | PSPM | 1 | 531756 | WPLAN | SYS-ISOL | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 390789 | Work Order Description - 390789 - PSPM | PSPM | 1 | 480749 | WSCHD | TPS | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | INTEGRITY | SUBSEA | 8
2019-03-31 | 390791 | Work Order Description - 390791 - PSPM | PSPM | 1 | 665691 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | WELLS | WELLS | 3
2019-03-31 | 390793 | Work Order Description - 390793 - PM | PM | 4 | 18947 | WSCHD | EQUIP-ISOL | 2019-02-01 | 2019-09-18 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 390795 | Work Order Description - 390795 - PM | PM | 4 | 58419 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | OPERATIONS | OPERATIONS | 4
2019-03-31 | 390797 | Work Order Description - 390797 - PM | PM | 4 | 547502 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 390799 | Work Order Description - 390799 - PM | PM | 4 | 48100 | WSCHD | TPS | 2019-02-20 | 2019-07-26 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 390801 | Work Order Description - 390801 - PSPM | PSPM | 1 | 678318 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 9
2019-03-31 | 390803 | Work Order Description - 390803 - PSPM | PSPM | 1 | 361881 | WSCHD | NORM-OPS | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390805 | Work Order Description - 390805 - PSPM | PSPM | 1 | 361916 | WSCHD | TPS | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | OPERATIONS | INSTRUMENTS | 12
2019-03-31 | 390807 | Work Order Description - 390807 - PSPM | PSPM | 1 | 361917 | WSCHD | SUBSYS-ISOL | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390809 | Work Order Description - 390809 - PSPM | PSPM | 1 | 520071 | WSCHD | SUBSYS-ISOL | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390811 | Work Order Description - 390811 - PSPM | PSPM | 1 | 273468 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 390813 | Work Order Description - 390813 - PSPM | PSPM | 1 | 470878 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 390815 | Work Order Description - 390815 - PSPM | PSPM | 1 | 480207 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 390817 | Work Order Description - 390817 - PSPM | PSPM | 1 | 321203 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 390819 | Work Order Description - 390819 - PSPM | PSPM | 1 | 321218 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 390821 | Work Order Description - 390821 - PM | PM | 4 | 457525 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | SAFETY | 3
2019-03-31 | 390823 | Work Order Description - 390823 - PSPM | PSPM | 1 | 538631 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 390825 | Work Order Description - 390825 - PSPM | PSPM | 1 | 273470 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 390827 | Work Order Description - 390827 - PSPM | PSPM | 1 | 538632 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 390829 | Work Order Description - 390829 - PM | PM | 4 | 535884 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | OPERATIONS | MEDIC | 3
2019-03-31 | 390831 | Work Order Description - 390831 - PM | PM | 4 | 676326 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | OPERATIONS | MEDIC | 2
2019-03-31 | 390833 | Work Order Description - 390833 - PSPM | PSPM | 1 | 678318 | WSCHD | TPS | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 390835 | Work Order Description - 390835 - PSPM | PSPM | 1 | 678318 | WSCHD | TPS | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390837 | Work Order Description - 390837 - PSPM | PSPM | 1 | 457527 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | OPERATIONS | SAFETY | 6
2019-03-31 | 390839 | Work Order Description - 390839 - PSPM | PSPM | 1 | 267870 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | OPERATIONS | SAFETY | 6
2019-03-31 | 390841 | Work Order Description - 390841 - PSPM | PSPM | 1 | 292659 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | OPERATIONS | SAFETY | 6
2019-03-31 | 390843 | Work Order Description - 390843 - PSPM | PSPM | 1 | 547543 | WSCHD | NORM-OPS | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390845 | Work Order Description - 390845 - PSPM | PSPM | 1 | 361889 | WSCHD | SUBSYS-ISOL | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390847 | Work Order Description - 390847 - PSPM | PSPM | 1 | 399406 | WSCHD | SUBSYS-ISOL | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | OPERATIONS | INSTRUMENTS | 12
2019-03-31 | 390849 | Work Order Description - 390849 - PSPM | PSPM | 1 | 361921 | WSCHD | SUBSYS-ISOL | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | OPERATIONS | INSTRUMENTS | 11
2019-03-31 | 390851 | Work Order Description - 390851 - PSPM | PSPM | 1 | 361952 | WSCHD | TPS | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | OPERATIONS | INSTRUMENTS | 11
2019-03-31 | 390853 | Work Order Description - 390853 - PSPM | PSPM | 1 | 480749 | WSCHD | TPS | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 390855 | Work Order Description - 390855 - PM | PM | 4 | 666204 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390857 | Work Order Description - 390857 - PM | PM | 4 | 294916 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 390859 | Work Order Description - 390859 - PM | PM | 4 | 481408 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | MEDIC | 25
2019-03-31 | 390861 | Work Order Description - 390861 - PM | PM | 4 | 295994 | WSCHD | NORM-OPS | 2019-02-01 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | MEDIC | 20
2019-03-31 | 390863 | Work Order Description - 390863 - PM | PM | 4 | 458436 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-09-18 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 390865 | Work Order Description - 390865 - PM | PM | 3 | 215998 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 390867 | Work Order Description - 390867 - PSPM | PSPM | 1 | 479363 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | ELECTRICAL | 191
2019-03-31 | 390869 | Work Order Description - 390869 - PSPM | PSPM | 1 | 479364 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | ELECTRICAL | 153
2019-03-31 | 390871 | Work Order Description - 390871 - PSPM | PSPM | 1 | 491403 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 390873 | Work Order Description - 390873 - PM | PM | 4 | 188825 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 390875 | Work Order Description - 390875 - PM | PM | 4 | 176719 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 390877 | Work Order Description - 390877 - PM | PM | 4 | 176720 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 390879 | Work Order Description - 390879 - PM | PM | 4 | 309635 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 390881 | Work Order Description - 390881 - PM | PM | 4 | 257256 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 390883 | Work Order Description - 390883 - PM | PM | 4 | 555211 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 390885 | Work Order Description - 390885 - PM | PM | 4 | 403170 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 390887 | Work Order Description - 390887 - PM | PM | 4 | 180380 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 390889 | Work Order Description - 390889 - PM | PM | 4 | 259940 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390891 | Work Order Description - 390891 - PSPM | PSPM | 1 | 32838 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | OPERATIONS | SAFETY | 7
2019-03-31 | 390893 | Work Order Description - 390893 - PM | PM | 4 | 323513 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-11-11 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 390895 | Work Order Description - 390895 - PM | PM | 4 | 29873 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-11-11 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 390897 | Work Order Description - 390897 - PM | PM | 4 | 324380 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-11-11 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 390899 | Work Order Description - 390899 - PM | PM | 4 | 323514 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-11-11 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 390901 | Work Order Description - 390901 - PM | PM | 4 | 555546 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-11-11 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 390903 | Work Order Description - 390903 - PM | PM | 4 | 555547 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-11-11 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 390905 | Work Order Description - 390905 - PM | PM | 4 | 324404 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-11-11 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 390907 | Work Order Description - 390907 - PM | PM | 4 | 29137 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 390909 | Work Order Description - 390909 - PM | PM | 4 | 29710 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 390911 | Work Order Description - 390911 - PSPM | PSPM | 1 | 499149 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 390913 | Work Order Description - 390913 - PM | PM | 4 | 479286 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 3 | OPERATIONS | SAFETY | 5
2019-03-31 | 390915 | Work Order Description - 390915 - PM | PM | 4 | 479287 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | SAFETY | 3
2019-03-31 | 390917 | Work Order Description - 390917 - PSPM | PSPM | 1 | 492125 | SCHD | TPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 390919 | Work Order Description - 390919 - PSPM | PSPM | 4 | 383657 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 390921 | Work Order Description - 390921 - PSPM | PSPM | 1 | 583867 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | OPERATIONS | SAFETY | 5
2019-03-31 | 390923 | Work Order Description - 390923 - PM | PM | 4 | 568109 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-11-11 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 390925 | Work Order Description - 390925 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 390927 | Work Order Description - 390927 - PSPM | PSPM | 1 | 458184 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | ELECTRICAL | 92
2019-03-31 | 390929 | Work Order Description - 390929 - PM | PM | 4 | 73091 | SCHD | NORM-OPS | 2019-02-04 | 2019-10-24 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | ELECTRICAL | 264
2019-03-31 | 390931 | Work Order Description - 390931 - PM | PM | 4 | 449523 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-08 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 390933 | Work Order Description - 390933 - PSPM | PSPM | 1 | 98010 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 390935 | Work Order Description - 390935 - PSPM | PSPM | 1 | 98010 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 390937 | Work Order Description - 390937 - PM | PM | 4 | 177386 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-11-11 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 390939 | Work Order Description - 390939 - PM | PM | 4 | 475685 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-11-11 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 390941 | Work Order Description - 390941 - PM | PM | 4 | 476159 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-11-11 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 390943 | Work Order Description - 390943 - PM | PM | 4 | 475671 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-11-11 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 390945 | Work Order Description - 390945 - PM | PM | 4 | 475683 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-11-11 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 390947 | Work Order Description - 390947 - PM | PM | 4 | 177387 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-11-11 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 390949 | Work Order Description - 390949 - PM | PM | 4 | 475686 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-11-11 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 390951 | Work Order Description - 390951 - PM | PM | 2 | 502749 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 390953 | Work Order Description - 390953 - PM | PM | 4 | 501445 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | INTEGRITY | INSPECTION | 72
2019-03-31 | 390955 | Work Order Description - 390955 - PM | PM | 4 | 472794 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | INTEGRITY | INSPECTION | 72
2019-03-31 | 390957 | Work Order Description - 390957 - PM | PM | 3 | 482462 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 390959 | Work Order Description - 390959 - PSPM | PSPM | 1 | 259570 | SCHD | SUBSYS-ISOL | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 390963 | Work Order Description - 390963 - PSPM | PSPM | 1 | 255899 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | ELECTRICAL | 22
2019-03-31 | 390965 | Work Order Description - 390965 - PSPM | PSPM | 1 | 255832 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | ELECTRICAL | 30
2019-03-31 | 390969 | Work Order Description - 390969 - PM | PM | 4 | 551618 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-05-25 | 2019-05-25 | 1 | INTEGRITY | OPERATIONS | 2
2019-03-31 | 390971 | Work Order Description - 390971 - PM | PM | 4 | 35256 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-05-25 | 2019-05-25 | 1 | INTEGRITY | OPERATIONS | 2
2019-03-31 | 390973 | Work Order Description - 390973 - PM | PM | 4 | 481645 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | OPERATIONS | MECHANICAL | 8
2019-03-31 | 390975 | Work Order Description - 390975 - PSPM | PSPM | 1 | 403514 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | OPERATIONS | MECHANICAL | 8
2019-03-31 | 390977 | Work Order Description - 390977 - PM | PM | 4 | 216158 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 390979 | Work Order Description - 390979 - PM | PM | 4 | 95502 | SCHD | PACK-ISOL | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 390981 | Work Order Description - 390981 - PM | PM | 4 | 501056 | SCHD | NORM-OPS | 2019-02-04 | 2019-08-31 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 390983 | Work Order Description - 390983 - PM | PM | 4 | 555301 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 4 | MAINTENANCE | MEDIC | 21
2019-03-31 | 391053 | Work Order Description - 391053 - PM | PM | 4 | 80369 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 391055 | Work Order Description - 391055 - PM | PM | 4 | 448769 | SCHD | SUBSYS-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391057 | Work Order Description - 391057 - PM | PM | 2 | 128836 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-23 | 2 | MAINTENANCE | MECHANICAL | 74
2019-03-31 | 391061 | Work Order Description - 391061 - PSPM | PSPM | 1 | 445511 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391063 | Work Order Description - 391063 - PSPM | PSPM | 1 | 445512 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391065 | Work Order Description - 391065 - PSPM | PSPM | 1 | 392053 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391067 | Work Order Description - 391067 - PM | PM | 3 | 375924 | WPLAN | TPS | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 2 | INTEGRITY | INSPECTION | 3
2019-03-31 | 391069 | Work Order Description - 391069 - PSPM | PSPM | 1 | 78294 | SCHD | NORM-OPS | 2019-02-13 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391073 | Work Order Description - 391073 - PSPM | PSPM | 1 | 441710 | WPLAN | TPS | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391075 | Work Order Description - 391075 - PM | PM | 3 | 527126 | WPLAN | EQUIP-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391077 | Work Order Description - 391077 - PM | PM | 3 | 527127 | WPLAN | EQUIP-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391079 | Work Order Description - 391079 - PSPM | PSPM | 1 | 527156 | WPLAN | SYS-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391081 | Work Order Description - 391081 - PSPM | PSPM | 1 | 527161 | WPLAN | SYS-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391083 | Work Order Description - 391083 - PM | PM | 3 | 74995 | WPLAN | PACK-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391085 | Work Order Description - 391085 - PM | PM | 3 | 74987 | WPLAN | EQUIP-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391087 | Work Order Description - 391087 - PSPM | PSPM | 1 | 527157 | WPLAN | SYS-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391089 | Work Order Description - 391089 - PSPM | PSPM | 1 | 663475 | WPLAN | PACK-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391091 | Work Order Description - 391091 - PSPM | PSPM | 1 | 392388 | WPLAN | PACK-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391093 | Work Order Description - 391093 - PSPM | PSPM | 1 | 663490 | WPLAN | PACK-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391095 | Work Order Description - 391095 - PSPM | PSPM | 1 | 128562 | WPLAN | SYS-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391097 | Work Order Description - 391097 - PM | PM | 3 | 449119 | WPLAN | EQUIP-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391099 | Work Order Description - 391099 - PSPM | PSPM | 1 | 435781 | WPLAN | PACK-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391101 | Work Order Description - 391101 - PSPM | PSPM | 1 | 449111 | WPLAN | SYS-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391103 | Work Order Description - 391103 - PM | PM | 3 | 449116 | WPLAN | EQUIP-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391105 | Work Order Description - 391105 - PSPM | PSPM | 1 | 449117 | WPLAN | SYS-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391107 | Work Order Description - 391107 - PM | PM | 4 | 87815 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391109 | Work Order Description - 391109 - PM | PM | 4 | 78409 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-08-31 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 391111 | Work Order Description - 391111 - PSPM | PSPM | 1 | 375477 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 391113 | Work Order Description - 391113 - PSPM | PSPM | 1 | 127844 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 391115 | Work Order Description - 391115 - PSPM | PSPM | 1 | 74889 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 391117 | Work Order Description - 391117 - PSPM | PSPM | 1 | 74890 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 391119 | Work Order Description - 391119 - PM | PM | 3 | 375889 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 391121 | Work Order Description - 391121 - PM | PM | 3 | 396017 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391123 | Work Order Description - 391123 - PM | PM | 3 | 78366 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391125 | Work Order Description - 391125 - PM | PM | 3 | 396018 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391127 | Work Order Description - 391127 - PSPM | PSPM | 1 | 396061 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391129 | Work Order Description - 391129 - PSPM | PSPM | 1 | 99595 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391131 | Work Order Description - 391131 - PSPM | PSPM | 1 | 99517 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391133 | Work Order Description - 391133 - PSPM | PSPM | 1 | 396149 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391135 | Work Order Description - 391135 - PSPM | PSPM | 1 | 78431 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391137 | Work Order Description - 391137 - PSPM | PSPM | 1 | 105850 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391139 | Work Order Description - 391139 - PSPM | PSPM | 1 | 78394 | SCHD | TPS | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391141 | Work Order Description - 391141 - PSPM | PSPM | 1 | 99634 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391143 | Work Order Description - 391143 - PSPM | PSPM | 1 | 445299 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391145 | Work Order Description - 391145 - PSPM | PSPM | 1 | 78436 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391147 | Work Order Description - 391147 - PSPM | PSPM | 1 | 186671 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391149 | Work Order Description - 391149 - PSPM | PSPM | 1 | 395993 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391151 | Work Order Description - 391151 - PSPM | PSPM | 1 | 105707 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391153 | Work Order Description - 391153 - PSPM | PSPM | 1 | 395971 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391155 | Work Order Description - 391155 - PSPM | PSPM | 1 | 445294 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391157 | Work Order Description - 391157 - PSPM | PSPM | 1 | 78370 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391159 | Work Order Description - 391159 - PSPM | PSPM | 1 | 99632 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391161 | Work Order Description - 391161 - PSPM | PSPM | 1 | 127431 | SCHD | TPS | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 27
2019-03-31 | 391163 | Work Order Description - 391163 - PSPM | PSPM | 1 | 445296 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391165 | Work Order Description - 391165 - PSPM | PSPM | 1 | 450992 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | SAFETY | 4
2019-03-31 | 391167 | Work Order Description - 391167 - PSPM | PSPM | 1 | 436705 | SCHD | TPS | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 391169 | Work Order Description - 391169 - PSPM | PSPM | 1 | 669993 | SCHD | TPS | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 391171 | Work Order Description - 391171 - PSPM | PSPM | 1 | 393042 | WPLAN | EQUIP-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-14 | 1 | INTEGRITY | MECHANICAL | 22
2019-03-31 | 391173 | Work Order Description - 391173 - PM | PM | 4 | 528193 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-16 | 1 | INTEGRITY | INSPECTION | 34
2019-03-31 | 391175 | Work Order Description - 391175 - PSPM | PSPM | 1 | 396021 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391177 | Work Order Description - 391177 - PSPM | PSPM | 1 | 99778 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391179 | Work Order Description - 391179 - PSPM | PSPM | 1 | 78357 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391181 | Work Order Description - 391181 - PSPM | PSPM | 1 | 105754 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391183 | Work Order Description - 391183 - PSPM | PSPM | 1 | 453840 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391185 | Work Order Description - 391185 - PSPM | PSPM | 1 | 105932 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391187 | Work Order Description - 391187 - PSPM | PSPM | 1 | 78430 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391189 | Work Order Description - 391189 - PSPM | PSPM | 1 | 396148 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391191 | Work Order Description - 391191 - PSPM | PSPM | 1 | 78428 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391193 | Work Order Description - 391193 - PSPM | PSPM | 1 | 78405 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391195 | Work Order Description - 391195 - PSPM | PSPM | 1 | 99488 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391197 | Work Order Description - 391197 - PSPM | PSPM | 1 | 78434 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391199 | Work Order Description - 391199 - PSPM | PSPM | 1 | 186672 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391201 | Work Order Description - 391201 - PSPM | PSPM | 1 | 105759 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391203 | Work Order Description - 391203 - PM | PM | 3 | 105711 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-18 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 391205 | Work Order Description - 391205 - PM | PM | 3 | 105738 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-18 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 391207 | Work Order Description - 391207 - PM | PM | 3 | 78377 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-18 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 391209 | Work Order Description - 391209 - PM | PM | 3 | 78384 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-18 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 391211 | Work Order Description - 391211 - PM | PM | 3 | 105795 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-18 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 391213 | Work Order Description - 391213 - PM | PM | 3 | 105822 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-18 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 391215 | Work Order Description - 391215 - PM | PM | 3 | 125690 | WPLAN | PACK-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391217 | Work Order Description - 391217 - PM | PM | 3 | 74996 | WPLAN | PACK-ISOL | 2019-02-01 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 391221 | Work Order Description - 391221 - PSPM | PSPM | 1 | 440666 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391223 | Work Order Description - 391223 - PSPM | PSPM | 1 | 78460 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391225 | Work Order Description - 391225 - PSPM | PSPM | 1 | 440670 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391227 | Work Order Description - 391227 - PSPM | PSPM | 1 | 440670 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391229 | Work Order Description - 391229 - PSPM | PSPM | 1 | 440670 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391231 | Work Order Description - 391231 - PSPM | PSPM | 1 | 125895 | SCHD | PACK-ISOL | 2019-03-06 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 391235 | Work Order Description - 391235 - PSPM | PSPM | 1 | 266278 | SCHD | PACK-ISOL | 2019-03-06 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 391239 | Work Order Description - 391239 - PSPM | PSPM | 1 | 125965 | SCHD | PACK-ISOL | 2019-03-06 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 391243 | Work Order Description - 391243 - PM | PM | 3 | 375887 | SCHD | PACK-ISOL | 2019-02-13 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 0
2019-03-31 | 391245 | Work Order Description - 391245 - PM | PM | 3 | 124294 | SCHD | PACK-ISOL | 2019-02-13 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 391247 | Work Order Description - 391247 - PM | PM | 3 | 125915 | SCHD | PACK-ISOL | 2019-02-13 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 0
2019-03-31 | 391249 | Work Order Description - 391249 - PM | PM | 3 | 80398 | SCHD | PACK-ISOL | 2019-02-13 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 391251 | Work Order Description - 391251 - PM | PM | 3 | 124264 | SCHD | PACK-ISOL | 2019-02-13 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 391253 | Work Order Description - 391253 - PM | PM | 3 | 80402 | SCHD | PACK-ISOL | 2019-02-13 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 391255 | Work Order Description - 391255 - PM | PM | 3 | 266328 | SCHD | PACK-ISOL | 2019-02-13 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 391257 | Work Order Description - 391257 - PM | PM | 3 | 670547 | SCHD | PACK-ISOL | 2019-02-13 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 391259 | Work Order Description - 391259 - PSPM | PSPM | 1 | 445262 | SCHD | PACK-ISOL | 2019-02-13 | 2019-08-31 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391261 | Work Order Description - 391261 - PM | PM | 2 | 449172 | WPLAN | PACK-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-22 | 1 | MAINTENANCE | MECHANICAL | 140
2019-03-31 | 391263 | Work Order Description - 391263 - PM | PM | 2 | 527194 | WPLAN | PACK-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-22 | 1 | MAINTENANCE | MECHANICAL | 140
2019-03-31 | 391265 | Work Order Description - 391265 - PM | PM | 2 | 75010 | WPLAN | PACK-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-22 | 1 | MAINTENANCE | MECHANICAL | 140
2019-03-31 | 391267 | Work Order Description - 391267 - PM | PM | 3 | 670544 | SCHD | PACK-ISOL | 2019-02-13 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 391269 | Work Order Description - 391269 - PM | PM | 3 | 124185 | SCHD | PACK-ISOL | 2019-02-13 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 391271 | Work Order Description - 391271 - PM | PM | 3 | 125912 | SCHD | PACK-ISOL | 2019-02-13 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 391273 | Work Order Description - 391273 - PM | PM | 3 | 124238 | SCHD | PACK-ISOL | 2019-02-13 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 391275 | Work Order Description - 391275 - PM | PM | 3 | 383952 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 391277 | Work Order Description - 391277 - PM | PM | 3 | 670546 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 0
2019-03-31 | 391279 | Work Order Description - 391279 - PM | PM | 3 | 78337 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391281 | Work Order Description - 391281 - PM | PM | 3 | 99589 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391283 | Work Order Description - 391283 - PM | PM | 3 | 78368 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391285 | Work Order Description - 391285 - PM | PM | 3 | 78367 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391287 | Work Order Description - 391287 - PM | PM | 3 | 99568 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391289 | Work Order Description - 391289 - PM | PM | 3 | 395968 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391291 | Work Order Description - 391291 - PM | PM | 3 | 186661 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391293 | Work Order Description - 391293 - PM | PM | 3 | 449173 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 391295 | Work Order Description - 391295 - PM | PM | 3 | 375808 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 391297 | Work Order Description - 391297 - PM | PM | 3 | 449176 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 391299 | Work Order Description - 391299 - PM | PM | 3 | 396020 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391301 | Work Order Description - 391301 - PM | PM | 3 | 99588 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391303 | Work Order Description - 391303 - PM | PM | 3 | 445055 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391305 | Work Order Description - 391305 - PM | PM | 3 | 99653 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 391307 | Work Order Description - 391307 - PSPM | PSPM | 1 | 92712 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 391309 | Work Order Description - 391309 - PSPM | PSPM | 1 | 277246 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 391311 | Work Order Description - 391311 - PSPM | PSPM | 1 | 396754 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 391313 | Work Order Description - 391313 - PSPM | PSPM | 1 | 277349 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 391315 | Work Order Description - 391315 - PM | PM | 3 | 527192 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 391317 | Work Order Description - 391317 - PM | PM | 3 | 527196 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 391319 | Work Order Description - 391319 - PM | PM | 3 | 527255 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 391321 | Work Order Description - 391321 - PSPM | PSPM | 1 | 179140 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391323 | Work Order Description - 391323 - PSPM | PSPM | 1 | 445295 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391325 | Work Order Description - 391325 - PSPM | PSPM | 1 | 105933 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391327 | Work Order Description - 391327 - PSPM | PSPM | 1 | 105937 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391329 | Work Order Description - 391329 - PSPM | PSPM | 1 | 78433 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391331 | Work Order Description - 391331 - PSPM | PSPM | 1 | 396177 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391333 | Work Order Description - 391333 - PSPM | PSPM | 1 | 89486 | WPLAN | SYS-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391335 | Work Order Description - 391335 - PSPM | PSPM | 1 | 105706 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391337 | Work Order Description - 391337 - PSPM | PSPM | 1 | 395970 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391339 | Work Order Description - 391339 - PSPM | PSPM | 1 | 78338 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391341 | Work Order Description - 391341 - PSPM | PSPM | 1 | 395974 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391343 | Work Order Description - 391343 - PSPM | PSPM | 1 | 99624 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391345 | Work Order Description - 391345 - PSPM | PSPM | 1 | 78369 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391347 | Work Order Description - 391347 - PSPM | PSPM | 1 | 99591 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391349 | Work Order Description - 391349 - PSPM | PSPM | 1 | 78371 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391351 | Work Order Description - 391351 - PSPM | PSPM | 1 | 105789 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391353 | Work Order Description - 391353 - PSPM | PSPM | 1 | 78372 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391355 | Work Order Description - 391355 - PSPM | PSPM | 1 | 99592 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391357 | Work Order Description - 391357 - PSPM | PSPM | 1 | 99651 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391359 | Work Order Description - 391359 - PSPM | PSPM | 1 | 99590 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391361 | Work Order Description - 391361 - PSPM | PSPM | 1 | 105788 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391363 | Work Order Description - 391363 - PSPM | PSPM | 1 | 106034 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391365 | Work Order Description - 391365 - PSPM | PSPM | 1 | 78356 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391367 | Work Order Description - 391367 - PSPM | PSPM | 1 | 105762 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391369 | Work Order Description - 391369 - PSPM | PSPM | 1 | 99542 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391371 | Work Order Description - 391371 - PSPM | PSPM | 1 | 664891 | WPLAN | SYS-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 391373 | Work Order Description - 391373 - PSPM | PSPM | 1 | 99232 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | SERVICES | 4
2019-03-31 | 391375 | Work Order Description - 391375 - PSPM | PSPM | 1 | 99434 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | SERVICES | 4
2019-03-31 | 391377 | Work Order Description - 391377 - PSPM | PSPM | 1 | 440611 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391379 | Work Order Description - 391379 - PSPM | PSPM | 1 | 105912 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391381 | Work Order Description - 391381 - PSPM | PSPM | 1 | 105913 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391383 | Work Order Description - 391383 - PSPM | PSPM | 1 | 78424 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391385 | Work Order Description - 391385 - PSPM | PSPM | 1 | 78425 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391387 | Work Order Description - 391387 - PSPM | PSPM | 1 | 99749 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391389 | Work Order Description - 391389 - PSPM | PSPM | 1 | 99771 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391391 | Work Order Description - 391391 - PSPM | PSPM | 1 | 99547 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391393 | Work Order Description - 391393 - PSPM | PSPM | 1 | 99544 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391395 | Work Order Description - 391395 - PSPM | PSPM | 1 | 99777 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391397 | Work Order Description - 391397 - PSPM | PSPM | 1 | 396212 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391399 | Work Order Description - 391399 - PSPM | PSPM | 1 | 99808 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391401 | Work Order Description - 391401 - PSPM | PSPM | 1 | 396216 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391403 | Work Order Description - 391403 - PSPM | PSPM | 1 | 396180 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391405 | Work Order Description - 391405 - PSPM | PSPM | 1 | 99806 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391407 | Work Order Description - 391407 - PSPM | PSPM | 1 | 99833 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391409 | Work Order Description - 391409 - PSPM | PSPM | 1 | 99631 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391412 | Work Order Description - 391412 - PSPM | PSPM | 1 | 105708 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391414 | Work Order Description - 391414 - PSPM | PSPM | 1 | 179118 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391416 | Work Order Description - 391416 - PSPM | PSPM | 1 | 392310 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 391418 | Work Order Description - 391418 - PSPM | PSPM | 1 | 227869 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 391420 | Work Order Description - 391420 - PSPM | PSPM | 1 | 445511 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391422 | Work Order Description - 391422 - PSPM | PSPM | 1 | 445512 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391424 | Work Order Description - 391424 - PSPM | PSPM | 1 | 392053 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391426 | Work Order Description - 391426 - PSPM | PSPM | 1 | 127636 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 391428 | Work Order Description - 391428 - PSPM | PSPM | 1 | 445511 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391430 | Work Order Description - 391430 - PSPM | PSPM | 1 | 445512 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391432 | Work Order Description - 391432 - PSPM | PSPM | 1 | 128021 | SCHD | EQUIP-ISOL | 2019-03-22 | 2019-07-02 | 2019-07-13 | 2019-07-14 | 1 | WELLS | WELLS | 8
2019-03-31 | 391434 | Work Order Description - 391434 - PM | PM | 4 | 99484 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 391436 | Work Order Description - 391436 - PM | PM | 3 | 78374 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 391438 | Work Order Description - 391438 - PSPM | PSPM | 1 | 659395 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 391440 | Work Order Description - 391440 - PM | PM | 4 | 528189 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 391442 | Work Order Description - 391442 - PM | PM | 3 | 99594 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 391444 | Work Order Description - 391444 - PSPM | PSPM | 1 | 127431 | SCHD | TPS | 2019-03-22 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | SUBSEA | 8
2019-03-31 | 391446 | Work Order Description - 391446 - PM | PM | 4 | 112922 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 391448 | Work Order Description - 391448 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391450 | Work Order Description - 391450 - PSPM | PSPM | 1 | 453835 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391452 | Work Order Description - 391452 - PSPM | PSPM | 1 | 74923 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 391454 | Work Order Description - 391454 - PSPM | PSPM | 1 | 450687 | SCHD | TPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 391456 | Work Order Description - 391456 - PSPM | PSPM | 1 | 441437 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 391458 | Work Order Description - 391458 - PSPM | PSPM | 1 | 450687 | SCHD | TPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 391460 | Work Order Description - 391460 - PSPM | PSPM | 1 | 450688 | SCHD | TPS | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 391462 | Work Order Description - 391462 - PSPM | PSPM | 1 | 449172 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391464 | Work Order Description - 391464 - PSPM | PSPM | 1 | 527194 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391466 | Work Order Description - 391466 - PSPM | PSPM | 1 | 75010 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391468 | Work Order Description - 391468 - PM | PM | 3 | 266661 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-15 | 2 | MAINTENANCE | MECHANICAL | 17
2019-03-31 | 391470 | Work Order Description - 391470 - PM | PM | 4 | 126203 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 391472 | Work Order Description - 391472 - PSPM | PSPM | 1 | 392053 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391474 | Work Order Description - 391474 - PSPM | PSPM | 1 | 445511 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391476 | Work Order Description - 391476 - PSPM | PSPM | 1 | 445512 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391478 | Work Order Description - 391478 - PSPM | PSPM | 1 | 392053 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391480 | Work Order Description - 391480 - PSPM | PSPM | 1 | 238339 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-07-02 | 2019-07-13 | 2019-07-14 | 1 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 391484 | Work Order Description - 391484 - PSPM | PSPM | 1 | 378270 | WPLAN | EQUIP-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-14 | 1 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 391488 | Work Order Description - 391488 - PSPM | PSPM | 1 | 123943 | WPLAN | EQUIP-ISOL | 2019-02-01 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 391490 | Work Order Description - 391490 - PSPM | PSPM | 1 | 80090 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 391492 | Work Order Description - 391492 - PSPM | PSPM | 1 | 377876 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 391494 | Work Order Description - 391494 - PSPM | PSPM | 1 | 377877 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 391496 | Work Order Description - 391496 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 391498 | Work Order Description - 391498 - PSPM | PSPM | 1 | 449144 | SCHD | PACK-ISOL | 2019-03-06 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 391500 | Work Order Description - 391500 - PM | PM | 4 | 106148 | SCHD | TPS | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 391502 | Work Order Description - 391502 - PSPM | PSPM | 1 | 78303 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391504 | Work Order Description - 391504 - PSPM | PSPM | 1 | 78471 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391506 | Work Order Description - 391506 - PSPM | PSPM | 1 | 105623 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391508 | Work Order Description - 391508 - PSPM | PSPM | 1 | 105852 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391510 | Work Order Description - 391510 - PSPM | PSPM | 1 | 78315 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391512 | Work Order Description - 391512 - PSPM | PSPM | 1 | 78305 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391514 | Work Order Description - 391514 - PSPM | PSPM | 1 | 396150 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391516 | Work Order Description - 391516 - PSPM | PSPM | 1 | 99489 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391518 | Work Order Description - 391518 - PSPM | PSPM | 1 | 396215 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391520 | Work Order Description - 391520 - PSPM | PSPM | 1 | 436729 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391522 | Work Order Description - 391522 - PSPM | PSPM | 1 | 78314 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391524 | Work Order Description - 391524 - PSPM | PSPM | 1 | 78297 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391526 | Work Order Description - 391526 - PSPM | PSPM | 1 | 440695 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391528 | Work Order Description - 391528 - PSPM | PSPM | 1 | 105999 | SCHD | TPS | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391530 | Work Order Description - 391530 - PSPM | PSPM | 1 | 395928 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391532 | Work Order Description - 391532 - PSPM | PSPM | 1 | 78473 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391534 | Work Order Description - 391534 - PSPM | PSPM | 1 | 178889 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391536 | Work Order Description - 391536 - PSPM | PSPM | 1 | 436704 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391538 | Work Order Description - 391538 - PSPM | PSPM | 1 | 186615 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391540 | Work Order Description - 391540 - PSPM | PSPM | 1 | 105626 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391542 | Work Order Description - 391542 - PSPM | PSPM | 1 | 105628 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391544 | Work Order Description - 391544 - PSPM | PSPM | 1 | 105853 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391546 | Work Order Description - 391546 - PSPM | PSPM | 1 | 178961 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391548 | Work Order Description - 391548 - PSPM | PSPM | 1 | 186674 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391550 | Work Order Description - 391550 - PSPM | PSPM | 1 | 105567 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391552 | Work Order Description - 391552 - PSPM | PSPM | 1 | 78401 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391554 | Work Order Description - 391554 - PSPM | PSPM | 1 | 178890 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391556 | Work Order Description - 391556 - PSPM | PSPM | 1 | 453778 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391558 | Work Order Description - 391558 - PSPM | PSPM | 1 | 78343 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391560 | Work Order Description - 391560 - PSPM | PSPM | 1 | 396179 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391562 | Work Order Description - 391562 - PSPM | PSPM | 1 | 78313 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391564 | Work Order Description - 391564 - PSPM | PSPM | 1 | 105565 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391566 | Work Order Description - 391566 - PSPM | PSPM | 1 | 78301 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391568 | Work Order Description - 391568 - PSPM | PSPM | 1 | 105593 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391570 | Work Order Description - 391570 - PSPM | PSPM | 1 | 78300 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391572 | Work Order Description - 391572 - PSPM | PSPM | 1 | 106117 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391574 | Work Order Description - 391574 - PSPM | PSPM | 1 | 440697 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391576 | Work Order Description - 391576 - PSPM | PSPM | 1 | 78299 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391578 | Work Order Description - 391578 - PSPM | PSPM | 1 | 105565 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 391580 | Work Order Description - 391580 - PSPM | PSPM | 1 | 105623 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391582 | Work Order Description - 391582 - PSPM | PSPM | 1 | 99958 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391584 | Work Order Description - 391584 - PSPM | PSPM | 1 | 396174 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391586 | Work Order Description - 391586 - PM | PM | 4 | 105565 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391588 | Work Order Description - 391588 - PM | PM | 3 | 83774 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2019-07-13 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 391590 | Work Order Description - 391590 - PSPM | PSPM | 1 | 74897 | SCHD | SUBSYS-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 391592 | Work Order Description - 391592 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 391594 | Work Order Description - 391594 - PM | PM | 2 | 670468 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-26 | 2020-07-28 | 2020-08-07 | 2 | MAINTENANCE | MECHANICAL | 140
2019-03-31 | 391596 | Work Order Description - 391596 - PSPM | PSPM | 1 | 445512 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 391598 | Work Order Description - 391598 - PSPM | PSPM | 1 | 445511 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-02 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 393357 | Work Order Description - 393357 - BR | BR | 3 | 259104 | WSCHD | SYS-ISOL | 2019-02-01 | 2019-08-03 |  |  | 3 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 393377 | Work Order Description - 393377 - BR | BR | 3 | 671640 | SCHD | EQUIP-ISOL | 2019-02-01 | 2021-01-30 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 393406 | Work Order Description - 393406 - PRJ | PRJ | 4 | 29137 | SCHD | NORM-OPS | 2019-03-15 | 2021-01-30 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | CONSTRUCTION | 804
2019-03-31 | 393414 | Work Order Description - 393414 - PRJ | PRJ | 4 | 29137 | SCHD | NORM-OPS | 2019-03-29 | 2021-01-30 | 2019-03-23 | 2019-03-23 | 4 | MAINTENANCE | ELECTRICAL | 516
2019-03-31 | 393436 | Work Order Description - 393436 - BR | BR | 1 | 227861 | SCHD | EQUIP-ISOL | 2019-02-13 | 2021-01-30 | 2020-01-31 | 2020-02-01 | 4 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 393475 | Work Order Description - 393475 - PSCM | PSCM | 1 | 675037 | SCHD | EQUIP-ISOL | 2019-02-21 | 2021-01-30 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 393479 | Work Order Description - 393479 - PRJ | PRJ | 4 | 29137 | WPLAN | NORM-OPS | 2019-02-04 | 2021-01-30 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | CONSTRUCTION | 1056
2019-03-31 | 393482 | Work Order Description - 393482 - PRJ | PRJ | 4 | 29137 | WPLAN | NORM-OPS | 2019-02-04 | 2021-01-30 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | CONSTRUCTION | 804
2019-03-31 | 393496 | Work Order Description - 393496 - PRJ | PRJ | 4 | 29137 | SCHD | NORM-OPS | 2019-02-04 | 2021-01-30 | 2020-01-31 | 2020-01-31 | 4 | MAINTENANCE | SERVICES | 258
2019-03-31 | 393539 | Work Order Description - 393539 - BR | BR | 2 | 85177 | SCHD | PACK-ISOL | 2019-03-06 | 2021-01-31 | 2020-12-19 | 2020-12-20 | 4 | MAINTENANCE | INSTRUMENTS | 23
2019-03-31 | 393549 | Work Order Description - 393549 - PM | PM | 2 | 572308 | WSCHD | NORM-OPS | 2019-02-02 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 393551 | Work Order Description - 393551 - PM | PM | 4 | 580762 | WSCHD | NORM-OPS | 2019-02-02 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 393553 | Work Order Description - 393553 - PSPM | PSPM | 1 | 410324 | WSCHD | NORM-OPS | 2019-02-02 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 393555 | Work Order Description - 393555 - PM | PM | 4 | 313220 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 393557 | Work Order Description - 393557 - PM | PM | 4 | 259881 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 393559 | Work Order Description - 393559 - PM | PM | 4 | 259882 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 393561 | Work Order Description - 393561 - PM | PM | 4 | 309636 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 393563 | Work Order Description - 393563 - PM | PM | 4 | 28498 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 393565 | Work Order Description - 393565 - PM | PM | 4 | 555212 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 393567 | Work Order Description - 393567 - PM | PM | 4 | 555236 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 393569 | Work Order Description - 393569 - PM | PM | 4 | 324721 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 393571 | Work Order Description - 393571 - PM | PM | 4 | 257241 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 393573 | Work Order Description - 393573 - PM | PM | 4 | 176721 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 393575 | Work Order Description - 393575 - PM | PM | 4 | 555237 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 393577 | Work Order Description - 393577 - PM | PM | 4 | 403849 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 393579 | Work Order Description - 393579 - PSPM | PSPM | 1 | 216926 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | OPERATIONS | OPERATIONS | 12
2019-03-31 | 393581 | Work Order Description - 393581 - PSPM | PSPM | 1 | 447441 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 393583 | Work Order Description - 393583 - PM | PM | 1 | 446516 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 393585 | Work Order Description - 393585 - PM | PM | 1 | 501092 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | SAFETY | 6
2019-03-31 | 393587 | Work Order Description - 393587 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 2 | MAINTENANCE | SAFETY | 7
2019-03-31 | 393589 | Work Order Description - 393589 - PM | PM | 4 | 670583 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 393591 | Work Order Description - 393591 - PSPM | PSPM | 1 | 659058 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | OPERATIONS | SAFETY | 1
2019-03-31 | 393593 | Work Order Description - 393593 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 393595 | Work Order Description - 393595 - PSPM | PSPM | 1 | 669726 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 393597 | Work Order Description - 393597 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 393717 | Work Order Description - 393717 - CM | CM | 4 | 478639 | WPLAN | SYS-ISOL | 2019-02-04 | 2021-01-31 | 2020-02-01 | 2020-02-01 | 4 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 393718 | Work Order Description - 393718 - BR | BR | 3 | 395483 | SCHD | NORM-OPS | 2019-02-13 | 2021-01-31 | 2020-02-01 | 2020-02-01 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 393720 | Work Order Description - 393720 - CM | CM | 3 | 478643 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-04 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 393728 | Work Order Description - 393728 - BR | BR | 3 | 398439 | SCHD | NORM-OPS | 2019-02-04 | 2020-02-02 | 2019-08-03 | 2019-08-03 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 393734 | Work Order Description - 393734 - CM | CM | 4 | 30031 | WMATL | NORM-OPS | 2019-03-08 | 2021-01-31 | 2020-02-01 | 2020-02-01 | 4 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 393737 | Work Order Description - 393737 - CM | CM | 1 | 649797 | WSCHD | NORM-OPS | 2019-02-05 | 2020-02-02 | 2019-08-03 | 2019-08-03 | 3 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 393739 | Work Order Description - 393739 - PRJ | PRJ | 4 | 320153 | WPLAN | NORM-OPS | 2019-02-04 | 2021-01-31 | 2020-02-01 | 2020-02-01 | 4 | ENGINEERING | INSPECTION | 4
2019-03-31 | 393740 | Work Order Description - 393740 - BR | BR | 4 | 464259 | WSCHD | SYS-ISOL | 2019-02-02 | 2020-02-02 |  |  | 3 | INTEGRITY | MECHANICAL | 0
2019-03-31 | 393741 | Work Order Description - 393741 - CM | CM | 4 | 314182 | WSCHD | NORM-OPS | 2019-02-09 | 2020-02-02 | 2019-08-03 | 2019-08-03 | 3 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 393766 | Work Order Description - 393766 - BR | BR | 4 | 123022 | SCHD | NORM-OPS | 2019-02-13 | 2021-01-31 | 2020-01-05 | 2020-01-05 | 4 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 393776 | Work Order Description - 393776 - CM | CM | 1 | 649865 | WSCHD | NORM-OPS | 2019-02-05 | 2020-02-02 | 2019-08-03 | 2019-08-03 | 3 | MAINTENANCE | ELECTRICAL | 7
2019-03-31 | 393778 | Work Order Description - 393778 - PRJ | PRJ | 4 | 556357 | WPLAN | NORM-OPS | 2019-02-04 | 2021-01-31 | 2020-02-01 | 2020-02-01 | 4 | ENGINEERING | CONSTRUCTION | 42
2019-03-31 | 393785 | Work Order Description - 393785 - CM | CM | 4 | 361501 | WSCHD | NORM-OPS | 2019-02-06 | 2021-01-31 | 2020-02-01 | 2020-02-01 | 4 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 393792 | Work Order Description - 393792 - PSCM | PSCM | 1 | 361956 | WSCHD | NORM-OPS | 2019-02-06 | 2021-01-31 | 2020-02-01 | 2020-02-01 | 4 | MAINTENANCE | ELECTRICAL | 7
2019-03-31 | 393800 | Work Order Description - 393800 - PRJ | PRJ | 4 | 479580 | SCHD | NORM-OPS | 2019-02-13 | 2021-01-31 | 2020-02-01 | 2020-02-01 | 4 | ENGINEERING | INSTRUMENTS | 12
2019-03-31 | 393840 | Work Order Description - 393840 - CM | CM | 3 | 272735 | SCHD | EQUIP-ISOL | 2019-02-05 | 2021-01-31 | 2019-07-20 | 2019-07-20 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 393849 | Work Order Description - 393849 - PM | PM | 4 | 18317 | WSCHD | EQUIP-ISOL | 2019-02-03 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 393851 | Work Order Description - 393851 - PM | PM | 4 | 18316 | WSCHD | EQUIP-ISOL | 2019-02-03 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 393853 | Work Order Description - 393853 - PM | PM | 4 | 666316 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 393855 | Work Order Description - 393855 - PM | PM | 4 | 417521 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 393857 | Work Order Description - 393857 - PM | PM | 4 | 50099 | WSCHD | EQUIP-ISOL | 2019-02-03 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 393859 | Work Order Description - 393859 - PM | PM | 4 | 50098 | WSCHD | EQUIP-ISOL | 2019-02-03 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 393861 | Work Order Description - 393861 - PM | PM | 4 | 411571 | WSCHD | NORM-OPS | 2019-02-03 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 393863 | Work Order Description - 393863 - PM | PM | 4 | 358159 | WSCHD | NORM-OPS | 2019-02-03 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 393865 | Work Order Description - 393865 - PM | PM | 4 | 540667 | WSCHD | NORM-OPS | 2019-02-03 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 393867 | Work Order Description - 393867 - PM | PM | 4 | 678551 | WSCHD | NORM-OPS | 2019-02-03 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 393869 | Work Order Description - 393869 - PSPM | PSPM | 1 | 470877 | WSCHD | NORM-OPS | 2019-02-03 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 393871 | Work Order Description - 393871 - PSPM | PSPM | 1 | 361798 | WSCHD | NORM-OPS | 2019-02-03 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 393873 | Work Order Description - 393873 - PM | PM | 4 | 360243 | WSCHD | NORM-OPS | 2019-02-03 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 393875 | Work Order Description - 393875 - PSPM | PSPM | 1 | 320057 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 393877 | Work Order Description - 393877 - PM | PM | 4 | 555305 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 393879 | Work Order Description - 393879 - PSPM | PSPM | 1 | 477566 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 393881 | Work Order Description - 393881 - PSPM | PSPM | 1 | 492108 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 393883 | Work Order Description - 393883 - PSPM | PSPM | 1 | 259535 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 393885 | Work Order Description - 393885 - PM | PM | 3 | 552989 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 393887 | Work Order Description - 393887 - PM | PM | 3 | 552990 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-09-20 | 2019-06-03 | 2019-06-03 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 393889 | Work Order Description - 393889 - PM | PM | 4 | 556260 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 393891 | Work Order Description - 393891 - PM | PM | 2 | 216011 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 393893 | Work Order Description - 393893 - PM | PM | 4 | 320026 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 393895 | Work Order Description - 393895 - PM | PM | 4 | 74216 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 393903 | Work Order Description - 393903 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 393905 | Work Order Description - 393905 - PM | PM | 4 | 659496 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 394013 | Work Order Description - 394013 - BR | BR | 2 | 438521 | WPLAN | PACK-ISOL | 2019-02-05 | 2021-02-01 | 2020-02-02 | 2020-02-02 | 4 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 394020 | Work Order Description - 394020 - PRJ | PRJ | 4 | 555977 | SCHD | NORM-OPS | 2019-02-04 | 2021-02-01 | 2020-02-02 | 2020-02-02 | 4 | ENGINEERING | SERVICES | 154
2019-03-31 | 394025 | Work Order Description - 394025 - BR | BR | 2 | 493534 | WPLAN | EQUIP-ISOL | 2019-02-05 | 2021-02-01 | 2020-02-02 | 2020-02-02 | 4 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 394049 | Work Order Description - 394049 - BR | BR | 3 | 387836 | SCHD | TPS | 2019-02-13 | 2021-02-01 | 2019-07-13 | 2019-07-15 | 4 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 394059 | Work Order Description - 394059 - CM | CM | 4 | 457862 | WMATL | SYS-ISOL | 2019-03-25 | 2021-02-01 | 2020-02-02 | 2020-02-02 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 394090 | Work Order Description - 394090 - PRJ | PRJ | 4 | 479551 | WPLAN | NORM-OPS | 2019-02-04 | 2021-02-01 | 2020-02-03 | 2020-02-03 | 4 | ENGINEERING | CONSTRUCTION | 7
2019-03-31 | 394092 | Work Order Description - 394092 - CM | CM | 1 | 19017 | WPLAN | NORM-OPS | 2019-02-10 | 2021-02-01 | 2020-02-02 | 2020-02-02 | 4 | INTEGRITY | SERVICES | 32
2019-03-31 | 394094 | Work Order Description - 394094 - PSCM | PSCM | 1 | 19017 | WSCHD | NORM-OPS | 2019-02-06 | 2020-02-03 | 2019-08-04 | 2019-08-04 | 3 | INTEGRITY | SERVICES | 18
2019-03-31 | 394105 | Work Order Description - 394105 - CM | CM | 1 | 19017 | WSCHD | NORM-OPS | 2019-02-09 | 2021-02-01 | 2020-02-02 | 2020-02-02 | 4 | INTEGRITY | CONSTRUCTION | 12
2019-03-31 | 394124 | Work Order Description - 394124 - CM | CM | 1 | 35655 | SCHD | EQUIP-ISOL | 2019-02-13 | 2021-02-02 | 2020-02-03 | 2020-02-04 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 394125 | Work Order Description - 394125 - CM | CM | 1 | 35346 | SCHD | EQUIP-ISOL | 2019-02-13 | 2021-02-02 | 2020-02-03 | 2020-02-04 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 394127 | Work Order Description - 394127 - CM | CM | 1 | 35347 | SCHD | EQUIP-ISOL | 2019-02-13 | 2021-02-02 | 2020-02-03 | 2020-02-04 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 394129 | Work Order Description - 394129 - CM | CM | 1 | 537088 | SCHD | EQUIP-ISOL | 2019-02-13 | 2021-02-02 | 2020-02-03 | 2020-02-04 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 394142 | Work Order Description - 394142 - PM | PM | 4 | 450481 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 2 | OPERATIONS | OPERATIONS | 5
2019-03-31 | 394144 | Work Order Description - 394144 - PM | PM | 2 | 312683 | SCHD | PACK-ISOL | 2019-02-08 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 394148 | Work Order Description - 394148 - PM | PM | 4 | 481609 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 394150 | Work Order Description - 394150 - PSPM | PSPM | 1 | 462436 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 394153 | Work Order Description - 394153 - PM | PM | 4 | 476154 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 394155 | Work Order Description - 394155 - PM | PM | 3 | 309675 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 394157 | Work Order Description - 394157 - PM | PM | 3 | 309675 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 394159 | Work Order Description - 394159 - PM | PM | 4 | 472933 | SCHD | EQUIP-ISOL | 2019-02-04 | 2019-09-21 | 2019-06-04 | 2019-06-04 | 2 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 394161 | Work Order Description - 394161 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 394165 | Work Order Description - 394165 - PSPM | PSPM | 4 | 403503 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 394167 | Work Order Description - 394167 - PSPM | PSPM | 1 | 392215 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 394169 | Work Order Description - 394169 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-02-04 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 394305 | Work Order Description - 394305 - BR | BR | 4 | 227861 | SCHD | EQUIP-ISOL | 2019-02-13 | 2021-02-02 | 2020-02-03 | 2020-02-03 | 4 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 394311 | Work Order Description - 394311 - BR | BR | 3 | 656290 | WSCHD | PACK-ISOL | 2019-02-06 | 2019-08-06 | 2019-05-06 | 2019-05-06 | 3 | MAINTENANCE | MECHANICAL | 95
2019-03-31 | 394314 | Work Order Description - 394314 - BR | BR | 1 | 356363 | WSCHD | NORM-OPS | 2019-02-06 | 2021-02-05 | 2019-08-02 | 2019-08-02 | 4 | MAINTENANCE | CONSTRUCTION | 0
2019-03-31 | 394323 | Work Order Description - 394323 - CM | CM | 4 | 403920 | WPLAN | NORM-OPS | 2019-02-08 | 2019-08-06 | 2019-05-06 | 2019-05-06 | 3 | INTEGRITY | FABRIC | 0
2019-03-31 | 394360 | Work Order Description - 394360 - CM | CM | 4 | 403920 | WPLAN | NORM-OPS | 2019-02-08 | 2020-02-04 | 2019-08-05 | 2019-08-19 | 3 | INTEGRITY | FABRIC | 100
2019-03-31 | 394362 | Work Order Description - 394362 - CM | CM | 4 | 403920 | WPLAN | NORM-OPS | 2019-02-08 | 2020-02-04 | 2019-08-05 | 2019-08-16 | 3 | INTEGRITY | FABRIC | 75
2019-03-31 | 394365 | Work Order Description - 394365 - BR | BR | 1 | 669989 | WPLAN | NORM-OPS | 2019-02-13 | 2021-02-02 | 2020-02-03 | 2020-02-06 | 4 | MAINTENANCE | INSTRUMENTS | 40
2019-03-31 | 394385 | Work Order Description - 394385 - BR | BR | 3 | 227646 | WPLAN | PACK-ISOL | 2019-02-10 | 2021-02-02 | 2020-02-03 | 2020-02-03 | 4 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 394386 | Work Order Description - 394386 - CM | CM | 2 | 361657 | WPLAN | EQUIP-ISOL | 2019-02-10 | 2021-02-02 | 2020-02-03 | 2020-02-03 | 4 | INTEGRITY | CONSTRUCTION | 9
2019-03-31 | 394390 | Work Order Description - 394390 - CM | CM | 2 | 361657 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2020-02-04 | 2019-08-05 | 2019-08-05 | 3 | INTEGRITY | CONSTRUCTION | 7
2019-03-31 | 394439 | Work Order Description - 394439 - CM | CM | 1 | 307886 | WSCHD | NORM-OPS | 2019-02-05 | 2020-02-04 | 2019-08-05 | 2019-08-05 | 3 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 394440 | Work Order Description - 394440 - CM | CM | 3 | 361657 | WPLAN | TPS | 2019-03-10 | 2021-03-02 | 2021-01-18 | 2021-01-18 | 4 | INTEGRITY | CONSTRUCTION | 48
2019-03-31 | 394444 | Work Order Description - 394444 - CM | CM | 1 | 406666 | WSCHD | NORM-OPS | 2019-02-05 | 2020-02-04 | 2019-08-05 | 2019-08-05 | 3 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 394450 | Work Order Description - 394450 - BR | BR | 3 | 189071 | SCHD | SYS-ISOL | 2019-02-13 | 2019-08-06 | 2019-05-07 | 2019-05-07 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 394451 | Work Order Description - 394451 - CM | CM | 4 | 472797 | WPLAN | NORM-OPS | 2019-02-08 | 2020-02-04 | 2019-08-06 | 2019-09-24 | 3 | INTEGRITY | FABRIC | 350
2019-03-31 | 394456 | Work Order Description - 394456 - CM | CM | 4 | 544350 | SCHD | NORM-OPS | 2019-03-15 | 2021-02-02 | 2020-02-03 | 2020-02-03 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 394465 | Work Order Description - 394465 - CM | CM | 3 | 361657 | WPLAN | NORM-OPS | 2019-03-19 | 2021-02-02 | 2020-12-21 | 2020-12-21 | 4 | INTEGRITY | SERVICES | 256
2019-03-31 | 394486 | Work Order Description - 394486 - BR | BR | 4 | 51688 | WSCHD | NORM-OPS | 2019-02-06 | 2021-02-02 | 2020-02-03 | 2020-02-03 | 4 | MAINTENANCE | SERVICES | 16
2019-03-31 | 394495 | Work Order Description - 394495 - PM | PM | 4 | 540691 | WSCHD | NORM-OPS | 2019-02-05 | 2019-07-06 | 2019-06-05 | 2019-06-05 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 394497 | Work Order Description - 394497 - PM | PM | 4 | 481470 | WSCHD | NORM-OPS | 2019-02-05 | 2019-07-06 | 2019-06-05 | 2019-06-05 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 394499 | Work Order Description - 394499 - PM | PM | 2 | 305395 | WSCHD | NORM-OPS | 2019-02-05 | 2019-07-06 | 2019-06-05 | 2019-06-05 | 2 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 394502 | Work Order Description - 394502 - PSPM | PSPM | 1 | 652220 | WSCHD | NORM-OPS | 2019-02-20 | 2019-07-06 | 2019-06-05 | 2019-06-05 | 1 | MAINTENANCE | SERVICES | 10
2019-03-31 | 394504 | Work Order Description - 394504 - PSPM | PSPM | 1 | 325450 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-06 | 2019-06-05 | 2019-06-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 394506 | Work Order Description - 394506 - PSPM | PSPM | 1 | 262439 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-06 | 2019-06-05 | 2019-06-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 394508 | Work Order Description - 394508 - PSPM | PSPM | 1 | 262578 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-06 | 2019-06-05 | 2019-06-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 394510 | Work Order Description - 394510 - PSPM | PSPM | 1 | 499275 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-06 | 2019-06-05 | 2019-06-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 394512 | Work Order Description - 394512 - PSPM | PSPM | 1 | 262579 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-06 | 2019-06-05 | 2019-06-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 394514 | Work Order Description - 394514 - PSPM | PSPM | 1 | 325577 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-06 | 2019-06-05 | 2019-06-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 394516 | Work Order Description - 394516 - PM | PM | 4 | 501105 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-06 | 2019-06-08 | 2019-06-08 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 394518 | Work Order Description - 394518 - PM | PM | 4 | 99579 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-06 | 2019-06-05 | 2019-06-05 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 394520 | Work Order Description - 394520 - PM | PM | 4 | 128236 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-06 | 2019-06-29 | 2019-06-29 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 394522 | Work Order Description - 394522 - PM | PM | 3 | 20477 | SCHD | EQUIP-ISOL | 2019-02-08 | 2019-07-06 | 2019-06-05 | 2019-06-05 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 394524 | Work Order Description - 394524 - PM | PM | 3 | 482752 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-06 | 2019-06-05 | 2019-06-05 | 2 | MAINTENANCE | MECHANICAL | 4.25
2019-03-31 | 394526 | Work Order Description - 394526 - PM | PM | 4 | 460846 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-06 | 2019-06-05 | 2019-06-05 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 394710 | Work Order Description - 394710 - CM | CM | 3 | 411321 | WPLAN | TPS | 2019-02-11 | 2021-02-04 | 2020-02-04 | 2020-02-04 | 4 | INTEGRITY | FABRIC | 168
2019-03-31 | 394720 | Work Order Description - 394720 - CM | CM | 3 | 247357 | WPLAN | NORM-OPS | 2019-02-10 | 2020-02-05 | 2019-08-06 | 2019-08-06 | 3 | INTEGRITY | FABRIC | 16
2019-03-31 | 394765 | Work Order Description - 394765 - PRJ | PRJ | 4 | 481714 | SCHD | NORM-OPS | 2019-03-29 | 2021-02-03 | 2020-12-22 | 2020-12-22 | 4 | ENGINEERING | SERVICES | 1764
2019-03-31 | 394776 | Work Order Description - 394776 - CM | CM | 3 | 408273 | WPLAN | EQUIP-ISOL | 2019-02-07 | 2019-08-09 | 2019-05-09 | 2019-05-09 | 3 | INTEGRITY | CONSTRUCTION | 184
2019-03-31 | 394777 | Work Order Description - 394777 - PM | PM | 4 | 440934 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-06 | 2019-05-20 | 2019-05-20 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 394779 | Work Order Description - 394779 - PM | PM | 4 | 100270 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-19 | 2019-04-25 | 2019-04-25 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 394781 | Work Order Description - 394781 - PM | PM | 4 | 441093 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-19 | 2019-04-25 | 2019-04-25 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 394783 | Work Order Description - 394783 - PM | PM | 4 | 78626 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-28 | 2019-06-03 | 2019-06-03 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 394785 | Work Order Description - 394785 - PM | PM | 2 | 113097 | WPLAN | PACK-ISOL | 2019-02-05 | 2020-04-21 | 2019-04-26 | 2019-04-26 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 394787 | Work Order Description - 394787 - PM | PM | 4 | 78626 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-20 | 2019-06-03 | 2019-06-04 | 2 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 394789 | Work Order Description - 394789 - PSPM | PSPM | 1 | 266641 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-04 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 394791 | Work Order Description - 394791 - PSPM | PSPM | 1 | 238048 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-29 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 394793 | Work Order Description - 394793 - PSPM | PSPM | 1 | 238048 | SCHD | NORM-OPS | 2019-02-13 | 2019-06-28 | 2019-05-28 | 2019-05-28 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 394795 | Work Order Description - 394795 - PM | PM | 4 | 97748 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-18 | 2019-05-24 | 2019-05-24 | 2 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 394799 | Work Order Description - 394799 - PM | PM | 4 | 80108 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-18 | 2019-05-24 | 2019-05-24 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 394801 | Work Order Description - 394801 - PM | PM | 4 | 441275 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-09-10 | 2019-05-24 | 2019-05-24 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 394803 | Work Order Description - 394803 - PM | PM | 4 | 383314 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-09-10 | 2019-05-24 | 2019-05-24 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 394805 | Work Order Description - 394805 - PM | PM | 4 | 383343 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-09-10 | 2019-05-24 | 2019-05-24 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 394807 | Work Order Description - 394807 - PM | PM | 4 | 441276 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-09-10 | 2019-05-24 | 2019-05-24 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 394809 | Work Order Description - 394809 - PM | PM | 4 | 78619 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-09-10 | 2019-05-24 | 2019-05-24 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 394811 | Work Order Description - 394811 - PM | PM | 4 | 125622 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 394813 | Work Order Description - 394813 - PM | PM | 4 | 110872 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-28 | 2019-06-03 | 2019-06-03 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 394815 | Work Order Description - 394815 - PM | PM | 4 | 110873 | SCHD | PACK-ISOL | 2019-02-13 | 2019-05-12 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 394817 | Work Order Description - 394817 - PM | PM | 4 | 375789 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 394819 | Work Order Description - 394819 - PM | PM | 4 | 375789 | WPLAN | PACK-ISOL | 2019-02-05 | 2019-09-02 | 2019-06-03 | 2019-06-06 | 4 | MAINTENANCE | MECHANICAL | 72
2019-03-31 | 394821 | Work Order Description - 394821 - PM | PM | 4 | 383313 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-09-10 | 2019-05-24 | 2019-05-24 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 394825 | Work Order Description - 394825 - PM | PM | 4 | 111048 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-19 | 2019-04-25 | 2019-04-25 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 394827 | Work Order Description - 394827 - PM | PM | 4 | 126108 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-18 | 2019-05-24 | 2019-05-24 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 394831 | Work Order Description - 394831 - PSPM | PSPM | 1 | 670511 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-18 | 2019-04-18 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 394834 | Work Order Description - 394834 - PSPM | PSPM | 1 | 375789 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-04 | 2019-06-03 | 2019-06-05 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 394841 | Work Order Description - 394841 - PSPM | PSPM | 1 | 670511 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-18 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 394843 | Work Order Description - 394843 - PSPM | PSPM | 1 | 375789 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 394850 | Work Order Description - 394850 - PM | PM | 4 | 375789 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-04 | 2019-06-03 | 2019-06-15 | 1 | MAINTENANCE | MECHANICAL | 185
2019-03-31 | 394852 | Work Order Description - 394852 - PM | PM | 4 | 110847 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-04 | 2019-06-03 | 2019-06-04 | 1 | MAINTENANCE | ELECTRICAL | 13
2019-03-31 | 394854 | Work Order Description - 394854 - PSPM | PSPM | 1 | 670511 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-18 | 2019-04-19 | 2019-04-19 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 394856 | Work Order Description - 394856 - PM | PM | 4 | 670509 | SCHD | PACK-ISOL | 2019-02-13 | 2019-04-18 | 2019-05-18 | 2019-05-19 | 1 | MAINTENANCE | ELECTRICAL | 13
2019-03-31 | 394858 | Work Order Description - 394858 - PM | PM | 4 | 80463 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-11-03 | 2019-05-24 | 2019-05-24 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 394864 | Work Order Description - 394864 - PM | PM | 4 | 111006 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-18 | 2019-04-24 | 2019-04-24 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 394866 | Work Order Description - 394866 - PM | PM | 4 | 670574 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-18 | 2019-04-24 | 2019-04-24 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 394868 | Work Order Description - 394868 - PM | PM | 4 | 80406 | SCHD | PACK-ISOL | 2019-02-13 | 2019-06-19 | 2019-04-25 | 2019-04-25 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 394872 | Work Order Description - 394872 - PM | PM | 4 | 441374 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-20 | 2019-06-03 | 2019-06-03 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 394888 | Work Order Description - 394888 - PM | PM | 4 | 100429 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-20 | 2019-06-03 | 2019-06-03 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 394890 | Work Order Description - 394890 - PM | PM | 4 | 441087 | SCHD | PACK-ISOL | 2019-02-13 | 2019-08-12 | 2019-04-25 | 2019-04-25 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 394892 | Work Order Description - 394892 - PM | PM | 4 | 664282 | SCHD | PACK-ISOL | 2019-03-22 | 2020-05-15 | 2019-05-20 | 2019-05-20 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 394894 | Work Order Description - 394894 - PM | PM | 2 | 383066 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-14 | 2019-05-20 | 2019-05-29 | 2 | MAINTENANCE | MECHANICAL | 80
2019-03-31 | 394898 | Work Order Description - 394898 - BR | BR | 3 | 308426 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2020-02-05 | 2019-08-06 | 2019-08-06 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 394915 | Work Order Description - 394915 - PSPM | PSPM | 1 | 697911 | SCHD | NORM-OPS | 2019-03-26 | 2019-07-16 | 2019-03-30 | 2019-04-12 | 1 | INTEGRITY | INSPECTION | 217.5
2019-03-31 | 394917 | Work Order Description - 394917 - PSPM | PSPM | 2 | 204613 | SCHD | NORM-OPS | 2019-03-13 | 2019-11-19 | 2019-04-06 | 2019-04-14 | 1 | INTEGRITY | INSPECTION | 16.5
2019-03-31 | 394919 | Work Order Description - 394919 - CM | CM | 4 | 375761 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-05-01 | 2019-04-14 | 2019-04-14 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 394921 | Work Order Description - 394921 - PRJ | PRJ | 4 | 294960 | WPLAN | EQUIP-ISOL | 2019-02-08 | 2019-08-07 | 2019-04-06 | 2019-04-10 | 3 | ENGINEERING | INSTRUMENTS | 39
2019-03-31 | 394927 | Work Order Description - 394927 - CM | CM | 1 | 308382 | WPLAN | NORM-OPS | 2019-02-09 | 2020-02-05 | 2019-08-06 | 2019-08-06 | 3 | MAINTENANCE | ELECTRICAL | 520
2019-03-31 | 394944 | Work Order Description - 394944 - CM | CM | 4 | 204611 | WPLAN | NORM-OPS | 2019-02-08 | 2020-02-05 | 2019-08-06 | 2019-08-06 | 3 | INTEGRITY | SERVICES | 56
2019-03-31 | 394973 | Work Order Description - 394973 - CM | CM | 3 | 668445 | WPLAN | TPS | 2019-02-26 | 2021-02-03 | 2019-07-14 | 2019-07-15 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 394977 | Work Order Description - 394977 - PM | PM | 4 | 354350 | WSCHD | NORM-OPS | 2019-02-06 | 2019-07-07 | 2019-06-06 | 2019-06-06 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 394979 | Work Order Description - 394979 - PM | PM | 4 | 660951 | WSCHD | NORM-OPS | 2019-02-06 | 2019-07-07 | 2019-06-06 | 2019-06-06 | 3 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 394983 | Work Order Description - 394983 - PM | PM | 4 | 294918 | WSCHD | NORM-OPS | 2019-02-20 | 2019-07-07 | 2019-06-06 | 2019-06-06 | 2 | MAINTENANCE | MECHANICAL | 10.5
2019-03-31 | 394985 | Work Order Description - 394985 - PM | PM | 4 | 584012 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-07 | 2019-06-06 | 2019-06-06 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 394987 | Work Order Description - 394987 - PM | PM | 4 | 501789 | SCHD | PACK-ISOL | 2019-02-08 | 2019-09-23 | 2019-06-06 | 2019-06-06 | 2 | MAINTENANCE | INSTRUMENTS | 84
2019-03-31 | 394989 | Work Order Description - 394989 - PM | PM | 2 | 312683 | SCHD | PACK-ISOL | 2019-02-08 | 2019-07-07 | 2019-06-06 | 2019-06-06 | 2 | MAINTENANCE | MECHANICAL | 40
2019-03-31 | 394995 | Work Order Description - 394995 - PSPM | PSPM | 1 | 176749 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-07 | 2019-06-06 | 2019-06-06 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 394997 | Work Order Description - 394997 - PSPM | PSPM | 1 | 462782 | SCHD | PACK-ISOL | 2019-02-08 | 2019-07-07 | 2019-06-06 | 2019-06-06 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 394999 | Work Order Description - 394999 - PM | PM | 2 | 312683 | SCHD | PACK-ISOL | 2019-02-08 | 2019-07-07 | 2019-06-06 | 2019-06-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395001 | Work Order Description - 395001 - PSPM | PSPM | 1 | 123510 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-07 | 2019-06-06 | 2019-06-06 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 395037 | Work Order Description - 395037 - PM | PM | 4 | 383143 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-31 | 2019-06-06 | 2019-06-06 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 395039 | Work Order Description - 395039 - PM | PM | 4 | 383119 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-31 | 2019-06-06 | 2019-06-06 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 395041 | Work Order Description - 395041 - PM | PM | 4 | 383143 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-31 | 2019-06-06 | 2019-06-06 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 395043 | Work Order Description - 395043 - PSPM | PSPM | 1 | 42961 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-07 | 2019-06-06 | 2019-06-06 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 395045 | Work Order Description - 395045 - PSPM | PSPM | 4 | 99232 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-07 | 2019-06-06 | 2019-06-07 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 395049 | Work Order Description - 395049 - PSPM | PSPM | 1 | 126920 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-07 | 2019-06-06 | 2019-06-06 | 1 | MAINTENANCE | ELECTRICAL | 1.5
2019-03-31 | 395051 | Work Order Description - 395051 - PSPM | PSPM | 1 | 659338 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-07 | 2019-06-06 | 2019-06-06 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 395053 | Work Order Description - 395053 - PSPM | PSPM | 1 | 659338 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-07 | 2019-06-06 | 2019-06-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395055 | Work Order Description - 395055 - PSPM | PSPM | 1 | 659338 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-07 | 2019-06-06 | 2019-06-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395057 | Work Order Description - 395057 - PSPM | PSPM | 1 | 659338 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-07 | 2019-06-06 | 2019-06-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395059 | Work Order Description - 395059 - PSPM | PSPM | 1 | 659338 | SCHD | PACK-ISOL | 2019-02-13 | 2019-07-07 | 2019-06-06 | 2019-06-06 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395062 | Work Order Description - 395062 - PM | PM | 4 | 126984 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-07 | 2019-06-06 | 2019-06-06 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 395070 | Work Order Description - 395070 - PM | PM | 4 | 78550 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-23 | 2019-06-06 | 2019-06-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395072 | Work Order Description - 395072 - PM | PM | 4 | 100210 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-23 | 2019-06-06 | 2019-06-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395074 | Work Order Description - 395074 - PM | PM | 4 | 383118 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-23 | 2019-06-06 | 2019-06-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395076 | Work Order Description - 395076 - PM | PM | 4 | 383117 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-23 | 2019-06-06 | 2019-06-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395078 | Work Order Description - 395078 - PM | PM | 4 | 383116 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-23 | 2019-06-06 | 2019-06-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395080 | Work Order Description - 395080 - PM | PM | 4 | 78551 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-23 | 2019-06-06 | 2019-06-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 395082 | Work Order Description - 395082 - PM | PM | 4 | 440927 | SCHD | PACK-ISOL | 2019-02-13 | 2019-09-23 | 2019-06-06 | 2019-06-06 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 395084 | Work Order Description - 395084 - PM | PM | 4 | 436496 | SCHD | PACK-ISOL | 2019-03-22 | 2020-06-01 | 2019-06-06 | 2019-06-06 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 395086 | Work Order Description - 395086 - PM | PM | 4 | 436471 | SCHD | PACK-ISOL | 2019-03-22 | 2020-06-01 | 2019-06-06 | 2019-06-06 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 395088 | Work Order Description - 395088 - PM | PM | 4 | 664280 | SCHD | PACK-ISOL | 2019-03-22 | 2020-06-01 | 2019-06-06 | 2019-06-06 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 395090 | Work Order Description - 395090 - PM | PM | 2 | 670212 | WPLAN | PACK-ISOL | 2019-02-06 | 2019-07-31 | 2019-04-27 | 2019-05-06 | 2 | MAINTENANCE | MECHANICAL | 140
2019-03-31 | 395231 | Work Order Description - 395231 - CM | CM | 4 | 402269 | WPLAN | PACK-ISOL | 2019-02-08 | 2021-02-04 | 2020-02-05 | 2020-02-05 | 4 | INTEGRITY | CONSTRUCTION | 7
2019-03-31 | 395237 | Work Order Description - 395237 - CM | CM | 3 | 531818 | SCHD | EQUIP-ISOL | 2019-03-22 | 2019-05-02 | 2019-03-30 | 2019-04-11 | 2 | INTEGRITY | CONSTRUCTION | 136
2019-03-31 | 395248 | Work Order Description - 395248 - CM | CM | 2 | 246646 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2020-02-06 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 395251 | Work Order Description - 395251 - CM | CM | 1 | 80471 | SCHD | NORM-OPS | 2019-02-13 | 2019-05-02 | 2019-03-31 | 2019-03-31 | 2 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 395254 | Work Order Description - 395254 - CM | CM | 2 | 655443 | SCHD | NORM-OPS | 2019-02-13 | 2020-02-07 | 2019-09-08 | 2019-09-08 | 3 | INTEGRITY | MECHANICAL | 2
2019-03-31 | 395255 | Work Order Description - 395255 - CM | CM | 3 | 186264 | SCHD | NORM-OPS | 2019-02-13 | 2019-08-09 | 2019-04-28 | 2019-04-28 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 395259 | Work Order Description - 395259 - BR | BR | 4 | 495700 | SCHD | EQUIP-ISOL | 2019-02-08 | 2021-02-04 | 2020-02-05 | 2020-02-05 | 4 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 395269 | Work Order Description - 395269 - BR | BR | 4 | 128814 | SCHD | TPS | 2019-03-06 | 2021-02-04 | 2019-07-14 | 2019-07-15 | 4 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 395272 | Work Order Description - 395272 - CM | CM | 1 | 677286 | WSCHD | NORM-OPS | 2019-02-07 | 2020-02-06 | 2019-08-07 | 2019-08-07 | 3 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 395280 | Work Order Description - 395280 - PRJ | PRJ | 1 | 74551 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2020-02-06 |  |  | 3 | ENGINEERING | ELECTRICAL | 0
2019-03-31 | 395293 | Work Order Description - 395293 - CM | CM | 1 | 378845 | SCHD | TPS | 2019-03-06 | 2019-08-08 | 2019-07-13 | 2019-07-15 | 3 | INTEGRITY | INSPECTION | 63
2019-03-31 | 395294 | Work Order Description - 395294 - CM | CM | 1 | 378844 | SCHD | NORM-OPS | 2019-02-13 | 2019-08-08 | 2019-05-08 | 2019-05-15 | 3 | INTEGRITY | CONSTRUCTION | 196
2019-03-31 | 395311 | Work Order Description - 395311 - PSPM | PSPM | 1 | 33419 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 395313 | Work Order Description - 395313 - PSPM | PSPM | 1 | 33419 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 395315 | Work Order Description - 395315 - PSPM | PSPM | 1 | 33416 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 395317 | Work Order Description - 395317 - PSPM | PSPM | 1 | 33416 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 395319 | Work Order Description - 395319 - PSPM | PSPM | 1 | 18766 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 395321 | Work Order Description - 395321 - PSPM | PSPM | 1 | 520415 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 395323 | Work Order Description - 395323 - PM | PM | 4 | 33427 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-09-21 | 2019-06-04 | 2019-06-04 | 3 | MAINTENANCE | MECHANICAL | 112
2019-03-31 | 395325 | Work Order Description - 395325 - PM | PM | 2 | 51659 | WPLAN | PACK-ISOL | 2019-02-06 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 395327 | Work Order Description - 395327 - PSPM | PSPM | 1 | 293228 | WPLAN | PACK-ISOL | 2019-02-06 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 35
2019-03-31 | 395329 | Work Order Description - 395329 - PSPM | PSPM | 1 | 293228 | WPLAN | PACK-ISOL | 2019-02-06 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 33
2019-03-31 | 395332 | Work Order Description - 395332 - PSPM | PSPM | 1 | 293228 | WPLAN | PACK-ISOL | 2019-02-06 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 395334 | Work Order Description - 395334 - PSPM | PSPM | 1 | 293228 | WPLAN | PACK-ISOL | 2019-02-06 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 25
2019-03-31 | 395340 | Work Order Description - 395340 - PSPM | PSPM | 1 | 293228 | WPLAN | PACK-ISOL | 2019-02-06 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 395342 | Work Order Description - 395342 - PSPM | PSPM | 1 | 51659 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395344 | Work Order Description - 395344 - PSPM | PSPM | 1 | 51659 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395346 | Work Order Description - 395346 - PSPM | PSPM | 1 | 249527 | WPLAN | PACK-ISOL | 2019-02-06 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 395348 | Work Order Description - 395348 - PSPM | PSPM | 1 | 249527 | WPLAN | PACK-ISOL | 2019-02-06 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 395351 | Work Order Description - 395351 - PM | PM | 2 | 33427 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-29 | 2019-06-04 | 2019-06-04 | 2 | MAINTENANCE | INSTRUMENTS | 35
2019-03-31 | 395353 | Work Order Description - 395353 - PM | PM | 2 | 33427 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-29 | 2019-06-04 | 2019-06-04 | 2 | MAINTENANCE | MECHANICAL | 199
2019-03-31 | 395361 | Work Order Description - 395361 - PSPM | PSPM | 1 | 57410 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395363 | Work Order Description - 395363 - PM | PM | 3 | 53172 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-09-18 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395365 | Work Order Description - 395365 - PSPM | PSPM | 1 | 262304 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395367 | Work Order Description - 395367 - PSPM | PSPM | 1 | 409593 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395369 | Work Order Description - 395369 - PSPM | PSPM | 1 | 53171 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395371 | Work Order Description - 395371 - PSPM | PSPM | 1 | 360510 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395373 | Work Order Description - 395373 - PSPM | PSPM | 1 | 54466 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395375 | Work Order Description - 395375 - PSPM | PSPM | 1 | 360511 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395377 | Work Order Description - 395377 - PSPM | PSPM | 1 | 409594 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395379 | Work Order Description - 395379 - PSPM | PSPM | 1 | 54469 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395381 | Work Order Description - 395381 - PSPM | PSPM | 1 | 409595 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395383 | Work Order Description - 395383 - PSPM | PSPM | 1 | 410050 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 395385 | Work Order Description - 395385 - PSPM | PSPM | 1 | 357390 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 395387 | Work Order Description - 395387 - PSPM | PSPM | 1 | 53405 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395389 | Work Order Description - 395389 - PSPM | PSPM | 1 | 360611 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395391 | Work Order Description - 395391 - PSPM | PSPM | 1 | 54683 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395393 | Work Order Description - 395393 - PSPM | PSPM | 1 | 357460 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 395395 | Work Order Description - 395395 - PSPM | PSPM | 1 | 410256 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 395397 | Work Order Description - 395397 - PSPM | PSPM | 1 | 410255 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 395399 | Work Order Description - 395399 - PSPM | PSPM | 1 | 53718 | WSCHD | EQUIP-ISOL | 2019-02-06 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 395401 | Work Order Description - 395401 - PM | PM | 4 | 137808 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 395403 | Work Order Description - 395403 - PM | PM | 2 | 33427 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-29 | 2019-06-04 | 2019-06-04 | 2 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 395407 | Work Order Description - 395407 - PM | PM | 2 | 33427 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-29 | 2019-06-04 | 2019-06-04 | 2 | MAINTENANCE | INSTRUMENTS | 69
2019-03-31 | 395409 | Work Order Description - 395409 - PM | PM | 4 | 54774 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 395412 | Work Order Description - 395412 - PM | PM | 4 | 545348 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 395414 | Work Order Description - 395414 - PM | PM | 2 | 293228 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 395416 | Work Order Description - 395416 - PM | PM | 4 | 653698 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-11-14 | 2019-06-04 | 2019-06-04 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 395418 | Work Order Description - 395418 - PM | PM | 2 | 33427 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-09-21 | 2019-06-04 | 2019-06-04 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 395420 | Work Order Description - 395420 - PM | PM | 2 | 33427 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 395424 | Work Order Description - 395424 - PM | PM | 3 | 54226 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 395426 | Work Order Description - 395426 - PSPM | PSPM | 1 | 54102 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 395428 | Work Order Description - 395428 - PSPM | PSPM | 1 | 653302 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 395430 | Work Order Description - 395430 - PSPM | PSPM | 1 | 357611 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 395432 | Work Order Description - 395432 - PSPM | PSPM | 1 | 653307 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 395434 | Work Order Description - 395434 - PSPM | PSPM | 1 | 399425 | WSCHD | SUBSYS-ISOL | 2019-02-20 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 395436 | Work Order Description - 395436 - PSPM | PSPM | 1 | 357587 | WSCHD | SUBSYS-ISOL | 2019-02-20 | 2019-07-05 | 2019-06-04 | 2019-06-04 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 395438 | Work Order Description - 395438 - PSPM | PSPM | 1 | 357655 | WSCHD | SUBSYS-ISOL | 2019-02-20 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 395440 | Work Order Description - 395440 - PSPM | PSPM | 1 | 656143 | WSCHD | SUBSYS-ISOL | 2019-02-20 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 395442 | Work Order Description - 395442 - PSPM | PSPM | 1 | 399701 | WSCHD | SUBSYS-ISOL | 2019-02-20 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 395444 | Work Order Description - 395444 - PSPM | PSPM | 1 | 357657 | WSCHD | SUBSYS-ISOL | 2019-02-20 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 395446 | Work Order Description - 395446 - PSPM | PSPM | 1 | 357656 | WSCHD | SUBSYS-ISOL | 2019-02-20 | 2019-07-03 | 2019-06-02 | 2019-06-02 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 395460 | Work Order Description - 395460 - CM | CM | 1 | 378847 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-08 | 2019-05-08 | 2019-05-11 | 3 | INTEGRITY | INSPECTION | 63
2019-03-31 | 395493 | Work Order Description - 395493 - CM | CM | 4 | 472797 | WPLAN | NORM-OPS | 2019-02-08 | 2020-02-06 | 2019-08-08 | 2019-08-22 | 3 | INTEGRITY | FABRIC | 100
2019-03-31 | 395515 | Work Order Description - 395515 - PSCM | PSCM | 1 | 353093 | WSCHD | EQUIP-ISOL | 2019-02-10 | 2021-02-04 | 2020-02-05 | 2020-02-05 | 4 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 395519 | Work Order Description - 395519 - PSCM | PSCM | 1 | 325850 | WSCHD | EQUIP-ISOL | 2019-02-10 | 2021-02-04 | 2020-02-05 | 2020-02-05 | 4 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 395526 | Work Order Description - 395526 - CM | CM | 3 | 262343 | WPLAN | EQUIP-ISOL | 2019-02-09 | 2020-02-06 | 2019-08-07 | 2019-08-07 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 395527 | Work Order Description - 395527 - CM | CM | 3 | 410879 | WRISKQ | EQUIP-ISOL | 2019-02-10 | 2020-02-06 |  |  | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 395528 | Work Order Description - 395528 - CM | CM | 1 | 471324 | WPLAN | EQUIP-ISOL | 2019-02-09 | 2020-02-06 | 2019-08-08 | 2019-08-08 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 395529 | Work Order Description - 395529 - CM | CM | 1 | 418083 | WPLAN | EQUIP-ISOL | 2019-02-10 | 2020-02-06 | 2019-08-08 | 2019-08-08 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 395530 | Work Order Description - 395530 - CM | CM | 1 | 658026 | WPLAN | EQUIP-ISOL | 2019-02-10 | 2021-02-04 | 2020-02-06 | 2020-02-07 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 395595 | Work Order Description - 395595 - PM | PM | 4 | 51202 | WSCHD | NORM-OPS | 2019-02-07 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395597 | Work Order Description - 395597 - PSPM | PSPM | 1 | 137445 | WPLAN | PACK-ISOL | 2019-02-07 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 395600 | Work Order Description - 395600 - PSPM | PSPM | 1 | 580769 | WSCHD | NORM-OPS | 2019-02-07 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 395602 | Work Order Description - 395602 - PM | PM | 4 | 246173 | WSCHD | NORM-OPS | 2019-02-07 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 1 | INTEGRITY | SERVICES | 2
2019-03-31 | 395604 | Work Order Description - 395604 - PM | PM | 4 | 546030 | WSCHD | NORM-OPS | 2019-02-07 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 395606 | Work Order Description - 395606 - PM | PM | 4 | 652482 | WSCHD | NORM-OPS | 2019-02-07 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 1 | INTEGRITY | SERVICES | 2
2019-03-31 | 395608 | Work Order Description - 395608 - PSPM | PSPM | 1 | 675037 | WSCHD | NORM-OPS | 2019-02-07 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 395610 | Work Order Description - 395610 - PSPM | PSPM | 1 | 671829 | WSCHD | NORM-OPS | 2019-02-07 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 395612 | Work Order Description - 395612 - PSPM | PSPM | 1 | 59336 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 395616 | Work Order Description - 395616 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 395618 | Work Order Description - 395618 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 395620 | Work Order Description - 395620 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 395622 | Work Order Description - 395622 - PSPM | PSPM | 1 | 255832 | SCHD | EQUIP-ISOL | 2019-02-08 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 1 | MAINTENANCE | ELECTRICAL | 18
2019-03-31 | 395628 | Work Order Description - 395628 - PM | PM | 4 | 266392 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-08-01 | 2019-06-07 | 2019-06-07 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 395632 | Work Order Description - 395632 - PM | PM | 4 | 124376 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-08-01 | 2019-06-07 | 2019-06-07 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 395636 | Work Order Description - 395636 - PSPM | PSPM | 1 | 663164 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 395638 | Work Order Description - 395638 - PM | PM | 4 | 383312 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395640 | Work Order Description - 395640 - PM | PM | 4 | 78604 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395642 | Work Order Description - 395642 - PM | PM | 4 | 441277 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-09-24 | 2019-06-07 | 2019-06-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395644 | Work Order Description - 395644 - PM | PM | 4 | 100407 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-09-24 | 2019-06-07 | 2019-06-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395646 | Work Order Description - 395646 - PM | PM | 4 | 78608 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-08-01 | 2019-06-07 | 2019-06-07 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 395648 | Work Order Description - 395648 - PM | PM | 4 | 441328 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-08-01 | 2019-06-07 | 2019-06-07 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 395650 | Work Order Description - 395650 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 395655 | Work Order Description - 395655 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-08 | 2019-06-07 | 2019-06-07 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 395663 | Work Order Description - 395663 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-08 | 2019-06-07 | 2019-06-09 | 3 | MAINTENANCE | MEDIC | 21
2019-03-31 | 395665 | Work Order Description - 395665 - PM | PM | 4 | 377244 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-08-01 | 2019-06-07 | 2019-06-07 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 395737 | Work Order Description - 395737 - BR | BR | 3 | 245873 | WPLAN | PACK-ISOL | 2019-02-09 | 2021-02-05 | 2020-02-06 | 2020-02-06 | 4 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 395770 | Work Order Description - 395770 - PM | PM | 4 | 451344 | SCHD | NORM-OPS | 2019-02-13 | 2019-03-19 | 2019-04-12 | 2019-04-12 | 2 | DRILLING | DRILLING | 240
2019-03-31 | 395774 | Work Order Description - 395774 - CM | CM | 1 | 501444 | SCHD | NORM-OPS | 2019-02-08 | 2019-08-09 | 2019-05-09 | 2019-05-09 | 3 | INTEGRITY | INSPECTION | 63
2019-03-31 | 395779 | Work Order Description - 395779 - BR | BR | 3 | 361602 | WPLAN | TPS | 2019-02-10 | 2019-08-09 | 2019-05-09 | 2019-05-09 | 3 | MAINTENANCE | MECHANICAL | 52
2019-03-31 | 395805 | Work Order Description - 395805 - PM | PM | 4 | 482732 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-20 | 2019-06-15 | 2019-06-15 | 2 | INTEGRITY | INSPECTION | 72
2019-03-31 | 395807 | Work Order Description - 395807 - PM | PM | 4 | 253297 | SCHD | NORM-OPS | 2019-02-08 | 2019-10-13 | 2019-06-15 | 2019-06-15 | 2 | INTEGRITY | INSPECTION | 72
2019-03-31 | 395809 | Work Order Description - 395809 - PM | PM | 4 | 253330 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-20 | 2019-06-15 | 2019-06-15 | 2 | INTEGRITY | INSPECTION | 72
2019-03-31 | 395811 | Work Order Description - 395811 - PSPM | PSPM | 1 | 481743 | SCHD | NORM-OPS | 2019-02-08 | 2019-10-09 | 2019-06-15 | 2019-06-15 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 395813 | Work Order Description - 395813 - PSPM | PSPM | 1 | 481744 | SCHD | NORM-OPS | 2019-02-08 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | INTEGRITY | INSPECTION | 225
2019-03-31 | 395815 | Work Order Description - 395815 - PSPM | PSPM | 1 | 403916 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-10 | 2019-06-09 | 2019-06-09 | 1 | INTEGRITY | INSPECTION | 474
2019-03-31 | 395817 | Work Order Description - 395817 - PSPM | PSPM | 1 | 403817 | SCHD | NORM-OPS | 2019-02-08 | 2019-09-19 | 2019-04-15 | 2019-04-15 | 1 | INTEGRITY | INSPECTION | 49
2019-03-31 | 395819 | Work Order Description - 395819 - PSPM | PSPM | 1 | 403916 | SCHD | NORM-OPS | 2019-02-08 | 2019-08-30 | 2019-07-30 | 2019-07-30 | 1 | INTEGRITY | INSPECTION | 474
2019-03-31 | 395821 | Work Order Description - 395821 - PSPM | PSPM | 1 | 479577 | SCHD | NORM-OPS | 2019-02-08 | 2019-11-21 | 2019-10-21 | 2019-10-21 | 1 | INTEGRITY | INSPECTION | 474
2019-03-31 | 395823 | Work Order Description - 395823 - PSPM | PSPM | 1 | 403916 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | INTEGRITY | INSPECTION | 105
2019-03-31 | 395825 | Work Order Description - 395825 - PSPM | PSPM | 1 | 403916 | SCHD | NORM-OPS | 2019-02-08 | 2019-09-22 | 2019-08-22 | 2019-08-22 | 1 | INTEGRITY | INSPECTION | 105
2019-03-31 | 395827 | Work Order Description - 395827 - PSPM | PSPM | 1 | 501448 | SCHD | NORM-OPS | 2019-02-08 | 2019-09-18 | 2019-08-18 | 2019-08-18 | 1 | INTEGRITY | INSPECTION | 294
2019-03-31 | 395829 | Work Order Description - 395829 - PSPM | PSPM | 1 | 584565 | SCHD | NORM-OPS | 2019-02-08 | 2019-09-21 | 2019-08-21 | 2019-08-21 | 1 | INTEGRITY | INSPECTION | 105
2019-03-31 | 395831 | Work Order Description - 395831 - PSPM | PSPM | 1 | 472796 | SCHD | NORM-OPS | 2019-02-08 | 2019-08-15 | 2019-06-15 | 2019-06-15 | 1 | INTEGRITY | INSPECTION | 474
2019-03-31 | 395833 | Work Order Description - 395833 - PSPM | PSPM | 1 | 584565 | SCHD | NORM-OPS | 2019-02-08 | 2019-09-21 | 2019-08-21 | 2019-08-21 | 1 | INTEGRITY | INSPECTION | 474
2019-03-31 | 395847 | Work Order Description - 395847 - BR | BR | 2 | 248468 | WPLAN | SYS-ISOL | 2019-02-08 | 2021-02-06 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 395867 | Work Order Description - 395867 - BR | BR | 2 | 248467 | WPLAN | SYS-ISOL | 2019-02-08 | 2021-02-06 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 395890 | Work Order Description - 395890 - BR | BR | 3 | 383738 | SCHD | NORM-OPS | 2019-02-13 | 2021-02-05 | 2019-03-17 | 2019-07-01 | 4 | MAINTENANCE | SERVICES | 2423
2019-03-31 | 395923 | Work Order Description - 395923 - PSPM | PSPM | 1 | 321203 | WSCHD | NORM-OPS | 2019-02-08 | 2019-07-09 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 395925 | Work Order Description - 395925 - PSPM | PSPM | 1 | 321218 | WSCHD | NORM-OPS | 2019-02-08 | 2019-07-09 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 395927 | Work Order Description - 395927 - PSPM | PSPM | 1 | 574963 | WSCHD | EQUIP-ISOL | 2019-02-08 | 2019-07-09 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | SERVICES | 4
2019-03-31 | 395929 | Work Order Description - 395929 - PM | PM | 4 | 294916 | WSCHD | NORM-OPS | 2019-02-08 | 2019-07-09 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 395931 | Work Order Description - 395931 - PM | PM | 4 | 403468 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-09 | 2019-06-08 | 2019-06-08 | 2 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 395933 | Work Order Description - 395933 - PSPM | PSPM | 1 | 320574 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-09 | 2019-06-08 | 2019-06-08 | 1 | OPERATIONS | OPERATIONS | 12
2019-03-31 | 395935 | Work Order Description - 395935 - PSPM | PSPM | 1 | 477563 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-09 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395937 | Work Order Description - 395937 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-09 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 395939 | Work Order Description - 395939 - PM | PM | 4 | 451898 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-09 | 2019-06-08 | 2019-06-08 | 1 | OPERATIONS | MEDIC | 13
2019-03-31 | 395943 | Work Order Description - 395943 - PM | PM | 4 | 448862 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-09 | 2019-06-08 | 2019-06-08 | 1 | OPERATIONS | MEDIC | 28
2019-03-31 | 395949 | Work Order Description - 395949 - PM | PM | 4 | 216158 | SCHD | NORM-OPS | 2019-02-08 | 2019-07-09 | 2019-06-08 | 2019-06-08 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 395957 | Work Order Description - 395957 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-09 | 2019-06-08 | 2019-06-08 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 395959 | Work Order Description - 395959 - PSPM | PSPM | 1 | 228343 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-09 | 2019-06-08 | 2019-06-09 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 395961 | Work Order Description - 395961 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-09 | 2019-06-08 | 2019-06-08 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 395963 | Work Order Description - 395963 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-09 | 2019-06-08 | 2019-06-08 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 396094 | Work Order Description - 396094 - CM | CM | 3 | 325570 | SCHD | EQUIP-ISOL | 2019-02-13 | 2021-02-06 | 2020-02-07 | 2020-02-07 | 4 | MAINTENANCE | MECHANICAL | 39
2019-03-31 | 396122 | Work Order Description - 396122 - PSPM | PSPM | 1 | 574963 | WSCHD | EQUIP-ISOL | 2019-02-08 | 2019-09-08 | 2019-08-08 | 2019-08-08 | 1 | MAINTENANCE | SERVICES | 4
2019-03-31 | 396134 | Work Order Description - 396134 - CM | CM | 2 | 262784 | WPLAN | NORM-OPS | 2019-03-06 | 2020-03-05 | 2020-03-04 | 2020-03-04 | 3 | INTEGRITY | CONSTRUCTION | 7
2019-03-31 | 396136 | Work Order Description - 396136 - BR | BR | 4 | 556432 | WPLAN | PACK-ISOL | 2019-03-02 | 2021-02-06 | 2020-12-25 | 2020-12-28 | 4 | MAINTENANCE | FABRIC | 24
2019-03-31 | 396166 | Work Order Description - 396166 - PSPM | PSPM | 1 | 136833 | SCHD | NORM-OPS | 2019-03-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 396168 | Work Order Description - 396168 - PSPM | PSPM | 1 | 136790 | SCHD | NORM-OPS | 2019-03-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 396170 | Work Order Description - 396170 - PSPM | PSPM | 1 | 315281 | SCHD | NORM-OPS | 2019-03-05 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 396172 | Work Order Description - 396172 - PSPM | PSPM | 1 | 407972 | SCHD | NORM-OPS | 2019-03-05 | 2019-05-02 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 396191 | Work Order Description - 396191 - CM | CM | 3 | 262409 | WPLAN | EQUIP-ISOL | 2019-02-11 | 2021-02-06 | 2019-05-18 | 2019-05-18 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 396202 | Work Order Description - 396202 - CM | CM | 2 | 29639 | WPLAN | EQUIP-ISOL | 2019-03-06 | 2020-03-05 | 2020-03-04 | 2020-03-04 | 3 | MAINTENANCE | CONSTRUCTION | 7
2019-03-31 | 396203 | Work Order Description - 396203 - CM | CM | 4 | 477531 | WPLAN | NORM-OPS | 2019-02-08 | 2021-02-06 | 2020-02-07 | 2020-02-07 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 396260 | Work Order Description - 396260 - CM | CM | 3 | 475467 | WMATL | EQUIP-ISOL | 2019-03-14 | 2019-05-04 | 2019-09-14 | 2019-09-14 | 2 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 396265 | Work Order Description - 396265 - BR | BR | 2 | 411264 | WSCHD | NORM-OPS | 2019-02-10 | 2021-02-08 | 2020-03-28 | 2020-03-28 | 4 | INTEGRITY | SERVICES | 18
2019-03-31 | 396276 | Work Order Description - 396276 - CM | CM | 3 | 265153 | WPLAN | EQUIP-ISOL | 2019-02-11 | 2019-08-10 | 2019-05-10 | 2019-05-10 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 396289 | Work Order Description - 396289 - PM | PM | 2 | 572308 | WSCHD | NORM-OPS | 2019-02-09 | 2019-07-10 | 2019-06-09 | 2019-06-09 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 396291 | Work Order Description - 396291 - PM | PM | 4 | 580762 | WSCHD | NORM-OPS | 2019-02-09 | 2019-07-10 | 2019-06-09 | 2019-06-09 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 396293 | Work Order Description - 396293 - PSPM | PSPM | 1 | 361803 | WSCHD | NORM-OPS | 2019-02-09 | 2019-07-10 | 2019-06-09 | 2019-06-09 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 396295 | Work Order Description - 396295 - PM | PM | 4 | 55960 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-10 | 2019-06-09 | 2019-06-09 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 396297 | Work Order Description - 396297 - PM | PM | 4 | 259883 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-10 | 2019-06-09 | 2019-06-09 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 396299 | Work Order Description - 396299 - PM | PM | 4 | 449365 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-10 | 2019-06-09 | 2019-06-09 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 396301 | Work Order Description - 396301 - PM | PM | 4 | 632580 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-10 | 2019-06-08 | 2019-06-08 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 396303 | Work Order Description - 396303 - PM | PM | 4 | 583919 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-10 | 2019-06-09 | 2019-06-09 | 3 | OPERATIONS | SAFETY | 4
2019-03-31 | 396305 | Work Order Description - 396305 - PM | PM | 4 | 122683 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-10 | 2019-06-08 | 2019-06-08 | 3 | OPERATIONS | SAFETY | 15
2019-03-31 | 396307 | Work Order Description - 396307 - PM | PM | 4 | 583934 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-10 | 2019-06-08 | 2019-06-08 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 396309 | Work Order Description - 396309 - PM | PM | 4 | 583934 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-10 | 2019-06-09 | 2019-06-09 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 396311 | Work Order Description - 396311 - PM | PM | 1 | 446516 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-10 | 2019-06-09 | 2019-06-09 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 396313 | Work Order Description - 396313 - PSPM | PSPM | 1 | 29041 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-10 | 2019-06-09 | 2019-06-09 | 1 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 396329 | Work Order Description - 396329 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-10 | 2019-06-09 | 2019-06-09 | 2 | MAINTENANCE | SAFETY | 7
2019-03-31 | 396331 | Work Order Description - 396331 - PM | PM | 4 | 74891 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-10 | 2019-06-09 | 2019-06-09 | 2 | OPERATIONS | OPERATIONS | 1
2019-03-31 | 396333 | Work Order Description - 396333 - PSPM | PSPM | 1 | 453251 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-10 | 2019-06-09 | 2019-06-10 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 396335 | Work Order Description - 396335 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-10 | 2019-06-09 | 2019-06-09 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 396337 | Work Order Description - 396337 - PSPM | PSPM | 1 | 669726 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-10 | 2019-06-09 | 2019-06-09 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 396339 | Work Order Description - 396339 - PSPM | PSPM | 1 | 528118 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-10 | 2019-06-09 | 2019-06-09 | 1 | INTEGRITY | SERVICES | 4
2019-03-31 | 396341 | Work Order Description - 396341 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-10 | 2019-06-09 | 2019-06-09 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 396490 | Work Order Description - 396490 - PRJ | PRJ | 4 | 228839 | SCHD | NORM-OPS | 2019-03-04 | 2021-02-07 | 2019-05-04 | 2019-05-10 | 4 | ENGINEERING | SERVICES | 1
2019-03-31 | 396494 | Work Order Description - 396494 - CM | CM | 4 | 401761 | WMATL | EQUIP-ISOL | 2019-03-14 | 2021-02-07 | 2020-02-08 | 2020-02-08 | 4 | MAINTENANCE | ELECTRICAL | 30
2019-03-31 | 396510 | Work Order Description - 396510 - PSPM | PSPM | 1 | 292677 | WSCHD | NORM-OPS | 2019-02-10 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 396512 | Work Order Description - 396512 - PSPM | PSPM | 1 | 457573 | WSCHD | NORM-OPS | 2019-02-10 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | OPERATIONS | SAFETY | 2
2019-03-31 | 396514 | Work Order Description - 396514 - PM | PM | 4 | 18317 | WSCHD | EQUIP-ISOL | 2019-02-10 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 396516 | Work Order Description - 396516 - PM | PM | 4 | 18316 | WSCHD | EQUIP-ISOL | 2019-02-10 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 396518 | Work Order Description - 396518 - PM | PM | 4 | 666316 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 396520 | Work Order Description - 396520 - PM | PM | 4 | 417521 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 396522 | Work Order Description - 396522 - PM | PM | 4 | 50099 | WSCHD | EQUIP-ISOL | 2019-02-10 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 396524 | Work Order Description - 396524 - PM | PM | 4 | 50098 | WSCHD | EQUIP-ISOL | 2019-02-10 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 396526 | Work Order Description - 396526 - PM | PM | 4 | 411571 | WSCHD | NORM-OPS | 2019-02-10 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 396528 | Work Order Description - 396528 - PM | PM | 4 | 358159 | WSCHD | NORM-OPS | 2019-02-10 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 396530 | Work Order Description - 396530 - PM | PM | 4 | 540667 | WSCHD | NORM-OPS | 2019-02-10 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 396532 | Work Order Description - 396532 - PM | PM | 4 | 678551 | WSCHD | NORM-OPS | 2019-02-10 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 396534 | Work Order Description - 396534 - PM | PM | 4 | 547429 | WSCHD | NORM-OPS | 2019-02-10 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 396536 | Work Order Description - 396536 - PSPM | PSPM | 1 | 470877 | WSCHD | NORM-OPS | 2019-02-10 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 396538 | Work Order Description - 396538 - PSPM | PSPM | 1 | 671828 | WSCHD | NORM-OPS | 2019-02-10 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 396540 | Work Order Description - 396540 - PSPM | PSPM | 1 | 547275 | WSCHD | NORM-OPS | 2019-02-10 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 396542 | Work Order Description - 396542 - PM | PM | 4 | 360243 | WSCHD | NORM-OPS | 2019-02-10 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 396544 | Work Order Description - 396544 - PSPM | PSPM | 1 | 309598 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 396546 | Work Order Description - 396546 - PSPM | PSPM | 1 | 189054 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 396548 | Work Order Description - 396548 - PSPM | PSPM | 1 | 325633 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 396550 | Work Order Description - 396550 - PSPM | PSPM | 1 | 81212 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | OPERATIONS | OPERATIONS | 1
2019-03-31 | 396552 | Work Order Description - 396552 - PM | PM | 4 | 568129 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-17 | 2019-06-10 | 2019-06-10 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 396554 | Work Order Description - 396554 - PM | PM | 4 | 631594 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 396556 | Work Order Description - 396556 - PM | PM | 4 | 499057 | SCHD | PACK-ISOL | 2019-02-13 | 2019-11-20 | 2019-06-10 | 2019-06-10 | 2 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 396560 | Work Order Description - 396560 - PM | PM | 4 | 499057 | SCHD | PACK-ISOL | 2019-02-13 | 2019-11-20 | 2019-06-10 | 2019-06-10 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 396562 | Work Order Description - 396562 - PM | PM | 3 | 462748 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 396564 | Work Order Description - 396564 - PM | PM | 3 | 462748 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 396566 | Work Order Description - 396566 - PM | PM | 3 | 462748 | SCHD | SYS-ISOL | 2019-02-13 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 396568 | Work Order Description - 396568 - PM | PM | 4 | 438720 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-09-27 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 396570 | Work Order Description - 396570 - PM | PM | 4 | 556260 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 396572 | Work Order Description - 396572 - PM | PM | 2 | 216011 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 396574 | Work Order Description - 396574 - PM | PM | 4 | 320026 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 396576 | Work Order Description - 396576 - PM | PM | 4 | 74216 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 396578 | Work Order Description - 396578 - PM | PM | 4 | 487367 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 396580 | Work Order Description - 396580 - PM | PM | 4 | 237629 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 396582 | Work Order Description - 396582 - PM | PM | 4 | 377675 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 396584 | Work Order Description - 396584 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 396586 | Work Order Description - 396586 - PSPM | PSPM | 1 | 450986 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-11 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 396740 | Work Order Description - 396740 - BR | BR | 3 | 493245 | WPLAN | EQUIP-ISOL | 2019-02-11 | 2020-02-10 | 2019-08-11 | 2019-08-11 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 396745 | Work Order Description - 396745 - CM | CM | 1 | 679711 | WPLAN | NORM-OPS | 2019-02-26 | 2021-02-24 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 396801 | Work Order Description - 396801 - PRJ | PRJ | 4 | 216028 | WPLAN | NORM-OPS | 2019-02-11 | 2020-02-11 | 2020-02-10 | 2020-02-10 | 3 | ENGINEERING | CONSTRUCTION | 1
2019-03-31 | 396813 | Work Order Description - 396813 - PM | PM | 4 | 481609 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-12 | 2019-06-11 | 2019-06-11 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 396815 | Work Order Description - 396815 - PM | PM | 4 | 476154 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-12 | 2019-06-11 | 2019-06-11 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 396817 | Work Order Description - 396817 - PSPM | PSPM | 1 | 477561 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-12 | 2019-06-11 | 2019-06-11 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 396819 | Work Order Description - 396819 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-12 | 2019-06-11 | 2019-06-11 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 396823 | Work Order Description - 396823 - PSPM | PSPM | 4 | 403503 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-12 | 2019-06-11 | 2019-06-11 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 396825 | Work Order Description - 396825 - PSPM | PSPM | 1 | 265552 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-12 | 2019-06-11 | 2019-06-11 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 396827 | Work Order Description - 396827 - PSPM | PSPM | 1 | 555584 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-12 | 2019-06-11 | 2019-06-11 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 396829 | Work Order Description - 396829 - PSPM | PSPM | 1 | 659056 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-12 | 2019-06-11 | 2019-06-11 | 1 | OPERATIONS | SAFETY | 6
2019-03-31 | 396831 | Work Order Description - 396831 - PSPM | PSPM | 1 | 392215 | SCHD | NORM-OPS | 2019-03-18 | 2019-07-12 | 2019-06-11 | 2019-06-11 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 396964 | Work Order Description - 396964 - BR | BR | 3 | 311475 | WPLAN | NORM-OPS | 2019-02-20 | 2021-02-09 | 2020-12-28 | 2020-12-28 | 4 | MAINTENANCE | CONSTRUCTION | 1
2019-03-31 | 396967 | Work Order Description - 396967 - CM | CM | 3 | 311475 | WPLAN | NORM-OPS | 2019-02-11 | 2019-05-07 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 396979 | Work Order Description - 396979 - PRJ | PRJ | 1 | 575064 | WSCHD | NORM-OPS | 2019-02-12 | 2019-08-13 | 2019-05-13 | 2019-05-13 | 3 | ENGINEERING | INSTRUMENTS | 304
2019-03-31 | 396992 | Work Order Description - 396992 - CM | CM | 3 | 376026 | SCHD | EQUIP-ISOL | 2019-03-06 | 2020-02-11 | 2019-04-21 | 2019-04-29 | 3 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 397021 | Work Order Description - 397021 - PRJ | PRJ | 4 | 294959 | WSCHD | NORM-OPS | 2019-02-12 | 2021-02-09 | 2020-02-10 | 2020-02-10 | 4 | ENGINEERING | INSTRUMENTS | 105
2019-03-31 | 397043 | Work Order Description - 397043 - PM | PM | 4 | 228839 | WPLAN | NORM-OPS | 2019-02-11 | 2019-09-05 | 2019-08-05 | 2019-08-05 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 397047 | Work Order Description - 397047 - PSPM | PSPM | 1 | 451342 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-09 | 2019-07-09 | 2019-07-31 | 2 | INTEGRITY | INSPECTION | 474
2019-03-31 | 397051 | Work Order Description - 397051 - PSPM | PSPM | 1 | 237449 | SCHD | NORM-OPS | 2019-03-18 | 2020-01-14 | 2019-05-25 | 2019-06-26 | 2 | INTEGRITY | INSPECTION | 675
2019-03-31 | 397053 | Work Order Description - 397053 - PSPM | PSPM | 1 | 237450 | SCHD | NORM-OPS | 2019-03-18 | 2019-09-20 | 2019-05-25 | 2019-06-26 | 2 | INTEGRITY | INSPECTION | 675
2019-03-31 | 397122 | Work Order Description - 397122 - CM | CM | 1 | 666948 | WSCHD | NORM-OPS | 2019-02-12 | 2020-02-11 | 2019-08-12 | 2019-08-12 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 397130 | Work Order Description - 397130 - CM | CM | 4 | 51163 | WSCHD | NORM-OPS | 2019-02-12 | 2021-02-09 | 2020-02-10 | 2020-02-10 | 4 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 397154 | Work Order Description - 397154 - BR | BR | 4 | 472585 | SCHD | EQUIP-ISOL | 2019-03-29 | 2021-02-09 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 397178 | Work Order Description - 397178 - CM | CM | 4 | 670454 | WMATL | EQUIP-ISOL | 2019-02-13 | 2020-02-11 | 2019-08-13 | 2019-08-14 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 397321 | Work Order Description - 397321 - CM | CM | 3 | 36417 | WPLAN | EQUIP-ISOL | 2019-02-23 | 2019-08-25 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 397326 | Work Order Description - 397326 - PRJ | PRJ | 4 | 499092 | WPLAN | SYS-ISOL | 2019-02-20 | 2021-02-09 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | CONSTRUCTION | 1711
2019-03-31 | 397332 | Work Order Description - 397332 - CM | CM | 1 | 355572 | WSCHD | NORM-OPS | 2019-02-12 | 2021-02-09 | 2020-02-10 | 2020-02-10 | 4 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 397333 | Work Order Description - 397333 - PSCM | PSCM | 1 | 457671 | WMATL | EQUIP-ISOL | 2019-03-06 | 2021-02-09 | 2020-02-10 | 2020-02-10 | 4 | MAINTENANCE | ELECTRICAL | 22
2019-03-31 | 397354 | Work Order Description - 397354 - PRJ | PRJ | 3 | 126954 | SCHD | NORM-OPS | 2019-02-22 | 2021-02-11 | 2019-03-17 | 2020-03-01 | 4 | ENGINEERING | SERVICES | 1734
2019-03-31 | 397367 | Work Order Description - 397367 - CM | CM | 4 | 450959 | WPLAN | NORM-OPS | 2019-02-26 | 2019-08-13 | 2019-05-13 | 2019-05-19 | 3 | MAINTENANCE | MECHANICAL | 40
2019-03-31 | 397368 | Work Order Description - 397368 - CM | CM | 4 | 361475 | WSCHD | NORM-OPS | 2019-02-12 | 2021-02-09 | 2020-02-10 | 2020-02-10 | 4 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 397384 | Work Order Description - 397384 - BR | BR | 3 | 51692 | WSCHD | EQUIP-ISOL | 2019-02-12 | 2020-02-11 | 2019-08-12 | 2019-08-12 | 3 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 397425 | Work Order Description - 397425 - CM | CM | 3 | 76977 | WMATL | SYS-ISOL | 2019-02-12 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 397443 | Work Order Description - 397443 - CM | CM | 4 | 570144 | WSCHD | NORM-OPS | 2019-02-12 | 2020-02-11 | 2019-08-12 | 2019-08-12 | 3 | INTEGRITY | CONSTRUCTION | 196
2019-03-31 | 397456 | Work Order Description - 397456 - CM | CM | 3 | 312718 | WPLAN | NORM-OPS | 2019-02-20 | 2020-02-11 | 2019-11-16 | 2019-11-17 | 3 | MAINTENANCE | FABRIC | 14
2019-03-31 | 397476 | Work Order Description - 397476 - PM | PM | 4 | 540691 | WSCHD | NORM-OPS | 2019-02-12 | 2019-07-13 | 2019-06-12 | 2019-06-12 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 397478 | Work Order Description - 397478 - PSPM | PSPM | 1 | 697891 | WSCHD | NORM-OPS | 2019-02-12 | 2019-07-13 | 2019-06-12 | 2019-06-12 | 1 | INTEGRITY | SERVICES | 4
2019-03-31 | 397480 | Work Order Description - 397480 - PM | PM | 4 | 481470 | WSCHD | NORM-OPS | 2019-02-12 | 2019-07-13 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 397482 | Work Order Description - 397482 - PSPM | PSPM | 1 | 675036 | WSCHD | NORM-OPS | 2019-02-12 | 2019-07-13 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 397484 | Work Order Description - 397484 - PSPM | PSPM | 1 | 519760 | WSCHD | NORM-OPS | 2019-02-12 | 2019-07-13 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 397486 | Work Order Description - 397486 - PSPM | PSPM | 1 | 59016 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-13 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | MECHANICAL | 33
2019-03-31 | 397494 | Work Order Description - 397494 - PSPM | PSPM | 1 | 477562 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-13 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 397496 | Work Order Description - 397496 - PM | PM | 4 | 460846 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-13 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 397502 | Work Order Description - 397502 - PSPM | PSPM | 1 | 528211 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-13 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 397504 | Work Order Description - 397504 - PSPM | PSPM | 1 | 659551 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-13 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 397506 | Work Order Description - 397506 - PSPM | PSPM | 1 | 441705 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-13 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 397508 | Work Order Description - 397508 - PSPM | PSPM | 1 | 227941 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-13 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 397510 | Work Order Description - 397510 - PM | PM | 4 | 450541 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-13 | 2019-06-12 | 2019-06-12 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 397584 | Work Order Description - 397584 - CM | CM | 1 | 309632 | WPLAN | EQUIP-ISOL | 2019-02-23 | 2020-02-12 | 2019-08-13 | 2019-08-13 | 3 | INTEGRITY | MECHANICAL | 11
2019-03-31 | 397589 | Work Order Description - 397589 - BR | BR | 3 | 650639 | WRISKQ | PACK-ISOL | 2019-02-12 | 2020-02-12 |  |  | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 397592 | Work Order Description - 397592 - BR | BR | 3 | 324333 | WSCHD | PACK-ISOL | 2019-02-12 | 2020-02-12 | 2019-08-13 | 2019-08-13 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 397600 | Work Order Description - 397600 - BR | BR | 1 | 50992 | WSCHD | NORM-OPS | 2019-02-12 | 2020-02-12 | 2019-08-13 | 2019-08-13 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 397621 | Work Order Description - 397621 - CM | CM | 1 | 659551 | WPLAN | PACK-ISOL | 2019-02-14 | 2020-02-12 | 2019-08-13 | 2019-08-15 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 397671 | Work Order Description - 397671 - CM | CM | 1 | 451342 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-14 | 2019-05-14 | 2019-05-20 | 3 | INTEGRITY | CONSTRUCTION | 94
2019-03-31 | 397675 | Work Order Description - 397675 - CM | CM | 1 | 451342 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-14 | 2019-05-14 | 2019-05-23 | 3 | INTEGRITY | CONSTRUCTION | 130
2019-03-31 | 397679 | Work Order Description - 397679 - CM | CM | 3 | 248468 | WPLAN | SYS-ISOL | 2019-03-01 | 2021-02-10 | 2020-12-29 | 2020-12-29 | 4 | MAINTENANCE | CONSTRUCTION | 14.5
2019-03-31 | 397685 | Work Order Description - 397685 - CM | CM | 1 | 528181 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-14 | 2019-05-14 | 2019-05-15 | 3 | INTEGRITY | CONSTRUCTION | 14
2019-03-31 | 397687 | Work Order Description - 397687 - CM | CM | 1 | 451342 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-14 | 2019-05-14 | 2019-05-19 | 3 | INTEGRITY | CONSTRUCTION | 70
2019-03-31 | 397694 | Work Order Description - 397694 - CM | CM | 4 | 528181 | SCHD | NORM-OPS | 2019-03-06 | 2020-02-12 | 2019-08-13 | 2019-08-20 | 3 | INTEGRITY | CONSTRUCTION | 166
2019-03-31 | 397695 | Work Order Description - 397695 - PM | PM | 2 | 215924 | SCHD | NORM-OPS | 2019-02-13 | 2019-04-05 | 2019-03-02 | 2019-03-02 | 3 | OPERATIONS | OPERATIONS | 9
2019-03-31 | 397702 | Work Order Description - 397702 - CM | CM | 4 | 528181 | SCHD | NORM-OPS | 2019-03-06 | 2020-02-12 | 2019-08-13 | 2019-08-15 | 3 | INTEGRITY | CONSTRUCTION | 28
2019-03-31 | 397709 | Work Order Description - 397709 - CM | CM | 4 | 528181 | SCHD | NORM-OPS | 2019-03-06 | 2020-02-12 | 2019-08-13 | 2019-08-31 | 3 | INTEGRITY | CONSTRUCTION | 364
2019-03-31 | 397714 | Work Order Description - 397714 - CM | CM | 4 | 528181 | WPLAN | NORM-OPS | 2019-02-14 | 2020-02-12 | 2019-08-13 | 2019-08-26 | 3 | INTEGRITY | ELECTRICAL | 322
2019-03-31 | 397715 | Work Order Description - 397715 - CM | CM | 1 | 353493 | WPLAN | NORM-OPS | 2019-02-25 | 2020-02-25 | 2020-02-24 | 2020-02-24 | 3 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 397724 | Work Order Description - 397724 - CM | CM | 1 | 451342 | SCHD | NORM-OPS | 2019-03-06 | 2020-02-12 | 2019-08-13 | 2019-08-17 | 3 | INTEGRITY | CONSTRUCTION | 72
2019-03-31 | 397725 | Work Order Description - 397725 - PRJ | PRJ | 4 | 450928 | SCHD | EQUIP-ISOL | 2019-03-06 | 2021-02-10 | 2019-03-09 | 2019-03-31 | 4 | ENGINEERING | ELECTRICAL | 1
2019-03-31 | 397729 | Work Order Description - 397729 - CM | CM | 1 | 451342 | SCHD | NORM-OPS | 2019-03-06 | 2020-02-12 | 2019-08-13 | 2019-08-20 | 3 | INTEGRITY | CONSTRUCTION | 150
2019-03-31 | 397733 | Work Order Description - 397733 - CM | CM | 4 | 567452 | WSCHD | EQUIP-ISOL | 2019-02-12 | 2021-02-10 |  |  | 4 | OPERATIONS | MECHANICAL | 0
2019-03-31 | 397737 | Work Order Description - 397737 - CM | CM | 4 | 184667 | WSCHD | EQUIP-ISOL | 2019-02-12 | 2021-02-10 |  |  | 4 | OPERATIONS | MECHANICAL | 0
2019-03-31 | 397740 | Work Order Description - 397740 - CM | CM | 4 | 528181 | SCHD | NORM-OPS | 2019-03-06 | 2020-02-12 | 2019-08-13 | 2019-08-14 | 3 | INTEGRITY | CONSTRUCTION | 14
2019-03-31 | 397743 | Work Order Description - 397743 - CM | CM | 4 | 528181 | SCHD | NORM-OPS | 2019-03-06 | 2020-02-12 | 2019-08-13 | 2019-08-21 | 3 | INTEGRITY | CONSTRUCTION | 140
2019-03-31 | 397753 | Work Order Description - 397753 - CM | CM | 1 | 451342 | SCHD | NORM-OPS | 2019-03-06 | 2020-02-12 | 2019-08-14 | 2019-08-25 | 3 | INTEGRITY | CONSTRUCTION | 160
2019-03-31 | 397756 | Work Order Description - 397756 - CM | CM | 1 | 451342 | SCHD | NORM-OPS | 2019-03-06 | 2020-02-12 | 2019-08-14 | 2019-08-17 | 3 | INTEGRITY | CONSTRUCTION | 56
2019-03-31 | 397780 | Work Order Description - 397780 - CM | CM | 1 | 451342 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-14 | 2019-05-15 | 2019-05-22 | 3 | INTEGRITY | CONSTRUCTION | 100
2019-03-31 | 397786 | Work Order Description - 397786 - CM | CM | 4 | 528181 | SCHD | NORM-OPS | 2019-03-06 | 2020-02-12 | 2019-08-14 | 2019-08-21 | 3 | INTEGRITY | CONSTRUCTION | 164
2019-03-31 | 397804 | Work Order Description - 397804 - BR | BR | 4 | 528181 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-14 | 2019-05-15 | 2019-05-16 | 3 | INTEGRITY | ELECTRICAL | 28
2019-03-31 | 397826 | Work Order Description - 397826 - PSPM | PSPM | 1 | 463456 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-09-06 | 2019-03-30 | 2019-03-30 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 397829 | Work Order Description - 397829 - CM | CM | 3 | 657331 | WPLAN | NORM-OPS | 2019-02-15 | 2021-02-11 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 397831 | Work Order Description - 397831 - PSPM | PSPM | 1 | 353371 | WSCHD | NORM-OPS | 2019-02-13 | 2019-07-14 | 2019-06-13 | 2019-06-13 | 1 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 397833 | Work Order Description - 397833 - PM | PM | 4 | 475799 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-14 | 2019-06-13 | 2019-06-13 | 2 | DRILLING | DRILLING | 4
2019-03-31 | 397835 | Work Order Description - 397835 - PM | PM | 4 | 475799 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-14 | 2019-06-13 | 2019-06-13 | 2 | DRILLING | DRILLING | 8
2019-03-31 | 397837 | Work Order Description - 397837 - PM | PM | 4 | 482054 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-14 | 2019-06-13 | 2019-06-13 | 2 | DRILLING | DRILLING | 4
2019-03-31 | 397839 | Work Order Description - 397839 - PM | PM | 4 | 482054 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-14 | 2019-06-13 | 2019-06-13 | 2 | DRILLING | DRILLING | 8
2019-03-31 | 397841 | Work Order Description - 397841 - PM | PM | 4 | 189029 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-20 | 2019-06-13 | 2019-06-13 | 3 | DRILLING | DRILLING | 4
2019-03-31 | 397843 | Work Order Description - 397843 - PM | PM | 4 | 310190 | SCHD | EQUIP-ISOL | 2019-02-13 | 2019-07-20 | 2019-06-13 | 2019-06-13 | 3 | DRILLING | DRILLING | 4
2019-03-31 | 397845 | Work Order Description - 397845 - PM | PM | 4 | 601923 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-14 | 2019-06-13 | 2019-06-13 | 2 | OPERATIONS | OPERATIONS | 60
2019-03-31 | 397857 | Work Order Description - 397857 - PSPM | PSPM | 1 | 123510 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-14 | 2019-06-13 | 2019-06-13 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 397863 | Work Order Description - 397863 - PSPM | PSPM | 1 | 42961 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-14 | 2019-06-13 | 2019-06-13 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 397865 | Work Order Description - 397865 - PSPM | PSPM | 4 | 99434 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-14 | 2019-06-13 | 2019-06-14 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 397867 | Work Order Description - 397867 - PSPM | PSPM | 1 | 126920 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-14 | 2019-06-13 | 2019-06-13 | 1 | MAINTENANCE | ELECTRICAL | 1.5
2019-03-31 | 397869 | Work Order Description - 397869 - PM | PM | 4 | 126984 | SCHD | NORM-OPS | 2019-02-13 | 2019-07-14 | 2019-06-13 | 2019-06-13 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 398011 | Work Order Description - 398011 - PRJ | PRJ | 4 | 228839 | SCHD | NORM-OPS | 2019-03-06 | 2021-02-11 | 2020-02-12 | 2020-02-26 | 4 | ENGINEERING | OPERATIONS | 49
2019-03-31 | 398027 | Work Order Description - 398027 - BR | BR | 4 | 528181 | SCHD | NORM-OPS | 2019-03-06 | 2019-05-09 | 2019-04-14 | 2019-04-15 | 2 | INTEGRITY | SERVICES | 28
2019-03-31 | 398030 | Work Order Description - 398030 - CM | CM | 4 | 528181 | SCHD | NORM-OPS | 2019-03-06 | 2020-02-13 | 2019-08-14 | 2019-08-21 | 3 | INTEGRITY | CONSTRUCTION | 100
2019-03-31 | 398039 | Work Order Description - 398039 - CM | CM | 4 | 528181 | SCHD | NORM-OPS | 2019-03-06 | 2021-02-11 | 2020-02-12 | 2020-02-17 | 4 | INTEGRITY | CONSTRUCTION | 70
2019-03-31 | 398044 | Work Order Description - 398044 - CM | CM | 4 | 528181 | WPLAN | NORM-OPS | 2019-02-18 | 2020-02-13 | 2019-08-14 | 2019-08-22 | 3 | INTEGRITY | FABRIC | 224
2019-03-31 | 398051 | Work Order Description - 398051 - CM | CM | 4 | 479578 | WPLAN | NORM-OPS | 2019-02-19 | 2020-02-13 | 2019-08-14 | 2019-09-04 | 3 | INTEGRITY | FABRIC | 150
2019-03-31 | 398075 | Work Order Description - 398075 - CM | CM | 1 | 579234 | WPLAN | NORM-OPS | 2019-02-19 | 2019-08-15 | 2019-05-15 | 2019-05-15 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 398076 | Work Order Description - 398076 - CM | CM | 4 | 478285 | WPLAN | NORM-OPS | 2019-02-19 | 2021-02-11 | 2020-12-30 | 2020-12-30 | 4 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 398077 | Work Order Description - 398077 - CM | CM | 1 | 180724 | WPLAN | NORM-OPS | 2019-02-19 | 2019-08-21 | 2019-05-21 | 2019-05-21 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 398079 | Work Order Description - 398079 - BR | BR | 3 | 50999 | WSCHD | EQUIP-ISOL | 2019-02-23 | 2019-05-19 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 15
2019-03-31 | 398085 | Work Order Description - 398085 - BR | BR | 1 | 657135 | WPLAN | EQUIP-ISOL | 2019-02-15 | 2021-02-11 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 398086 | Work Order Description - 398086 - CM | CM | 4 | 528181 | SCHD | NORM-OPS | 2019-03-06 | 2020-02-13 | 2019-08-14 | 2019-08-25 | 3 | INTEGRITY | SERVICES | 287
2019-03-31 | 398092 | Work Order Description - 398092 - CM | CM | 4 | 528181 | SCHD | NORM-OPS | 2019-03-06 | 2020-02-13 | 2019-08-14 | 2019-08-24 | 3 | INTEGRITY | INSPECTION | 196
2019-03-31 | 398111 | Work Order Description - 398111 - BR | BR | 4 | 99434 | SCHD | NORM-OPS | 2019-03-06 | 2021-02-11 | 2020-02-12 | 2020-02-14 | 4 | MAINTENANCE | SERVICES | 9
2019-03-31 | 398149 | Work Order Description - 398149 - PRJ | PRJ | 1 | 76924 | INPRG | NORM-OPS | 2019-02-26 | 2021-02-11 | 2019-09-29 | 2020-05-26 | 4 | MAINTENANCE | ELECTRICAL | 114
2019-03-31 | 398153 | Work Order Description - 398153 - CM | CM | 4 | 567562 | WSCHD | EQUIP-ISOL | 2019-02-13 | 2021-02-11 |  |  | 4 | OPERATIONS | MECHANICAL | 0
2019-03-31 | 398155 | Work Order Description - 398155 - CM | CM | 4 | 126130 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-05-09 | 2019-04-21 | 2019-04-22 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 398156 | Work Order Description - 398156 - CM | CM | 4 | 584883 | WSCHD | EQUIP-ISOL | 2019-02-13 | 2021-02-11 |  |  | 4 | OPERATIONS | MECHANICAL | 0
2019-03-31 | 398162 | Work Order Description - 398162 - CM | CM | 1 | 567646 | WSCHD | EQUIP-ISOL | 2019-02-13 | 2020-02-13 |  |  | 3 | OPERATIONS | MECHANICAL | 0
2019-03-31 | 398177 | Work Order Description - 398177 - PM | PM | 4 | 51202 | WSCHD | NORM-OPS | 2019-02-14 | 2019-07-15 | 2019-06-14 | 2019-06-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 398179 | Work Order Description - 398179 - PSPM | PSPM | 1 | 580769 | WSCHD | NORM-OPS | 2019-02-14 | 2019-07-15 | 2019-06-14 | 2019-06-14 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 398181 | Work Order Description - 398181 - PSPM | PSPM | 1 | 547298 | WSCHD | NORM-OPS | 2019-02-14 | 2019-07-15 | 2019-06-14 | 2019-06-14 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 398183 | Work Order Description - 398183 - PSPM | PSPM | 1 | 546068 | WSCHD | NORM-OPS | 2019-02-20 | 2019-07-15 | 2019-06-14 | 2019-06-14 | 1 | MAINTENANCE | SERVICES | 19
2019-03-31 | 398185 | Work Order Description - 398185 - PM | PM | 4 | 545298 | WSCHD | PACK-ISOL | 2019-03-05 | 2019-07-15 | 2019-06-14 | 2019-06-14 | 2 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 398187 | Work Order Description - 398187 - PSPM | PSPM | 1 | 309213 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-15 | 2019-06-14 | 2019-06-14 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 398191 | Work Order Description - 398191 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-15 | 2019-06-14 | 2019-06-14 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 398193 | Work Order Description - 398193 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-15 | 2019-06-14 | 2019-06-14 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 398195 | Work Order Description - 398195 - PM | PM | 4 | 479515 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-06-14 | 2019-06-14 | 2 | MAINTENANCE | SAFETY | 15
2019-03-31 | 398197 | Work Order Description - 398197 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-15 | 2019-06-14 | 2019-06-14 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 398199 | Work Order Description - 398199 - PSPM | PSPM | 1 | 255832 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-15 | 2019-06-14 | 2019-06-14 | 1 | MAINTENANCE | ELECTRICAL | 32
2019-03-31 | 398201 | Work Order Description - 398201 - PSPM | PSPM | 1 | 482174 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-15 | 2019-06-14 | 2019-06-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 398207 | Work Order Description - 398207 - PSPM | PSPM | 1 | 663164 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-15 | 2019-06-14 | 2019-06-14 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 398209 | Work Order Description - 398209 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-15 | 2019-06-14 | 2019-06-14 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 398212 | Work Order Description - 398212 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-15 | 2019-06-14 | 2019-06-14 | 3 | MAINTENANCE | ELECTRICAL | 0.5
2019-03-31 | 398214 | Work Order Description - 398214 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-15 | 2019-06-14 | 2019-06-16 | 3 | MAINTENANCE | MEDIC | 21
2019-03-31 | 398312 | Work Order Description - 398312 - BR | BR | 3 | 443006 | WPLAN | EQUIP-ISOL | 2019-02-17 | 2019-08-16 | 2019-05-16 | 2019-05-17 | 3 | INTEGRITY | CONSTRUCTION | 10
2019-03-31 | 398333 | Work Order Description - 398333 - CM | CM | 3 | 51538 | WRISKQ | SYS-ISOL | 2019-02-15 | 2019-05-10 |  |  | 2 | MAINTENANCE | CONSTRUCTION | 148
2019-03-31 | 398371 | Work Order Description - 398371 - CM | CM | 2 | 99232 | SCHD | NORM-OPS | 2019-03-06 | 2021-02-12 | 2020-02-13 | 2020-02-14 | 4 | MAINTENANCE | SERVICES | 9
2019-03-31 | 398520 | Work Order Description - 398520 - PRJ | PRJ | 2 | 320336 | WPLAN | PACK-ISOL | 2019-02-20 | 2020-02-14 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 398549 | Work Order Description - 398549 - CM | CM | 3 | 361485 | WSCHD | EQUIP-ISOL | 2019-03-18 | 2021-02-12 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 398605 | Work Order Description - 398605 - CM | CM | 4 | 378847 | WPLAN | NORM-OPS | 2019-02-18 | 2020-02-14 | 2019-08-16 | 2019-08-16 | 3 | INTEGRITY | FABRIC | 0
2019-03-31 | 398636 | Work Order Description - 398636 - PSPM | PSPM | 1 | 657680 | WSCHD | NORM-OPS | 2019-02-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 398638 | Work Order Description - 398638 - PSPM | PSPM | 1 | 321203 | WSCHD | NORM-OPS | 2019-02-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 398640 | Work Order Description - 398640 - PSPM | PSPM | 1 | 321218 | WSCHD | NORM-OPS | 2019-02-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 398642 | Work Order Description - 398642 - PSPM | PSPM | 1 | 546068 | WSCHD | NORM-OPS | 2019-02-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | SERVICES | 6
2019-03-31 | 398644 | Work Order Description - 398644 - PSPM | PSPM | 1 | 652220 | WSCHD | NORM-OPS | 2019-02-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | SERVICES | 6
2019-03-31 | 398646 | Work Order Description - 398646 - PM | PM | 4 | 666204 | WSCHD | NORM-OPS | 2019-02-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 398648 | Work Order Description - 398648 - PM | PM | 4 | 294916 | WSCHD | NORM-OPS | 2019-02-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 398650 | Work Order Description - 398650 - PSPM | PSPM | 1 | 552282 | SCHD | PACK-ISOL | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 398653 | Work Order Description - 398653 - PSPM | PSPM | 1 | 552282 | SCHD | PACK-ISOL | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 398655 | Work Order Description - 398655 - PSPM | PSPM | 1 | 552282 | SCHD | PACK-ISOL | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 398657 | Work Order Description - 398657 - PM | PM | 4 | 552838 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-22 | 2019-06-15 | 2019-06-15 | 3 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 398659 | Work Order Description - 398659 - PM | PM | 4 | 552838 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-22 | 2019-06-15 | 2019-06-15 | 3 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 398661 | Work Order Description - 398661 - PM | PM | 4 | 555977 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 398663 | Work Order Description - 398663 - PSPM | PSPM | 1 | 216927 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | OPERATIONS | MEDIC | 4
2019-03-31 | 398665 | Work Order Description - 398665 - PM | PM | 4 | 556383 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-11-25 | 2019-06-15 | 2019-06-15 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 398667 | Work Order Description - 398667 - PSPM | PSPM | 1 | 499149 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 398669 | Work Order Description - 398669 - PM | PM | 4 | 481636 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-16 | 2019-07-13 | 2019-07-13 | 3 | OPERATIONS | SAFETY | 15
2019-03-31 | 398671 | Work Order Description - 398671 - PM | PM | 4 | 481637 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-16 | 2019-07-06 | 2019-07-06 | 3 | OPERATIONS | SAFETY | 14
2019-03-31 | 398673 | Work Order Description - 398673 - PM | PM | 4 | 408896 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 398675 | Work Order Description - 398675 - PM | PM | 4 | 243163 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 2 | DRILLING | DRILLING | 4
2019-03-31 | 398677 | Work Order Description - 398677 - PM | PM | 4 | 472924 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-10-02 | 2019-06-15 | 2019-06-15 | 2 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 398679 | Work Order Description - 398679 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 398681 | Work Order Description - 398681 - PM | PM | 4 | 584765 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 398683 | Work Order Description - 398683 - PSPM | PSPM | 1 | 128338 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | OPERATIONS | OPERATIONS | 4
2019-03-31 | 398685 | Work Order Description - 398685 - PM | PM | 4 | 216612 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 2 | DRILLING | DRILLING | 9
2019-03-31 | 398689 | Work Order Description - 398689 - PM | PM | 4 | 243254 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 2 | DRILLING | DRILLING | 5
2019-03-31 | 398691 | Work Order Description - 398691 - PM | PM | 4 | 479007 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 2 | DRILLING | DRILLING | 8
2019-03-31 | 398693 | Work Order Description - 398693 - PM | PM | 4 | 216455 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-09 | 2019-06-15 | 2019-06-15 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 398695 | Work Order Description - 398695 - PM | PM | 4 | 479504 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-09 | 2019-06-15 | 2019-06-15 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 398697 | Work Order Description - 398697 - PM | PM | 4 | 216471 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-09 | 2019-06-15 | 2019-06-15 | 2 | DRILLING | DRILLING | 8
2019-03-31 | 398699 | Work Order Description - 398699 - PM | PM | 4 | 479115 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-09 | 2019-06-15 | 2019-06-15 | 2 | DRILLING | DRILLING | 3
2019-03-31 | 398701 | Work Order Description - 398701 - PM | PM | 4 | 502254 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-09 | 2019-06-15 | 2019-06-15 | 2 | DRILLING | DRILLING | 3
2019-03-31 | 398703 | Work Order Description - 398703 - PM | PM | 4 | 263031 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-09 | 2019-06-15 | 2019-06-15 | 2 | DRILLING | DRILLING | 4
2019-03-31 | 398705 | Work Order Description - 398705 - PM | PM | 4 | 552283 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 2 | DRILLING | DRILLING | 8
2019-03-31 | 398707 | Work Order Description - 398707 - PM | PM | 4 | 216084 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 2 | DRILLING | DRILLING | 5
2019-03-31 | 398711 | Work Order Description - 398711 - PM | PM | 4 | 502457 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 2 | DRILLING | DRILLING | 5
2019-03-31 | 398713 | Work Order Description - 398713 - PM | PM | 2 | 552282 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 2 | DRILLING | DRILLING | 18
2019-03-31 | 398717 | Work Order Description - 398717 - PM | PM | 4 | 320541 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 398721 | Work Order Description - 398721 - PM | PM | 2 | 552280 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 2 | DRILLING | DRILLING | 12
2019-03-31 | 398725 | Work Order Description - 398725 - PM | PM | 4 | 216158 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 398727 | Work Order Description - 398727 - PM | PM | 4 | 567819 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 398733 | Work Order Description - 398733 - PM | PM | 3 | 266661 | SCHD | NORM-OPS | 2019-03-29 | 2019-07-16 | 2019-06-15 | 2019-06-22 | 2 | MAINTENANCE | MECHANICAL | 54
2019-03-31 | 398735 | Work Order Description - 398735 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 398737 | Work Order Description - 398737 - PSPM | PSPM | 1 | 659055 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | OPERATIONS | SAFETY | 7
2019-03-31 | 398739 | Work Order Description - 398739 - PM | PM | 4 | 659501 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-09 | 2019-06-15 | 2019-06-16 | 2 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 398741 | Work Order Description - 398741 - PM | PM | 4 | 659501 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-09 | 2019-06-15 | 2019-06-16 | 2 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 398743 | Work Order Description - 398743 - PSPM | PSPM | 1 | 127752 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 398745 | Work Order Description - 398745 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 398747 | Work Order Description - 398747 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 398749 | Work Order Description - 398749 - PM | PM | 4 | 670525 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 398751 | Work Order Description - 398751 - PM | PM | 4 | 375852 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 398753 | Work Order Description - 398753 - PM | PM | 4 | 375646 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-09 | 2019-06-15 | 2019-06-15 | 2 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 398755 | Work Order Description - 398755 - PSPM | PSPM | 1 | 99434 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-16 | 2019-06-15 | 2019-06-16 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 398757 | Work Order Description - 398757 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-16 | 2019-06-15 | 2019-06-15 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 399148 | Work Order Description - 399148 - BR | BR | 4 | 66561 | WSCHD | EQUIP-ISOL | 2019-02-15 | 2021-02-13 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | DRILLING | 24
2019-03-31 | 399154 | Work Order Description - 399154 - BR | BR | 4 | 338658 | WSCHD | EQUIP-ISOL | 2019-02-15 | 2021-02-13 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | DRILLING | 24
2019-03-31 | 399166 | Work Order Description - 399166 - BR | BR | 1 | 657135 | WRISKREV | EQUIP-ISOL | 2019-03-31 | 2021-02-13 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 399186 | Work Order Description - 399186 - CM | CM | 4 | 451342 | SCHD | NORM-OPS | 2019-03-11 | 2019-08-17 | 2019-05-17 | 2019-05-25 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 399216 | Work Order Description - 399216 - PM | PM | 4 | 528208 | SCHD | NORM-OPS | 2019-03-06 | 2019-10-26 | 2019-09-01 | 2019-09-01 | 2 | OPERATIONS | SAFETY | 1
2019-03-31 | 399285 | Work Order Description - 399285 - PM | PM | 2 | 666083 | SCHD | NORM-OPS | 2019-03-22 | 2019-11-01 | 2019-10-01 | 2019-10-01 | 1 | INTEGRITY | SUBSEA | 0
2019-03-31 | 399288 | Work Order Description - 399288 - PM | PM | 2 | 666083 | SCHD | NORM-OPS | 2019-03-22 | 2019-11-01 | 2019-10-01 | 2019-10-01 | 1 | INTEGRITY | SUBSEA | 0
2019-03-31 | 399291 | Work Order Description - 399291 - PM | PM | 2 | 666083 | SCHD | NORM-OPS | 2019-03-22 | 2019-11-01 | 2019-10-01 | 2019-10-01 | 1 | INTEGRITY | SUBSEA | 0
2019-03-31 | 399303 | Work Order Description - 399303 - PSPM | PSPM | 1 | 601717 | SCHD | NORM-OPS | 2019-03-15 | 2019-11-01 | 2019-06-15 | 2019-06-15 | 1 | INTEGRITY | SUBSEA | 90
2019-03-31 | 399311 | Work Order Description - 399311 - PRJ | PRJ | 3 | 76032 | SCHD | NORM-OPS | 2019-03-06 | 2020-02-15 | 2019-04-14 | 2019-04-29 | 3 | INTEGRITY | SERVICES | 1
2019-03-31 | 399348 | Work Order Description - 399348 - PSPM | PSPM | 1 | 601717 | SCHD | NORM-OPS | 2019-03-15 | 2019-09-16 | 2019-08-16 | 2019-08-16 | 1 | INTEGRITY | SUBSEA | 4
2019-03-31 | 399350 | Work Order Description - 399350 - PSPM | PSPM | 1 | 601719 | SCHD | NORM-OPS | 2019-03-15 | 2019-09-24 | 2019-08-24 | 2019-08-24 | 1 | INTEGRITY | SUBSEA | 4
2019-03-31 | 399356 | Work Order Description - 399356 - CM | CM | 1 | 353024 | WRISKREV | EQUIP-ISOL | 2019-03-29 | 2021-02-13 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 23
2019-03-31 | 399400 | Work Order Description - 399400 - BR | BR | 2 | 363679 | WPLAN | EQUIP-ISOL | 2019-02-17 | 2020-02-16 | 2019-08-17 | 2019-08-17 | 3 | INTEGRITY | INSTRUMENTS | 12
2019-03-31 | 399406 | Work Order Description - 399406 - PM | PM | 2 | 572308 | WSCHD | NORM-OPS | 2019-02-16 | 2019-07-17 | 2019-06-16 | 2019-06-16 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 399408 | Work Order Description - 399408 - PM | PM | 4 | 651607 | WSCHD | NORM-OPS | 2019-02-16 | 2019-07-17 | 2019-06-16 | 2019-06-16 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 399410 | Work Order Description - 399410 - PM | PM | 4 | 580762 | WSCHD | NORM-OPS | 2019-02-16 | 2019-07-17 | 2019-06-16 | 2019-06-16 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 399412 | Work Order Description - 399412 - PM | PM | 4 | 256585 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-17 | 2019-06-16 | 2019-06-16 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 399414 | Work Order Description - 399414 - PM | PM | 4 | 256586 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-17 | 2019-06-16 | 2019-06-16 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 399416 | Work Order Description - 399416 - PSPM | PSPM | 1 | 447441 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-17 | 2019-06-16 | 2019-06-16 | 1 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 399418 | Work Order Description - 399418 - PM | PM | 1 | 446516 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-17 | 2019-06-16 | 2019-06-16 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 399420 | Work Order Description - 399420 - PM | PM | 4 | 482752 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-17 | 2019-06-16 | 2019-06-16 | 2 | MAINTENANCE | MECHANICAL | 34.25
2019-03-31 | 399426 | Work Order Description - 399426 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-17 | 2019-06-16 | 2019-06-16 | 2 | MAINTENANCE | SAFETY | 7
2019-03-31 | 399428 | Work Order Description - 399428 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-17 | 2019-06-16 | 2019-06-16 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 399430 | Work Order Description - 399430 - PSPM | PSPM | 1 | 669726 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-17 | 2019-06-16 | 2019-06-16 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 399432 | Work Order Description - 399432 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-17 | 2019-06-16 | 2019-06-16 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 399557 | Work Order Description - 399557 - BR | BR | 3 | 272088 | WPLAN | EQUIP-ISOL | 2019-02-21 | 2019-08-18 | 2019-04-13 | 2019-04-21 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 399597 | Work Order Description - 399597 - BR | BR | 2 | 411443 | SCHD | NORM-OPS | 2019-02-16 | 2019-05-12 | 2019-03-30 | 2019-03-30 | 2 | INTEGRITY | INSPECTION | 6
2019-03-31 | 399620 | Work Order Description - 399620 - BR | BR | 3 | 465837 | WPLAN | EQUIP-ISOL | 2019-02-23 | 2021-02-14 | 2021-01-02 | 2021-01-02 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 399621 | Work Order Description - 399621 - BR | BR | 3 | 249292 | WSCHD | EQUIP-ISOL | 2019-02-17 | 2019-08-19 | 2019-05-19 | 2019-05-19 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 399626 | Work Order Description - 399626 - BR | BR | 3 | 499291 | WPLAN | EQUIP-ISOL | 2019-02-17 | 2020-02-17 | 2019-08-18 | 2019-08-18 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 399637 | Work Order Description - 399637 - BR | BR | 3 | 189097 | WPLAN | NORM-OPS | 2019-02-19 | 2021-02-15 | 2021-01-03 | 2021-01-03 | 4 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 399638 | Work Order Description - 399638 - PM | PM | 4 | 18317 | WSCHD | EQUIP-ISOL | 2019-02-17 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 399640 | Work Order Description - 399640 - PM | PM | 4 | 18316 | WSCHD | EQUIP-ISOL | 2019-02-17 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 399642 | Work Order Description - 399642 - PM | PM | 4 | 666316 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 399644 | Work Order Description - 399644 - PM | PM | 4 | 417521 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 399646 | Work Order Description - 399646 - PM | PM | 4 | 50099 | WSCHD | EQUIP-ISOL | 2019-02-17 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 399648 | Work Order Description - 399648 - PM | PM | 4 | 50098 | WSCHD | EQUIP-ISOL | 2019-02-17 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 399650 | Work Order Description - 399650 - PM | PM | 4 | 411571 | WSCHD | NORM-OPS | 2019-02-17 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 399652 | Work Order Description - 399652 - PM | PM | 4 | 358159 | WSCHD | NORM-OPS | 2019-02-17 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 399654 | Work Order Description - 399654 - PM | PM | 4 | 540667 | WSCHD | NORM-OPS | 2019-02-17 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 399656 | Work Order Description - 399656 - PM | PM | 4 | 678551 | WSCHD | NORM-OPS | 2019-02-17 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 399658 | Work Order Description - 399658 - PSPM | PSPM | 1 | 470877 | WSCHD | NORM-OPS | 2019-02-17 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 399660 | Work Order Description - 399660 - PSPM | PSPM | 1 | 361799 | WSCHD | NORM-OPS | 2019-02-17 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 399662 | Work Order Description - 399662 - PM | PM | 4 | 360243 | WSCHD | NORM-OPS | 2019-02-17 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 399664 | Work Order Description - 399664 - PM | PM | 4 | 447064 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 399666 | Work Order Description - 399666 - PM | PM | 4 | 556260 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 399668 | Work Order Description - 399668 - PM | PM | 2 | 216011 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 399670 | Work Order Description - 399670 - PSPM | PSPM | 1 | 402269 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 399672 | Work Order Description - 399672 - PM | PM | 4 | 320026 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 399674 | Work Order Description - 399674 - PM | PM | 4 | 74216 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 399678 | Work Order Description - 399678 - PSPM | PSPM | 1 | 527317 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 1 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 399680 | Work Order Description - 399680 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-18 | 2019-06-17 | 2019-06-17 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 399829 | Work Order Description - 399829 - BR | BR | 3 | 548516 | WSCHD | TPS | 2019-02-17 | 2020-02-17 |  |  | 3 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 399870 | Work Order Description - 399870 - CM | CM | 4 | 262343 | WSCHD | EQUIP-ISOL | 2019-03-01 | 2021-02-15 | 2021-01-03 | 2021-01-03 | 4 | MAINTENANCE | MECHANICAL | 150
2019-03-31 | 399907 | Work Order Description - 399907 - BR | BR | 4 | 262343 | WPLAN | EQUIP-ISOL | 2019-02-19 | 2021-02-15 | 2020-02-16 | 2020-02-16 | 4 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 399923 | Work Order Description - 399923 - BR | BR | 4 | 262343 | WMATL | EQUIP-ISOL | 2019-03-01 | 2021-02-15 | 2021-01-03 | 2021-01-03 | 4 | MAINTENANCE | INSTRUMENTS | 22
2019-03-31 | 399932 | Work Order Description - 399932 - BR | BR | 4 | 262343 | WPLAN | EQUIP-ISOL | 2019-03-01 | 2021-02-15 | 2021-01-03 | 2021-01-03 | 4 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 399939 | Work Order Description - 399939 - BR | BR | 4 | 262343 | WPLAN | EQUIP-ISOL | 2019-03-01 | 2021-02-15 | 2021-01-03 | 2021-01-03 | 4 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 399964 | Work Order Description - 399964 - CM | CM | 2 | 127841 | SCHD | EQUIP-ISOL | 2019-03-06 | 2021-02-16 | 2021-01-04 | 2021-01-04 | 4 | WELLS | INSTRUMENTS | 3
2019-03-31 | 399965 | Work Order Description - 399965 - BR | BR | 3 | 35947 | WMATL | PACK-ISOL | 2019-03-18 | 2019-09-19 | 2019-05-25 | 2019-05-30 | 2 | MAINTENANCE | OPERATIONS | 12
2019-03-31 | 399978 | Work Order Description - 399978 - PM | PM | 3 | 595914 | WSCHD | TPS | 2019-02-20 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 399981 | Work Order Description - 399981 - PM | PM | 3 | 671142 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 399983 | Work Order Description - 399983 - PM | PM | 3 | 308001 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 399985 | Work Order Description - 399985 - PM | PM | 3 | 246620 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 399987 | Work Order Description - 399987 - PM | PM | 4 | 51688 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 399989 | Work Order Description - 399989 - PSPM | PSPM | 1 | 51688 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 399991 | Work Order Description - 399991 - PSPM | PSPM | 1 | 51688 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 399993 | Work Order Description - 399993 - PSPM | PSPM | 1 | 54501 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 399995 | Work Order Description - 399995 - PSPM | PSPM | 1 | 53299 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 399997 | Work Order Description - 399997 - PSPM | PSPM | 1 | 53300 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 399999 | Work Order Description - 399999 - PSPM | PSPM | 1 | 360558 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 400001 | Work Order Description - 400001 - PSPM | PSPM | 1 | 360560 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 400003 | Work Order Description - 400003 - PSPM | PSPM | 1 | 53304 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 400005 | Work Order Description - 400005 - PSPM | PSPM | 1 | 53305 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 400007 | Work Order Description - 400007 - PSPM | PSPM | 1 | 357426 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 400009 | Work Order Description - 400009 - PSPM | PSPM | 1 | 410145 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 400011 | Work Order Description - 400011 - PSPM | PSPM | 1 | 55010 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 400013 | Work Order Description - 400013 - PSPM | PSPM | 1 | 53659 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 400015 | Work Order Description - 400015 - PSPM | PSPM | 1 | 53660 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 400017 | Work Order Description - 400017 - PM | PM | 3 | 680522 | WSCHD | EQUIP-ISOL | 2019-02-18 | 2020-01-21 | 2019-06-18 | 2019-06-18 | 3 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 400019 | Work Order Description - 400019 - PSPM | PSPM | 1 | 653326 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 400021 | Work Order Description - 400021 - PSPM | PSPM | 1 | 656072 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 400023 | Work Order Description - 400023 - PSPM | PSPM | 1 | 653327 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 400025 | Work Order Description - 400025 - PSPM | PSPM | 1 | 357626 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 400027 | Work Order Description - 400027 - PSPM | PSPM | 1 | 309251 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | MECHANICAL | 33
2019-03-31 | 400035 | Work Order Description - 400035 - PM | PM | 4 | 59293 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 400037 | Work Order Description - 400037 - PM | PM | 4 | 481609 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 400039 | Work Order Description - 400039 - PSPM | PSPM | 1 | 462436 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 400041 | Work Order Description - 400041 - PM | PM | 4 | 476154 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 400043 | Work Order Description - 400043 - PSPM | PSPM | 1 | 265465 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | INTEGRITY | INSPECTION | 8
2019-03-31 | 400045 | Work Order Description - 400045 - PM | PM | 4 | 184686 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-10-05 | 2019-06-18 | 2019-06-18 | 2 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 400047 | Work Order Description - 400047 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 400051 | Work Order Description - 400051 - PM | PM | 2 | 312718 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-30 | 2019-11-16 | 2019-11-16 | 3 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 400053 | Work Order Description - 400053 - PM | PM | 4 | 256187 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | INTEGRITY | INSPECTION | 7
2019-03-31 | 400055 | Work Order Description - 400055 - PSPM | PSPM | 4 | 403503 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 400059 | Work Order Description - 400059 - PSPM | PSPM | 1 | 392215 | SCHD | NORM-OPS | 2019-03-18 | 2019-07-19 | 2019-06-18 | 2019-06-18 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 400192 | Work Order Description - 400192 - BR | BR | 3 | 501450 | SCHD | PACK-ISOL | 2019-03-08 | 2019-09-02 | 2019-03-02 | 2019-03-02 | 1 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 400262 | Work Order Description - 400262 - PM | PM | 4 | 376219 | WPLAN | EQUIP-ISOL | 2019-02-18 | 2019-06-24 | 2019-04-30 | 2019-05-01 | 2 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 400272 | Work Order Description - 400272 - PSCM | PSCM | 3 | 435781 | SCHD | TPS | 2019-03-06 | 2019-05-14 | 2019-07-13 | 2019-07-23 | 2 | INTEGRITY | MECHANICAL | 168
2019-03-31 | 400280 | Work Order Description - 400280 - BR | BR | 4 | 262343 | WSCHD | EQUIP-ISOL | 2019-02-25 | 2021-02-16 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 64
2019-03-31 | 400285 | Work Order Description - 400285 - BR | BR | 4 | 262343 | WSCHD | EQUIP-ISOL | 2019-02-25 | 2021-02-16 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | MECHANICAL | 64
2019-03-31 | 400297 | Work Order Description - 400297 - BR | BR | 3 | 555358 | WPLAN | TPS | 2019-02-19 | 2019-08-20 | 2019-05-20 | 2019-05-20 | 3 | MAINTENANCE | INSTRUMENTS | 96
2019-03-31 | 400329 | Work Order Description - 400329 - BR | BR | 4 | 666774 | WPLAN | EQUIP-ISOL | 2019-02-19 | 2021-02-17 | 2020-02-18 | 2020-02-18 | 4 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 400373 | Work Order Description - 400373 - PSPM | PSPM | 4 | 411443 | SCHD | NORM-OPS | 2019-03-05 | 2019-04-12 | 2019-05-18 | 2019-05-18 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 400381 | Work Order Description - 400381 - BR | BR | 1 | 399609 | WPLAN | NORM-OPS | 2019-02-19 | 2019-08-21 | 2019-05-21 | 2019-05-21 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 400384 | Work Order Description - 400384 - PM | PM | 4 | 540691 | WSCHD | NORM-OPS | 2019-02-19 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 400386 | Work Order Description - 400386 - PM | PM | 4 | 481470 | WSCHD | NORM-OPS | 2019-02-19 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 400388 | Work Order Description - 400388 - PSPM | PSPM | 1 | 294959 | WSCHD | NORM-OPS | 2019-02-19 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 400390 | Work Order Description - 400390 - PSPM | PSPM | 1 | 652220 | WSCHD | NORM-OPS | 2019-02-20 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | SERVICES | 12
2019-03-31 | 400392 | Work Order Description - 400392 - PSPM | PSPM | 1 | 403503 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 5.5
2019-03-31 | 400394 | Work Order Description - 400394 - PSPM | PSPM | 1 | 27535 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 400396 | Work Order Description - 400396 - PM | PM | 4 | 99579 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 400398 | Work Order Description - 400398 - PSPM | PSPM | 1 | 567452 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 400400 | Work Order Description - 400400 - PSPM | PSPM | 1 | 184667 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 400402 | Work Order Description - 400402 - PSPM | PSPM | 1 | 567562 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 400404 | Work Order Description - 400404 - PSPM | PSPM | 1 | 584883 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 400406 | Work Order Description - 400406 - PSPM | PSPM | 1 | 567646 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 400408 | Work Order Description - 400408 - PM | PM | 4 | 316451 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 2 | DRILLING | DRILLING | 4
2019-03-31 | 400410 | Work Order Description - 400410 - PM | PM | 4 | 325215 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 2 | INTEGRITY | INSPECTION | 14
2019-03-31 | 400412 | Work Order Description - 400412 - PSPM | PSPM | 1 | 476157 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 400414 | Work Order Description - 400414 - PM | PM | 4 | 262928 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 400416 | Work Order Description - 400416 - PM | PM | 4 | 460846 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 400418 | Work Order Description - 400418 - PSPM | PSPM | 1 | 34240 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 400420 | Work Order Description - 400420 - PM | PM | 4 | 499149 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 400424 | Work Order Description - 400424 - PSPM | PSPM | 1 | 392100 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-20 | 2019-06-19 | 2019-06-20 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 400426 | Work Order Description - 400426 - PSPM | PSPM | 1 | 179515 | SCHD | NORM-OPS | 2019-03-29 | 2019-07-20 | 2019-06-19 | 2019-06-20 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 400428 | Work Order Description - 400428 - PSPM | PSPM | 1 | 527315 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-20 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 400540 | Work Order Description - 400540 - BR | BR | 3 | 323238 | WPLAN | TPS | 2019-02-19 | 2019-08-21 | 2019-05-21 | 2019-05-21 | 3 | MAINTENANCE | CONSTRUCTION | 96
2019-03-31 | 400551 | Work Order Description - 400551 - BR | BR | 1 | 410206 | WPLAN | EQUIP-ISOL | 2019-02-22 | 2019-08-22 | 2019-05-22 | 2019-05-22 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 400571 | Work Order Description - 400571 - PRJ | PRJ | 4 | 266628 | SCHD | NORM-OPS | 2019-03-06 | 2021-02-17 | 2019-03-09 | 2019-09-10 | 4 | INTEGRITY | CONSTRUCTION | 1433
2019-03-31 | 400615 | Work Order Description - 400615 - PM | PM | 1 | 375789 | SCHD | PACK-ISOL | 2019-03-22 | 2019-07-04 | 2019-06-03 | 2019-06-03 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 400656 | Work Order Description - 400656 - PSCM | PSCM | 1 | 179014 | SCHD | NORM-OPS | 2019-03-06 | 2021-02-17 | 2021-01-05 | 2021-01-06 | 4 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 400665 | Work Order Description - 400665 - PM | PM | 4 | 127906 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-12-31 | 2019-09-13 | 2019-09-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 400672 | Work Order Description - 400672 - PSPM | PSPM | 1 | 676294 | WSCHD | PACK-ISOL | 2019-02-20 | 2019-09-30 | 2019-08-18 | 2019-08-18 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 400674 | Work Order Description - 400674 - PSPM | PSPM | 1 | 363730 | WPLAN | PACK-ISOL | 2019-02-19 | 2019-09-30 | 2019-08-18 | 2019-08-18 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 400676 | Work Order Description - 400676 - PSPM | PSPM | 1 | 676295 | WPLAN | PACK-ISOL | 2019-02-19 | 2019-09-30 | 2019-08-30 | 2019-08-30 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 400678 | Work Order Description - 400678 - PSPM | PSPM | 1 | 676296 | WPLAN | PACK-ISOL | 2019-02-19 | 2019-09-30 | 2019-08-18 | 2019-08-18 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 400680 | Work Order Description - 400680 - PSPM | PSPM | 1 | 18320 | WPLAN | SUBSYS-ISOL | 2019-02-19 | 2019-10-31 | 2019-09-18 | 2019-09-18 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 400682 | Work Order Description - 400682 - PSPM | PSPM | 1 | 363754 | WPLAN | SYS-ISOL | 2019-02-19 | 2019-10-31 | 2019-09-18 | 2019-09-18 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 400684 | Work Order Description - 400684 - PSPM | PSPM | 1 | 56682 | WPLAN | SYS-ISOL | 2019-02-19 | 2019-10-31 | 2019-09-18 | 2019-09-18 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 400686 | Work Order Description - 400686 - PSPM | PSPM | 1 | 56658 | WPLAN | SYS-ISOL | 2019-02-19 | 2019-10-31 | 2019-09-18 | 2019-09-18 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 400688 | Work Order Description - 400688 - PSPM | PSPM | 1 | 56657 | WPLAN | SYS-ISOL | 2019-02-19 | 2019-10-31 | 2019-09-18 | 2019-09-18 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 400691 | Work Order Description - 400691 - PSPM | PSPM | 1 | 325359 | SCHD | PACK-ISOL | 2019-03-15 | 2019-06-05 | 2019-05-05 | 2019-05-05 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 400693 | Work Order Description - 400693 - PSPM | PSPM | 1 | 216248 | SCHD | PACK-ISOL | 2019-03-15 | 2019-05-16 | 2019-04-15 | 2019-04-15 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 400698 | Work Order Description - 400698 - PRJ | PRJ | 1 | 92605 | SCHD | NORM-OPS | 2019-03-06 | 2021-02-17 | 2019-04-02 | 2019-05-21 | 4 | MAINTENANCE | ELECTRICAL | 1298
2019-03-31 | 400699 | Work Order Description - 400699 - BR | BR | 4 | 361803 | WPLAN | EQUIP-ISOL | 2019-02-25 | 2019-08-21 | 2019-04-20 | 2019-04-20 | 3 | OPERATIONS | MECHANICAL | 115
2019-03-31 | 400707 | Work Order Description - 400707 - CM | CM | 3 | 555841 | SCHD | PACK-ISOL | 2019-03-15 | 2019-05-15 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 400720 | Work Order Description - 400720 - PM | PM | 2 | 492146 | SCHD | PACK-ISOL | 2019-03-15 | 2020-02-21 | 2019-11-04 | 2019-11-04 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 400722 | Work Order Description - 400722 - PM | PM | 2 | 492147 | SCHD | PACK-ISOL | 2019-03-15 | 2020-02-28 | 2019-11-11 | 2019-11-11 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 400724 | Work Order Description - 400724 - PM | PM | 4 | 325342 | SCHD | NORM-OPS | 2019-03-15 | 2020-03-06 | 2019-11-18 | 2019-11-18 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 400727 | Work Order Description - 400727 - PM | PM | 4 | 188499 | WMATL | TPS | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 52
2019-03-31 | 400736 | Work Order Description - 400736 - PSCM | PSCM | 1 | 360830 | WPLAN | EQUIP-ISOL | 2019-02-22 | 2019-05-18 | 2019-04-05 | 2019-04-07 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 400771 | Work Order Description - 400771 - BR | BR | 3 | 245465 | WPLAN | EQUIP-ISOL | 2019-02-25 | 2019-08-27 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 400773 | Work Order Description - 400773 - PSPM | PSPM | 1 | 353374 | WSCHD | NORM-OPS | 2019-02-20 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 400775 | Work Order Description - 400775 - PSPM | PSPM | 1 | 57120 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-08-14 | 2019-07-17 | 2019-07-17 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 400777 | Work Order Description - 400777 - PSPM | PSPM | 1 | 360334 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-07-21 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 400779 | Work Order Description - 400779 - PSPM | PSPM | 1 | 57219 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-07-21 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 400781 | Work Order Description - 400781 - PSPM | PSPM | 1 | 262082 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-08-14 | 2019-07-17 | 2019-07-17 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 400783 | Work Order Description - 400783 - PM | PM | 4 | 660951 | WSCHD | NORM-OPS | 2019-02-20 | 2019-07-21 | 2019-06-08 | 2019-06-08 | 3 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 400787 | Work Order Description - 400787 - PSPM | PSPM | 1 | 547276 | WSCHD | NORM-OPS | 2019-02-20 | 2019-07-21 | 2019-06-08 | 2019-06-08 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 400789 | Work Order Description - 400789 - PM | PM | 4 | 652637 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-11-30 | 2019-09-09 | 2019-09-09 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 400791 | Work Order Description - 400791 - PM | PM | 4 | 313577 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-11-30 | 2019-09-09 | 2019-09-09 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 400793 | Work Order Description - 400793 - PM | PM | 4 | 652638 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-11-30 | 2019-09-09 | 2019-09-09 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 400795 | Work Order Description - 400795 - PM | PM | 4 | 138200 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-11-30 | 2019-09-09 | 2019-09-09 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 400797 | Work Order Description - 400797 - PM | PM | 4 | 138201 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-11-30 | 2019-09-09 | 2019-09-09 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 400799 | Work Order Description - 400799 - PM | PM | 4 | 138202 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-11-30 | 2019-09-09 | 2019-09-09 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 400801 | Work Order Description - 400801 - PM | PM | 4 | 652639 | WSCHD | EQUIP-ISOL | 2019-02-20 | 2019-11-30 | 2019-09-09 | 2019-09-09 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 400803 | Work Order Description - 400803 - PSPM | PSPM | 1 | 309456 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-21 | 2019-06-20 | 2019-06-23 | 1 | INTEGRITY | MECHANICAL | 90
2019-03-31 | 400805 | Work Order Description - 400805 - PSPM | PSPM | 1 | 29639 | SCHD | PACK-ISOL | 2019-03-15 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 400808 | Work Order Description - 400808 - PSPM | PSPM | 1 | 29639 | SCHD | PACK-ISOL | 2019-03-15 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 400810 | Work Order Description - 400810 - PM | PM | 4 | 325633 | SCHD | PACK-ISOL | 2019-03-15 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 400812 | Work Order Description - 400812 - PM | PM | 4 | 460846 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-10-07 | 2019-06-20 | 2019-06-20 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 400814 | Work Order Description - 400814 - PM | PM | 4 | 27535 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-10-07 | 2019-06-20 | 2019-06-20 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 400816 | Work Order Description - 400816 - PSPM | PSPM | 1 | 216946 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-21 | 2019-07-13 | 2019-07-13 | 1 | OPERATIONS | SAFETY | 4
2019-03-31 | 400818 | Work Order Description - 400818 - PSPM | PSPM | 1 | 29041 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 400820 | Work Order Description - 400820 - PM | PM | 1 | 323663 | SCHD | PACK-ISOL | 2019-03-15 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 400822 | Work Order Description - 400822 - PSPM | PSPM | 1 | 462436 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 400824 | Work Order Description - 400824 - PM | PM | 4 | 401353 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 400826 | Work Order Description - 400826 - PSPM | PSPM | 1 | 170113 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 400828 | Work Order Description - 400828 - PSPM | PSPM | 1 | 122617 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-21 | 2019-07-13 | 2019-07-13 | 1 | OPERATIONS | SAFETY | 7
2019-03-31 | 400830 | Work Order Description - 400830 - PSPM | PSPM | 1 | 567354 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 400832 | Work Order Description - 400832 - PSPM | PSPM | 1 | 99577 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 400834 | Work Order Description - 400834 - PM | PM | 4 | 325633 | SCHD | PACK-ISOL | 2019-03-15 | 2019-08-05 | 2019-06-20 | 2019-06-20 | 4 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 400836 | Work Order Description - 400836 - PSPM | PSPM | 1 | 123510 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 400842 | Work Order Description - 400842 - PM | PM | 4 | 527375 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 400844 | Work Order Description - 400844 - PM | PM | 4 | 659575 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | SAFETY | 7
2019-03-31 | 400846 | Work Order Description - 400846 - PM | PM | 4 | 659576 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | SAFETY | 7
2019-03-31 | 400848 | Work Order Description - 400848 - PM | PM | 4 | 527399 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 400850 | Work Order Description - 400850 - PM | PM | 4 | 450998 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | OPERATIONS | SAFETY | 1
2019-03-31 | 400852 | Work Order Description - 400852 - PM | PM | 4 | 450999 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | OPERATIONS | SAFETY | 1
2019-03-31 | 400854 | Work Order Description - 400854 - PSPM | PSPM | 1 | 42961 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 400856 | Work Order Description - 400856 - PSPM | PSPM | 4 | 99232 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-21 | 2019-06-20 | 2019-06-21 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 400858 | Work Order Description - 400858 - PSPM | PSPM | 1 | 126920 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | ELECTRICAL | 1.5
2019-03-31 | 400860 | Work Order Description - 400860 - PM | PM | 4 | 126984 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 400862 | Work Order Description - 400862 - PSPM | PSPM | 1 | 527317 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-21 | 2019-06-20 | 2019-06-22 | 1 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 400868 | Work Order Description - 400868 - CM | CM | 3 | 50998 | WPLAN | EQUIP-ISOL | 2019-02-25 | 2020-02-20 | 2019-08-31 | 2019-08-31 | 3 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 401045 | Work Order Description - 401045 - CM | CM | 3 | 678377 | WPLAN | EQUIP-ISOL | 2019-02-25 | 2019-08-27 | 2019-08-31 | 2019-08-31 | 3 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 401066 | Work Order Description - 401066 - CM | CM | 3 | 482462 | WPLAN | PACK-ISOL | 2019-02-20 | 2020-02-20 | 2019-08-21 | 2019-08-21 | 3 | INTEGRITY | CONSTRUCTION | 52
2019-03-31 | 401083 | Work Order Description - 401083 - PM | PM | 3 | 186606 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-09-03 | 2019-07-10 | 2019-07-10 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 401085 | Work Order Description - 401085 - PM | PM | 4 | 100130 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-09-03 | 2019-07-10 | 2019-07-10 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 401087 | Work Order Description - 401087 - PM | PM | 3 | 78352 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-08-12 | 2019-07-12 | 2019-07-12 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401089 | Work Order Description - 401089 - PM | PM | 3 | 186605 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-09-03 | 2019-07-10 | 2019-07-10 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 401091 | Work Order Description - 401091 - PM | PM | 3 | 105828 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 401093 | Work Order Description - 401093 - PM | PM | 3 | 99516 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 401095 | Work Order Description - 401095 - PSPM | PSPM | 1 | 105854 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401097 | Work Order Description - 401097 - PSPM | PSPM | 1 | 383390 | SCHD | SYS-ISOL | 2019-03-22 | 2019-08-10 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401099 | Work Order Description - 401099 - BR | BR | 3 | 266276 | SCHD | PACK-ISOL | 2019-03-06 | 2019-08-22 | 2019-07-13 | 2019-07-21 | 3 | MAINTENANCE | ELECTRICAL | 111
2019-03-31 | 401100 | Work Order Description - 401100 - PSPM | PSPM | 1 | 396123 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-10 | 2019-08-31 | 2019-08-31 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 401102 | Work Order Description - 401102 - PSPM | PSPM | 1 | 105880 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-10 | 2019-08-31 | 2019-08-31 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 401104 | Work Order Description - 401104 - PSPM | PSPM | 1 | 440647 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 401106 | Work Order Description - 401106 - PSPM | PSPM | 1 | 99927 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401109 | Work Order Description - 401109 - PSPM | PSPM | 1 | 106003 | SCHD | SYS-ISOL | 2019-03-22 | 2019-08-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 401111 | Work Order Description - 401111 - PSPM | PSPM | 1 | 186615 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 401113 | Work Order Description - 401113 - PSPM | PSPM | 1 | 113837 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-01 | 2019-06-22 | 2019-06-22 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 401115 | Work Order Description - 401115 - PSPM | PSPM | 1 | 105756 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 401117 | Work Order Description - 401117 - PSPM | PSPM | 1 | 99540 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 401119 | Work Order Description - 401119 - PSPM | PSPM | 1 | 99864 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 401126 | Work Order Description - 401126 - PSPM | PSPM | 1 | 669995 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 401128 | Work Order Description - 401128 - PM | PM | 4 | 440672 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-09-21 | 2019-07-10 | 2019-07-10 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 401131 | Work Order Description - 401131 - PSPM | PSPM | 1 | 448768 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 401133 | Work Order Description - 401133 - BR | BR | 1 | 655981 | SCHD | TPS | 2019-03-06 | 2019-08-22 | 2019-07-13 | 2019-07-14 | 3 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 401134 | Work Order Description - 401134 - PSPM | PSPM | 1 | 127843 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 401137 | Work Order Description - 401137 - PM | PM | 4 | 671040 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-09-03 | 2019-07-10 | 2019-07-10 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401139 | Work Order Description - 401139 - PM | PM | 4 | 127969 | SCHD | PACK-ISOL | 2019-03-22 | 2019-09-03 | 2019-07-10 | 2019-07-11 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 401143 | Work Order Description - 401143 - PM | PM | 4 | 105620 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-09-21 | 2019-07-10 | 2019-07-10 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 401145 | Work Order Description - 401145 - PM | PM | 4 | 74937 | SCHD | PACK-ISOL | 2019-03-22 | 2019-09-03 | 2019-07-10 | 2019-07-11 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 401147 | Work Order Description - 401147 - PM | PM | 3 | 95329 | SCHD | PACK-ISOL | 2019-03-22 | 2019-10-27 | 2019-07-10 | 2019-07-10 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 401149 | Work Order Description - 401149 - PM | PM | 4 | 449144 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 401151 | Work Order Description - 401151 - PM | PM | 4 | 450947 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-10 | 2019-05-28 | 2019-06-06 | 1 | MAINTENANCE | ELECTRICAL | 140
2019-03-31 | 401153 | Work Order Description - 401153 - PSPM | PSPM | 1 | 450947 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-10 | 2019-05-28 | 2019-06-22 | 1 | MAINTENANCE | ELECTRICAL | 360
2019-03-31 | 401156 | Work Order Description - 401156 - BR | BR | 4 | 247674 | WSCHD | NORM-OPS | 2019-03-08 | 2021-02-18 | 2021-01-06 | 2021-01-06 | 4 | MAINTENANCE | MECHANICAL | 140
2019-03-31 | 401163 | Work Order Description - 401163 - CM | CM | 3 | 655476 | WPLAN | NORM-OPS | 2019-02-26 | 2021-02-18 | 2021-01-06 | 2021-01-07 | 4 | INTEGRITY | INSPECTION | 10
2019-03-31 | 401164 | Work Order Description - 401164 - BR | BR | 3 | 655330 | WMATL | TPS | 2019-03-15 | 2019-03-21 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 401181 | Work Order Description - 401181 - BR | BR | 3 | 547130 | WSCHD | EQUIP-ISOL | 2019-02-25 | 2021-02-18 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 401194 | Work Order Description - 401194 - PRJ | PRJ | 4 | 27635 | WPLAN | NORM-OPS | 2019-02-23 | 2020-02-20 | 2019-08-21 | 2019-08-21 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 401208 | Work Order Description - 401208 - PRJ | PRJ | 4 | 535419 | WPLAN | NORM-OPS | 2019-02-23 | 2020-02-20 | 2019-08-21 | 2019-08-21 | 3 | INTEGRITY | FABRIC | 0
2019-03-31 | 401213 | Work Order Description - 401213 - PSPM | PSPM | 1 | 81186 | SCHD | SUBSYS-ISOL | 2019-03-15 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 401215 | Work Order Description - 401215 - PSPM | PSPM | 1 | 503248 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-03-23 | 2019-04-06 | 2019-04-06 | 1 | MAINTENANCE | ELECTRICAL | 1.5
2019-03-31 | 401219 | Work Order Description - 401219 - PM | PM | 3 | 189054 | SCHD | NORM-OPS | 2019-03-15 | 2019-05-23 | 2019-04-22 | 2019-04-22 | 2 | MAINTENANCE | MECHANICAL | 4.25
2019-03-31 | 401221 | Work Order Description - 401221 - PM | PM | 3 | 189054 | SCHD | NORM-OPS | 2019-03-15 | 2019-06-22 | 2019-05-22 | 2019-05-22 | 2 | MAINTENANCE | MECHANICAL | 4.25
2019-03-31 | 401231 | Work Order Description - 401231 - BR | BR | 3 | 228100 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-08-22 | 2019-05-23 | 2019-05-26 | 3 | INTEGRITY | MECHANICAL | 48
2019-03-31 | 401251 | Work Order Description - 401251 - PRJ | PRJ | 4 | 80122 | SCHD | NORM-OPS | 2019-03-06 | 2021-02-18 | 2021-01-07 | 2021-01-19 | 4 | ENGINEERING | FABRIC | 231.5
2019-03-31 | 401258 | Work Order Description - 401258 - PSCM | PSCM | 1 | 422375 | WSCHD | NORM-OPS | 2019-03-07 | 2020-02-22 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 401259 | Work Order Description - 401259 - CM | CM | 1 | 422375 | WSCHD | NORM-OPS | 2019-02-25 | 2021-02-20 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 401275 | Work Order Description - 401275 - PM | PM | 4 | 51662 | WSCHD | NORM-OPS | 2019-02-21 | 2019-07-22 | 2019-06-09 | 2019-06-09 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 401277 | Work Order Description - 401277 - PM | PM | 4 | 51202 | WSCHD | NORM-OPS | 2019-02-21 | 2019-07-22 | 2019-06-09 | 2019-06-09 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401279 | Work Order Description - 401279 - PM | PM | 4 | 18972 | WSCHD | NORM-OPS | 2019-02-21 | 2019-07-22 | 2019-06-09 | 2019-06-09 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 401281 | Work Order Description - 401281 - PM | PM | 4 | 355546 | WSCHD | NORM-OPS | 2019-02-21 | 2019-07-22 | 2019-06-09 | 2019-06-09 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 401283 | Work Order Description - 401283 - PM | PM | 4 | 18973 | WSCHD | NORM-OPS | 2019-02-21 | 2019-07-22 | 2019-06-09 | 2019-06-09 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 401285 | Work Order Description - 401285 - PM | PM | 4 | 355547 | WSCHD | NORM-OPS | 2019-02-21 | 2019-07-22 | 2019-06-09 | 2019-06-09 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 401287 | Work Order Description - 401287 - PM | PM | 4 | 18985 | WSCHD | NORM-OPS | 2019-02-21 | 2019-07-22 | 2019-06-09 | 2019-06-09 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 401289 | Work Order Description - 401289 - PM | PM | 4 | 355548 | WSCHD | NORM-OPS | 2019-02-21 | 2019-07-22 | 2019-06-09 | 2019-06-09 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 401291 | Work Order Description - 401291 - PSPM | PSPM | 1 | 580769 | WSCHD | NORM-OPS | 2019-02-21 | 2019-07-22 | 2019-06-21 | 2019-06-21 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 401293 | Work Order Description - 401293 - PM | PM | 4 | 267676 | WSCHD | NORM-OPS | 2019-02-21 | 2019-07-22 | 2019-06-09 | 2019-06-09 | 2 | OPERATIONS | SAFETY | 2
2019-03-31 | 401295 | Work Order Description - 401295 - PM | PM | 4 | 246173 | WSCHD | NORM-OPS | 2019-02-21 | 2019-07-22 | 2019-06-09 | 2019-06-09 | 1 | INTEGRITY | SERVICES | 2
2019-03-31 | 401297 | Work Order Description - 401297 - PM | PM | 4 | 546030 | WSCHD | NORM-OPS | 2019-02-21 | 2019-07-22 | 2019-06-09 | 2019-06-09 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 401299 | Work Order Description - 401299 - PM | PM | 4 | 652482 | WSCHD | NORM-OPS | 2019-02-21 | 2019-07-22 | 2019-06-09 | 2019-06-09 | 1 | INTEGRITY | SERVICES | 2
2019-03-31 | 401301 | Work Order Description - 401301 - PM | PM | 4 | 363762 | WSCHD | NORM-OPS | 2019-03-05 | 2019-07-22 | 2019-06-21 | 2019-06-21 | 2 | MAINTENANCE | MECHANICAL | 65
2019-03-31 | 401303 | Work Order Description - 401303 - PSPM | PSPM | 1 | 481467 | WSCHD | NORM-OPS | 2019-03-05 | 2019-07-22 | 2019-06-09 | 2019-06-09 | 1 | OPERATIONS | OPERATIONS | 15
2019-03-31 | 401305 | Work Order Description - 401305 - PSPM | PSPM | 1 | 675037 | WSCHD | NORM-OPS | 2019-02-21 | 2019-07-22 | 2019-06-09 | 2019-06-09 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 401307 | Work Order Description - 401307 - PSPM | PSPM | 1 | 671829 | WSCHD | NORM-OPS | 2019-02-21 | 2019-07-22 | 2019-06-09 | 2019-06-09 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 401309 | Work Order Description - 401309 - PM | PM | 4 | 98009 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-22 | 2019-06-21 | 2019-06-21 | 1 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 401311 | Work Order Description - 401311 - PM | PM | 4 | 482470 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-09-02 | 2019-08-31 | 2019-08-31 | 3 | INTEGRITY | SERVICES | 30
2019-03-31 | 401313 | Work Order Description - 401313 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-22 | 2019-06-21 | 2019-06-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 401315 | Work Order Description - 401315 - PSPM | PSPM | 1 | 304656 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-22 | 2019-06-21 | 2019-06-21 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401317 | Work Order Description - 401317 - PSPM | PSPM | 1 | 409080 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-22 | 2019-06-21 | 2019-06-21 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401319 | Work Order Description - 401319 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-22 | 2019-06-21 | 2019-06-21 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 401321 | Work Order Description - 401321 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-22 | 2019-06-21 | 2019-06-21 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 401323 | Work Order Description - 401323 - PM | PM | 3 | 490624 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-22 | 2019-06-21 | 2019-06-21 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 401327 | Work Order Description - 401327 - PSPM | PSPM | 1 | 663164 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-22 | 2019-06-21 | 2019-06-21 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 401329 | Work Order Description - 401329 - PM | PM | 4 | 441326 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-10-08 | 2019-06-21 | 2019-06-21 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401331 | Work Order Description - 401331 - PM | PM | 4 | 100412 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-10-08 | 2019-06-21 | 2019-06-21 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401333 | Work Order Description - 401333 - PM | PM | 4 | 78615 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-10-08 | 2019-06-21 | 2019-06-21 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401335 | Work Order Description - 401335 - PM | PM | 4 | 383308 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-08-15 | 2019-06-21 | 2019-06-21 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 401337 | Work Order Description - 401337 - PM | PM | 4 | 78603 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-10-08 | 2019-06-21 | 2019-06-21 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401339 | Work Order Description - 401339 - PM | PM | 4 | 179305 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-08-15 | 2019-06-21 | 2019-06-21 | 2 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 401343 | Work Order Description - 401343 - PM | PM | 4 | 441305 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-10-08 | 2019-06-21 | 2019-06-21 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401345 | Work Order Description - 401345 - PM | PM | 4 | 383309 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-10-08 | 2019-06-21 | 2019-06-21 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401347 | Work Order Description - 401347 - PM | PM | 4 | 78607 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-10-08 | 2019-06-21 | 2019-06-21 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401349 | Work Order Description - 401349 - PM | PM | 4 | 383344 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-10-08 | 2019-06-21 | 2019-06-21 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401351 | Work Order Description - 401351 - PM | PM | 4 | 78620 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-10-08 | 2019-06-21 | 2019-06-21 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401353 | Work Order Description - 401353 - PM | PM | 4 | 80464 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-12-01 | 2019-06-21 | 2019-06-21 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 401355 | Work Order Description - 401355 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-22 | 2019-06-21 | 2019-06-21 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 401359 | Work Order Description - 401359 - PM | PM | 4 | 80464 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-12-01 | 2019-06-21 | 2019-06-21 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 401361 | Work Order Description - 401361 - PM | PM | 4 | 266550 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-08-15 | 2019-06-21 | 2019-06-21 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 401363 | Work Order Description - 401363 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-22 | 2019-06-21 | 2019-06-23 | 3 | MAINTENANCE | MEDIC | 21
2019-03-31 | 401528 | Work Order Description - 401528 - CM | CM | 3 | 531934 | WSCHD | NORM-OPS | 2019-02-25 | 2019-08-23 | 2019-05-23 | 2019-05-23 | 3 | INTEGRITY | FABRIC | 140
2019-03-31 | 401530 | Work Order Description - 401530 - BR | BR | 3 | 126211 | WPLAN | NORM-OPS | 2019-02-26 | 2019-05-17 | 2019-04-11 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 401534 | Work Order Description - 401534 - BR | BR | 3 | 352804 | WSCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-23 | 2019-05-23 | 2019-05-23 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 401538 | Work Order Description - 401538 - BR | BR | 3 | 189052 | WSCHD | EQUIP-ISOL | 2019-02-21 | 2019-09-28 |  |  | 3 | MAINTENANCE | ELECTRICAL | 1170
2019-03-31 | 401550 | Work Order Description - 401550 - BR | BR | 3 | 652972 | WRISKQ | NORM-OPS | 2019-02-27 | 2021-02-19 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 21
2019-03-31 | 401551 | Work Order Description - 401551 - PM | PM | 3 | 98446 | SCHD | PACK-ISOL | 2019-03-22 | 2019-10-27 | 2019-07-10 | 2019-07-10 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 401566 | Work Order Description - 401566 - PSPM | PSPM | 1 | 375803 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-10 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 401569 | Work Order Description - 401569 - PSPM | PSPM | 1 | 531816 | WPLAN | SYS-ISOL | 2019-02-21 | 2021-06-01 | 2021-04-19 | 2021-04-19 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 401571 | Work Order Description - 401571 - PSPM | PSPM | 1 | 375805 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-10 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 401573 | Work Order Description - 401573 - PSPM | PSPM | 1 | 449175 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-10 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 401584 | Work Order Description - 401584 - CM | CM | 4 | 29041 | WPLAN | NORM-OPS | 2019-02-23 | 2019-05-19 | 2019-05-11 | 2019-05-12 | 2 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 401586 | Work Order Description - 401586 - PRJ | PRJ | 4 | 303784 | WPLAN | NORM-OPS | 2019-02-23 | 2020-02-21 | 2019-08-22 | 2019-08-22 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 401588 | Work Order Description - 401588 - PRJ | PRJ | 4 | 540266 | WPLAN | NORM-OPS | 2019-02-23 | 2020-02-21 | 2019-08-22 | 2019-08-22 | 3 | INTEGRITY | FABRIC | 1
2019-03-31 | 401594 | Work Order Description - 401594 - BR | BR | 1 | 113349 | SCHD | EQUIP-ISOL | 2019-03-06 | 2020-02-21 | 2019-08-22 | 2019-08-23 | 3 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 401606 | Work Order Description - 401606 - PSCM | PSCM | 1 | 547275 | WSCHD | NORM-OPS | 2019-03-17 | 2020-02-22 | 2019-04-13 | 2019-04-13 | 3 | OPERATIONS | MECHANICAL | 11
2019-03-31 | 401615 | Work Order Description - 401615 - PSCM | PSCM | 3 | 123619 | SCHD | TPS | 2019-03-06 | 2020-02-21 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 401626 | Work Order Description - 401626 - PRJ | PRJ | 3 | 451477 | SCHD | PACK-ISOL | 2019-03-06 | 2021-02-19 | 2019-04-13 | 2019-04-24 | 4 | ENGINEERING | ELECTRICAL | 84
2019-03-31 | 401638 | Work Order Description - 401638 - CM | CM | 1 | 408076 | WSCHD | NORM-OPS | 2019-03-11 | 2021-02-19 | 2021-01-07 | 2021-01-07 | 4 | MAINTENANCE | ELECTRICAL | 70
2019-03-31 | 401645 | Work Order Description - 401645 - PSCM | PSCM | 1 | 547276 | WSCHD | EQUIP-ISOL | 2019-03-15 | 2020-02-25 | 2019-04-13 | 2019-04-13 | 3 | OPERATIONS | MECHANICAL | 11
2019-03-31 | 401660 | Work Order Description - 401660 - PSPM | PSPM | 1 | 321203 | WSCHD | NORM-OPS | 2019-02-22 | 2019-07-23 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 401662 | Work Order Description - 401662 - PSPM | PSPM | 1 | 321218 | WSCHD | NORM-OPS | 2019-02-22 | 2019-07-23 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 401664 | Work Order Description - 401664 - PM | PM | 4 | 294916 | WSCHD | NORM-OPS | 2019-02-22 | 2019-07-23 | 2019-06-10 | 2019-06-10 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 401666 | Work Order Description - 401666 - PSPM | PSPM | 1 | 447441 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-23 | 2019-06-22 | 2019-06-22 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 401668 | Work Order Description - 401668 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-23 | 2019-06-22 | 2019-06-22 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 401670 | Work Order Description - 401670 - PSPM | PSPM | 1 | 632455 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-23 | 2019-06-22 | 2019-06-22 | 1 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 401672 | Work Order Description - 401672 - PM | PM | 3 | 189054 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-23 | 2019-06-22 | 2019-06-22 | 2 | MAINTENANCE | MECHANICAL | 4.25
2019-03-31 | 401674 | Work Order Description - 401674 - PM | PM | 4 | 216158 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-23 | 2019-06-22 | 2019-06-22 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 401682 | Work Order Description - 401682 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-23 | 2019-06-22 | 2019-06-22 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401684 | Work Order Description - 401684 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-23 | 2019-06-22 | 2019-06-22 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 401686 | Work Order Description - 401686 - PSPM | PSPM | 1 | 99232 | SCHD | PACK-ISOL | 2019-03-18 | 2019-07-23 | 2019-06-22 | 2019-06-25 | 1 | MAINTENANCE | SERVICES | 24
2019-03-31 | 401688 | Work Order Description - 401688 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-23 | 2019-06-22 | 2019-06-22 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 401802 | Work Order Description - 401802 - BR | BR | 3 | 552699 | WPLAN | EQUIP-ISOL | 2019-02-23 | 2021-02-20 | 2021-01-08 | 2021-01-08 | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 401804 | Work Order Description - 401804 - PSCM | PSCM | 3 | 383735 | WPLAN | EQUIP-ISOL | 2019-02-26 | 2021-02-20 | 2021-01-08 | 2021-01-10 | 4 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 401805 | Work Order Description - 401805 - CM | CM | 3 | 555399 | WPLAN | EQUIP-ISOL | 2019-02-23 | 2019-08-25 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 401906 | Work Order Description - 401906 - BR | BR | 4 | 549171 | INPRG | NORM-OPS | 2019-03-07 | 2021-02-20 | 2019-03-30 | 2019-03-30 | 4 | INTEGRITY | MECHANICAL | 442
2019-03-31 | 401922 | Work Order Description - 401922 - PSCM | PSCM | 1 | 482049 | WPLAN | NORM-OPS | 2019-02-23 | 2019-05-19 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 401930 | Work Order Description - 401930 - CM | CM | 3 | 18978 | SCHD | NORM-OPS | 2019-03-13 | 2019-08-24 | 2019-03-30 | 2019-04-10 | 3 | INTEGRITY | INSPECTION | 163.5
2019-03-31 | 401936 | Work Order Description - 401936 - BR | BR | 3 | 671670 | SCHD | EQUIP-ISOL | 2019-02-22 | 2019-05-18 | 2019-04-13 | 2019-04-21 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 401954 | Work Order Description - 401954 - PM | PM | 2 | 572308 | WSCHD | NORM-OPS | 2019-02-23 | 2019-07-24 | 2019-06-11 | 2019-06-11 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 401956 | Work Order Description - 401956 - PSPM | PSPM | 1 | 457538 | WSCHD | NORM-OPS | 2019-02-23 | 2019-07-24 | 2019-06-11 | 2019-06-11 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 401958 | Work Order Description - 401958 - PM | PM | 4 | 580762 | WSCHD | NORM-OPS | 2019-02-23 | 2019-07-24 | 2019-06-11 | 2019-06-11 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 401960 | Work Order Description - 401960 - PSPM | PSPM | 1 | 555259 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-24 | 2019-06-23 | 2019-06-23 | 1 | OPERATIONS | OPERATIONS | 12
2019-03-31 | 401962 | Work Order Description - 401962 - PM | PM | 1 | 446516 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-24 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 401964 | Work Order Description - 401964 - PSPM | PSPM | 1 | 29041 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-24 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 401976 | Work Order Description - 401976 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-24 | 2019-06-23 | 2019-06-23 | 2 | MAINTENANCE | SAFETY | 7
2019-03-31 | 401978 | Work Order Description - 401978 - PSPM | PSPM | 1 | 451271 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-24 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 401980 | Work Order Description - 401980 - PM | PM | 4 | 450692 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-24 | 2019-06-23 | 2019-06-23 | 1 | OPERATIONS | SAFETY | 2
2019-03-31 | 401982 | Work Order Description - 401982 - PSPM | PSPM | 1 | 664573 | SCHD | NORM-OPS | 2019-03-18 | 2019-07-24 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | SAFETY | 3
2019-03-31 | 401984 | Work Order Description - 401984 - PSPM | PSPM | 1 | 669726 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-07-24 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 401986 | Work Order Description - 401986 - PSPM | PSPM | 1 | 669726 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-07-24 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 401988 | Work Order Description - 401988 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-24 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 401990 | Work Order Description - 401990 - PSPM | PSPM | 1 | 669726 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-24 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 401992 | Work Order Description - 401992 - PSPM | PSPM | 1 | 128836 | SCHD | PACK-ISOL | 2019-03-22 | 2019-07-24 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 401994 | Work Order Description - 401994 - PSPM | PSPM | 1 | 128836 | SCHD | PACK-ISOL | 2019-03-22 | 2019-07-24 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401996 | Work Order Description - 401996 - PSPM | PSPM | 1 | 128836 | SCHD | PACK-ISOL | 2019-03-22 | 2019-07-24 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 401998 | Work Order Description - 401998 - PSPM | PSPM | 1 | 128836 | SCHD | PACK-ISOL | 2019-03-22 | 2019-07-24 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 402001 | Work Order Description - 402001 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-24 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 402003 | Work Order Description - 402003 - PM | PM | 2 | 450548 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-24 | 2019-06-23 | 2019-06-23 | 3 | OPERATIONS | OPERATIONS | 4
2019-03-31 | 402005 | Work Order Description - 402005 - PM | PM | 4 | 100274 | SCHD | PACK-ISOL | 2019-03-22 | 2019-10-10 | 2019-06-23 | 2019-06-23 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 402122 | Work Order Description - 402122 - CM | CM | 1 | 547275 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2021-03-01 | 2021-01-17 | 2021-01-17 | 4 | OPERATIONS | MECHANICAL | 20
2019-03-31 | 402150 | Work Order Description - 402150 - CM | CM | 4 | 442863 | WPLAN | EQUIP-ISOL | 2019-02-26 | 2021-02-21 | 2021-01-09 | 2021-01-11 | 4 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 402154 | Work Order Description - 402154 - CM | CM | 3 | 260234 | WSCHD | PACK-ISOL | 2019-02-25 | 2019-08-27 | 2019-09-07 | 2019-09-07 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 402156 | Work Order Description - 402156 - CM | CM | 3 | 110715 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-05-19 | 2019-04-06 | 2019-04-08 | 2 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 402164 | Work Order Description - 402164 - CM | CM | 3 | 449175 | WPLAN | PACK-ISOL | 2019-02-26 | 2020-02-23 | 2019-07-13 | 2019-07-15 | 3 | MAINTENANCE | ELECTRICAL | 17
2019-03-31 | 402181 | Work Order Description - 402181 - BR | BR | 3 | 491791 | WRISKREV | TPS | 2019-02-23 | 2019-03-24 |  |  | 2 | MAINTENANCE | MECHANICAL | 0
2019-03-31 | 402192 | Work Order Description - 402192 - BR | BR | 3 | 520151 | WPLAN | NORM-OPS | 2019-02-26 | 2019-05-19 | 2019-04-07 | 2019-04-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 402193 | Work Order Description - 402193 - PM | PM | 4 | 18317 | WSCHD | EQUIP-ISOL | 2019-02-24 | 2019-07-25 | 2019-06-12 | 2019-06-12 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 402195 | Work Order Description - 402195 - PM | PM | 4 | 18316 | WSCHD | EQUIP-ISOL | 2019-02-24 | 2019-07-25 | 2019-06-12 | 2019-06-12 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 402197 | Work Order Description - 402197 - PM | PM | 4 | 666316 | WSCHD | EQUIP-ISOL | 2019-03-05 | 2019-07-25 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 402199 | Work Order Description - 402199 - PM | PM | 4 | 417521 | WSCHD | EQUIP-ISOL | 2019-03-05 | 2019-07-25 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 402201 | Work Order Description - 402201 - PM | PM | 4 | 50099 | WSCHD | EQUIP-ISOL | 2019-02-24 | 2019-07-25 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 402203 | Work Order Description - 402203 - PM | PM | 4 | 50098 | WSCHD | EQUIP-ISOL | 2019-02-24 | 2019-07-25 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 402205 | Work Order Description - 402205 - PM | PM | 4 | 411571 | WSCHD | NORM-OPS | 2019-02-24 | 2019-07-25 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 402207 | Work Order Description - 402207 - PM | PM | 4 | 358159 | WSCHD | NORM-OPS | 2019-02-24 | 2019-07-25 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 402209 | Work Order Description - 402209 - PM | PM | 4 | 540667 | WSCHD | NORM-OPS | 2019-02-24 | 2019-07-25 | 2019-06-12 | 2019-06-12 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 402211 | Work Order Description - 402211 - PM | PM | 4 | 678551 | WSCHD | NORM-OPS | 2019-02-24 | 2019-07-25 | 2019-06-12 | 2019-06-12 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 402213 | Work Order Description - 402213 - PM | PM | 4 | 547429 | WSCHD | NORM-OPS | 2019-02-24 | 2019-07-25 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 402215 | Work Order Description - 402215 - PSPM | PSPM | 1 | 470877 | WSCHD | NORM-OPS | 2019-02-24 | 2019-07-25 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 402217 | Work Order Description - 402217 - PSPM | PSPM | 1 | 671828 | WSCHD | NORM-OPS | 2019-02-24 | 2019-07-25 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 402219 | Work Order Description - 402219 - PSPM | PSPM | 1 | 519759 | WSCHD | NORM-OPS | 2019-02-24 | 2019-07-25 | 2019-06-12 | 2019-06-12 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 402221 | Work Order Description - 402221 - PM | PM | 4 | 360243 | WSCHD | NORM-OPS | 2019-02-24 | 2019-07-25 | 2019-06-12 | 2019-06-12 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 402223 | Work Order Description - 402223 - PM | PM | 4 | 212354 | WSCHD | NORM-OPS | 2019-02-24 | 2019-07-25 | 2019-06-12 | 2019-06-12 | 2 | INTEGRITY | INSPECTION | 2
2019-03-31 | 402225 | Work Order Description - 402225 - PSPM | PSPM | 1 | 189054 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-25 | 2019-06-24 | 2019-06-24 | 1 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 402228 | Work Order Description - 402228 - PSPM | PSPM | 1 | 325633 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-25 | 2019-06-24 | 2019-06-24 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 402230 | Work Order Description - 402230 - PSPM | PSPM | 1 | 81212 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-25 | 2019-06-24 | 2019-06-24 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 402232 | Work Order Description - 402232 - PSPM | PSPM | 1 | 482190 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-25 | 2019-06-24 | 2019-06-24 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 402234 | Work Order Description - 402234 - PSPM | PSPM | 1 | 482189 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-25 | 2019-06-24 | 2019-06-24 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 402236 | Work Order Description - 402236 - PSPM | PSPM | 1 | 482188 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-25 | 2019-06-24 | 2019-06-24 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 402238 | Work Order Description - 402238 - PM | PM | 4 | 556260 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-25 | 2019-06-24 | 2019-06-24 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 402240 | Work Order Description - 402240 - PM | PM | 2 | 216011 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-25 | 2019-06-24 | 2019-06-24 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 402242 | Work Order Description - 402242 - PM | PM | 4 | 320026 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-25 | 2019-06-24 | 2019-06-24 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 402244 | Work Order Description - 402244 - PM | PM | 4 | 74216 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-25 | 2019-06-24 | 2019-06-24 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 402248 | Work Order Description - 402248 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-25 | 2019-06-24 | 2019-06-24 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 402250 | Work Order Description - 402250 - PSPM | PSPM | 1 | 528213 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-25 | 2019-06-24 | 2019-06-24 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 402252 | Work Order Description - 402252 - PSPM | PSPM | 1 | 668570 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-25 | 2019-06-24 | 2019-06-25 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 402254 | Work Order Description - 402254 - PSPM | PSPM | 1 | 450986 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-25 | 2019-06-24 | 2019-06-24 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 402498 | Work Order Description - 402498 - CM | CM | 3 | 300473 | WPLAN | TPS | 2019-02-26 | 2020-02-24 | 2019-08-25 | 2019-08-25 | 3 | MAINTENANCE | CONSTRUCTION | 140
2019-03-31 | 402523 | Work Order Description - 402523 - BR | BR | 2 | 471097 | SCHD | NORM-OPS | 2019-03-28 | 2021-02-22 | 2019-03-30 | 2019-03-30 | 4 | INTEGRITY | MECHANICAL | 2
2019-03-31 | 402544 | Work Order Description - 402544 - BR | BR | 3 | 189043 | INPRG | EQUIP-ISOL | 2019-03-23 | 2019-05-20 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 402558 | Work Order Description - 402558 - PSCM | PSCM | 1 | 398778 | WPLAN | EQUIP-ISOL | 2019-02-26 | 2021-02-22 | 2021-01-10 | 2021-01-12 | 4 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 402581 | Work Order Description - 402581 - BR | BR | 1 | 34399 | WPLAN | EQUIP-ISOL | 2019-02-28 | 2021-02-22 | 2021-01-10 | 2021-01-10 | 4 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 402586 | Work Order Description - 402586 - BR | BR | 1 | 551165 | WMATL | EQUIP-ISOL | 2019-03-25 | 2021-02-22 | 2021-01-10 | 2021-01-10 | 4 | MAINTENANCE | INSTRUMENTS | 32
2019-03-31 | 402615 | Work Order Description - 402615 - CM | CM | 4 | 95768 | SCHD | NORM-OPS | 2019-03-29 | 2021-02-22 | 2021-01-10 | 2021-01-10 | 4 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 402618 | Work Order Description - 402618 - BR | BR | 3 | 545222 | SCHD | NORM-OPS | 2019-03-05 | 2021-02-22 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 402621 | Work Order Description - 402621 - BR | BR | 2 | 555761 | SCHD | NORM-OPS | 2019-03-15 | 2021-02-22 | 2021-01-11 | 2021-01-11 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 402624 | Work Order Description - 402624 - PM | PM | 2 | 312718 | SCHD | PACK-ISOL | 2019-03-15 | 2019-07-26 | 2019-06-25 | 2019-06-25 | 2 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 402628 | Work Order Description - 402628 - PM | PM | 4 | 481609 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-26 | 2019-06-25 | 2019-06-25 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 402630 | Work Order Description - 402630 - PSPM | PSPM | 1 | 303827 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-26 | 2019-06-25 | 2019-06-25 | 1 | INTEGRITY | INSPECTION | 12
2019-03-31 | 402632 | Work Order Description - 402632 - PSPM | PSPM | 1 | 303784 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-26 | 2019-06-25 | 2019-06-25 | 1 | INTEGRITY | OPERATIONS | 12
2019-03-31 | 402634 | Work Order Description - 402634 - PSPM | PSPM | 1 | 256565 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-26 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | INSPECTION | 12
2019-03-31 | 402636 | Work Order Description - 402636 - PSPM | PSPM | 1 | 626120 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-26 | 2019-06-25 | 2019-06-25 | 1 | INTEGRITY | OPERATIONS | 12
2019-03-31 | 402638 | Work Order Description - 402638 - PSPM | PSPM | 1 | 535419 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-26 | 2019-06-25 | 2019-06-25 | 1 | INTEGRITY | OPERATIONS | 12
2019-03-31 | 402640 | Work Order Description - 402640 - PM | PM | 4 | 476154 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-26 | 2019-06-25 | 2019-06-25 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 402642 | Work Order Description - 402642 - PM | PM | 4 | 99579 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-26 | 2019-06-25 | 2019-06-25 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 402644 | Work Order Description - 402644 - PSPM | PSPM | 1 | 632581 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-26 | 2019-07-13 | 2019-07-13 | 1 | OPERATIONS | SAFETY | 5
2019-03-31 | 402646 | Work Order Description - 402646 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-26 | 2019-06-25 | 2019-06-25 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 402650 | Work Order Description - 402650 - PSPM | PSPM | 4 | 403503 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-26 | 2019-06-25 | 2019-06-25 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 402652 | Work Order Description - 402652 - PSPM | PSPM | 1 | 392215 | SCHD | NORM-OPS | 2019-03-18 | 2019-07-26 | 2019-06-25 | 2019-06-25 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 402800 | Work Order Description - 402800 - BR | BR | 4 | 685304 | SCHD | NORM-OPS | 2019-02-27 | 2021-02-23 | 2019-03-30 | 2019-04-26 | 4 | MAINTENANCE | INSTRUMENTS | 147
2019-03-31 | 402858 | Work Order Description - 402858 - CM | CM | 4 | 447441 | WSCHD | EQUIP-ISOL | 2019-02-25 | 2021-02-23 |  |  | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 402867 | Work Order Description - 402867 - CM | CM | 1 | 19074 | WPLAN | NORM-OPS | 2019-02-26 | 2020-02-25 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | CONSTRUCTION | 70
2019-03-31 | 402879 | Work Order Description - 402879 - PM | PM | 4 | 670506 | SCHD | NORM-OPS | 2019-03-06 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 402881 | Work Order Description - 402881 - PM | PM | 4 | 670506 | SCHD | NORM-OPS | 2019-03-06 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 402883 | Work Order Description - 402883 - PM | PM | 4 | 375761 | SCHD | NORM-OPS | 2019-03-06 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 402885 | Work Order Description - 402885 - PM | PM | 4 | 375764 | SCHD | NORM-OPS | 2019-03-06 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 402887 | Work Order Description - 402887 - PM | PM | 4 | 375764 | SCHD | NORM-OPS | 2019-03-06 | 2019-06-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 402889 | Work Order Description - 402889 - PM | PM | 4 | 375764 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 402891 | Work Order Description - 402891 - PM | PM | 4 | 375764 | SCHD | NORM-OPS | 2019-03-06 | 2019-05-02 | 2019-04-14 | 2019-04-14 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 402893 | Work Order Description - 402893 - PM | PM | 4 | 375764 | SCHD | NORM-OPS | 2019-03-06 | 2019-06-01 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 402895 | Work Order Description - 402895 - PM | PM | 4 | 375764 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 402907 | Work Order Description - 402907 - CM | CM | 1 | 568106 | SCHD | EQUIP-ISOL | 2019-03-29 | 2021-02-23 | 2021-01-11 | 2021-01-11 | 4 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 402919 | Work Order Description - 402919 - CM | CM | 4 | 570144 | WPLAN | NORM-OPS | 2019-02-26 | 2020-02-25 | 2019-04-20 | 2019-04-20 | 3 | INTEGRITY | CONSTRUCTION | 98
2019-03-31 | 402925 | Work Order Description - 402925 - CM | CM | 4 | 266246 | WPLAN | EQUIP-ISOL | 2019-03-06 | 2020-02-25 | 2020-02-24 | 2020-02-25 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 402932 | Work Order Description - 402932 - BR | BR | 4 | 481543 | SCHD | NORM-OPS | 2019-02-26 | 2021-02-23 | 2021-01-11 | 2021-01-11 | 4 | OPERATIONS | INSPECTION | 22
2019-03-31 | 402939 | Work Order Description - 402939 - BR | BR | 1 | 551165 | WPLAN | EQUIP-ISOL | 2019-02-28 | 2021-02-23 | 2021-01-11 | 2021-01-11 | 4 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 402947 | Work Order Description - 402947 - BR | BR | 1 | 551165 | WPLAN | EQUIP-ISOL | 2019-02-28 | 2021-02-23 | 2021-01-11 | 2021-01-11 | 4 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 402952 | Work Order Description - 402952 - BR | BR | 1 | 551165 | WPLAN | EQUIP-ISOL | 2019-02-28 | 2021-02-23 | 2021-01-11 | 2021-01-11 | 4 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 402979 | Work Order Description - 402979 - PSCM | PSCM | 1 | 58336 | WPLAN | PACK-ISOL | 2019-02-27 | 2019-08-29 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 402981 | Work Order Description - 402981 - PSPM | PSPM | 1 | 659885 | SCHD | NORM-OPS | 2019-03-22 | 2019-07-01 | 2019-05-31 | 2019-06-02 | 1 | MAINTENANCE | ELECTRICAL | 68
2019-03-31 | 402983 | Work Order Description - 402983 - PSPM | PSPM | 1 | 659886 | SCHD | NORM-OPS | 2019-03-22 | 2019-07-01 | 2019-05-31 | 2019-06-01 | 1 | MAINTENANCE | ELECTRICAL | 42
2019-03-31 | 402985 | Work Order Description - 402985 - PSPM | PSPM | 1 | 527609 | SCHD | NORM-OPS | 2019-03-22 | 2019-07-01 | 2019-05-31 | 2019-06-05 | 1 | MAINTENANCE | ELECTRICAL | 160
2019-03-31 | 402987 | Work Order Description - 402987 - PSPM | PSPM | 1 | 659887 | SCHD | NORM-OPS | 2019-03-22 | 2019-07-01 | 2019-05-31 | 2019-06-07 | 1 | MAINTENANCE | ELECTRICAL | 159
2019-03-31 | 402989 | Work Order Description - 402989 - PSPM | PSPM | 1 | 527610 | SCHD | NORM-OPS | 2019-03-22 | 2019-07-01 | 2019-05-31 | 2019-06-01 | 1 | MAINTENANCE | ELECTRICAL | 44
2019-03-31 | 402991 | Work Order Description - 402991 - PSPM | PSPM | 1 | 659888 | SCHD | NORM-OPS | 2019-03-22 | 2019-07-01 | 2019-05-31 | 2019-06-03 | 1 | MAINTENANCE | ELECTRICAL | 81
2019-03-31 | 402993 | Work Order Description - 402993 - PSCM | PSCM | 1 | 308226 | WPLAN | PACK-ISOL | 2019-02-27 | 2019-08-29 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 403014 | Work Order Description - 403014 - PSCM | PSCM | 1 | 263093 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-03-31 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | ELECTRICAL | 63.5
2019-03-31 | 403041 | Work Order Description - 403041 - PM | PM | 4 | 650444 | WSCHD | NORM-OPS | 2019-02-26 | 2019-07-27 | 2019-06-14 | 2019-06-14 | 3 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 403043 | Work Order Description - 403043 - PM | PM | 4 | 540691 | WSCHD | NORM-OPS | 2019-02-26 | 2019-07-27 | 2019-06-14 | 2019-06-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 403045 | Work Order Description - 403045 - PM | PM | 4 | 481470 | WSCHD | NORM-OPS | 2019-02-26 | 2019-07-27 | 2019-06-14 | 2019-06-14 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 403047 | Work Order Description - 403047 - PSPM | PSPM | 1 | 650444 | WSCHD | NORM-OPS | 2019-02-26 | 2019-07-27 | 2019-06-26 | 2019-06-26 | 1 | OPERATIONS | OPERATIONS | 15
2019-03-31 | 403049 | Work Order Description - 403049 - PSPM | PSPM | 1 | 675036 | WSCHD | NORM-OPS | 2019-02-26 | 2019-07-27 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 403051 | Work Order Description - 403051 - PM | PM | 4 | 446840 | SCHD | PACK-ISOL | 2019-03-15 | 2019-07-27 | 2019-06-26 | 2019-06-26 | 1 | INTEGRITY | MECHANICAL | 16
2019-03-31 | 403057 | Work Order Description - 403057 - PSPM | PSPM | 1 | 460846 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-27 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 403059 | Work Order Description - 403059 - PM | PM | 4 | 320150 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-27 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 403061 | Work Order Description - 403061 - PM | PM | 4 | 460846 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-27 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 403065 | Work Order Description - 403065 - PM | PM | 4 | 99925 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-11-18 | 2019-06-26 | 2019-06-26 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 403067 | Work Order Description - 403067 - PM | PM | 4 | 106057 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-11-18 | 2019-06-26 | 2019-06-26 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 403069 | Work Order Description - 403069 - PM | PM | 4 | 527339 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-27 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 403071 | Work Order Description - 403071 - PSPM | PSPM | 1 | 449144 | SCHD | PACK-ISOL | 2019-03-22 | 2019-07-27 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 403073 | Work Order Description - 403073 - PSPM | PSPM | 1 | 659551 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-27 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 403075 | Work Order Description - 403075 - PSPM | PSPM | 1 | 227941 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-27 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 403077 | Work Order Description - 403077 - PM | PM | 4 | 449144 | WPLAN | PACK-ISOL | 2019-02-26 | 2019-07-27 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 403187 | Work Order Description - 403187 - BR | BR | 1 | 18736 | WSCHD | PACK-ISOL | 2019-03-01 | 2019-05-22 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 71
2019-03-31 | 403199 | Work Order Description - 403199 - CM | CM | 1 | 477682 | WPLAN | NORM-OPS | 2019-02-28 | 2019-05-24 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 403200 | Work Order Description - 403200 - CM | CM | 1 | 422376 | WSCHD | NORM-OPS | 2019-02-27 | 2021-02-25 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | ELECTRICAL | 16
2019-03-31 | 403201 | Work Order Description - 403201 - PSCM | PSCM | 1 | 422376 | WSCHD | NORM-OPS | 2019-03-08 | 2020-02-26 | 2019-08-27 | 2019-08-27 | 3 | MAINTENANCE | ELECTRICAL | 16
2019-03-31 | 403219 | Work Order Description - 403219 - CM | CM | 3 | 463217 | WSCHD | EQUIP-ISOL | 2019-03-29 | 2019-05-22 | 2019-04-09 | 2019-04-09 | 2 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 403248 | Work Order Description - 403248 - CM | CM | 4 | 338629 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2020-02-26 | 2019-04-19 | 2019-04-19 | 3 | DRILLING | DRILLING | 100
2019-03-31 | 403261 | Work Order Description - 403261 - CM | CM | 1 | 669632 | WSCHD | EQUIP-ISOL | 2019-03-29 | 2020-02-26 | 2019-10-26 | 2019-10-26 | 3 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 403280 | Work Order Description - 403280 - PSPM | PSPM | 1 | 25401 | SCHD | NORM-OPS | 2019-03-15 | 2019-05-31 | 2020-04-04 | 2020-04-04 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 403325 | Work Order Description - 403325 - CM | CM | 3 | 73706 | WPLAN | SYS-ISOL | 2019-03-02 | 2019-05-22 | 2019-05-04 | 2019-05-04 | 2 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 403350 | Work Order Description - 403350 - PSPM | PSPM | 1 | 399513 | WSCHD | PACK-ISOL | 2019-03-05 | 2019-05-02 | 2019-04-13 | 2019-04-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 403356 | Work Order Description - 403356 - BR | BR | 4 | 308541 | WSCHD | NORM-OPS | 2019-02-27 | 2021-02-25 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 403377 | Work Order Description - 403377 - PSPM | PSPM | 1 | 661008 | WSCHD | NORM-OPS | 2019-02-27 | 2019-07-28 | 2019-06-15 | 2019-06-15 | 1 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 403379 | Work Order Description - 403379 - PM | PM | 4 | 595820 | SCHD | EQUIP-ISOL | 2019-02-27 | 2019-07-28 | 2019-06-15 | 2019-06-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 403381 | Work Order Description - 403381 - PM | PM | 4 | 267676 | WSCHD | NORM-OPS | 2019-02-27 | 2019-07-28 | 2019-06-15 | 2019-06-15 | 2 | MAINTENANCE | SAFETY | 4
2019-03-31 | 403383 | Work Order Description - 403383 - PM | PM | 4 | 98009 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-28 | 2019-06-27 | 2019-06-27 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 403385 | Work Order Description - 403385 - PSPM | PSPM | 1 | 122684 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-28 | 2019-06-29 | 2019-06-29 | 1 | OPERATIONS | SAFETY | 5
2019-03-31 | 403387 | Work Order Description - 403387 - PM | PM | 4 | 601923 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-28 | 2019-06-27 | 2019-06-27 | 2 | OPERATIONS | OPERATIONS | 60
2019-03-31 | 403399 | Work Order Description - 403399 - PSPM | PSPM | 1 | 123510 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-28 | 2019-06-27 | 2019-06-27 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 403401 | Work Order Description - 403401 - PSPM | PSPM | 1 | 42961 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-28 | 2019-06-27 | 2019-06-27 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 403403 | Work Order Description - 403403 - PSPM | PSPM | 4 | 99434 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-28 | 2019-06-27 | 2019-06-28 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 403405 | Work Order Description - 403405 - PM | PM | 4 | 670506 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-28 | 2019-06-27 | 2019-06-30 | 3 | MAINTENANCE | MECHANICAL | 72
2019-03-31 | 403407 | Work Order Description - 403407 - PSPM | PSPM | 1 | 126920 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-28 | 2019-06-27 | 2019-06-27 | 1 | MAINTENANCE | ELECTRICAL | 1.5
2019-03-31 | 403409 | Work Order Description - 403409 - PM | PM | 4 | 126984 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-28 | 2019-06-27 | 2019-06-27 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 403503 | Work Order Description - 403503 - PM | PM | 3 | 248333 | WSCHD | PACK-ISOL | 2019-03-05 | 2019-08-03 | 2019-06-21 | 2019-06-21 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 403518 | Work Order Description - 403518 - CM | CM | 4 | 419553 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2020-02-27 | 2020-02-26 | 2020-02-26 | 3 | MAINTENANCE | DRILLING | 48
2019-03-31 | 403535 | Work Order Description - 403535 - CM | CM | 4 | 338651 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2020-02-27 | 2020-02-26 | 2020-02-26 | 3 | DRILLING | DRILLING | 44
2019-03-31 | 403536 | Work Order Description - 403536 - PRJ | PRJ | 3 | 74956 | SCHD | NORM-OPS | 2019-03-06 | 2021-02-25 | 2019-04-06 | 2019-04-07 | 4 | ENGINEERING | INSPECTION | 14
2019-03-31 | 403543 | Work Order Description - 403543 - CM | CM | 4 | 338659 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2020-02-27 | 2020-02-26 | 2020-02-26 | 3 | DRILLING | DRILLING | 68
2019-03-31 | 403544 | Work Order Description - 403544 - PRJ | PRJ | 4 | 403817 | WPLAN | NORM-OPS | 2019-03-02 | 2021-02-25 | 2019-03-30 | 2019-03-30 | 4 | ENGINEERING | CONSTRUCTION | 120
2019-03-31 | 403549 | Work Order Description - 403549 - CM | CM | 1 | 136847 | WSCHD | NORM-OPS | 2019-03-11 | 2020-02-27 | 2019-08-28 | 2019-08-28 | 3 | MAINTENANCE | ELECTRICAL | 62
2019-03-31 | 403557 | Work Order Description - 403557 - CM | CM | 4 | 383836 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-05-23 | 2019-04-10 | 2019-04-11 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 403558 | Work Order Description - 403558 - PRJ | PRJ | 3 | 126954 | SCHD | NORM-OPS | 2019-03-06 | 2021-02-25 | 2019-03-23 | 2019-04-13 | 4 | ENGINEERING | SERVICES | 300
2019-03-31 | 403564 | Work Order Description - 403564 - CM | CM | 4 | 570144 | WPLAN | NORM-OPS | 2019-03-01 | 2021-02-25 | 2020-02-26 | 2020-02-26 | 4 | INTEGRITY | CONSTRUCTION | 182
2019-03-31 | 403574 | Work Order Description - 403574 - CM | CM | 4 | 570144 | WPLAN | NORM-OPS | 2019-03-01 | 2021-02-25 | 2021-01-13 | 2021-01-13 | 4 | INTEGRITY | CONSTRUCTION | 42
2019-03-31 | 403586 | Work Order Description - 403586 - CM | CM | 4 | 155742 | WPLAN | NORM-OPS | 2019-02-28 | 2020-02-27 | 2019-08-28 | 2019-08-28 | 3 | INTEGRITY | CONSTRUCTION | 224
2019-03-31 | 403619 | Work Order Description - 403619 - PRJ | PRJ | 1 | 379257 | SCHD | TPS | 2019-03-06 | 2019-05-23 | 2019-07-13 | 2019-07-19 | 2 | ENGINEERING | INSPECTION | 111
2019-03-31 | 403633 | Work Order Description - 403633 - PSCM | PSCM | 1 | 556288 | WPLAN | SYS-ISOL | 2019-03-06 | 2019-05-23 | 2019-05-11 | 2019-05-12 | 2 | INTEGRITY | INSTRUMENTS | 12
2019-03-31 | 403656 | Work Order Description - 403656 - BR | BR | 3 | 308564 | WPLAN | EQUIP-ISOL | 2019-02-28 | 2021-02-25 | 2021-01-13 | 2021-01-13 | 4 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 403681 | Work Order Description - 403681 - BR | BR | 4 | 51659 | WSCHD | NORM-OPS | 2019-03-04 | 2021-02-25 | 2021-01-13 | 2021-01-13 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 403687 | Work Order Description - 403687 - CM | CM | 4 | 570144 | WPLAN | NORM-OPS | 2019-03-01 | 2020-02-27 | 2020-02-26 | 2020-02-26 | 3 | INTEGRITY | CONSTRUCTION | 56
2019-03-31 | 403691 | Work Order Description - 403691 - CM | CM | 4 | 670468 | SCHD | PACK-ISOL | 2019-03-26 | 2019-03-28 | 2019-03-09 | 2019-03-22 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 403769 | Work Order Description - 403769 - PM | PM | 4 | 51202 | WSCHD | NORM-OPS | 2019-02-28 | 2019-07-29 | 2019-06-16 | 2019-06-16 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 403771 | Work Order Description - 403771 - PSPM | PSPM | 1 | 580769 | WSCHD | NORM-OPS | 2019-02-28 | 2019-07-29 | 2019-06-28 | 2019-06-28 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 403773 | Work Order Description - 403773 - PSPM | PSPM | 1 | 546068 | WSCHD | NORM-OPS | 2019-03-05 | 2019-07-29 | 2019-06-16 | 2019-06-16 | 1 | MAINTENANCE | SERVICES | 10
2019-03-31 | 403775 | Work Order Description - 403775 - PM | PM | 2 | 363762 | WSCHD | NORM-OPS | 2019-03-05 | 2019-07-29 | 2019-06-16 | 2019-06-16 | 2 | MAINTENANCE | MECHANICAL | 3.5
2019-03-31 | 403777 | Work Order Description - 403777 - PM | PM | 4 | 54763 | WSCHD | PACK-ISOL | 2019-03-05 | 2019-07-29 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 403779 | Work Order Description - 403779 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-29 | 2019-06-28 | 2019-06-28 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 403781 | Work Order Description - 403781 - PSPM | PSPM | 1 | 216958 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-29 | 2019-07-13 | 2019-07-13 | 1 | OPERATIONS | SAFETY | 6
2019-03-31 | 403783 | Work Order Description - 403783 - PSPM | PSPM | 1 | 632640 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-29 | 2019-07-20 | 2019-07-20 | 1 | OPERATIONS | SAFETY | 6
2019-03-31 | 403785 | Work Order Description - 403785 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-29 | 2019-06-28 | 2019-06-28 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 403787 | Work Order Description - 403787 - PSPM | PSPM | 1 | 583857 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-29 | 2019-07-13 | 2019-07-13 | 1 | OPERATIONS | SAFETY | 7
2019-03-31 | 403789 | Work Order Description - 403789 - PM | PM | 4 | 122684 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-29 | 2019-07-20 | 2019-07-20 | 3 | OPERATIONS | SAFETY | 2
2019-03-31 | 403791 | Work Order Description - 403791 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-29 | 2019-06-28 | 2019-06-28 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 403793 | Work Order Description - 403793 - PSPM | PSPM | 1 | 555932 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-29 | 2019-06-28 | 2019-06-28 | 1 | OPERATIONS | OPERATIONS | 16
2019-03-31 | 403795 | Work Order Description - 403795 - PM | PM | 4 | 491877 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-29 | 2019-06-28 | 2019-06-28 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 403801 | Work Order Description - 403801 - PSPM | PSPM | 1 | 663164 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-29 | 2019-06-28 | 2019-06-28 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 403803 | Work Order Description - 403803 - PM | PM | 4 | 527749 | SCHD | NORM-OPS | 2019-03-18 | 2019-07-29 | 2019-06-28 | 2019-06-28 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 403805 | Work Order Description - 403805 - PSPM | PSPM | 1 | 450984 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-29 | 2019-06-28 | 2019-06-28 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 403807 | Work Order Description - 403807 - PSPM | PSPM | 1 | 238048 | SCHD | NORM-OPS | 2019-03-29 | 2019-07-29 | 2019-06-28 | 2019-06-28 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 403809 | Work Order Description - 403809 - PM | PM | 3 | 375585 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-29 | 2019-06-28 | 2019-06-28 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 403811 | Work Order Description - 403811 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-29 | 2019-06-28 | 2019-06-28 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 403816 | Work Order Description - 403816 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-29 | 2019-06-28 | 2019-06-28 | 3 | MAINTENANCE | INSTRUMENTS | 0.5
2019-03-31 | 403819 | Work Order Description - 403819 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-29 | 2019-06-28 | 2019-06-30 | 3 | MAINTENANCE | MEDIC | 21
2019-03-31 | 404008 | Work Order Description - 404008 - CM | CM | 3 | 500981 | WPLAN | NORM-OPS | 2019-03-16 | 2021-02-26 | 2021-01-14 | 2021-01-20 | 4 | INTEGRITY | MECHANICAL | 48
2019-03-31 | 404030 | Work Order Description - 404030 - PSPM | PSPM | 1 | 528193 | SCHD | NORM-OPS | 2019-03-18 | 2019-10-09 | 2019-09-08 | 2019-09-22 | 2 | INTEGRITY | INSPECTION | 200
2019-03-31 | 404037 | Work Order Description - 404037 - BR | BR | 4 | 479302 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-05-26 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 404041 | Work Order Description - 404041 - BR | BR | 3 | 668630 | WPLAN | TPS | 2019-03-05 | 2019-05-24 | 2019-07-13 | 2019-07-15 | 2 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 404045 | Work Order Description - 404045 - CM | CM | 4 | 547276 | WSCHD | NORM-OPS | 2019-03-03 | 2021-02-26 | 2021-01-14 | 2021-01-14 | 4 | OPERATIONS | MECHANICAL | 16
2019-03-31 | 404049 | Work Order Description - 404049 - CM | CM | 1 | 408063 | WSCHD | NORM-OPS | 2019-02-28 | 2020-03-06 |  |  | 3 | MAINTENANCE | ELECTRICAL | 114
2019-03-31 | 404052 | Work Order Description - 404052 - BR | BR | 3 | 668632 | SCHD | TPS | 2019-03-06 | 2019-05-24 | 2019-07-13 | 2019-07-15 | 2 | MAINTENANCE | INSTRUMENTS | 22
2019-03-31 | 404057 | Work Order Description - 404057 - BR | BR | 3 | 393104 | SCHD | TPS | 2019-03-06 | 2019-08-30 | 2019-07-13 | 2019-07-15 | 3 | MAINTENANCE | INSTRUMENTS | 22
2019-03-31 | 404062 | Work Order Description - 404062 - BR | BR | 3 | 668648 | WPLAN | TPS | 2019-03-05 | 2019-08-30 | 2019-07-13 | 2019-07-15 | 3 | MAINTENANCE | INSTRUMENTS | 22
2019-03-31 | 404066 | Work Order Description - 404066 - BR | BR | 3 | 97843 | WPLAN | TPS | 2019-03-05 | 2019-08-30 | 2019-07-13 | 2019-07-15 | 3 | MAINTENANCE | INSTRUMENTS | 17
2019-03-31 | 404070 | Work Order Description - 404070 - BR | BR | 3 | 393105 | WPLAN | TPS | 2019-03-05 | 2019-08-30 | 2019-07-13 | 2019-07-15 | 3 | MAINTENANCE | INSTRUMENTS | 22
2019-03-31 | 404077 | Work Order Description - 404077 - PRJ | PRJ | 3 | 375637 | SCHD | NORM-OPS | 2019-03-26 | 2019-05-24 | 2019-03-10 | 2019-04-08 | 2 | MAINTENANCE | ELECTRICAL | 240
2019-03-31 | 404087 | Work Order Description - 404087 - PRJ | PRJ | 3 | 375932 | SCHD | NORM-OPS | 2019-03-06 | 2020-02-28 | 2019-04-23 | 2019-04-25 | 3 | ENGINEERING | CONSTRUCTION | 1
2019-03-31 | 404121 | Work Order Description - 404121 - CM | CM | 4 | 570144 | WPLAN | NORM-OPS | 2019-03-01 | 2020-02-28 | 2019-08-29 | 2019-08-29 | 3 | INTEGRITY | CONSTRUCTION | 182
2019-03-31 | 404125 | Work Order Description - 404125 - CM | CM | 4 | 570144 | WPLAN | NORM-OPS | 2019-03-01 | 2021-02-26 | 2021-01-14 | 2021-01-14 | 4 | INTEGRITY | FABRIC | 140
2019-03-31 | 404149 | Work Order Description - 404149 - CM | CM | 4 | 570144 | WPLAN | NORM-OPS | 2019-03-01 | 2020-02-28 | 2019-08-29 | 2019-08-29 | 3 | INTEGRITY | CONSTRUCTION | 154
2019-03-31 | 404173 | Work Order Description - 404173 - CM | CM | 4 | 570144 | WPLAN | NORM-OPS | 2019-03-01 | 2020-02-28 | 2020-02-26 | 2020-02-26 | 3 | INTEGRITY | CONSTRUCTION | 28
2019-03-31 | 404181 | Work Order Description - 404181 - CM | CM | 4 | 570144 | WPLAN | NORM-OPS | 2019-03-01 | 2021-02-26 | 2020-02-26 | 2020-02-26 | 4 | INTEGRITY | CONSTRUCTION | 28
2019-03-31 | 404183 | Work Order Description - 404183 - BR | BR | 4 | 247360 | WPLAN | NORM-OPS | 2019-03-01 | 2021-02-26 | 2020-02-26 | 2020-02-26 | 4 | INTEGRITY | CONSTRUCTION | 6
2019-03-31 | 404185 | Work Order Description - 404185 - CM | CM | 1 | 570144 | WPLAN | NORM-OPS | 2019-03-01 | 2019-08-30 | 2019-05-30 | 2019-05-30 | 3 | INTEGRITY | CONSTRUCTION | 140
2019-03-31 | 404198 | Work Order Description - 404198 - CM | CM | 4 | 527132 | SCHD | NORM-OPS | 2019-03-06 | 2020-03-01 | 2019-08-31 | 2019-09-01 | 3 | OPERATIONS | MECHANICAL | 4
2019-03-31 | 404205 | Work Order Description - 404205 - CM | CM | 4 | 227703 | SCHD | NORM-OPS | 2019-03-06 | 2020-03-01 | 2019-08-31 | 2019-09-01 | 3 | OPERATIONS | MECHANICAL | 4
2019-03-31 | 404206 | Work Order Description - 404206 - CM | CM | 4 | 450899 | SCHD | NORM-OPS | 2019-03-06 | 2020-03-01 | 2019-08-31 | 2019-09-01 | 3 | OPERATIONS | MECHANICAL | 4
2019-03-31 | 404207 | Work Order Description - 404207 - CM | CM | 4 | 659308 | SCHD | NORM-OPS | 2019-03-06 | 2020-03-01 | 2019-08-31 | 2019-09-01 | 3 | OPERATIONS | MECHANICAL | 4
2019-03-31 | 404213 | Work Order Description - 404213 - CM | CM | 4 | 570144 | WPLAN | NORM-OPS | 2019-03-01 | 2019-08-30 | 2019-05-30 | 2019-05-30 | 3 | INTEGRITY | CONSTRUCTION | 280
2019-03-31 | 404221 | Work Order Description - 404221 - CM | CM | 4 | 570144 | WPLAN | NORM-OPS | 2019-03-01 | 2020-02-28 | 2019-08-29 | 2019-08-29 | 3 | INTEGRITY | CONSTRUCTION | 140
2019-03-31 | 404235 | Work Order Description - 404235 - BR | BR | 1 | 26888 | WPLAN | NORM-OPS | 2019-03-02 | 2019-05-26 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 404239 | Work Order Description - 404239 - PSPM | PSPM | 1 | 321203 | WSCHD | NORM-OPS | 2019-03-01 | 2019-07-30 | 2019-06-17 | 2019-06-17 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 404241 | Work Order Description - 404241 - PSPM | PSPM | 1 | 321218 | WSCHD | NORM-OPS | 2019-03-01 | 2019-07-30 | 2019-06-17 | 2019-06-17 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 404243 | Work Order Description - 404243 - PM | PM | 4 | 666204 | WSCHD | NORM-OPS | 2019-03-01 | 2019-07-30 | 2019-06-17 | 2019-06-17 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 404245 | Work Order Description - 404245 - PM | PM | 4 | 294916 | WSCHD | NORM-OPS | 2019-03-01 | 2019-07-30 | 2019-06-17 | 2019-06-17 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 404247 | Work Order Description - 404247 - PSPM | PSPM | 1 | 29816 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-30 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 404249 | Work Order Description - 404249 - PSPM | PSPM | 1 | 304040 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-30 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 404251 | Work Order Description - 404251 - PSPM | PSPM | 1 | 303774 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-30 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 404253 | Work Order Description - 404253 - PSPM | PSPM | 1 | 535485 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-30 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 404255 | Work Order Description - 404255 - PSPM | PSPM | 1 | 499149 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-30 | 2019-06-29 | 2019-06-29 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 404257 | Work Order Description - 404257 - PSPM | PSPM | 1 | 320575 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-30 | 2019-06-29 | 2019-06-29 | 1 | OPERATIONS | OPERATIONS | 12
2019-03-31 | 404259 | Work Order Description - 404259 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-30 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 404261 | Work Order Description - 404261 - PM | PM | 4 | 631597 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-30 | 2019-06-29 | 2019-06-29 | 2 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 404263 | Work Order Description - 404263 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-30 | 2019-06-29 | 2019-06-29 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 404265 | Work Order Description - 404265 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-30 | 2019-06-29 | 2019-06-29 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 404267 | Work Order Description - 404267 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-30 | 2019-06-29 | 2019-06-29 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 404322 | Work Order Description - 404322 - PRJ | PRJ | 1 | 127636 | SCHD | NORM-OPS | 2019-03-01 | 2021-02-27 | 2019-03-14 | 2019-04-23 | 4 | ENGINEERING | OPERATIONS | 340
2019-03-31 | 404405 | Work Order Description - 404405 - PSCM | PSCM | 1 | 138633 | WPLAN | EQUIP-ISOL | 2019-03-01 | 2020-02-29 | 2020-02-28 | 2020-02-28 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 404420 | Work Order Description - 404420 - CM | CM | 4 | 570144 | WPLAN | NORM-OPS | 2019-03-01 | 2020-02-29 | 2020-02-28 | 2020-02-28 | 3 | INTEGRITY | CONSTRUCTION | 140
2019-03-31 | 404432 | Work Order Description - 404432 - CM | CM | 4 | 411258 | WPLAN | NORM-OPS | 2019-03-04 | 2020-02-29 | 2019-08-30 | 2019-08-30 | 3 | INTEGRITY | SERVICES | 4
2019-03-31 | 404435 | Work Order Description - 404435 - BR | BR | 1 | 99232 | SCHD | EQUIP-ISOL | 2019-03-06 | 2021-02-27 | 2021-01-15 | 2021-01-15 | 4 | MAINTENANCE | SERVICES | 10
2019-03-31 | 404436 | Work Order Description - 404436 - BR | BR | 3 | 540309 | WPLAN | NORM-OPS | 2019-03-02 | 2021-02-27 | 2021-01-15 | 2021-01-15 | 4 | MAINTENANCE | OPERATIONS | 1
2019-03-31 | 404453 | Work Order Description - 404453 - BR | BR | 4 | 100389 | WPLAN | EQUIP-ISOL | 2019-03-05 | 2021-02-27 | 2021-01-15 | 2021-01-19 | 4 | MAINTENANCE | ELECTRICAL | 30
2019-03-31 | 404457 | Work Order Description - 404457 - CM | CM | 1 | 670509 | WSCHD | EQUIP-ISOL | 2019-03-29 | 2019-05-25 | 2019-04-12 | 2019-04-13 | 2 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 404458 | Work Order Description - 404458 - CM | CM | 1 | 470026 | WPLAN | EQUIP-ISOL | 2019-03-02 | 2021-02-27 | 2021-01-15 | 2021-01-15 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 404459 | Work Order Description - 404459 - CM | CM | 1 | 504004 | WPLAN | EQUIP-ISOL | 2019-03-02 | 2020-03-01 | 2019-08-31 | 2019-08-31 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 404460 | Work Order Description - 404460 - CM | CM | 1 | 469999 | WPLAN | EQUIP-ISOL | 2019-03-02 | 2020-03-01 | 2019-08-31 | 2019-08-31 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 404472 | Work Order Description - 404472 - CM | CM | 1 | 482308 | WMATL | NORM-OPS | 2019-03-15 | 2020-02-29 | 2019-08-30 | 2019-08-30 | 3 | MAINTENANCE | MECHANICAL | 44
2019-03-31 | 404478 | Work Order Description - 404478 - BR | BR | 3 | 501450 | WPLAN | EQUIP-ISOL | 2019-03-02 | 2019-07-20 | 2019-01-20 | 2019-01-20 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 404483 | Work Order Description - 404483 - PSPM | PSPM | 1 | 402622 | SCHD | SUBSYS-ISOL | 2019-03-12 | 2019-10-31 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 20
2019-03-31 | 404486 | Work Order Description - 404486 - BR | BR | 1 | 363050 | WMATL | NORM-OPS | 2019-03-11 | 2021-02-27 | 2021-01-15 | 2021-01-15 | 4 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 404496 | Work Order Description - 404496 - BR | BR | 4 | 81104 | WPLAN | EQUIP-ISOL | 2019-03-02 | 2019-08-31 | 2019-05-31 | 2019-05-31 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 404500 | Work Order Description - 404500 - CM | CM | 1 | 458752 | WPLAN | EQUIP-ISOL | 2019-03-02 | 2019-08-31 | 2019-05-31 | 2019-05-31 | 3 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 404503 | Work Order Description - 404503 - CM | CM | 3 | 375637 | WPLAN | PACK-ISOL | 2019-03-05 | 2019-05-25 | 2019-04-26 | 2019-05-04 | 2 | MAINTENANCE | ELECTRICAL | 15
2019-03-31 | 404505 | Work Order Description - 404505 - CM | CM | 4 | 570144 | WSCHD | NORM-OPS | 2019-03-01 | 2019-08-31 | 2019-05-31 | 2019-05-31 | 3 | INTEGRITY | CONSTRUCTION | 84
2019-03-31 | 404506 | Work Order Description - 404506 - BR | BR | 4 | 155742 | WPLAN | NORM-OPS | 2019-03-04 | 2020-02-29 | 2019-08-30 | 2019-08-30 | 3 | INTEGRITY | FABRIC | 65
2019-03-31 | 404518 | Work Order Description - 404518 - BR | BR | 2 | 387529 | WPLAN | NORM-OPS | 2019-03-05 | 2021-02-27 | 2021-01-16 | 2021-01-16 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 404531 | Work Order Description - 404531 - CM | CM | 1 | 447441 | WPLAN | NORM-OPS | 2019-03-02 | 2019-08-31 | 2019-06-01 | 2019-06-04 | 3 | MAINTENANCE | CONSTRUCTION | 24
2019-03-31 | 404541 | Work Order Description - 404541 - BR | BR | 4 | 475157 | WPLAN | NORM-OPS | 2019-03-02 | 2021-02-27 | 2021-01-15 | 2021-01-15 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 404548 | Work Order Description - 404548 - PSPM | PSPM | 1 | 669989 | SCHD | PACK-ISOL | 2019-03-22 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 404550 | Work Order Description - 404550 - PSPM | PSPM | 1 | 185409 | SCHD | PACK-ISOL | 2019-03-22 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 404558 | Work Order Description - 404558 - BR | BR | 2 | 262484 | WPLAN | EQUIP-ISOL | 2019-03-02 | 2021-02-27 | 2021-01-16 | 2021-01-16 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 404559 | Work Order Description - 404559 - BR | BR | 3 | 321506 | WPLAN | SYS-ISOL | 2019-03-03 | 2019-05-25 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404562 | Work Order Description - 404562 - PM | PM | 2 | 572308 | WSCHD | NORM-OPS | 2019-03-02 | 2019-07-31 | 2019-06-18 | 2019-06-18 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 404564 | Work Order Description - 404564 - PM | PM | 4 | 580762 | WSCHD | NORM-OPS | 2019-03-02 | 2019-07-31 | 2019-06-18 | 2019-06-18 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 404566 | Work Order Description - 404566 - PM | PM | 4 | 188855 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404568 | Work Order Description - 404568 - PM | PM | 4 | 188858 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404570 | Work Order Description - 404570 - PM | PM | 4 | 309678 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404572 | Work Order Description - 404572 - PSPM | PSPM | 1 | 502744 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | SAFETY | 10
2019-03-31 | 404574 | Work Order Description - 404574 - PM | PM | 4 | 309671 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404576 | Work Order Description - 404576 - PM | PM | 4 | 498446 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404578 | Work Order Description - 404578 - PM | PM | 4 | 188835 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404580 | Work Order Description - 404580 - PM | PM | 4 | 188836 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404582 | Work Order Description - 404582 - PM | PM | 4 | 498447 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404584 | Work Order Description - 404584 - PM | PM | 4 | 498497 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 404586 | Work Order Description - 404586 - PM | PM | 4 | 188840 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404588 | Work Order Description - 404588 - PM | PM | 4 | 188839 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404590 | Work Order Description - 404590 - PM | PM | 4 | 498448 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404592 | Work Order Description - 404592 - PM | PM | 4 | 188841 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404594 | Work Order Description - 404594 - PM | PM | 4 | 188842 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404596 | Work Order Description - 404596 - PM | PM | 4 | 324747 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404598 | Work Order Description - 404598 - PM | PM | 4 | 324748 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404600 | Work Order Description - 404600 - PM | PM | 4 | 498445 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404602 | Work Order Description - 404602 - PM | PM | 4 | 188837 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404604 | Work Order Description - 404604 - PM | PM | 4 | 324782 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404606 | Work Order Description - 404606 - PM | PM | 4 | 498461 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404608 | Work Order Description - 404608 - PM | PM | 4 | 324783 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404610 | Work Order Description - 404610 - PM | PM | 4 | 498462 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404612 | Work Order Description - 404612 - PM | PM | 4 | 309706 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404614 | Work Order Description - 404614 - PM | PM | 4 | 309707 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404616 | Work Order Description - 404616 - PM | PM | 4 | 324784 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404618 | Work Order Description - 404618 - PM | PM | 4 | 324805 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404620 | Work Order Description - 404620 - PM | PM | 4 | 498466 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404622 | Work Order Description - 404622 - PM | PM | 4 | 309736 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-08-03 | 2019-08-03 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404624 | Work Order Description - 404624 - PM | PM | 4 | 324806 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404626 | Work Order Description - 404626 - PM | PM | 4 | 309708 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404628 | Work Order Description - 404628 - PM | PM | 4 | 188856 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404630 | Work Order Description - 404630 - PM | PM | 4 | 309709 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404632 | Work Order Description - 404632 - PM | PM | 4 | 188853 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404634 | Work Order Description - 404634 - PM | PM | 4 | 324807 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404636 | Work Order Description - 404636 - PM | PM | 4 | 498463 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404638 | Work Order Description - 404638 - PM | PM | 4 | 309711 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404640 | Work Order Description - 404640 - PM | PM | 4 | 324808 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404642 | Work Order Description - 404642 - PM | PM | 4 | 324809 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404644 | Work Order Description - 404644 - PM | PM | 4 | 324810 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404646 | Work Order Description - 404646 - PM | PM | 4 | 498465 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404648 | Work Order Description - 404648 - PM | PM | 4 | 309712 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404650 | Work Order Description - 404650 - PM | PM | 4 | 309713 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404652 | Work Order Description - 404652 - PM | PM | 4 | 188857 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404654 | Work Order Description - 404654 - PM | PM | 4 | 498464 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404656 | Work Order Description - 404656 - PM | PM | 4 | 188855 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404658 | Work Order Description - 404658 - PM | PM | 4 | 324811 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404660 | Work Order Description - 404660 - PM | PM | 4 | 324812 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404662 | Work Order Description - 404662 - PM | PM | 4 | 309735 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404664 | Work Order Description - 404664 - PM | PM | 4 | 309637 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404666 | Work Order Description - 404666 - PM | PM | 4 | 188826 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404668 | Work Order Description - 404668 - PM | PM | 4 | 324741 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404670 | Work Order Description - 404670 - PM | PM | 4 | 309704 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404672 | Work Order Description - 404672 - PM | PM | 4 | 309705 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404674 | Work Order Description - 404674 - PM | PM | 4 | 324781 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404676 | Work Order Description - 404676 - PM | PM | 4 | 262537 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 404678 | Work Order Description - 404678 - PM | PM | 4 | 25182 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 404680 | Work Order Description - 404680 - PM | PM | 4 | 310099 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 404682 | Work Order Description - 404682 - PM | PM | 4 | 313220 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 404684 | Work Order Description - 404684 - PM | PM | 4 | 188825 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404686 | Work Order Description - 404686 - PM | PM | 4 | 309636 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404688 | Work Order Description - 404688 - PM | PM | 4 | 324721 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404690 | Work Order Description - 404690 - PM | PM | 4 | 324749 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404692 | Work Order Description - 404692 - PM | PM | 4 | 498449 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404694 | Work Order Description - 404694 - PM | PM | 4 | 25247 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 404696 | Work Order Description - 404696 - PM | PM | 4 | 254649 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404698 | Work Order Description - 404698 - PM | PM | 2 | 324833 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404700 | Work Order Description - 404700 - PM | PM | 2 | 324834 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404702 | Work Order Description - 404702 - PM | PM | 4 | 324814 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404704 | Work Order Description - 404704 - PM | PM | 4 | 309638 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404706 | Work Order Description - 404706 - PM | PM | 4 | 309639 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404708 | Work Order Description - 404708 - PM | PM | 4 | 188843 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 404710 | Work Order Description - 404710 - PSPM | PSPM | 1 | 555259 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | OPERATIONS | OPERATIONS | 12
2019-03-31 | 404712 | Work Order Description - 404712 - PSPM | PSPM | 1 | 447441 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 404714 | Work Order Description - 404714 - PM | PM | 1 | 446516 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 404716 | Work Order Description - 404716 - PSPM | PSPM | 1 | 320534 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 404718 | Work Order Description - 404718 - PSPM | PSPM | 1 | 320534 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 404720 | Work Order Description - 404720 - PSPM | PSPM | 1 | 320534 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 404722 | Work Order Description - 404722 - PSPM | PSPM | 1 | 487482 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 404724 | Work Order Description - 404724 - PSPM | PSPM | 1 | 479577 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | INTEGRITY | INSPECTION | 105
2019-03-31 | 404728 | Work Order Description - 404728 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | SAFETY | 7
2019-03-31 | 404730 | Work Order Description - 404730 - PM | PM | 4 | 378688 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 404732 | Work Order Description - 404732 - PM | PM | 4 | 659554 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 404734 | Work Order Description - 404734 - PM | PM | 4 | 450989 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 404736 | Work Order Description - 404736 - PM | PM | 4 | 450988 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 404738 | Work Order Description - 404738 - PSPM | PSPM | 1 | 396803 | SCHD | NORM-OPS | 2019-03-18 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | SAFETY | 4
2019-03-31 | 404740 | Work Order Description - 404740 - PM | PM | 4 | 659501 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-07-02 | 1 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 404742 | Work Order Description - 404742 - PM | PM | 4 | 450974 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-07-02 | 1 | MAINTENANCE | ELECTRICAL | 16
2019-03-31 | 404744 | Work Order Description - 404744 - PSPM | PSPM | 1 | 227935 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 404746 | Work Order Description - 404746 - PSPM | PSPM | 1 | 227935 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 404748 | Work Order Description - 404748 - PSPM | PSPM | 1 | 227935 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 404750 | Work Order Description - 404750 - PSPM | PSPM | 1 | 80727 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 404752 | Work Order Description - 404752 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 404754 | Work Order Description - 404754 - PSPM | PSPM | 1 | 669726 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 404756 | Work Order Description - 404756 - PSPM | PSPM | 1 | 528118 | SCHD | PACK-ISOL | 2019-03-18 | 2019-07-31 | 2019-06-30 | 2019-07-03 | 1 | OPERATIONS | SERVICES | 32
2019-03-31 | 404758 | Work Order Description - 404758 - PSPM | PSPM | 1 | 375803 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 404760 | Work Order Description - 404760 - PSPM | PSPM | 1 | 375805 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 404762 | Work Order Description - 404762 - PSPM | PSPM | 1 | 449175 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 404764 | Work Order Description - 404764 - PSPM | PSPM | 1 | 669725 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-04-28 | 2019-04-28 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 404766 | Work Order Description - 404766 - PSPM | PSPM | 1 | 128836 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 404768 | Work Order Description - 404768 - PSPM | PSPM | 1 | 227935 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 404770 | Work Order Description - 404770 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 404772 | Work Order Description - 404772 - PM | PM | 4 | 95325 | SCHD | NORM-OPS | 2019-03-06 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 404972 | Work Order Description - 404972 - CM | CM | 1 | 422376 | WSCHD | NORM-OPS | 2019-03-08 | 2020-03-01 | 2020-02-29 | 2020-02-29 | 3 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 404994 | Work Order Description - 404994 - CM | CM | 4 | 361671 | WSCHD | NORM-OPS | 2019-03-19 | 2021-02-28 | 2021-01-16 | 2021-01-16 | 4 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 404997 | Work Order Description - 404997 - BR | BR | 3 | 674095 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-04-03 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 405006 | Work Order Description - 405006 - BR | BR | 1 | 18762 | WPLAN | PACK-ISOL | 2019-03-03 | 2019-05-26 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 405017 | Work Order Description - 405017 - BR | BR | 3 | 98444 | SCHD | EQUIP-ISOL | 2019-03-06 | 2021-02-28 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 405033 | Work Order Description - 405033 - CM | CM | 3 | 469472 | WSCHD | EQUIP-ISOL | 2019-03-02 | 2019-05-26 |  |  | 2 | MAINTENANCE | ELECTRICAL | 56
2019-03-31 | 405065 | Work Order Description - 405065 - PSPM | PSPM | 1 | 541315 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 405067 | Work Order Description - 405067 - PSPM | PSPM | 1 | 541315 | WSCHD | EQUIP-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 405069 | Work Order Description - 405069 - PSPM | PSPM | 1 | 541315 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 405071 | Work Order Description - 405071 - PSPM | PSPM | 1 | 356355 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 405073 | Work Order Description - 405073 - PSPM | PSPM | 1 | 18947 | WSCHD | SUBSYS-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 405075 | Work Order Description - 405075 - PSPM | PSPM | 1 | 531789 | WSCHD | SUBSYS-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 405077 | Work Order Description - 405077 - PSPM | PSPM | 1 | 671541 | WSCHD | SUBSYS-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 405079 | Work Order Description - 405079 - PSPM | PSPM | 1 | 18978 | WSCHD | SUBSYS-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 405081 | Work Order Description - 405081 - PSPM | PSPM | 1 | 481466 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 405083 | Work Order Description - 405083 - PM | PM | 4 | 314186 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405085 | Work Order Description - 405085 - PM | PM | 4 | 314186 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405087 | Work Order Description - 405087 - PM | PM | 4 | 531470 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-25 | 2019-07-28 | 2019-07-28 | 2 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 405089 | Work Order Description - 405089 - PM | PM | 4 | 18317 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405091 | Work Order Description - 405091 - PM | PM | 4 | 18316 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405093 | Work Order Description - 405093 - PM | PM | 4 | 666316 | WSCHD | EQUIP-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405095 | Work Order Description - 405095 - PM | PM | 4 | 417521 | WSCHD | EQUIP-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405097 | Work Order Description - 405097 - PM | PM | 4 | 50099 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 405099 | Work Order Description - 405099 - PM | PM | 4 | 50098 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 405101 | Work Order Description - 405101 - PM | PM | 4 | 411571 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405103 | Work Order Description - 405103 - PM | PM | 4 | 358159 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405105 | Work Order Description - 405105 - PSPM | PSPM | 1 | 273469 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 405107 | Work Order Description - 405107 - PM | PM | 4 | 540667 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 405109 | Work Order Description - 405109 - PM | PM | 4 | 678551 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 405111 | Work Order Description - 405111 - PSPM | PSPM | 1 | 408320 | WSCHD | PACK-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | SERVICES | 34
2019-03-31 | 405113 | Work Order Description - 405113 - PSPM | PSPM | 1 | 675037 | WSCHD | PACK-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 405115 | Work Order Description - 405115 - PSPM | PSPM | 1 | 361166 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | INTEGRITY | INSPECTION | 30
2019-03-31 | 405117 | Work Order Description - 405117 - PM | PM | 2 | 580380 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 405119 | Work Order Description - 405119 - PSPM | PSPM | 4 | 19079 | WPLAN | SUBSYS-ISOL | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | INTEGRITY | MECHANICAL | 12
2019-03-31 | 405121 | Work Order Description - 405121 - PSPM | PSPM | 1 | 247294 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | INTEGRITY | INSPECTION | 30
2019-03-31 | 405123 | Work Order Description - 405123 - PM | PM | 4 | 247217 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | INSPECTION | 30
2019-03-31 | 405125 | Work Order Description - 405125 - PM | PM | 4 | 247217 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | INSPECTION | 4
2019-03-31 | 405127 | Work Order Description - 405127 - PM | PM | 4 | 247217 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-04-14 | 2019-04-14 | 3 | INTEGRITY | INSPECTION | 30
2019-03-31 | 405129 | Work Order Description - 405129 - PM | PM | 4 | 247217 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-04-27 | 2019-04-27 | 3 | INTEGRITY | INSPECTION | 30
2019-03-31 | 405131 | Work Order Description - 405131 - PM | PM | 4 | 247296 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 405133 | Work Order Description - 405133 - PSPM | PSPM | 4 | 361166 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | INTEGRITY | INSPECTION | 210
2019-03-31 | 405135 | Work Order Description - 405135 - PSPM | PSPM | 4 | 247294 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | INTEGRITY | INSPECTION | 53
2019-03-31 | 405137 | Work Order Description - 405137 - PM | PM | 4 | 247294 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-04-27 | 2019-04-27 | 2 | INTEGRITY | INSPECTION | 53
2019-03-31 | 405139 | Work Order Description - 405139 - PSPM | PSPM | 1 | 422627 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 405141 | Work Order Description - 405141 - PM | PM | 4 | 469328 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 405143 | Work Order Description - 405143 - PM | PM | 2 | 530958 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 405145 | Work Order Description - 405145 - PM | PM | 4 | 469328 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 405147 | Work Order Description - 405147 - PM | PM | 2 | 530958 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 405149 | Work Order Description - 405149 - PSPM | PSPM | 1 | 671541 | WSCHD | PACK-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 405151 | Work Order Description - 405151 - PSPM | PSPM | 1 | 308463 | WSCHD | PACK-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 405153 | Work Order Description - 405153 - PSPM | PSPM | 1 | 308463 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 405155 | Work Order Description - 405155 - PSPM | PSPM | 1 | 671541 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 405157 | Work Order Description - 405157 - PM | PM | 4 | 363667 | WSCHD | EQUIP-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | INTEGRITY | MECHANICAL | 9
2019-03-31 | 405159 | Work Order Description - 405159 - PM | PM | 2 | 321199 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 405161 | Work Order Description - 405161 - PM | PM | 4 | 545152 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 405163 | Work Order Description - 405163 - PSPM | PSPM | 1 | 679745 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 405165 | Work Order Description - 405165 - PSPM | PSPM | 1 | 679720 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 38
2019-03-31 | 405167 | Work Order Description - 405167 - PSPM | PSPM | 1 | 674741 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 405169 | Work Order Description - 405169 - PSPM | PSPM | 1 | 308464 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 405171 | Work Order Description - 405171 - PM | PM | 4 | 248490 | WSCHD | EQUIP-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 405173 | Work Order Description - 405173 - PM | PM | 4 | 399968 | WSCHD | EQUIP-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 405175 | Work Order Description - 405175 - PM | PM | 4 | 261311 | WSCHD | EQUIP-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 405177 | Work Order Description - 405177 - PM | PM | 4 | 248492 | WSCHD | EQUIP-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 405179 | Work Order Description - 405179 - PSPM | PSPM | 1 | 681800 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 405181 | Work Order Description - 405181 - PSPM | PSPM | 1 | 595639 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 405183 | Work Order Description - 405183 - PSPM | PSPM | 1 | 18419 | WSCHD | PACK-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | INTEGRITY | INSPECTION | 6
2019-03-31 | 405185 | Work Order Description - 405185 - PM | PM | 4 | 53026 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-25 | 2019-07-28 | 2019-07-28 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 405187 | Work Order Description - 405187 - PSPM | PSPM | 1 | 360389 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 405189 | Work Order Description - 405189 - PM | PM | 4 | 409853 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-09-12 | 2019-08-06 | 2019-08-06 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 405191 | Work Order Description - 405191 - PM | PM | 4 | 360621 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-09-12 | 2019-08-06 | 2019-08-06 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 405193 | Work Order Description - 405193 - PM | PM | 4 | 480132 | WPLAN | EQUIP-ISOL | 2019-03-03 | 2019-08-25 | 2019-07-28 | 2019-07-28 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 405195 | Work Order Description - 405195 - PM | PM | 4 | 48608 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-25 | 2019-07-28 | 2019-07-28 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 405197 | Work Order Description - 405197 - PM | PM | 4 | 657197 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 405199 | Work Order Description - 405199 - PM | PM | 4 | 545951 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 405201 | Work Order Description - 405201 - PM | PM | 4 | 138016 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 405203 | Work Order Description - 405203 - PM | PM | 4 | 657423 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 405205 | Work Order Description - 405205 - PM | PM | 4 | 653261 | WSCHD | PACK-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 13
2019-03-31 | 405209 | Work Order Description - 405209 - PSPM | PSPM | 1 | 470877 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 405211 | Work Order Description - 405211 - PSPM | PSPM | 1 | 273468 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 405213 | Work Order Description - 405213 - PSPM | PSPM | 1 | 470878 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 405215 | Work Order Description - 405215 - PSPM | PSPM | 1 | 480207 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 405217 | Work Order Description - 405217 - PSPM | PSPM | 1 | 292669 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | SAFETY | 10
2019-03-31 | 405219 | Work Order Description - 405219 - PM | PM | 4 | 457525 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 405221 | Work Order Description - 405221 - PSPM | PSPM | 1 | 538631 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 405223 | Work Order Description - 405223 - PSPM | PSPM | 1 | 273470 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 405225 | Work Order Description - 405225 - PSPM | PSPM | 1 | 538632 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 405227 | Work Order Description - 405227 - PM | PM | 4 | 535884 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | OPERATIONS | MEDIC | 3
2019-03-31 | 405229 | Work Order Description - 405229 - PM | PM | 4 | 676326 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | OPERATIONS | MEDIC | 2
2019-03-31 | 405231 | Work Order Description - 405231 - PM | PM | 4 | 204614 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | INTEGRITY | INSPECTION | 12
2019-03-31 | 405233 | Work Order Description - 405233 - PM | PM | 4 | 652578 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-12-11 | 2019-09-20 | 2019-09-20 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 405235 | Work Order Description - 405235 - PM | PM | 4 | 138185 | WSCHD | EQUIP-ISOL | 2019-03-03 | 2019-12-11 | 2019-09-20 | 2019-09-20 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 405237 | Work Order Description - 405237 - PSPM | PSPM | 1 | 570144 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 405239 | Work Order Description - 405239 - PSPM | PSPM | 1 | 399672 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405241 | Work Order Description - 405241 - PSPM | PSPM | 1 | 357646 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405243 | Work Order Description - 405243 - PSPM | PSPM | 1 | 357645 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405245 | Work Order Description - 405245 - PM | PM | 4 | 360243 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 405247 | Work Order Description - 405247 - PM | PM | 4 | 307915 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 405249 | Work Order Description - 405249 - PM | PM | 3 | 671601 | WSCHD | EQUIP-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 405253 | Work Order Description - 405253 - PM | PM | 3 | 308530 | WSCHD | EQUIP-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 405257 | Work Order Description - 405257 - PM | PM | 4 | 353354 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 405259 | Work Order Description - 405259 - PSPM | PSPM | 1 | 296000 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 405261 | Work Order Description - 405261 - PSPM | PSPM | 1 | 457490 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | OPERATIONS | SAFETY | 2
2019-03-31 | 405263 | Work Order Description - 405263 - PSPM | PSPM | 1 | 457527 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | OPERATIONS | SAFETY | 12
2019-03-31 | 405265 | Work Order Description - 405265 - PSPM | PSPM | 1 | 267870 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | OPERATIONS | SAFETY | 12
2019-03-31 | 405267 | Work Order Description - 405267 - PSPM | PSPM | 1 | 292659 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | OPERATIONS | SAFETY | 12
2019-03-31 | 405269 | Work Order Description - 405269 - PM | PM | 4 | 292870 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 405271 | Work Order Description - 405271 - PM | PM | 4 | 416374 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | SAFETY | 3
2019-03-31 | 405273 | Work Order Description - 405273 - PM | PM | 4 | 294864 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | OPERATIONS | MEDIC | 4
2019-03-31 | 405275 | Work Order Description - 405275 - PSPM | PSPM | 1 | 248101 | WSCHD | PACK-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 405277 | Work Order Description - 405277 - PSPM | PSPM | 1 | 357637 | WSCHD | SUBSYS-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405279 | Work Order Description - 405279 - PSPM | PSPM | 1 | 653336 | WSCHD | SUBSYS-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405281 | Work Order Description - 405281 - PSPM | PSPM | 1 | 399673 | WSCHD | SUBSYS-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405283 | Work Order Description - 405283 - PSPM | PSPM | 1 | 399624 | WSCHD | SUBSYS-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405285 | Work Order Description - 405285 - PSPM | PSPM | 1 | 399625 | WSCHD | SUBSYS-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405287 | Work Order Description - 405287 - PSPM | PSPM | 1 | 357642 | WSCHD | SUBSYS-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405289 | Work Order Description - 405289 - PSPM | PSPM | 1 | 399622 | WSCHD | SUBSYS-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405291 | Work Order Description - 405291 - PSPM | PSPM | 1 | 357647 | WSCHD | SUBSYS-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405293 | Work Order Description - 405293 - PSPM | PSPM | 1 | 399626 | WSCHD | SUBSYS-ISOL | 2019-03-05 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405295 | Work Order Description - 405295 - PM | PM | 2 | 411324 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-04-27 | 2019-04-27 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 405297 | Work Order Description - 405297 - PM | PM | 2 | 411324 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-05-11 | 2019-05-11 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 405299 | Work Order Description - 405299 - PM | PM | 4 | 481408 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 4 | MAINTENANCE | MEDIC | 25
2019-03-31 | 405301 | Work Order Description - 405301 - PM | PM | 4 | 295994 | WSCHD | NORM-OPS | 2019-03-03 | 2019-08-01 | 2019-06-19 | 2019-06-19 | 2 | MAINTENANCE | MEDIC | 20
2019-03-31 | 405303 | Work Order Description - 405303 - PM | PM | 3 | 215998 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 405305 | Work Order Description - 405305 - PSPM | PSPM | 1 | 216248 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 405307 | Work Order Description - 405307 - PSPM | PSPM | 1 | 552280 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 405309 | Work Order Description - 405309 - PSPM | PSPM | 1 | 481607 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-08-31 | 2019-08-31 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 405311 | Work Order Description - 405311 - PSPM | PSPM | 1 | 481608 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 405313 | Work Order Description - 405313 - PM | PM | 4 | 478652 | SCHD | SYS-ISOL | 2019-03-15 | 2019-12-11 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 405315 | Work Order Description - 405315 - PM | PM | 4 | 478653 | SCHD | SYS-ISOL | 2019-03-15 | 2019-12-11 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 405317 | Work Order Description - 405317 - PM | PM | 4 | 259169 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 405319 | Work Order Description - 405319 - PSPM | PSPM | 1 | 491403 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 405321 | Work Order Description - 405321 - PSPM | PSPM | 1 | 462750 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 405323 | Work Order Description - 405323 - PSPM | PSPM | 1 | 462750 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 405325 | Work Order Description - 405325 - PM | PM | 4 | 553007 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-25 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 405327 | Work Order Description - 405327 - PM | PM | 4 | 320850 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | DRILLING | DRILLING | 3
2019-03-31 | 405329 | Work Order Description - 405329 - PSPM | PSPM | 1 | 469980 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | ELECTRICAL | 84
2019-03-31 | 405331 | Work Order Description - 405331 - PM | PM | 3 | 216984 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 405333 | Work Order Description - 405333 - PM | PM | 2 | 498468 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405335 | Work Order Description - 405335 - PM | PM | 4 | 479286 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | SAFETY | 3
2019-03-31 | 405337 | Work Order Description - 405337 - PM | PM | 4 | 479287 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | SAFETY | 3
2019-03-31 | 405339 | Work Order Description - 405339 - PM | PM | 4 | 257426 | SCHD | NORM-OPS | 2019-03-15 | 2019-09-12 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405341 | Work Order Description - 405341 - PSPM | PSPM | 4 | 383657 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 405343 | Work Order Description - 405343 - PM | PM | 4 | 568110 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 405345 | Work Order Description - 405345 - PM | PM | 4 | 81258 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 405347 | Work Order Description - 405347 - PSPM | PSPM | 1 | 185355 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 405349 | Work Order Description - 405349 - PSPM | PSPM | 1 | 458300 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | ELECTRICAL | 70
2019-03-31 | 405351 | Work Order Description - 405351 - PM | PM | 4 | 458300 | SCHD | NORM-OPS | 2019-03-15 | 2019-11-23 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | ELECTRICAL | 126
2019-03-31 | 405353 | Work Order Description - 405353 - PSPM | PSPM | 1 | 458432 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 405355 | Work Order Description - 405355 - PM | PM | 4 | 458432 | SCHD | NORM-OPS | 2019-03-15 | 2019-11-23 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | ELECTRICAL | 36
2019-03-31 | 405357 | Work Order Description - 405357 - PSPM | PSPM | 1 | 631404 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | ELECTRICAL | 144
2019-03-31 | 405359 | Work Order Description - 405359 - PM | PM | 4 | 631404 | SCHD | NORM-OPS | 2019-03-15 | 2019-11-23 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | ELECTRICAL | 172
2019-03-31 | 405361 | Work Order Description - 405361 - PSPM | PSPM | 1 | 99120 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | ELECTRICAL | 58
2019-03-31 | 405363 | Work Order Description - 405363 - PM | PM | 4 | 99120 | SCHD | NORM-OPS | 2019-03-15 | 2019-11-23 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | ELECTRICAL | 110
2019-03-31 | 405365 | Work Order Description - 405365 - PSPM | PSPM | 1 | 631961 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 405367 | Work Order Description - 405367 - PM | PM | 4 | 631961 | SCHD | NORM-OPS | 2019-03-15 | 2019-11-23 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | ELECTRICAL | 38
2019-03-31 | 405369 | Work Order Description - 405369 - PSPM | PSPM | 1 | 457997 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | ELECTRICAL | 30
2019-03-31 | 405371 | Work Order Description - 405371 - PM | PM | 4 | 457997 | SCHD | NORM-OPS | 2019-03-15 | 2019-11-23 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | ELECTRICAL | 172
2019-03-31 | 405373 | Work Order Description - 405373 - PM | PM | 4 | 446978 | SCHD | NORM-OPS | 2019-03-15 | 2019-11-23 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | ELECTRICAL | 98
2019-03-31 | 405375 | Work Order Description - 405375 - PM | PM | 4 | 458527 | SCHD | NORM-OPS | 2019-03-15 | 2019-11-23 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | ELECTRICAL | 78
2019-03-31 | 405377 | Work Order Description - 405377 - PM | PM | 4 | 450026 | SCHD | NORM-OPS | 2019-03-15 | 2019-09-12 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405379 | Work Order Description - 405379 - PM | PM | 4 | 450520 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 405381 | Work Order Description - 405381 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 405383 | Work Order Description - 405383 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 405385 | Work Order Description - 405385 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 405387 | Work Order Description - 405387 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 405389 | Work Order Description - 405389 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 405391 | Work Order Description - 405391 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 405393 | Work Order Description - 405393 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 405395 | Work Order Description - 405395 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 405397 | Work Order Description - 405397 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 405399 | Work Order Description - 405399 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 405401 | Work Order Description - 405401 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 405403 | Work Order Description - 405403 - PM | PM | 4 | 501143 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 405405 | Work Order Description - 405405 - PM | PM | 4 | 188825 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405407 | Work Order Description - 405407 - PM | PM | 4 | 309635 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405409 | Work Order Description - 405409 - PM | PM | 4 | 309636 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405411 | Work Order Description - 405411 - PM | PM | 4 | 324749 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405413 | Work Order Description - 405413 - PM | PM | 4 | 498449 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405415 | Work Order Description - 405415 - PM | PM | 4 | 315662 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | DRILLING | DRILLING | 4
2019-03-31 | 405417 | Work Order Description - 405417 - PM | PM | 4 | 119613 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 405419 | Work Order Description - 405419 - PM | PM | 4 | 216274 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | DRILLING | DRILLING | 4
2019-03-31 | 405421 | Work Order Description - 405421 - PM | PM | 4 | 479632 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 405425 | Work Order Description - 405425 - PM | PM | 4 | 243815 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | DRILLING | DRILLING | 7
2019-03-31 | 405429 | Work Order Description - 405429 - PM | PM | 4 | 216158 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | DRILLING | DRILLING | 12
2019-03-31 | 405431 | Work Order Description - 405431 - PM | PM | 4 | 320549 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | DRILLING | DRILLING | 3.5
2019-03-31 | 405433 | Work Order Description - 405433 - PM | PM | 2 | 502749 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-20 | 2019-07-20 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 405435 | Work Order Description - 405435 - PM | PM | 4 | 215925 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | INTEGRITY | INSPECTION | 48
2019-03-31 | 405437 | Work Order Description - 405437 - PM | PM | 4 | 263395 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 405439 | Work Order Description - 405439 - PM | PM | 4 | 556260 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 405441 | Work Order Description - 405441 - PSPM | PSPM | 1 | 401356 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 405443 | Work Order Description - 405443 - PM | PM | 2 | 216011 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 405445 | Work Order Description - 405445 - PSPM | PSPM | 1 | 177313 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 405447 | Work Order Description - 405447 - PSPM | PSPM | 1 | 177320 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | ELECTRICAL | 26
2019-03-31 | 405449 | Work Order Description - 405449 - PSPM | PSPM | 1 | 177328 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | ELECTRICAL | 20
2019-03-31 | 405451 | Work Order Description - 405451 - PSPM | PSPM | 1 | 469775 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 405453 | Work Order Description - 405453 - PSPM | PSPM | 1 | 401744 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 405455 | Work Order Description - 405455 - PM | PM | 4 | 216158 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 405457 | Work Order Description - 405457 - PSPM | PSPM | 1 | 477468 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 50
2019-03-31 | 405460 | Work Order Description - 405460 - PM | PM | 4 | 320026 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 405462 | Work Order Description - 405462 - PSPM | PSPM | 1 | 320595 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-20 | 2019-07-20 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 405464 | Work Order Description - 405464 - PSPM | PSPM | 1 | 259477 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 405466 | Work Order Description - 405466 - PSPM | PSPM | 1 | 253500 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 405468 | Work Order Description - 405468 - PSPM | PSPM | 1 | 490533 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 405470 | Work Order Description - 405470 - PSPM | PSPM | 1 | 475790 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 405472 | Work Order Description - 405472 - PSPM | PSPM | 1 | 478300 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 405474 | Work Order Description - 405474 - PM | PM | 4 | 216158 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 405476 | Work Order Description - 405476 - PM | PM | 4 | 81493 | SCHD | PACK-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 405478 | Work Order Description - 405478 - PM | PM | 4 | 74216 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 405480 | Work Order Description - 405480 - PM | PM | 4 | 99564 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 50
2019-03-31 | 405482 | Work Order Description - 405482 - PM | PM | 4 | 257426 | SCHD | NORM-OPS | 2019-03-15 | 2019-09-12 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 405484 | Work Order Description - 405484 - PM | PM | 4 | 95502 | SCHD | PACK-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 405486 | Work Order Description - 405486 - PM | PM | 4 | 501056 | SCHD | NORM-OPS | 2019-03-15 | 2019-09-30 | 2019-07-01 | 2019-07-01 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 405488 | Work Order Description - 405488 - PM | PM | 3 | 123510 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 405490 | Work Order Description - 405490 - PM | PM | 4 | 481647 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 405492 | Work Order Description - 405492 - PM | PM | 4 | 555301 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 4 | MAINTENANCE | MEDIC | 21
2019-03-31 | 405494 | Work Order Description - 405494 - PM | PM | 4 | 81494 | SCHD | PACK-ISOL | 2019-03-15 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 405578 | Work Order Description - 405578 - PM | PM | 4 | 399134 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 3 | INTEGRITY | INSPECTION | 3
2019-03-31 | 405580 | Work Order Description - 405580 - PM | PM | 4 | 376251 | WPLAN | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 405582 | Work Order Description - 405582 - PSPM | PSPM | 1 | 383544 | WPLAN | PACK-ISOL | 2019-03-03 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 53
2019-03-31 | 405584 | Work Order Description - 405584 - PSPM | PSPM | 1 | 383547 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | SAFETY | 53
2019-03-31 | 405586 | Work Order Description - 405586 - PSPM | PSPM | 1 | 670366 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | SAFETY | 53
2019-03-31 | 405588 | Work Order Description - 405588 - PSPM | PSPM | 1 | 670372 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | SAFETY | 53
2019-03-31 | 405590 | Work Order Description - 405590 - PSPM | PSPM | 1 | 450992 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | SAFETY | 4
2019-03-31 | 405592 | Work Order Description - 405592 - PM | PM | 4 | 528193 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-04 | 1 | INTEGRITY | INSPECTION | 34
2019-03-31 | 405594 | Work Order Description - 405594 - PM | PM | 4 | 277349 | WPLAN | PACK-ISOL | 2019-03-03 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 405598 | Work Order Description - 405598 - PSPM | PSPM | 1 | 92712 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 405600 | Work Order Description - 405600 - PSPM | PSPM | 1 | 277246 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 405602 | Work Order Description - 405602 - PSPM | PSPM | 1 | 396754 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 405604 | Work Order Description - 405604 - PSPM | PSPM | 1 | 277349 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 405606 | Work Order Description - 405606 - PSPM | PSPM | 1 | 123391 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 405608 | Work Order Description - 405608 - PSPM | PSPM | 1 | 99232 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | SERVICES | 4
2019-03-31 | 405610 | Work Order Description - 405610 - PSPM | PSPM | 1 | 99434 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | SERVICES | 4
2019-03-31 | 405612 | Work Order Description - 405612 - PSPM | PSPM | 1 | 392310 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 405614 | Work Order Description - 405614 - PSPM | PSPM | 1 | 450798 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | OPERATIONS | SAFETY | 2
2019-03-31 | 405616 | Work Order Description - 405616 - PSPM | PSPM | 1 | 227869 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 405618 | Work Order Description - 405618 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 405620 | Work Order Description - 405620 - PM | PM | 2 | 227830 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 405622 | Work Order Description - 405622 - PSPM | PSPM | 1 | 227935 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-30 | 2019-07-30 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 405624 | Work Order Description - 405624 - PSPM | PSPM | 1 | 127636 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 405626 | Work Order Description - 405626 - PM | PM | 4 | 528189 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 405628 | Work Order Description - 405628 - PM | PM | 4 | 445291 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-10-18 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 405630 | Work Order Description - 405630 - PM | PM | 2 | 238033 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 405632 | Work Order Description - 405632 - PM | PM | 3 | 387790 | WPLAN | EQUIP-ISOL | 2019-03-03 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | MECHANICAL | 57
2019-03-31 | 405643 | Work Order Description - 405643 - PSPM | PSPM | 1 | 659554 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-02 | 1 | MAINTENANCE | SAFETY | 14
2019-03-31 | 405645 | Work Order Description - 405645 - PSPM | PSPM | 1 | 450989 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-02 | 1 | MAINTENANCE | SAFETY | 14
2019-03-31 | 405647 | Work Order Description - 405647 - PSPM | PSPM | 1 | 450988 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-02 | 1 | MAINTENANCE | SAFETY | 14
2019-03-31 | 405649 | Work Order Description - 405649 - PSPM | PSPM | 1 | 375795 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 405651 | Work Order Description - 405651 - PSPM | PSPM | 1 | 110854 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 405653 | Work Order Description - 405653 - PM | PM | 4 | 375764 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 405655 | Work Order Description - 405655 - PM | PM | 4 | 375764 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 405657 | Work Order Description - 405657 - PSPM | PSPM | 1 | 227943 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | SAFETY | 4
2019-03-31 | 405659 | Work Order Description - 405659 - PSPM | PSPM | 1 | 528193 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-01 | 2019-04-17 | 2019-04-17 | 2 | INTEGRITY | INSPECTION | 200
2019-03-31 | 405661 | Work Order Description - 405661 - PSPM | PSPM | 1 | 527364 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 405663 | Work Order Description - 405663 - PM | PM | 4 | 387912 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 405665 | Work Order Description - 405665 - PSPM | PSPM | 1 | 659510 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 405668 | Work Order Description - 405668 - PSPM | PSPM | 1 | 527372 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 405670 | Work Order Description - 405670 - PSPM | PSPM | 1 | 659557 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-02 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 405672 | Work Order Description - 405672 - PSPM | PSPM | 1 | 659557 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 405674 | Work Order Description - 405674 - PSPM | PSPM | 1 | 227944 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-02 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 405676 | Work Order Description - 405676 - PSPM | PSPM | 1 | 227944 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-02 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 405678 | Work Order Description - 405678 - PSPM | PSPM | 1 | 227958 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-01 | 2019-07-01 | 2019-07-02 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 405680 | Work Order Description - 405680 - PM | PM | 4 | 80349 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 2 | OPERATIONS | MECHANICAL | 7
2019-03-31 | 405682 | Work Order Description - 405682 - PM | PM | 4 | 110824 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-25 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 405684 | Work Order Description - 405684 - PSPM | PSPM | 1 | 218107 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | WELLS | WELLS | 1
2019-03-31 | 405686 | Work Order Description - 405686 - PSPM | PSPM | 1 | 74871 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | WELLS | WELLS | 1
2019-03-31 | 405688 | Work Order Description - 405688 - PSPM | PSPM | 1 | 74949 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | WELLS | WELLS | 1
2019-03-31 | 405690 | Work Order Description - 405690 - PSPM | PSPM | 1 | 218111 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | WELLS | WELLS | 1
2019-03-31 | 405692 | Work Order Description - 405692 - PSPM | PSPM | 1 | 74876 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | WELLS | WELLS | 1
2019-03-31 | 405694 | Work Order Description - 405694 - PSPM | PSPM | 1 | 127776 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | WELLS | WELLS | 1
2019-03-31 | 405696 | Work Order Description - 405696 - PSPM | PSPM | 1 | 128021 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-01 | 2019-07-13 | 2019-07-13 | 1 | WELLS | WELLS | 1
2019-03-31 | 405698 | Work Order Description - 405698 - PSPM | PSPM | 1 | 74875 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | WELLS | WELLS | 1
2019-03-31 | 405700 | Work Order Description - 405700 - PSPM | PSPM | 1 | 74946 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | WELLS | WELLS | 1
2019-03-31 | 405702 | Work Order Description - 405702 - PSPM | PSPM | 1 | 128022 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-01 | 2019-07-01 | 2019-07-01 | 1 | WELLS | WELLS | 1
2019-03-31 | 407576 | Work Order Description - 407576 - BR | BR | 3 | 266276 | SCHD | SYS-ISOL | 2019-03-06 | 2019-10-01 | 2019-07-13 | 2019-07-14 | 1 | MAINTENANCE | ELECTRICAL | 9
2019-03-31 | 407633 | Work Order Description - 407633 - CM | CM | 3 | 487398 | WPLAN | PACK-ISOL | 2019-03-05 | 2019-05-27 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 23
2019-03-31 | 407673 | Work Order Description - 407673 - PM | PM | 3 | 356932 | WSCHD | NORM-OPS | 2019-03-04 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 407675 | Work Order Description - 407675 - PM | PM | 3 | 356932 | WSCHD | NORM-OPS | 2019-03-04 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 407677 | Work Order Description - 407677 - PM | PM | 4 | 308893 | WSCHD | NORM-OPS | 2019-03-04 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 407679 | Work Order Description - 407679 - PM | PM | 3 | 357054 | WSCHD | EQUIP-ISOL | 2019-03-04 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 407681 | Work Order Description - 407681 - PM | PM | 3 | 246492 | WSCHD | EQUIP-ISOL | 2019-03-04 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 407683 | Work Order Description - 407683 - PM | PM | 3 | 243499 | WSCHD | NORM-OPS | 2019-03-04 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 407685 | Work Order Description - 407685 - PM | PM | 3 | 356932 | WSCHD | NORM-OPS | 2019-03-04 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 407687 | Work Order Description - 407687 - PM | PM | 3 | 356932 | WSCHD | NORM-OPS | 2019-03-04 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 407689 | Work Order Description - 407689 - PSPM | PSPM | 1 | 293229 | WSCHD | NORM-OPS | 2019-03-04 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 407691 | Work Order Description - 407691 - PSPM | PSPM | 1 | 575050 | WSCHD | NORM-OPS | 2019-03-04 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 407693 | Work Order Description - 407693 - PSPM | PSPM | 1 | 293228 | WSCHD | NORM-OPS | 2019-03-04 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 407695 | Work Order Description - 407695 - PSPM | PSPM | 1 | 681801 | WSCHD | EQUIP-ISOL | 2019-03-04 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 407697 | Work Order Description - 407697 - PSPM | PSPM | 1 | 575051 | WSCHD | NORM-OPS | 2019-03-04 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 407699 | Work Order Description - 407699 - PM | PM | 4 | 361798 | WSCHD | NORM-OPS | 2019-03-05 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 407701 | Work Order Description - 407701 - PSPM | PSPM | 1 | 410324 | WSCHD | NORM-OPS | 2019-03-04 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 407703 | Work Order Description - 407703 - PM | PM | 4 | 353354 | WSCHD | NORM-OPS | 2019-03-04 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 407705 | Work Order Description - 407705 - PM | PM | 4 | 574924 | WSCHD | NORM-OPS | 2019-03-04 | 2019-08-02 | 2019-06-20 | 2019-06-20 | 1 | OPERATIONS | SAFETY | 2
2019-03-31 | 407707 | Work Order Description - 407707 - PM | PM | 4 | 481609 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 407709 | Work Order Description - 407709 - PSPM | PSPM | 1 | 462436 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 407711 | Work Order Description - 407711 - PM | PM | 4 | 476154 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 407713 | Work Order Description - 407713 - PM | PM | 4 | 403849 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 2 | MAINTENANCE | ELECTRICAL | 24
2019-03-31 | 407715 | Work Order Description - 407715 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 407719 | Work Order Description - 407719 - PM | PM | 1 | 501092 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-02 | 2019-07-20 | 2019-07-20 | 1 | MAINTENANCE | SAFETY | 6
2019-03-31 | 407721 | Work Order Description - 407721 - PSPM | PSPM | 4 | 403503 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 407723 | Work Order Description - 407723 - PSPM | PSPM | 1 | 215897 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 1 | INTEGRITY | INSPECTION | 2
2019-03-31 | 407741 | Work Order Description - 407741 - PM | PM | 4 | 663518 | WPLAN | PACK-ISOL | 2019-03-04 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 2 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 407743 | Work Order Description - 407743 - PM | PM | 4 | 659514 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 407745 | Work Order Description - 407745 - PM | PM | 4 | 527315 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-26 | 2019-07-02 | 2019-07-02 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 407747 | Work Order Description - 407747 - PM | PM | 4 | 527315 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-26 | 2019-07-02 | 2019-07-02 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 407749 | Work Order Description - 407749 - PM | PM | 4 | 451338 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-02 | 2019-07-02 | 2019-07-03 | 2 | INTEGRITY | INSPECTION | 8
2019-03-31 | 407751 | Work Order Description - 407751 - PM | PM | 4 | 451323 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 2 | INTEGRITY | INSPECTION | 2
2019-03-31 | 407753 | Work Order Description - 407753 - PM | PM | 4 | 441790 | WPLAN | PACK-ISOL | 2019-03-04 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 2 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 407755 | Work Order Description - 407755 - PM | PM | 4 | 686592 | WPLAN | PACK-ISOL | 2019-03-04 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 2 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 407757 | Work Order Description - 407757 - PM | PM | 4 | 392493 | WPLAN | PACK-ISOL | 2019-03-04 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 2 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 407759 | Work Order Description - 407759 - PM | PM | 4 | 670583 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 407761 | Work Order Description - 407761 - PSPM | PSPM | 1 | 659058 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 1 | OPERATIONS | SAFETY | 1
2019-03-31 | 407763 | Work Order Description - 407763 - PSPM | PSPM | 1 | 527367 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 407765 | Work Order Description - 407765 - PSPM | PSPM | 1 | 659514 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 407767 | Work Order Description - 407767 - PSPM | PSPM | 1 | 659514 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 407769 | Work Order Description - 407769 - PSPM | PSPM | 1 | 392215 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 407771 | Work Order Description - 407771 - PSPM | PSPM | 1 | 659560 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-02 | 2019-07-02 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 407773 | Work Order Description - 407773 - PSPM | PSPM | 1 | 527367 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 407775 | Work Order Description - 407775 - PSPM | PSPM | 1 | 527367 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 407777 | Work Order Description - 407777 - PSPM | PSPM | 1 | 659514 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 407779 | Work Order Description - 407779 - PSPM | PSPM | 1 | 527367 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-02 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 407781 | Work Order Description - 407781 - PM | PM | 4 | 440720 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-08-26 | 2019-07-02 | 2019-07-02 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 407783 | Work Order Description - 407783 - PM | PM | 4 | 440722 | SCHD | EQUIP-ISOL | 2019-03-06 | 2019-10-19 | 2019-07-02 | 2019-07-02 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 407883 | Work Order Description - 407883 - BR | BR | 4 | 495104 | WPLAN | EQUIP-ISOL | 2019-03-04 | 2021-03-02 | 2021-01-18 | 2021-01-18 | 4 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 407895 | Work Order Description - 407895 - BR | BR | 4 | 545222 | WPLAN | NORM-OPS | 2019-03-10 | 2021-03-02 | 2021-01-18 | 2021-01-18 | 4 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 407901 | Work Order Description - 407901 - BR | BR | 3 | 257996 | WPLAN | SYS-ISOL | 2019-03-06 | 2020-03-03 | 2019-09-02 | 2019-09-02 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 407903 | Work Order Description - 407903 - BR | BR | 3 | 266246 | WPLAN | SYS-ISOL | 2019-03-05 | 2019-09-03 | 2019-06-03 | 2019-06-05 | 3 | MAINTENANCE | ELECTRICAL | 15
2019-03-31 | 407909 | Work Order Description - 407909 - BR | BR | 1 | 375805 | SCHD | PACK-ISOL | 2019-03-06 | 2019-09-03 | 2019-06-03 | 2019-06-04 | 3 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 407914 | Work Order Description - 407914 - CM | CM | 1 | 409272 | WPLAN | EQUIP-ISOL | 2019-03-06 | 2020-03-03 | 2020-03-02 | 2020-03-02 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 407916 | Work Order Description - 407916 - BR | BR | 3 | 259535 | WPLAN | SYS-ISOL | 2019-03-04 | 2019-09-03 | 2019-06-03 | 2019-06-03 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 407917 | Work Order Description - 407917 - BR | BR | 4 | 358151 | WSCHD | NORM-OPS | 2019-03-04 | 2021-03-02 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 407921 | Work Order Description - 407921 - CM | CM | 1 | 30547 | WPLAN | EQUIP-ISOL | 2019-03-06 | 2019-05-28 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 407923 | Work Order Description - 407923 - BR | BR | 1 | 383857 | WPLAN | EQUIP-ISOL | 2019-03-05 | 2021-03-02 | 2021-01-18 | 2021-01-19 | 4 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 407931 | Work Order Description - 407931 - BR | BR | 1 | 447441 | WPLAN | EQUIP-ISOL | 2019-03-30 | 2019-05-28 | 2019-04-15 | 2019-04-15 | 2 | MAINTENANCE | ELECTRICAL | 42
2019-03-31 | 407954 | Work Order Description - 407954 - BR | BR | 3 | 216030 | SCHD | SYS-ISOL | 2019-03-15 | 2019-09-03 | 2019-03-30 | 2019-03-30 | 3 | INTEGRITY | OPERATIONS | 2496
2019-03-31 | 407972 | Work Order Description - 407972 - PSPM | PSPM | 1 | 503248 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-05-02 | 2019-04-01 | 2019-04-01 | 1 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 407982 | Work Order Description - 407982 - CM | CM | 3 | 262382 | SCHD | PACK-ISOL | 2019-03-15 | 2020-03-03 | 2020-03-02 | 2020-03-02 | 3 | MAINTENANCE | CONSTRUCTION | 20
2019-03-31 | 407984 | Work Order Description - 407984 - BR | BR | 2 | 80922 | SCHD | EQUIP-ISOL | 2019-03-29 | 2020-03-04 | 2019-09-03 | 2019-09-03 | 3 | INTEGRITY | INSTRUMENTS | 8
2019-03-31 | 407993 | Work Order Description - 407993 - PSCM | PSCM | 1 | 697913 | WSCHD | NORM-OPS | 2019-03-08 | 2019-09-03 | 2019-06-03 | 2019-06-03 | 3 | INTEGRITY | ELECTRICAL | 480
2019-03-31 | 408002 | Work Order Description - 408002 - BR | BR | 1 | 705976 | WMATL | EQUIP-ISOL | 2019-03-18 | 2019-09-03 | 2019-06-03 | 2019-06-03 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 408003 | Work Order Description - 408003 - PSPM | PSPM | 1 | 462436 | SCHD | PACK-ISOL | 2019-03-15 | 2019-07-31 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | MECHANICAL | 326
2019-03-31 | 408020 | Work Order Description - 408020 - BR | BR | 1 | 705977 | WMATL | EQUIP-ISOL | 2019-03-18 | 2019-09-03 | 2019-06-03 | 2019-06-03 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 408024 | Work Order Description - 408024 - BR | BR | 1 | 705984 | WMATL | PACK-ISOL | 2019-03-18 | 2019-09-03 | 2019-06-03 | 2019-06-03 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 408030 | Work Order Description - 408030 - BR | BR | 3 | 655322 | WPLAN | PACK-ISOL | 2019-03-05 | 2019-09-03 | 2019-06-04 | 2019-06-07 | 3 | MAINTENANCE | MECHANICAL | 70
2019-03-31 | 408035 | Work Order Description - 408035 - PSCM | PSCM | 2 | 361657 | WSCHD | NORM-OPS | 2019-03-19 | 2020-03-03 | 2019-09-02 | 2019-09-02 | 3 | INTEGRITY | SERVICES | 6
2019-03-31 | 408036 | Work Order Description - 408036 - BR | BR | 1 | 705978 | WMATL | PACK-ISOL | 2019-03-18 | 2019-09-03 | 2019-06-03 | 2019-06-03 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 408040 | Work Order Description - 408040 - BR | BR | 1 | 705968 | WMATL | PACK-ISOL | 2019-03-18 | 2019-09-03 | 2019-06-03 | 2019-06-03 | 3 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 408046 | Work Order Description - 408046 - BR | BR | 1 | 124266 | SCHD | EQUIP-ISOL | 2019-03-05 | 2021-03-02 | 2021-01-19 | 2021-01-20 | 4 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 408057 | Work Order Description - 408057 - PSCM | PSCM | 1 | 675036 | WSCHD | EQUIP-ISOL | 2019-03-08 | 2019-09-03 | 2019-06-03 | 2019-06-03 | 3 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 408071 | Work Order Description - 408071 - CM | CM | 3 | 361657 | WSCHD | EQUIP-ISOL | 2019-03-04 | 2021-03-02 |  |  | 4 | INTEGRITY | CONSTRUCTION | 7
2019-03-31 | 408100 | Work Order Description - 408100 - PSPM | PSPM | 1 | 541316 | WSCHD | EQUIP-ISOL | 2019-03-05 | 2019-08-03 | 2019-06-21 | 2019-06-21 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 408102 | Work Order Description - 408102 - PSPM | PSPM | 1 | 657137 | WSCHD | EQUIP-ISOL | 2019-03-05 | 2019-08-03 | 2019-06-21 | 2019-06-21 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 408104 | Work Order Description - 408104 - PM | PM | 4 | 540691 | WSCHD | NORM-OPS | 2019-03-05 | 2019-08-03 | 2019-06-21 | 2019-06-21 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 408106 | Work Order Description - 408106 - PM | PM | 4 | 481470 | WSCHD | NORM-OPS | 2019-03-05 | 2019-08-03 | 2019-06-21 | 2019-06-21 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 408108 | Work Order Description - 408108 - PM | PM | 4 | 547275 | WSCHD | PACK-ISOL | 2019-03-05 | 2019-08-03 | 2019-06-21 | 2019-06-21 | 1 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 408110 | Work Order Description - 408110 - PSPM | PSPM | 1 | 361798 | WSCHD | NORM-OPS | 2019-03-05 | 2019-08-03 | 2019-06-21 | 2019-06-21 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 408112 | Work Order Description - 408112 - PSPM | PSPM | 1 | 653132 | WSCHD | NORM-OPS | 2019-03-05 | 2019-08-03 | 2019-06-21 | 2019-06-21 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 408114 | Work Order Description - 408114 - PSPM | PSPM | 1 | 652220 | WSCHD | NORM-OPS | 2019-03-05 | 2019-08-03 | 2019-06-21 | 2019-06-21 | 1 | MAINTENANCE | SERVICES | 10
2019-03-31 | 408116 | Work Order Description - 408116 - PSPM | PSPM | 1 | 181000 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-03 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | MECHANICAL | 29
2019-03-31 | 408122 | Work Order Description - 408122 - PSPM | PSPM | 1 | 320057 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-03 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 408124 | Work Order Description - 408124 - PM | PM | 4 | 555305 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-03 | 2019-07-20 | 2019-07-20 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 408126 | Work Order Description - 408126 - PSPM | PSPM | 1 | 492109 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-03 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 408128 | Work Order Description - 408128 - PM | PM | 4 | 99579 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-03 | 2019-07-03 | 2019-07-03 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 408130 | Work Order Description - 408130 - PSPM | PSPM | 1 | 544199 | SCHD | SUBSYS-ISOL | 2019-03-15 | 2019-08-03 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 408132 | Work Order Description - 408132 - PM | PM | 4 | 328692 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-03 | 2019-07-03 | 2019-07-03 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 408134 | Work Order Description - 408134 - PM | PM | 4 | 460846 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-03 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 408136 | Work Order Description - 408136 - PSPM | PSPM | 1 | 479577 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-03 | 2019-07-03 | 2019-07-03 | 1 | INTEGRITY | INSPECTION | 105
2019-03-31 | 408148 | Work Order Description - 408148 - PM | PM | 4 | 388221 | WPLAN | EQUIP-ISOL | 2019-03-05 | 2019-08-03 | 2019-07-03 | 2019-07-03 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 408150 | Work Order Description - 408150 - PM | PM | 4 | 80369 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-03 | 2019-07-03 | 2019-07-03 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 408152 | Work Order Description - 408152 - PM | PM | 4 | 388194 | WPLAN | EQUIP-ISOL | 2019-03-05 | 2019-08-03 | 2019-07-03 | 2019-07-03 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 408154 | Work Order Description - 408154 - PM | PM | 4 | 89581 | WPLAN | EQUIP-ISOL | 2019-03-05 | 2019-08-03 | 2019-07-03 | 2019-07-03 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 408156 | Work Order Description - 408156 - PSPM | PSPM | 1 | 659562 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-03 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | SAFETY | 3
2019-03-31 | 408158 | Work Order Description - 408158 - PM | PM | 4 | 659574 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-03 | 2019-07-03 | 2019-07-03 | 1 | OPERATIONS | SAFETY | 2
2019-03-31 | 408160 | Work Order Description - 408160 - PM | PM | 4 | 659496 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-03 | 2019-07-03 | 2019-07-03 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 408162 | Work Order Description - 408162 - PSPM | PSPM | 1 | 528118 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-03 | 2019-07-03 | 2019-07-03 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 408319 | Work Order Description - 408319 - BR | BR | 3 | 545222 | WSCHD | SYS-ISOL | 2019-03-16 | 2021-03-03 | 2019-08-19 | 2019-08-19 | 4 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 408320 | Work Order Description - 408320 - BR | BR | 1 | 705965 | WMATL | EQUIP-ISOL | 2019-03-18 | 2021-03-03 | 2021-01-19 | 2021-01-19 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 408361 | Work Order Description - 408361 - PSCM | PSCM | 1 | 453091 | SCHD | EQUIP-ISOL | 2019-03-06 | 2021-03-03 | 2021-01-19 | 2021-01-20 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 408383 | Work Order Description - 408383 - CM | CM | 4 | 110715 | SCHD | PACK-ISOL | 2019-03-15 | 2019-09-04 | 2019-06-04 | 2019-06-06 | 3 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 408414 | Work Order Description - 408414 - PSCM | PSCM | 4 | 570144 | WSCHD | NORM-OPS | 2019-03-25 | 2020-03-24 | 2019-10-26 | 2019-10-26 | 3 | INTEGRITY | ELECTRICAL | 1600
2019-03-31 | 408432 | Work Order Description - 408432 - PSCM | PSCM | 4 | 697913 | WSCHD | NORM-OPS | 2019-03-25 | 2020-03-24 | 2019-10-26 | 2019-10-26 | 3 | INTEGRITY | ELECTRICAL | 540
2019-03-31 | 408438 | Work Order Description - 408438 - BR | BR | 4 | 697913 | WSCHD | NORM-OPS | 2019-03-05 | 2019-09-04 |  |  | 3 | INTEGRITY | ELECTRICAL | 150
2019-03-31 | 408520 | Work Order Description - 408520 - PM | PM | 4 | 472269 | SCHD | NORM-OPS | 2019-03-15 | 2019-06-10 | 2019-05-10 | 2019-05-10 | 2 | OPERATIONS | OPERATIONS | 16
2019-03-31 | 408533 | Work Order Description - 408533 - CM | CM | 4 | 670468 | SCHD | PACK-ISOL | 2019-03-15 | 2019-05-29 | 2019-04-17 | 2019-04-18 | 2 | MAINTENANCE | ELECTRICAL | 9
2019-03-31 | 408554 | Work Order Description - 408554 - PRJ | PRJ | 3 | 481880 | WRISKREV | NORM-OPS | 2019-03-05 | 2019-05-29 |  |  | 2 | ENGINEERING | OPERATIONS | 2
2019-03-31 | 408562 | Work Order Description - 408562 - BR | BR | 1 | 631593 | WPLAN | EQUIP-ISOL | 2019-03-06 | 2019-09-04 | 2019-06-04 | 2019-06-04 | 3 | MAINTENANCE | INSTRUMENTS | 50
2019-03-31 | 408569 | Work Order Description - 408569 - PM | PM | 4 | 481466 | WSCHD | EQUIP-ISOL | 2019-03-06 | 2019-08-04 | 2019-06-22 | 2019-06-22 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 408571 | Work Order Description - 408571 - PSPM | PSPM | 1 | 360373 | WSCHD | EQUIP-ISOL | 2019-03-06 | 2019-08-04 | 2019-06-22 | 2019-06-22 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 408573 | Work Order Description - 408573 - PSPM | PSPM | 4 | 671263 | WSCHD | NORM-OPS | 2019-03-06 | 2019-08-04 | 2019-06-22 | 2019-06-22 | 1 | INTEGRITY | INSPECTION | 2
2019-03-31 | 408575 | Work Order Description - 408575 - PM | PM | 4 | 660951 | WSCHD | NORM-OPS | 2019-03-06 | 2019-08-04 | 2019-06-22 | 2019-06-22 | 3 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 408579 | Work Order Description - 408579 - PM | PM | 4 | 249173 | WSCHD | NORM-OPS | 2019-03-06 | 2019-08-04 | 2019-06-22 | 2019-06-22 | 2 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 408581 | Work Order Description - 408581 - PM | PM | 4 | 249173 | WSCHD | NORM-OPS | 2019-03-06 | 2019-08-04 | 2019-06-22 | 2019-06-22 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 408583 | Work Order Description - 408583 - PSPM | PSPM | 1 | 361198 | WPLAN | EQUIP-ISOL | 2019-03-06 | 2019-08-04 | 2019-06-22 | 2019-06-22 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 408585 | Work Order Description - 408585 - PM | PM | 4 | 450481 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-04 | 2019-07-04 | 2019-07-04 | 2 | OPERATIONS | OPERATIONS | 5
2019-03-31 | 408587 | Work Order Description - 408587 - PM | PM | 2 | 312683 | SCHD | PACK-ISOL | 2019-03-15 | 2019-08-04 | 2019-07-04 | 2019-07-04 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 408591 | Work Order Description - 408591 - PM | PM | 3 | 309675 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-04 | 2019-07-04 | 2019-07-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 408593 | Work Order Description - 408593 - PM | PM | 3 | 309675 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-04 | 2019-07-04 | 2019-07-04 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 408595 | Work Order Description - 408595 - PSPM | PSPM | 1 | 30717 | SCHD | SUBSYS-ISOL | 2019-03-15 | 2019-08-04 | 2019-07-04 | 2019-07-04 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 408597 | Work Order Description - 408597 - PSPM | PSPM | 1 | 584204 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-04 | 2019-07-04 | 2019-07-04 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 408599 | Work Order Description - 408599 - PSPM | PSPM | 1 | 123510 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-04 | 2019-07-04 | 2019-07-04 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 408605 | Work Order Description - 408605 - PM | PM | 4 | 659515 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-28 | 2019-07-04 | 2019-07-08 | 2 | MAINTENANCE | ELECTRICAL | 30
2019-03-31 | 408607 | Work Order Description - 408607 - PM | PM | 4 | 659515 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-28 | 2019-07-04 | 2019-07-08 | 2 | MAINTENANCE | ELECTRICAL | 30
2019-03-31 | 408609 | Work Order Description - 408609 - PSPM | PSPM | 1 | 42961 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-04 | 2019-07-04 | 2019-07-04 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 408611 | Work Order Description - 408611 - PSPM | PSPM | 4 | 99232 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-04 | 2019-07-04 | 2019-07-05 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 408613 | Work Order Description - 408613 - PSPM | PSPM | 1 | 659514 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-04 | 2019-07-04 | 2019-07-04 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 408615 | Work Order Description - 408615 - PSPM | PSPM | 1 | 126920 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-04 | 2019-07-04 | 2019-07-04 | 1 | MAINTENANCE | ELECTRICAL | 1.5
2019-03-31 | 408617 | Work Order Description - 408617 - PSPM | PSPM | 1 | 527869 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-04 | 2019-07-04 | 2019-07-21 | 2 | INTEGRITY | INSPECTION | 250
2019-03-31 | 408619 | Work Order Description - 408619 - PSPM | PSPM | 1 | 659514 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-04 | 2019-07-04 | 2019-07-04 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 408621 | Work Order Description - 408621 - PM | PM | 4 | 126984 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-04 | 2019-07-04 | 2019-07-04 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 408623 | Work Order Description - 408623 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-03-06 | 2019-08-04 | 2019-07-04 | 2019-07-04 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 408626 | Work Order Description - 408626 - PM | PM | 4 | 217148 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-28 | 2019-07-04 | 2019-07-04 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 408628 | Work Order Description - 408628 - PM | PM | 4 | 217149 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-28 | 2019-07-04 | 2019-07-08 | 2 | MAINTENANCE | ELECTRICAL | 31
2019-03-31 | 408837 | Work Order Description - 408837 - BR | BR | 3 | 499275 | WPLAN | EQUIP-ISOL | 2019-03-06 | 2019-04-04 | 2019-03-20 | 2019-03-20 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 408843 | Work Order Description - 408843 - BR | BR | 3 | 475677 | WPLAN | EQUIP-ISOL | 2019-03-06 | 2019-04-04 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 408886 | Work Order Description - 408886 - BR | BR | 3 | 19008 | WSCHD | SYS-ISOL | 2019-03-08 | 2021-03-04 | 2019-05-04 | 2019-05-04 | 4 | INTEGRITY | CONSTRUCTION | 6648
2019-03-31 | 408934 | Work Order Description - 408934 - PSPM | PSPM | 1 | 369790 | WSCHD | NORM-OPS | 2019-03-06 | 2019-12-22 | 2019-11-09 | 2019-11-09 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 408936 | Work Order Description - 408936 - PSPM | PSPM | 1 | 570144 | WSCHD | NORM-OPS | 2019-03-06 | 2019-11-28 | 2019-09-16 | 2019-09-16 | 1 | INTEGRITY | INSPECTION | 441
2019-03-31 | 408938 | Work Order Description - 408938 - PSPM | PSPM | 1 | 204611 | WSCHD | NORM-OPS | 2019-03-06 | 2019-12-01 | 2019-10-19 | 2019-10-19 | 1 | INTEGRITY | INSPECTION | 294
2019-03-31 | 408941 | Work Order Description - 408941 - PSPM | PSPM | 1 | 557760 | WSCHD | NORM-OPS | 2019-03-06 | 2020-01-09 | 2019-11-27 | 2019-11-27 | 1 | INTEGRITY | INSPECTION | 294
2019-03-31 | 408945 | Work Order Description - 408945 - PSPM | PSPM | 1 | 292440 | WSCHD | NORM-OPS | 2019-03-06 | 2019-08-17 | 2019-07-05 | 2019-07-05 | 1 | INTEGRITY | INSPECTION | 441
2019-03-31 | 408952 | Work Order Description - 408952 - PSCM | PSCM | 4 | 697913 | WSCHD | NORM-OPS | 2019-03-25 | 2020-03-24 | 2019-10-26 | 2019-10-26 | 3 | INTEGRITY | ELECTRICAL | 360
2019-03-31 | 408961 | Work Order Description - 408961 - BR | BR | 3 | 262343 | WSCHD | PACK-ISOL | 2019-03-07 | 2020-03-05 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 89
2019-03-31 | 408972 | Work Order Description - 408972 - PSPM | PSPM | 1 | 401159 | SCHD | EQUIP-ISOL | 2019-03-15 | 2020-05-02 | 2020-04-01 | 2020-04-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 408979 | Work Order Description - 408979 - PRJ | PRJ | 3 | 451477 | SCHD | PACK-ISOL | 2019-03-15 | 2020-03-05 | 2019-09-04 | 2019-09-09 | 3 | ENGINEERING | ELECTRICAL | 31
2019-03-31 | 408981 | Work Order Description - 408981 - BR | BR | 3 | 410880 | WSCHD | PACK-ISOL | 2019-03-08 | 2020-03-05 | 2019-07-20 | 2019-07-20 | 3 | MAINTENANCE | MECHANICAL | 89
2019-03-31 | 408998 | Work Order Description - 408998 - PSCM | PSCM | 1 | 655328 | SCHD | PACK-ISOL | 2019-03-07 | 2019-09-05 | 2019-06-06 | 2019-06-06 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 409001 | Work Order Description - 409001 - BR | BR | 4 | 697913 | WSCHD | NORM-OPS | 2019-03-07 | 2019-09-06 | 2019-06-06 | 2019-06-06 | 3 | INTEGRITY | ELECTRICAL | 540
2019-03-31 | 409023 | Work Order Description - 409023 - PRJ | PRJ | 3 | 451477 | SCHD | PACK-ISOL | 2019-03-15 | 2020-03-05 | 2019-09-05 | 2019-09-05 | 3 | ENGINEERING | ELECTRICAL | 0
2019-03-31 | 409035 | Work Order Description - 409035 - PSCM | PSCM | 1 | 18736 | WSCHD | NORM-OPS | 2019-03-08 | 2020-03-05 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 409040 | Work Order Description - 409040 - PSCM | PSCM | 1 | 18736 | WSCHD | NORM-OPS | 2019-03-08 | 2020-03-05 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 409049 | Work Order Description - 409049 - PM | PM | 4 | 301660 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 409051 | Work Order Description - 409051 - PM | PM | 4 | 308893 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 409053 | Work Order Description - 409053 - PM | PM | 4 | 51202 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 409055 | Work Order Description - 409055 - PM | PM | 4 | 308006 | WPLAN | EQUIP-ISOL | 2019-03-07 | 2019-08-29 | 2019-08-01 | 2019-08-01 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 409057 | Work Order Description - 409057 - PSPM | PSPM | 1 | 471324 | WPLAN | PACK-ISOL | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 409060 | Work Order Description - 409060 - PSPM | PSPM | 1 | 308482 | WPLAN | PACK-ISOL | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 409062 | Work Order Description - 409062 - PSPM | PSPM | 1 | 357251 | WPLAN | PACK-ISOL | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 409064 | Work Order Description - 409064 - PSPM | PSPM | 1 | 308482 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409066 | Work Order Description - 409066 - PSPM | PSPM | 1 | 137445 | WPLAN | PACK-ISOL | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 409068 | Work Order Description - 409068 - PSPM | PSPM | 1 | 471324 | WPLAN | PACK-ISOL | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 409070 | Work Order Description - 409070 - PSPM | PSPM | 1 | 671601 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409072 | Work Order Description - 409072 - PSPM | PSPM | 1 | 674772 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409074 | Work Order Description - 409074 - PSPM | PSPM | 1 | 137445 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409076 | Work Order Description - 409076 - PSPM | PSPM | 1 | 357251 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409078 | Work Order Description - 409078 - PSPM | PSPM | 1 | 671604 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409080 | Work Order Description - 409080 - PSPM | PSPM | 1 | 580769 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 409082 | Work Order Description - 409082 - PM | PM | 2 | 305395 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 2 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 409085 | Work Order Description - 409085 - PSPM | PSPM | 1 | 308484 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409089 | Work Order Description - 409089 - PSPM | PSPM | 1 | 308530 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409091 | Work Order Description - 409091 - PSPM | PSPM | 1 | 671605 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409093 | Work Order Description - 409093 - PSPM | PSPM | 1 | 471324 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409095 | Work Order Description - 409095 - PM | PM | 4 | 246173 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | INTEGRITY | SERVICES | 2
2019-03-31 | 409097 | Work Order Description - 409097 - PM | PM | 4 | 546030 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 409099 | Work Order Description - 409099 - PM | PM | 4 | 652482 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | INTEGRITY | SERVICES | 2
2019-03-31 | 409101 | Work Order Description - 409101 - PSPM | PSPM | 1 | 675037 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 409103 | Work Order Description - 409103 - PSPM | PSPM | 1 | 671829 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 409105 | Work Order Description - 409105 - PM | PM | 4 | 547298 | WPLAN | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 409107 | Work Order Description - 409107 - PSPM | PSPM | 1 | 267676 | WSCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-06-23 | 2019-06-23 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 409109 | Work Order Description - 409109 - PSPM | PSPM | 1 | 445681 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409111 | Work Order Description - 409111 - PSPM | PSPM | 1 | 445682 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409113 | Work Order Description - 409113 - PSPM | PSPM | 1 | 445683 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409115 | Work Order Description - 409115 - PSPM | PSPM | 1 | 95531 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409122 | Work Order Description - 409122 - PSPM | PSPM | 1 | 498284 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409124 | Work Order Description - 409124 - PSPM | PSPM | 1 | 262766 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409126 | Work Order Description - 409126 - PSPM | PSPM | 1 | 498285 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409128 | Work Order Description - 409128 - PSPM | PSPM | 1 | 262768 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409130 | Work Order Description - 409130 - PSPM | PSPM | 1 | 189139 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409132 | Work Order Description - 409132 - PSPM | PSPM | 1 | 29639 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 409134 | Work Order Description - 409134 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 409136 | Work Order Description - 409136 - PM | PM | 4 | 501105 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 409138 | Work Order Description - 409138 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 409140 | Work Order Description - 409140 - PM | PM | 4 | 128236 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 409142 | Work Order Description - 409142 - PM | PM | 3 | 20477 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 409144 | Work Order Description - 409144 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 409146 | Work Order Description - 409146 - PSPM | PSPM | 1 | 477477 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 409148 | Work Order Description - 409148 - PSPM | PSPM | 1 | 551286 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 409150 | Work Order Description - 409150 - PSPM | PSPM | 1 | 478298 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 409152 | Work Order Description - 409152 - PM | PM | 4 | 450480 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 2 | MAINTENANCE | INSTRUMENTS | 50
2019-03-31 | 409158 | Work Order Description - 409158 - PM | PM | 4 | 228280 | SCHD | PACK-ISOL | 2019-03-18 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 2 | INTEGRITY | INSPECTION | 8
2019-03-31 | 409160 | Work Order Description - 409160 - PSPM | PSPM | 1 | 450957 | SCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409162 | Work Order Description - 409162 - PSPM | PSPM | 1 | 450957 | SCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409164 | Work Order Description - 409164 - PSPM | PSPM | 1 | 663164 | SCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 409166 | Work Order Description - 409166 - PM | PM | 4 | 266218 | SCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409168 | Work Order Description - 409168 - PSPM | PSPM | 1 | 217169 | SCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409170 | Work Order Description - 409170 - PSPM | PSPM | 1 | 376109 | SCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409172 | Work Order Description - 409172 - PSPM | PSPM | 1 | 376190 | SCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409174 | Work Order Description - 409174 - PSPM | PSPM | 1 | 217214 | SCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409176 | Work Order Description - 409176 - PSPM | PSPM | 1 | 383905 | SCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409178 | Work Order Description - 409178 - PSPM | PSPM | 1 | 375822 | SCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409180 | Work Order Description - 409180 - PSPM | PSPM | 1 | 375821 | SCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409182 | Work Order Description - 409182 - PSPM | PSPM | 1 | 375823 | SCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 409184 | Work Order Description - 409184 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2019-03-07 | 2019-08-05 | 2019-07-05 | 2019-07-07 | 3 | MAINTENANCE | MEDIC | 21
2019-03-31 | 409433 | Work Order Description - 409433 - CM | CM | 4 | 479363 | WRISKREV | NORM-OPS | 2019-03-07 | 2021-03-05 | 2019-06-07 | 2019-06-08 | 4 | MAINTENANCE | ELECTRICAL | 15
2019-03-31 | 409434 | Work Order Description - 409434 - CM | CM | 1 | 479363 | WRISKREV | NORM-OPS | 2019-03-07 | 2021-03-05 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 409435 | Work Order Description - 409435 - CM | CM | 1 | 479363 | WRISKREV | NORM-OPS | 2019-03-07 | 2021-03-05 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 409436 | Work Order Description - 409436 - CM | CM | 1 | 479363 | WRISKREV | NORM-OPS | 2019-03-07 | 2021-03-05 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 409437 | Work Order Description - 409437 - CM | CM | 1 | 479363 | WRISKREV | NORM-OPS | 2019-03-07 | 2020-03-06 |  |  | 3 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 409438 | Work Order Description - 409438 - CM | CM | 1 | 479363 | WRISKREV | NORM-OPS | 2019-03-07 | 2021-03-05 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 409439 | Work Order Description - 409439 - PSCM | PSCM | 1 | 403292 | SCHD | EQUIP-ISOL | 2019-03-15 | 2020-03-06 | 2020-03-05 | 2020-03-05 | 3 | OPERATIONS | SAFETY | 8
2019-03-31 | 409443 | Work Order Description - 409443 - CM | CM | 3 | 498803 | WPLAN | EQUIP-ISOL | 2019-03-08 | 2020-03-06 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 0
2019-03-31 | 409518 | Work Order Description - 409518 - CM | CM | 4 | 674361 | WPLAN | NORM-OPS | 2019-03-07 | 2021-03-05 | 2021-01-21 | 2021-01-21 | 4 | MAINTENANCE | MECHANICAL | 23
2019-03-31 | 409519 | Work Order Description - 409519 - PRJ | PRJ | 4 | 450925 | SCHD | NORM-OPS | 2019-03-13 | 2021-03-05 | 2019-04-06 | 2019-04-07 | 4 | ENGINEERING | ELECTRICAL | 14
2019-03-31 | 409557 | Work Order Description - 409557 - CM | CM | 4 | 570144 | WPLAN | NORM-OPS | 2019-03-10 | 2020-03-06 | 2019-09-05 | 2019-09-05 | 3 | INTEGRITY | FABRIC | 140
2019-03-31 | 409565 | Work Order Description - 409565 - CM | CM | 1 | 538931 | WMATL | NORM-OPS | 2019-03-11 | 2020-03-10 | 2019-06-06 | 2019-06-06 | 3 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 409568 | Work Order Description - 409568 - CM | CM | 4 | 531923 | WSCHD | NORM-OPS | 2019-03-11 | 2019-09-06 | 2019-06-06 | 2019-06-06 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 409572 | Work Order Description - 409572 - CM | CM | 4 | 468614 | WMATL | NORM-OPS | 2019-03-11 | 2019-09-06 | 2019-06-06 | 2019-06-06 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 409575 | Work Order Description - 409575 - CM | CM | 1 | 538933 | WSCHD | NORM-OPS | 2019-03-11 | 2019-09-06 | 2019-06-06 | 2019-06-06 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 409577 | Work Order Description - 409577 - BR | BR | 1 | 353083 | WSCHD | EQUIP-ISOL | 2019-03-08 | 2020-03-06 | 2019-09-05 | 2019-09-05 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 409578 | Work Order Description - 409578 - CM | CM | 1 | 651081 | WMATL | NORM-OPS | 2019-03-11 | 2020-03-07 | 2019-09-06 | 2019-09-06 | 3 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 409585 | Work Order Description - 409585 - CM | CM | 1 | 531925 | WMATL | NORM-OPS | 2019-03-11 | 2019-09-06 | 2019-06-06 | 2019-06-06 | 3 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 409591 | Work Order Description - 409591 - CM | CM | 1 | 531927 | WMATL | NORM-OPS | 2019-03-11 | 2019-09-06 | 2019-06-06 | 2019-06-06 | 3 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 409596 | Work Order Description - 409596 - CM | CM | 4 | 531925 | WMATL | NORM-OPS | 2019-03-11 | 2019-09-06 | 2019-06-06 | 2019-06-06 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 409601 | Work Order Description - 409601 - CM | CM | 1 | 538956 | WSCHD | NORM-OPS | 2019-03-11 | 2019-09-06 | 2019-06-06 | 2019-06-06 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 409603 | Work Order Description - 409603 - CM | CM | 4 | 651425 | WMATL | NORM-OPS | 2019-03-11 | 2019-09-06 | 2019-06-06 | 2019-06-06 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 409607 | Work Order Description - 409607 - CM | CM | 4 | 417555 | WMATL | NORM-OPS | 2019-03-08 | 2020-03-06 | 2019-09-05 | 2019-09-05 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 409614 | Work Order Description - 409614 - PM | PM | 4 | 552877 | SCHD | NORM-OPS | 2019-03-15 | 2020-05-27 | 2019-11-16 | 2019-11-16 | 2 | MAINTENANCE | ELECTRICAL | 144
2019-03-31 | 409616 | Work Order Description - 409616 - BR | BR | 1 | 375805 | WPLAN | TPS | 2019-03-07 | 2019-09-06 | 2019-07-14 | 2019-07-14 | 3 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 409617 | Work Order Description - 409617 - CM | CM | 4 | 272342 | WMATL | NORM-OPS | 2019-03-11 | 2019-09-06 | 2019-06-06 | 2019-06-06 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 409621 | Work Order Description - 409621 - PSCM | PSCM | 1 | 674325 | WMATL | NORM-OPS | 2019-03-11 | 2020-03-10 | 2019-06-06 | 2019-06-06 | 3 | MAINTENANCE | MECHANICAL | 40
2019-03-31 | 409629 | Work Order Description - 409629 - CM | CM | 1 | 363627 | WPLAN | NORM-OPS | 2019-03-08 | 2021-03-05 | 2021-01-21 | 2021-01-21 | 4 | INTEGRITY | CONSTRUCTION | 45
2019-03-31 | 409630 | Work Order Description - 409630 - PSCM | PSCM | 1 | 538415 | WMATL | NORM-OPS | 2019-03-11 | 2020-03-10 | 2019-06-06 | 2019-06-06 | 3 | MAINTENANCE | MECHANICAL | 46
2019-03-31 | 409640 | Work Order Description - 409640 - PSCM | PSCM | 1 | 538448 | WMATL | NORM-OPS | 2019-03-11 | 2020-03-10 | 2019-06-06 | 2019-06-06 | 3 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 409645 | Work Order Description - 409645 - CM | CM | 4 | 378847 | SCHD | NORM-OPS | 2019-03-15 | 2019-09-06 | 2019-06-07 | 2019-06-09 | 3 | INTEGRITY | INSPECTION | 20
2019-03-31 | 409647 | Work Order Description - 409647 - CM | CM | 4 | 272355 | WMATL | NORM-OPS | 2019-03-11 | 2021-03-06 | 2021-01-22 | 2021-01-22 | 4 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 409651 | Work Order Description - 409651 - CM | CM | 1 | 272337 | WMATL | NORM-OPS | 2019-03-11 | 2020-03-10 | 2019-06-06 | 2019-06-06 | 3 | MAINTENANCE | MECHANICAL | 42
2019-03-31 | 409659 | Work Order Description - 409659 - CM | CM | 1 | 674303 | WMATL | NORM-OPS | 2019-03-11 | 2020-03-10 | 2019-06-06 | 2019-06-06 | 3 | MAINTENANCE | MECHANICAL | 44
2019-03-31 | 409677 | Work Order Description - 409677 - CM | CM | 3 | 411324 | WPLAN | TPS | 2019-03-25 | 2021-03-05 | 2020-03-05 | 2020-03-05 | 4 | INTEGRITY | CONSTRUCTION | 12
2019-03-31 | 409681 | Work Order Description - 409681 - PM | PM | 4 | 527308 | WPLAN | PACK-ISOL | 2019-03-07 | 2019-04-07 | 2019-04-07 | 2019-04-08 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 409683 | Work Order Description - 409683 - BR | BR | 4 | 262382 | WMATL | SYS-ISOL | 2019-03-15 | 2021-03-06 | 2019-08-03 | 2019-08-04 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 409684 | Work Order Description - 409684 - BR | BR | 4 | 189046 | SCHD | SYS-ISOL | 2019-03-25 | 2021-03-06 | 2019-03-16 | 2019-03-17 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 409685 | Work Order Description - 409685 - PSPM | PSPM | 1 | 531853 | WSCHD | NORM-OPS | 2019-03-08 | 2019-08-06 | 2019-06-24 | 2019-06-24 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 409687 | Work Order Description - 409687 - PM | PM | 4 | 354350 | WSCHD | NORM-OPS | 2019-03-08 | 2019-08-06 | 2019-06-24 | 2019-06-24 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 409689 | Work Order Description - 409689 - PM | PM | 4 | 321142 | WPLAN | PACK-ISOL | 2019-03-08 | 2019-08-06 | 2019-06-24 | 2019-06-24 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 409695 | Work Order Description - 409695 - PSPM | PSPM | 1 | 321203 | WSCHD | NORM-OPS | 2019-03-08 | 2019-08-06 | 2019-06-24 | 2019-06-24 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 409697 | Work Order Description - 409697 - PSPM | PSPM | 1 | 321218 | WSCHD | NORM-OPS | 2019-03-08 | 2019-08-06 | 2019-06-24 | 2019-06-24 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 409699 | Work Order Description - 409699 - PM | PM | 4 | 294918 | WPLAN | NORM-OPS | 2019-03-08 | 2019-08-06 | 2019-06-24 | 2019-06-24 | 2 | MAINTENANCE | MECHANICAL | 10.5
2019-03-31 | 409701 | Work Order Description - 409701 - PM | PM | 4 | 294916 | WSCHD | NORM-OPS | 2019-03-08 | 2019-08-06 | 2019-06-24 | 2019-06-24 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 409703 | Work Order Description - 409703 - PM | PM | 4 | 584012 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-06 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 409705 | Work Order Description - 409705 - PSPM | PSPM | 1 | 446837 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-06 | 2019-07-06 | 2019-07-06 | 1 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 409709 | Work Order Description - 409709 - PSPM | PSPM | 1 | 320575 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-06 | 2019-07-06 | 2019-07-06 | 1 | OPERATIONS | OPERATIONS | 12
2019-03-31 | 409711 | Work Order Description - 409711 - PM | PM | 4 | 482734 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-06 | 2019-07-06 | 2019-07-06 | 2 | INTEGRITY | INSPECTION | 72
2019-03-31 | 409713 | Work Order Description - 409713 - PSPM | PSPM | 1 | 128233 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-06 | 2019-07-06 | 2019-07-06 | 1 | MAINTENANCE | SAFETY | 24
2019-03-31 | 409715 | Work Order Description - 409715 - PM | PM | 4 | 584765 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-06 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 409717 | Work Order Description - 409717 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-06 | 2019-07-06 | 2019-07-06 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 409719 | Work Order Description - 409719 - PSPM | PSPM | 1 | 99577 | SCHD | NORM-OPS | 2019-03-15 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 409767 | Work Order Description - 409767 - PSPM | PSPM | 1 | 659084 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-06 | 2019-07-06 | 2019-07-07 | 1 | OPERATIONS | SAFETY | 14
2019-03-31 | 409769 | Work Order Description - 409769 - PM | PM | 4 | 126059 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-06 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 409771 | Work Order Description - 409771 - PM | PM | 4 | 80446 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-06 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 409773 | Work Order Description - 409773 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-06 | 2019-07-06 | 2019-07-06 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 409775 | Work Order Description - 409775 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-06 | 2019-07-06 | 2019-07-06 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 409777 | Work Order Description - 409777 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-06 | 2019-07-06 | 2019-07-06 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 410008 | Work Order Description - 410008 - PRJ | PRJ | 1 | 213813 | WSCHD | NORM-OPS | 2019-03-10 | 2021-03-06 | 2021-01-22 | 2021-01-22 | 4 | ENGINEERING | INSTRUMENTS | 150
2019-03-31 | 410017 | Work Order Description - 410017 - PSCM | PSCM | 1 | 361959 | WSCHD | NORM-OPS | 2019-03-10 | 2021-03-06 | 2021-01-22 | 2021-01-22 | 4 | MAINTENANCE | MECHANICAL | 33
2019-03-31 | 410028 | Work Order Description - 410028 - CM | CM | 4 | 462658 | SCHD | NORM-OPS | 2019-03-15 | 2021-03-06 | 2019-03-30 | 2019-03-30 | 4 | INTEGRITY | FABRIC | 8
2019-03-31 | 410066 | Work Order Description - 410066 - BR | BR | 3 | 217108 | INPRG | EQUIP-ISOL | 2019-03-11 | 2019-06-01 | 2019-04-21 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 410079 | Work Order Description - 410079 - BR | BR | 1 | 368281 | WSCHD | NORM-OPS | 2019-03-11 | 2020-03-07 | 2019-08-10 | 2019-08-10 | 3 | INTEGRITY | CONSTRUCTION | 50
2019-03-31 | 410094 | Work Order Description - 410094 - PRJ | PRJ | 3 | 127636 | SCHD | NORM-OPS | 2019-03-08 | 2019-04-06 | 2019-03-09 | 2019-03-18 | 2 | ENGINEERING | MECHANICAL | 1
2019-03-31 | 410120 | Work Order Description - 410120 - BR | BR | 3 | 479296 | INPRG | EQUIP-ISOL | 2019-03-19 | 2019-06-01 | 2019-04-19 | 2019-04-19 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410138 | Work Order Description - 410138 - CM | CM | 1 | 368279 | WPLAN | NORM-OPS | 2019-03-25 | 2019-09-07 | 2019-06-07 | 2019-06-07 | 3 | INTEGRITY | CONSTRUCTION | 1
2019-03-31 | 410157 | Work Order Description - 410157 - CM | CM | 4 | 72735 | SCHD | NORM-OPS | 2019-03-09 | 2021-03-06 | 2021-01-22 | 2021-01-24 | 4 | INTEGRITY | INSPECTION | 1
2019-03-31 | 410160 | Work Order Description - 410160 - PRJ | PRJ | 3 | 127779 | WPLAN | NORM-OPS | 2019-03-09 | 2021-03-06 | 2019-04-06 | 2019-05-15 | 4 | ENGINEERING | WELLS | 6184
2019-03-31 | 410169 | Work Order Description - 410169 - BR | BR | 3 | 666270 | WSCHD | TPS | 2019-03-10 | 2021-03-06 | 2021-01-22 | 2021-01-22 | 4 | MAINTENANCE | MECHANICAL | 108
2019-03-31 | 410177 | Work Order Description - 410177 - BR | BR | 4 | 204611 | SCHD | NORM-OPS | 2019-03-08 | 2021-03-06 | 2019-04-20 | 2019-04-20 | 4 | INTEGRITY | SERVICES | 18
2019-03-31 | 410204 | Work Order Description - 410204 - CM | CM | 3 | 501256 | SCHD | NORM-OPS | 2019-03-15 | 2020-03-07 | 2020-03-07 | 2020-03-07 | 3 | MAINTENANCE | ELECTRICAL | 15
2019-03-31 | 410205 | Work Order Description - 410205 - BR | BR | 3 | 214986 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2020-03-09 | 2020-03-08 | 2020-03-08 | 3 | MAINTENANCE | CONSTRUCTION | 6
2019-03-31 | 410213 | Work Order Description - 410213 - BR | BR | 3 | 495400 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2020-03-09 | 2020-03-08 | 2020-03-08 | 3 | MAINTENANCE | CONSTRUCTION | 6
2019-03-31 | 410220 | Work Order Description - 410220 - BR | BR | 3 | 495421 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2020-03-09 | 2020-03-08 | 2020-03-08 | 3 | MAINTENANCE | CONSTRUCTION | 6
2019-03-31 | 410228 | Work Order Description - 410228 - BR | BR | 3 | 215010 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2020-03-09 | 2020-03-08 | 2020-03-08 | 3 | MAINTENANCE | CONSTRUCTION | 6
2019-03-31 | 410259 | Work Order Description - 410259 - PSPM | PSPM | 1 | 540544 | WSCHD | EQUIP-ISOL | 2019-03-09 | 2019-08-07 | 2019-06-25 | 2019-06-25 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 410261 | Work Order Description - 410261 - PM | PM | 2 | 572308 | WSCHD | NORM-OPS | 2019-03-09 | 2019-08-07 | 2019-06-25 | 2019-06-25 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 410263 | Work Order Description - 410263 - PM | PM | 4 | 245662 | WPLAN | PACK-ISOL | 2019-03-09 | 2019-08-07 | 2019-06-25 | 2019-06-25 | 2 | MAINTENANCE | MECHANICAL | 87
2019-03-31 | 410274 | Work Order Description - 410274 - PM | PM | 4 | 580762 | WSCHD | NORM-OPS | 2019-03-09 | 2019-08-07 | 2019-06-25 | 2019-06-25 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 410276 | Work Order Description - 410276 - PM | PM | 2 | 533276 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410278 | Work Order Description - 410278 - PM | PM | 4 | 464022 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 410280 | Work Order Description - 410280 - PM | PM | 1 | 446516 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 410282 | Work Order Description - 410282 - PSPM | PSPM | 1 | 29041 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 410284 | Work Order Description - 410284 - PSPM | PSPM | 1 | 260184 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 410286 | Work Order Description - 410286 - PSPM | PSPM | 1 | 458750 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 410288 | Work Order Description - 410288 - PSPM | PSPM | 1 | 458751 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 410290 | Work Order Description - 410290 - PSPM | PSPM | 1 | 259478 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 410292 | Work Order Description - 410292 - PSPM | PSPM | 1 | 551259 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 410294 | Work Order Description - 410294 - PSPM | PSPM | 1 | 458749 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 410296 | Work Order Description - 410296 - PSPM | PSPM | 1 | 458749 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 410298 | Work Order Description - 410298 - PSPM | PSPM | 1 | 476292 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410300 | Work Order Description - 410300 - PSPM | PSPM | 1 | 502999 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 410302 | Work Order Description - 410302 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 2 | MAINTENANCE | SAFETY | 7
2019-03-31 | 410304 | Work Order Description - 410304 - PM | PM | 4 | 396255 | WPLAN | EQUIP-ISOL | 2019-03-09 | 2019-08-07 | 2019-07-07 | 2019-07-08 | 1 | INTEGRITY | MECHANICAL | 10
2019-03-31 | 410308 | Work Order Description - 410308 - PM | PM | 1 | 99955 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-31 | 2019-07-07 | 2019-07-07 | 2 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 410310 | Work Order Description - 410310 - PM | PM | 1 | 105627 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-31 | 2019-07-07 | 2019-07-07 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 410312 | Work Order Description - 410312 - PM | PM | 4 | 100182 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-31 | 2019-07-07 | 2019-07-07 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 410314 | Work Order Description - 410314 - PM | PM | 4 | 185339 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 410316 | Work Order Description - 410316 - PM | PM | 4 | 185344 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 410318 | Work Order Description - 410318 - PM | PM | 4 | 669981 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 410320 | Work Order Description - 410320 - PM | PM | 4 | 185367 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 410322 | Work Order Description - 410322 - PM | PM | 4 | 436674 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 410324 | Work Order Description - 410324 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 410326 | Work Order Description - 410326 - PSPM | PSPM | 1 | 669726 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 410328 | Work Order Description - 410328 - PSPM | PSPM | 1 | 378468 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 410330 | Work Order Description - 410330 - PSPM | PSPM | 1 | 528118 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | INTEGRITY | SERVICES | 4
2019-03-31 | 410332 | Work Order Description - 410332 - PSPM | PSPM | 1 | 186616 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 410334 | Work Order Description - 410334 - PSPM | PSPM | 1 | 99955 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 410336 | Work Order Description - 410336 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 410338 | Work Order Description - 410338 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 410343 | Work Order Description - 410343 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-07 | 2019-07-07 | 2019-07-07 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 410569 | Work Order Description - 410569 - BR | BR | 1 | 315540 | WPLAN | NORM-OPS | 2019-03-10 | 2021-03-07 | 2021-01-23 | 2021-01-23 | 4 | MAINTENANCE | ELECTRICAL | 16
2019-03-31 | 410578 | Work Order Description - 410578 - CM | CM | 3 | 215142 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2020-03-09 | 2020-03-08 | 2020-03-08 | 3 | MAINTENANCE | CONSTRUCTION | 6
2019-03-31 | 410581 | Work Order Description - 410581 - PRJ | PRJ | 4 | 435784 | SCHD | PACK-ISOL | 2019-03-15 | 2019-09-08 | 2019-06-08 | 2019-06-13 | 3 | MAINTENANCE | MECHANICAL | 36
2019-03-31 | 410603 | Work Order Description - 410603 - BR | BR | 1 | 361798 | WPLAN | EQUIP-ISOL | 2019-03-10 | 2021-03-07 | 2021-01-23 | 2021-01-23 | 4 | OPERATIONS | MECHANICAL | 21
2019-03-31 | 410604 | Work Order Description - 410604 - BR | BR | 1 | 547275 | WPLAN | EQUIP-ISOL | 2019-03-10 | 2021-03-07 | 2021-01-23 | 2021-01-23 | 4 | OPERATIONS | MECHANICAL | 18
2019-03-31 | 410623 | Work Order Description - 410623 - PSPM | PSPM | 1 | 540576 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 410625 | Work Order Description - 410625 - PSPM | PSPM | 1 | 541344 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 410627 | Work Order Description - 410627 - PSPM | PSPM | 1 | 541344 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 410629 | Work Order Description - 410629 - PSPM | PSPM | 1 | 541344 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | INSTRUMENTS | 40
2019-03-31 | 410631 | Work Order Description - 410631 - PSPM | PSPM | 1 | 541344 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | INSTRUMENTS | 40
2019-03-31 | 410633 | Work Order Description - 410633 - PSPM | PSPM | 1 | 541344 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 410635 | Work Order Description - 410635 - PM | PM | 4 | 541035 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410637 | Work Order Description - 410637 - PM | PM | 4 | 541035 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410639 | Work Order Description - 410639 - PM | PM | 4 | 541035 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410641 | Work Order Description - 410641 - PM | PM | 4 | 313581 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410643 | Work Order Description - 410643 - PM | PM | 4 | 357148 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410645 | Work Order Description - 410645 - PM | PM | 4 | 546662 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410647 | Work Order Description - 410647 - PM | PM | 4 | 674416 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410649 | Work Order Description - 410649 - PM | PM | 4 | 18317 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410651 | Work Order Description - 410651 - PM | PM | 4 | 18316 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410653 | Work Order Description - 410653 - PM | PM | 4 | 666316 | WPLAN | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410655 | Work Order Description - 410655 - PM | PM | 4 | 417521 | WPLAN | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410657 | Work Order Description - 410657 - PM | PM | 4 | 50099 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 410659 | Work Order Description - 410659 - PM | PM | 4 | 50098 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 410661 | Work Order Description - 410661 - PM | PM | 4 | 411571 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410663 | Work Order Description - 410663 - PM | PM | 4 | 358159 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410665 | Work Order Description - 410665 - PM | PM | 4 | 540667 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 410667 | Work Order Description - 410667 - PM | PM | 4 | 678551 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 410669 | Work Order Description - 410669 - PM | PM | 4 | 674306 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 410671 | Work Order Description - 410671 - PM | PM | 4 | 308006 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 410673 | Work Order Description - 410673 - PM | PM | 4 | 361470 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 410675 | Work Order Description - 410675 - PM | PM | 4 | 546054 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410677 | Work Order Description - 410677 - PM | PM | 4 | 541035 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410679 | Work Order Description - 410679 - PM | PM | 4 | 541035 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410681 | Work Order Description - 410681 - PM | PM | 4 | 541035 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410683 | Work Order Description - 410683 - PM | PM | 4 | 541035 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410685 | Work Order Description - 410685 - PM | PM | 3 | 314432 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 410687 | Work Order Description - 410687 - PM | PM | 3 | 400406 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 410689 | Work Order Description - 410689 - PSPM | PSPM | 1 | 294961 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | OPERATIONS | SAFETY | 2
2019-03-31 | 410691 | Work Order Description - 410691 - PM | PM | 3 | 408210 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410693 | Work Order Description - 410693 - PM | PM | 4 | 353518 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410695 | Work Order Description - 410695 - PM | PM | 4 | 249681 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410697 | Work Order Description - 410697 - PSPM | PSPM | 1 | 678021 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 410711 | Work Order Description - 410711 - PSPM | PSPM | 1 | 360506 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 410713 | Work Order Description - 410713 - PSPM | PSPM | 1 | 261935 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 410715 | Work Order Description - 410715 - PM | PM | 4 | 547429 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 410717 | Work Order Description - 410717 - PSPM | PSPM | 1 | 681835 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 410719 | Work Order Description - 410719 - PSPM | PSPM | 1 | 470877 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 410721 | Work Order Description - 410721 - PSPM | PSPM | 1 | 671828 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 410723 | Work Order Description - 410723 - PM | PM | 4 | 519760 | WPLAN | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 410725 | Work Order Description - 410725 - PM | PM | 4 | 361803 | WPLAN | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 410727 | Work Order Description - 410727 - PSPM | PSPM | 1 | 481409 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 410729 | Work Order Description - 410729 - PM | PM | 4 | 360243 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 410731 | Work Order Description - 410731 - PM | PM | 4 | 416276 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | SAFETY | 3
2019-03-31 | 410733 | Work Order Description - 410733 - PM | PM | 4 | 457519 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 410735 | Work Order Description - 410735 - PSPM | PSPM | 1 | 292871 | WSCHD | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 410737 | Work Order Description - 410737 - PSPM | PSPM | 1 | 260895 | WPLAN | PACK-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 410739 | Work Order Description - 410739 - PSPM | PSPM | 1 | 360506 | WSCHD | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-06-26 | 2019-06-26 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 410741 | Work Order Description - 410741 - PM | PM | 4 | 450390 | SCHD | PACK-ISOL | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 3 | INTEGRITY | MECHANICAL | 34
2019-03-31 | 410749 | Work Order Description - 410749 - PSPM | PSPM | 1 | 189054 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 410751 | Work Order Description - 410751 - PSPM | PSPM | 1 | 325633 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 410753 | Work Order Description - 410753 - PSPM | PSPM | 1 | 81212 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 410755 | Work Order Description - 410755 - PSPM | PSPM | 1 | 567229 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 410757 | Work Order Description - 410757 - PSPM | PSPM | 1 | 180457 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 410759 | Work Order Description - 410759 - PSPM | PSPM | 1 | 180458 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 410761 | Work Order Description - 410761 - PSPM | PSPM | 1 | 458748 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 410763 | Work Order Description - 410763 - PM | PM | 4 | 556260 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 410765 | Work Order Description - 410765 - PM | PM | 2 | 216011 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 410767 | Work Order Description - 410767 - PM | PM | 4 | 320026 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 410769 | Work Order Description - 410769 - PM | PM | 4 | 216158 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 410771 | Work Order Description - 410771 - PM | PM | 4 | 74216 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 410773 | Work Order Description - 410773 - PSPM | PSPM | 1 | 659510 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 410775 | Work Order Description - 410775 - PSPM | PSPM | 1 | 659510 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 410777 | Work Order Description - 410777 - PSPM | PSPM | 1 | 659510 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 410779 | Work Order Description - 410779 - PSPM | PSPM | 1 | 659510 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 410781 | Work Order Description - 410781 - PSPM | PSPM | 1 | 396377 | WPLAN | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 410783 | Work Order Description - 410783 - PSPM | PSPM | 1 | 396378 | WPLAN | EQUIP-ISOL | 2019-03-10 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 410785 | Work Order Description - 410785 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 410787 | Work Order Description - 410787 - PSPM | PSPM | 1 | 659510 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 410789 | Work Order Description - 410789 - PSPM | PSPM | 1 | 663482 | WPLAN | NORM-OPS | 2019-03-10 | 2019-08-08 | 2019-07-08 | 2019-07-09 | 1 | INTEGRITY | INSPECTION | 8
2019-03-31 | 410791 | Work Order Description - 410791 - PSPM | PSPM | 1 | 375669 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 410793 | Work Order Description - 410793 - PSPM | PSPM | 1 | 375680 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 410795 | Work Order Description - 410795 - PSPM | PSPM | 1 | 228343 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-09 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 410797 | Work Order Description - 410797 - PSPM | PSPM | 1 | 450986 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 410799 | Work Order Description - 410799 - PM | PM | 4 | 670525 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 410802 | Work Order Description - 410802 - PSPM | PSPM | 1 | 227942 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 410804 | Work Order Description - 410804 - PM | PM | 4 | 375852 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 410807 | Work Order Description - 410807 - PSPM | PSPM | 1 | 659552 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 411128 | Work Order Description - 411128 - CM | CM | 3 | 449592 | SCHD | EQUIP-ISOL | 2019-03-29 | 2020-03-09 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | ELECTRICAL | 176
2019-03-31 | 411137 | Work Order Description - 411137 - CM | CM | 3 | 186054 | SCHD | EQUIP-ISOL | 2019-03-29 | 2020-03-09 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | ELECTRICAL | 96
2019-03-31 | 411145 | Work Order Description - 411145 - PRJ | PRJ | 3 | 177113 | SCHD | NORM-OPS | 2019-03-29 | 2021-03-08 | 2019-05-25 | 2019-05-25 | 4 | MAINTENANCE | ELECTRICAL | 108
2019-03-31 | 411161 | Work Order Description - 411161 - BR | BR | 3 | 245331 | WSCHD | NORM-OPS | 2019-03-11 | 2021-03-09 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | SERVICES | 144
2019-03-31 | 411210 | Work Order Description - 411210 - BR | BR | 4 | 402408 | SCHD | NORM-OPS | 2019-03-29 | 2021-03-08 | 2021-01-24 | 2021-01-24 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 411212 | Work Order Description - 411212 - BR | BR | 3 | 122545 | WPLAN | TPS | 2019-03-12 | 2021-03-08 | 2019-07-14 | 2019-07-16 | 4 | MAINTENANCE | OPERATIONS | 21
2019-03-31 | 411217 | Work Order Description - 411217 - BR | BR | 4 | 480051 | SCHD | TPS | 2019-03-29 | 2021-03-08 | 2021-01-24 | 2021-01-24 | 4 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 411223 | Work Order Description - 411223 - CM | CM | 4 | 670468 | SCHD | PACK-ISOL | 2019-03-12 | 2019-10-03 | 2019-05-05 | 2019-05-11 | 1 | MAINTENANCE | MECHANICAL | 64
2019-03-31 | 411269 | Work Order Description - 411269 - CM | CM | 3 | 18476 | WPLAN | PACK-ISOL | 2019-03-11 | 2019-06-03 | 2019-04-27 | 2019-04-27 | 2 | INTEGRITY | CONSTRUCTION | 1032
2019-03-31 | 411291 | Work Order Description - 411291 - CM | CM | 4 | 468584 | WMATL | NORM-OPS | 2019-03-11 | 2021-03-08 | 2021-01-24 | 2021-01-24 | 4 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 411326 | Work Order Description - 411326 - BR | BR | 2 | 125349 | WPLAN | SYS-ISOL | 2019-03-12 | 2020-03-10 | 2019-09-09 | 2019-09-11 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 411329 | Work Order Description - 411329 - PSPM | PSPM | 1 | 595879 | WSCHD | EQUIP-ISOL | 2019-03-11 | 2019-08-09 | 2019-06-27 | 2019-06-27 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 411331 | Work Order Description - 411331 - PSPM | PSPM | 1 | 679179 | WSCHD | EQUIP-ISOL | 2019-03-11 | 2019-08-09 | 2019-06-27 | 2019-06-27 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 411333 | Work Order Description - 411333 - PM | PM | 3 | 681000 | WSCHD | NORM-OPS | 2019-03-11 | 2019-08-09 | 2019-06-27 | 2019-06-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 411335 | Work Order Description - 411335 - PM | PM | 3 | 681000 | WSCHD | NORM-OPS | 2019-03-11 | 2019-08-09 | 2019-06-27 | 2019-06-27 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 411337 | Work Order Description - 411337 - PM | PM | 3 | 681000 | WSCHD | NORM-OPS | 2019-03-11 | 2019-08-09 | 2019-06-27 | 2019-06-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 411339 | Work Order Description - 411339 - PM | PM | 3 | 681000 | WSCHD | NORM-OPS | 2019-03-11 | 2019-08-09 | 2019-06-27 | 2019-06-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 411341 | Work Order Description - 411341 - PM | PM | 3 | 681000 | WSCHD | NORM-OPS | 2019-03-11 | 2019-08-09 | 2019-06-27 | 2019-06-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 411343 | Work Order Description - 411343 - PSPM | PSPM | 1 | 361803 | WSCHD | NORM-OPS | 2019-03-11 | 2019-08-09 | 2019-06-27 | 2019-06-27 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 411345 | Work Order Description - 411345 - PM | PM | 4 | 137798 | WPLAN | PACK-ISOL | 2019-03-11 | 2019-08-09 | 2019-07-12 | 2019-07-12 | 2 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 411347 | Work Order Description - 411347 - PSPM | PSPM | 1 | 59055 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 1 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 411351 | Work Order Description - 411351 - PM | PM | 4 | 481609 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 411353 | Work Order Description - 411353 - PM | PM | 4 | 476154 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 411355 | Work Order Description - 411355 - PM | PM | 4 | 479289 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-15 | 2019-07-09 | 2019-07-09 | 3 | OPERATIONS | SAFETY | 2
2019-03-31 | 411357 | Work Order Description - 411357 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 411361 | Work Order Description - 411361 - PM | PM | 4 | 632580 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 411363 | Work Order Description - 411363 - PM | PM | 4 | 583919 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 3 | OPERATIONS | SAFETY | 14
2019-03-31 | 411365 | Work Order Description - 411365 - PM | PM | 4 | 122683 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 3 | OPERATIONS | SAFETY | 4
2019-03-31 | 411367 | Work Order Description - 411367 - PM | PM | 4 | 583934 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 411369 | Work Order Description - 411369 - PM | PM | 4 | 583934 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 3 | OPERATIONS | SAFETY | 3
2019-03-31 | 411371 | Work Order Description - 411371 - PSPM | PSPM | 4 | 403503 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 411385 | Work Order Description - 411385 - PM | PM | 4 | 74891 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 2 | OPERATIONS | OPERATIONS | 1
2019-03-31 | 411387 | Work Order Description - 411387 - PSPM | PSPM | 1 | 659510 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 411389 | Work Order Description - 411389 - PSPM | PSPM | 1 | 450984 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 411391 | Work Order Description - 411391 - PSPM | PSPM | 1 | 450984 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 411393 | Work Order Description - 411393 - PSPM | PSPM | 1 | 450984 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 411395 | Work Order Description - 411395 - PSPM | PSPM | 1 | 450984 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 411397 | Work Order Description - 411397 - PSPM | PSPM | 1 | 392215 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 411399 | Work Order Description - 411399 - PSPM | PSPM | 1 | 453251 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-10 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 411401 | Work Order Description - 411401 - PM | PM | 3 | 83954 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-09 | 2019-07-09 | 2019-07-09 | 1 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 411530 | Work Order Description - 411530 - CM | CM | 1 | 29041 | WPLAN | NORM-OPS | 2019-03-29 | 2019-09-28 | 2019-06-28 | 2019-07-01 | 3 | MAINTENANCE | SERVICES | 24
2019-03-31 | 411549 | Work Order Description - 411549 - PSPM | PSPM | 1 | 93317 | WPLAN | SYS-ISOL | 2019-03-11 | 2020-04-14 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 411551 | Work Order Description - 411551 - CM | CM | 4 | 99664 | SCHD | NORM-OPS | 2019-03-15 | 2021-03-09 | 2019-03-30 | 2019-04-20 | 4 | MAINTENANCE | ELECTRICAL | 42
2019-03-31 | 411556 | Work Order Description - 411556 - PSPM | PSPM | 1 | 89492 | WPLAN | EQUIP-ISOL | 2019-03-11 | 2020-04-11 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 411560 | Work Order Description - 411560 - PSPM | PSPM | 1 | 388111 | WPLAN | EQUIP-ISOL | 2019-03-11 | 2020-04-12 | 2019-07-13 | 2019-07-13 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 411577 | Work Order Description - 411577 - CM | CM | 1 | 262054 | WSCHD | NORM-OPS | 2019-03-17 | 2019-09-16 | 2019-10-26 | 2019-10-26 | 3 | MAINTENANCE | ELECTRICAL | 345
2019-03-31 | 411591 | Work Order Description - 411591 - BR | BR | 1 | 457572 | WRISKQ | NORM-OPS | 2019-03-16 | 2021-03-09 |  |  | 4 | MAINTENANCE | MECHANICAL | 0
2019-03-31 | 411597 | Work Order Description - 411597 - CM | CM | 2 | 675037 | SCHD | EQUIP-ISOL | 2019-03-29 | 2020-03-14 | 2019-03-30 | 2019-03-30 | 3 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 411598 | Work Order Description - 411598 - PSCM | PSCM | 3 | 18476 | WSCHD | PACK-ISOL | 2019-03-11 | 2019-06-04 | 2019-04-22 | 2019-04-22 | 2 | INTEGRITY | CONSTRUCTION | 396
2019-03-31 | 411609 | Work Order Description - 411609 - CM | CM | 1 | 528176 | SCHD | EQUIP-ISOL | 2019-03-15 | 2020-03-10 | 2019-09-09 | 2019-09-15 | 3 | INTEGRITY | INSPECTION | 126
2019-03-31 | 411630 | Work Order Description - 411630 - BR | BR | 1 | 262054 | WSCHD | NORM-OPS | 2019-03-11 | 2020-03-10 |  |  | 3 | MAINTENANCE | ELECTRICAL | 450
2019-03-31 | 411632 | Work Order Description - 411632 - BR | BR | 1 | 262054 | WSCHD | NORM-OPS | 2019-03-17 | 2019-09-16 | 2019-10-26 | 2019-10-26 | 3 | MAINTENANCE | ELECTRICAL | 600
2019-03-31 | 411644 | Work Order Description - 411644 - CM | CM | 4 | 451342 | SCHD | NORM-OPS | 2019-03-15 | 2020-03-10 | 2019-09-09 | 2019-09-14 | 3 | INTEGRITY | FABRIC | 120
2019-03-31 | 411667 | Work Order Description - 411667 - CM | CM | 4 | 378847 | WPLAN | NORM-OPS | 2019-03-12 | 2020-03-10 | 2019-09-10 | 2019-09-21 | 3 | INTEGRITY | FABRIC | 336
2019-03-31 | 411672 | Work Order Description - 411672 - CM | CM | 4 | 451342 | WPLAN | NORM-OPS | 2019-03-12 | 2020-03-10 | 2019-09-10 | 2019-09-25 | 3 | INTEGRITY | FABRIC | 448
2019-03-31 | 411673 | Work Order Description - 411673 - CM | CM | 1 | 481656 | SCHD | NORM-OPS | 2019-03-29 | 2019-09-10 | 2019-06-11 | 2019-06-13 | 3 | MAINTENANCE | ELECTRICAL | 80
2019-03-31 | 411676 | Work Order Description - 411676 - CM | CM | 1 | 481656 | WPLAN | NORM-OPS | 2019-03-16 | 2021-03-09 | 2021-01-25 | 2021-01-25 | 4 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 411694 | Work Order Description - 411694 - BR | BR | 3 | 183627 | WPLAN | NORM-OPS | 2019-03-16 | 2019-06-04 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 411698 | Work Order Description - 411698 - PSPM | PSPM | 1 | 540579 | WSCHD | EQUIP-ISOL | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 411700 | Work Order Description - 411700 - PM | PM | 4 | 314187 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 411702 | Work Order Description - 411702 - PM | PM | 4 | 314187 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 411704 | Work Order Description - 411704 - PM | PM | 4 | 314187 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 411706 | Work Order Description - 411706 - PSPM | PSPM | 1 | 292677 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 411708 | Work Order Description - 411708 - PSPM | PSPM | 1 | 457573 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 1 | OPERATIONS | SAFETY | 2
2019-03-31 | 411710 | Work Order Description - 411710 - PM | PM | 4 | 540691 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 411712 | Work Order Description - 411712 - PSPM | PSPM | 1 | 697891 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 1 | INTEGRITY | SERVICES | 4
2019-03-31 | 411714 | Work Order Description - 411714 - PM | PM | 4 | 674307 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 411716 | Work Order Description - 411716 - PM | PM | 4 | 671166 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 411718 | Work Order Description - 411718 - PM | PM | 4 | 361473 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 411720 | Work Order Description - 411720 - PM | PM | 4 | 546298 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 411722 | Work Order Description - 411722 - PM | PM | 4 | 314187 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 411724 | Work Order Description - 411724 - PM | PM | 4 | 314187 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 411726 | Work Order Description - 411726 - PM | PM | 4 | 314187 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 411728 | Work Order Description - 411728 - PM | PM | 4 | 314187 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 411730 | Work Order Description - 411730 - PSPM | PSPM | 1 | 547275 | WPLAN | PACK-ISOL | 2019-03-12 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 411734 | Work Order Description - 411734 - PSPM | PSPM | 1 | 547276 | WPLAN | PACK-ISOL | 2019-03-12 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 411738 | Work Order Description - 411738 - PSPM | PSPM | 1 | 519760 | WPLAN | PACK-ISOL | 2019-03-12 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 411742 | Work Order Description - 411742 - PSPM | PSPM | 1 | 547298 | WPLAN | PACK-ISOL | 2019-03-12 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 411746 | Work Order Description - 411746 - PSPM | PSPM | 1 | 410324 | WPLAN | PACK-ISOL | 2019-03-12 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 411750 | Work Order Description - 411750 - PSPM | PSPM | 1 | 361798 | WPLAN | PACK-ISOL | 2019-03-12 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 411754 | Work Order Description - 411754 - PSPM | PSPM | 1 | 361799 | WPLAN | PACK-ISOL | 2019-03-12 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 411758 | Work Order Description - 411758 - PSPM | PSPM | 1 | 361803 | WPLAN | PACK-ISOL | 2019-03-12 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 411762 | Work Order Description - 411762 - PSPM | PSPM | 1 | 519759 | WPLAN | PACK-ISOL | 2019-03-12 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | MECHANICAL | 18
2019-03-31 | 411766 | Work Order Description - 411766 - PM | PM | 4 | 481470 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 411768 | Work Order Description - 411768 - PSPM | PSPM | 1 | 545260 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 411770 | Work Order Description - 411770 - PSPM | PSPM | 1 | 545261 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 411772 | Work Order Description - 411772 - PSPM | PSPM | 1 | 51662 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 411774 | Work Order Description - 411774 - PSPM | PSPM | 1 | 361165 | WPLAN | PACK-ISOL | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 411776 | Work Order Description - 411776 - PSPM | PSPM | 1 | 675036 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 411778 | Work Order Description - 411778 - PSPM | PSPM | 1 | 547275 | WSCHD | NORM-OPS | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 411780 | Work Order Description - 411780 - PSPM | PSPM | 1 | 248338 | WPLAN | EQUIP-ISOL | 2019-03-12 | 2019-08-10 | 2019-06-28 | 2019-06-28 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 411782 | Work Order Description - 411782 - PM | PM | 4 | 401566 | SCHD | PACK-ISOL | 2019-03-15 | 2019-08-25 | 2019-07-10 | 2019-07-10 | 4 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 411786 | Work Order Description - 411786 - PM | PM | 4 | 458029 | SCHD | NORM-OPS | 2019-03-15 | 2019-09-21 | 2019-07-10 | 2019-07-10 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 411788 | Work Order Description - 411788 - PM | PM | 4 | 568549 | SCHD | NORM-OPS | 2019-03-15 | 2019-09-21 | 2019-07-10 | 2019-07-10 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 411790 | Work Order Description - 411790 - PM | PM | 4 | 176795 | SCHD | EQUIP-ISOL | 2019-03-15 | 2020-07-05 | 2019-07-10 | 2019-07-10 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 411792 | Work Order Description - 411792 - PM | PM | 4 | 176893 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-12-20 | 2019-07-10 | 2019-07-10 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 411794 | Work Order Description - 411794 - PM | PM | 4 | 262750 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 411796 | Work Order Description - 411796 - PSPM | PSPM | 1 | 408731 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 411798 | Work Order Description - 411798 - PM | PM | 4 | 460846 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 411800 | Work Order Description - 411800 - PM | PM | 4 | 487367 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 411808 | Work Order Description - 411808 - PSPM | PSPM | 1 | 99434 | WPLAN | PACK-ISOL | 2019-03-12 | 2019-08-10 | 2019-07-10 | 2019-07-11 | 1 | MAINTENANCE | MECHANICAL | 60
2019-03-31 | 411810 | Work Order Description - 411810 - PM | PM | 4 | 237629 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 411812 | Work Order Description - 411812 - PM | PM | 4 | 377675 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 411814 | Work Order Description - 411814 - PSPM | PSPM | 1 | 527182 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 411816 | Work Order Description - 411816 - PM | PM | 4 | 227897 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-10 | 2019-07-10 | 2019-07-11 | 2 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 411818 | Work Order Description - 411818 - PSPM | PSPM | 1 | 450984 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 411820 | Work Order Description - 411820 - PSPM | PSPM | 1 | 659513 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 411822 | Work Order Description - 411822 - PSPM | PSPM | 1 | 659513 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 411824 | Work Order Description - 411824 - PSPM | PSPM | 1 | 449144 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 411826 | Work Order Description - 411826 - PSPM | PSPM | 1 | 659551 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 411828 | Work Order Description - 411828 - PSPM | PSPM | 1 | 440646 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 411830 | Work Order Description - 411830 - PSPM | PSPM | 1 | 227941 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-10 | 2019-07-10 | 2019-07-10 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 411979 | Work Order Description - 411979 - CM | CM | 1 | 53520 | WPLAN | EQUIP-ISOL | 2019-03-14 | 2021-03-12 | 2021-01-28 | 2021-01-28 | 4 | INTEGRITY | MECHANICAL | 35
2019-03-31 | 411997 | Work Order Description - 411997 - PSCM | PSCM | 1 | 18762 | SCHD | NORM-OPS | 2019-03-26 | 2019-06-05 | 2019-03-30 | 2019-03-30 | 2 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 412000 | Work Order Description - 412000 - PSCM | PSCM | 1 | 18762 | WSCHD | NORM-OPS | 2019-03-12 | 2019-06-05 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 412003 | Work Order Description - 412003 - PSCM | PSCM | 1 | 531547 | WSCHD | NORM-OPS | 2019-03-12 | 2019-06-05 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 412010 | Work Order Description - 412010 - PSCM | PSCM | 1 | 531547 | WSCHD | NORM-OPS | 2019-03-12 | 2019-09-11 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 412012 | Work Order Description - 412012 - PSCM | PSCM | 1 | 531547 | WSCHD | NORM-OPS | 2019-03-12 | 2019-09-11 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 412018 | Work Order Description - 412018 - CM | CM | 4 | 462464 | WMATL | NORM-OPS | 2019-03-19 | 2019-06-05 | 2019-04-23 | 2019-04-23 | 2 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 412034 | Work Order Description - 412034 - PSCM | PSCM | 1 | 18765 | WSCHD | NORM-OPS | 2019-03-12 | 2019-09-11 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 412036 | Work Order Description - 412036 - PSCM | PSCM | 1 | 18765 | WSCHD | NORM-OPS | 2019-03-12 | 2019-09-11 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 412038 | Work Order Description - 412038 - PSCM | PSCM | 1 | 18765 | WSCHD | NORM-OPS | 2019-03-12 | 2019-09-11 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 412040 | Work Order Description - 412040 - PSCM | PSCM | 1 | 50507 | WSCHD | NORM-OPS | 2019-03-12 | 2019-09-11 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 412042 | Work Order Description - 412042 - PSCM | PSCM | 1 | 50507 | WSCHD | NORM-OPS | 2019-03-12 | 2019-09-11 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 412044 | Work Order Description - 412044 - PSCM | PSCM | 1 | 50507 | WSCHD | NORM-OPS | 2019-03-12 | 2019-09-11 | 2019-06-01 | 2019-06-01 | 3 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 412048 | Work Order Description - 412048 - CM | CM | 4 | 651077 | WMATL | NORM-OPS | 2019-03-18 | 2020-03-11 | 2019-09-10 | 2019-09-10 | 3 | MAINTENANCE | MECHANICAL | 45
2019-03-31 | 412089 | Work Order Description - 412089 - PM | PM | 4 | 266627 | WPLAN | EQUIP-ISOL | 2019-03-12 | 2020-01-31 | 2019-12-31 | 2020-01-07 | 2 | INTEGRITY | INSPECTION | 350
2019-03-31 | 412102 | Work Order Description - 412102 - PRJ | PRJ | 4 | 464992 | SCHD | NORM-OPS | 2019-03-29 | 2021-03-10 | 2019-03-30 | 2019-03-30 | 4 | WELLS | CONSTRUCTION | 168
2019-03-31 | 412109 | Work Order Description - 412109 - CM | CM | 1 | 451342 | WPLAN | NORM-OPS | 2019-03-16 | 2020-03-11 | 2019-09-10 | 2019-09-10 | 3 | INTEGRITY | FABRIC | 14
2019-03-31 | 412117 | Work Order Description - 412117 - BR | BR | 3 | 657770 | WRISKQ | SYS-ISOL | 2019-03-17 | 2021-03-10 |  |  | 4 | MAINTENANCE | MECHANICAL | 270
2019-03-31 | 412177 | Work Order Description - 412177 - PSPM | PSPM | 1 | 408375 | WPLAN | PACK-ISOL | 2019-03-13 | 2019-08-11 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 412179 | Work Order Description - 412179 - PM | PM | 4 | 314187 | WSCHD | NORM-OPS | 2019-03-13 | 2019-09-04 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 412181 | Work Order Description - 412181 - PSPM | PSPM | 1 | 408376 | WPLAN | PACK-ISOL | 2019-03-13 | 2019-08-11 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 412183 | Work Order Description - 412183 - PSPM | PSPM | 1 | 356338 | WSCHD | EQUIP-ISOL | 2019-03-13 | 2019-08-11 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 412185 | Work Order Description - 412185 - PSPM | PSPM | 1 | 356338 | WSCHD | EQUIP-ISOL | 2019-03-13 | 2019-08-11 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 412187 | Work Order Description - 412187 - PSPM | PSPM | 1 | 51903 | WSCHD | EQUIP-ISOL | 2019-03-13 | 2019-08-11 | 2019-06-29 | 2019-06-29 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 412189 | Work Order Description - 412189 - PSPM | PSPM | 1 | 247294 | WSCHD | NORM-OPS | 2019-03-13 | 2019-08-11 | 2019-06-29 | 2019-06-29 | 1 | INTEGRITY | INSPECTION | 30
2019-03-31 | 412191 | Work Order Description - 412191 - PM | PM | 4 | 541035 | WSCHD | NORM-OPS | 2019-03-13 | 2019-09-04 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 412193 | Work Order Description - 412193 - PM | PM | 4 | 541035 | WSCHD | NORM-OPS | 2019-03-13 | 2019-09-04 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 412195 | Work Order Description - 412195 - PM | PM | 4 | 314187 | WSCHD | NORM-OPS | 2019-03-13 | 2019-09-04 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 412197 | Work Order Description - 412197 - PM | PM | 4 | 314535 | WSCHD | EQUIP-ISOL | 2019-03-13 | 2019-08-11 | 2019-06-29 | 2019-06-29 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 412199 | Work Order Description - 412199 - PM | PM | 4 | 261965 | WSCHD | EQUIP-ISOL | 2019-03-13 | 2019-08-11 | 2019-06-29 | 2019-06-29 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 412201 | Work Order Description - 412201 - PSPM | PSPM | 1 | 361157 | WPLAN | PACK-ISOL | 2019-03-13 | 2019-08-11 | 2019-06-29 | 2019-06-29 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 412203 | Work Order Description - 412203 - PSPM | PSPM | 1 | 399693 | WPLAN | PACK-ISOL | 2019-03-13 | 2019-08-11 | 2019-06-29 | 2019-06-29 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 412205 | Work Order Description - 412205 - PM | PM | 4 | 547429 | WSCHD | EQUIP-ISOL | 2019-03-13 | 2019-08-11 | 2019-06-29 | 2019-06-29 | 1 | INTEGRITY | SERVICES | 7
2019-03-31 | 412207 | Work Order Description - 412207 - PM | PM | 4 | 652482 | WSCHD | EQUIP-ISOL | 2019-03-13 | 2019-08-11 | 2019-06-29 | 2019-06-29 | 1 | INTEGRITY | SERVICES | 7
2019-03-31 | 412209 | Work Order Description - 412209 - PM | PM | 4 | 652482 | WSCHD | EQUIP-ISOL | 2019-03-13 | 2019-08-11 | 2019-06-29 | 2019-06-29 | 1 | INTEGRITY | SERVICES | 7
2019-03-31 | 412211 | Work Order Description - 412211 - PM | PM | 4 | 601923 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-11 | 2019-07-11 | 2019-07-11 | 2 | OPERATIONS | OPERATIONS | 60
2019-03-31 | 412223 | Work Order Description - 412223 - PSPM | PSPM | 1 | 123510 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-11 | 2019-07-11 | 2019-07-11 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 412229 | Work Order Description - 412229 - PM | PM | 4 | 186613 | SCHD | PACK-ISOL | 2019-03-18 | 2019-09-04 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 412231 | Work Order Description - 412231 - PSPM | PSPM | 1 | 659056 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-11 | 2019-07-11 | 2019-07-11 | 1 | OPERATIONS | SAFETY | 6
2019-03-31 | 412233 | Work Order Description - 412233 - PSPM | PSPM | 1 | 42961 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-11 | 2019-07-11 | 2019-07-11 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 412235 | Work Order Description - 412235 - PSPM | PSPM | 4 | 99434 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-11 | 2019-07-11 | 2019-07-12 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 412237 | Work Order Description - 412237 - PSPM | PSPM | 1 | 450984 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-11 | 2019-07-11 | 2019-07-11 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 412239 | Work Order Description - 412239 - PSPM | PSPM | 1 | 126920 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-11 | 2019-07-11 | 2019-07-11 | 1 | MAINTENANCE | ELECTRICAL | 1.5
2019-03-31 | 412241 | Work Order Description - 412241 - PSPM | PSPM | 1 | 450679 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-11 | 2019-07-11 | 2019-07-14 | 2 | INTEGRITY | INSPECTION | 44
2019-03-31 | 412243 | Work Order Description - 412243 - PM | PM | 4 | 126984 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-11 | 2019-07-11 | 2019-07-11 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 412245 | Work Order Description - 412245 - PSPM | PSPM | 1 | 668649 | WPLAN | NORM-OPS | 2019-03-13 | 2019-08-11 | 2019-07-11 | 2019-07-24 | 2 | MAINTENANCE | MECHANICAL | 119
2019-03-31 | 412247 | Work Order Description - 412247 - PM | PM | 4 | 105599 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-09-04 | 2019-07-11 | 2019-07-11 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 412249 | Work Order Description - 412249 - PSPM | PSPM | 1 | 378209 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-11 | 2019-07-11 | 2019-07-11 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 412407 | Work Order Description - 412407 - BR | BR | 3 | 354614 | SCHD | EQUIP-ISOL | 2019-03-29 | 2020-03-12 | 2019-03-30 | 2019-03-30 | 3 | MAINTENANCE | MECHANICAL | 23
2019-03-31 | 412420 | Work Order Description - 412420 - CM | CM | 1 | 378847 | SCHD | NORM-OPS | 2019-03-18 | 2019-09-12 | 2019-06-12 | 2019-06-12 | 3 | INTEGRITY | CONSTRUCTION | 40
2019-03-31 | 412429 | Work Order Description - 412429 - CM | CM | 4 | 378847 | SCHD | NORM-OPS | 2019-03-18 | 2020-03-12 | 2019-09-11 | 2019-09-11 | 3 | INTEGRITY | FABRIC | 560
2019-03-31 | 412434 | Work Order Description - 412434 - BR | BR | 4 | 57082 | SCHD | NORM-OPS | 2019-03-20 | 2021-03-11 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 412442 | Work Order Description - 412442 - PRJ | PRJ | 4 | 556358 | WSCHD | EQUIP-ISOL | 2019-03-13 | 2019-09-12 |  |  | 3 | ENGINEERING | INSPECTION | 21
2019-03-31 | 412443 | Work Order Description - 412443 - CM | CM | 1 | 680808 | WPLAN | EQUIP-ISOL | 2019-03-16 | 2020-03-12 | 2019-05-18 | 2019-05-18 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 412446 | Work Order Description - 412446 - PRJ | PRJ | 4 | 215925 | SCHD | NORM-OPS | 2019-03-29 | 2021-03-16 | 2021-02-01 | 2021-02-01 | 4 | ENGINEERING | OPERATIONS | 680
2019-03-31 | 412452 | Work Order Description - 412452 - BR | BR | 3 | 217108 | WMATL | EQUIP-ISOL | 2019-03-25 | 2019-06-11 | 2019-04-29 | 2019-04-29 | 2 | MAINTENANCE | ELECTRICAL | 11
2019-03-31 | 412463 | Work Order Description - 412463 - CM | CM | 4 | 671528 | WPLAN | EQUIP-ISOL | 2019-03-16 | 2020-03-12 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 412475 | Work Order Description - 412475 - PRJ | PRJ | 4 | 216028 | WPLAN | EQUIP-ISOL | 2019-03-16 | 2021-03-11 | 2021-01-27 | 2021-01-28 | 4 | ENGINEERING | CONSTRUCTION | 27
2019-03-31 | 412488 | Work Order Description - 412488 - PRJ | PRJ | 4 | 56395 | WSCHD | NORM-OPS | 2019-03-13 | 2021-03-11 |  |  | 4 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 412500 | Work Order Description - 412500 - PSPM | PSPM | 1 | 399575 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-01-01 | 2019-12-01 | 2019-12-01 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 412502 | Work Order Description - 412502 - PSPM | PSPM | 1 | 361119 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-01-01 | 2019-12-01 | 2019-12-01 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 412504 | Work Order Description - 412504 - PSPM | PSPM | 1 | 361062 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-01-01 | 2019-12-01 | 2019-12-01 | 1 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 412506 | Work Order Description - 412506 - PSPM | PSPM | 1 | 260758 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-01-01 | 2019-12-01 | 2019-12-01 | 1 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 412508 | Work Order Description - 412508 - PSPM | PSPM | 1 | 260759 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-01-01 | 2019-12-01 | 2019-12-01 | 1 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 412510 | Work Order Description - 412510 - PSPM | PSPM | 1 | 260779 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-01-01 | 2019-12-01 | 2019-12-01 | 1 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 412512 | Work Order Description - 412512 - PSPM | PSPM | 1 | 248027 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-01-01 | 2019-12-01 | 2019-12-01 | 1 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 412514 | Work Order Description - 412514 - PSPM | PSPM | 1 | 399495 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-01-01 | 2019-12-01 | 2019-12-01 | 1 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 412516 | Work Order Description - 412516 - PSPM | PSPM | 1 | 361070 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-01-01 | 2019-12-01 | 2019-12-01 | 1 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 412518 | Work Order Description - 412518 - PSPM | PSPM | 1 | 361090 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-01-01 | 2019-12-01 | 2019-12-01 | 1 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 412520 | Work Order Description - 412520 - PSPM | PSPM | 1 | 260891 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-01-01 | 2019-12-01 | 2019-12-01 | 1 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 412522 | Work Order Description - 412522 - PSPM | PSPM | 1 | 399537 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-01-01 | 2019-12-01 | 2019-12-01 | 1 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 412524 | Work Order Description - 412524 - PSPM | PSPM | 1 | 248188 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-01-01 | 2019-12-01 | 2019-12-01 | 1 | INTEGRITY | MECHANICAL | 20
2019-03-31 | 412526 | Work Order Description - 412526 - PSPM | PSPM | 1 | 248197 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-01-01 | 2019-12-01 | 2019-12-01 | 1 | INTEGRITY | MECHANICAL | 14
2019-03-31 | 412533 | Work Order Description - 412533 - PSPM | PSPM | 1 | 361063 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2022-03-27 | 2022-02-24 | 2022-02-24 | 1 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 412536 | Work Order Description - 412536 - PSPM | PSPM | 1 | 361064 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2022-03-27 | 2022-02-24 | 2022-02-24 | 1 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 412538 | Work Order Description - 412538 - PSPM | PSPM | 1 | 399490 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2022-03-27 | 2022-02-24 | 2022-02-24 | 1 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 412541 | Work Order Description - 412541 - PSPM | PSPM | 1 | 248032 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-11-10 | 2019-10-10 | 2019-10-10 | 1 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 412544 | Work Order Description - 412544 - PSPM | PSPM | 1 | 260810 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-07-01 | 2019-05-31 | 2019-05-31 | 1 | INTEGRITY | INSTRUMENTS | 4
2019-03-31 | 412549 | Work Order Description - 412549 - PSPM | PSPM | 1 | 248130 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-08-01 | 2020-07-01 | 2020-07-01 | 1 | INTEGRITY | MECHANICAL | 9
2019-03-31 | 412554 | Work Order Description - 412554 - PSPM | PSPM | 1 | 261002 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | MECHANICAL | 8
2019-03-31 | 412558 | Work Order Description - 412558 - PSPM | PSPM | 1 | 248155 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-04-13 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 8
2019-03-31 | 412562 | Work Order Description - 412562 - PSPM | PSPM | 1 | 399604 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-08-06 | 2019-07-06 | 2019-07-06 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 412566 | Work Order Description - 412566 - PSPM | PSPM | 1 | 361145 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2021-01-01 | 2020-12-01 | 2020-12-01 | 1 | INTEGRITY | MECHANICAL | 10
2019-03-31 | 412570 | Work Order Description - 412570 - PSPM | PSPM | 1 | 248578 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-08-01 | 2020-07-01 | 2020-07-01 | 1 | INTEGRITY | MECHANICAL | 15
2019-03-31 | 412572 | Work Order Description - 412572 - PSPM | PSPM | 1 | 248579 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-08-01 | 2020-07-01 | 2020-07-01 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 412574 | Work Order Description - 412574 - PSPM | PSPM | 1 | 361252 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 412576 | Work Order Description - 412576 - PSPM | PSPM | 1 | 248153 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-05-01 | 2019-09-28 | 2019-09-28 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 412578 | Work Order Description - 412578 - PSPM | PSPM | 1 | 399870 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-06-15 | 2020-05-15 | 2020-05-15 | 1 | INTEGRITY | MECHANICAL | 9
2019-03-31 | 412580 | Work Order Description - 412580 - PSPM | PSPM | 1 | 399646 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-05-01 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | MECHANICAL | 16
2019-03-31 | 412584 | Work Order Description - 412584 - PSPM | PSPM | 1 | 361268 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-09-01 | 2019-08-01 | 2019-08-01 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 412586 | Work Order Description - 412586 - PSPM | PSPM | 1 | 261508 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-11-01 | 2019-10-01 | 2019-10-01 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 412588 | Work Order Description - 412588 - PSPM | PSPM | 1 | 248666 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-05-27 | 2019-04-26 | 2019-04-26 | 1 | INTEGRITY | MECHANICAL | 8
2019-03-31 | 412590 | Work Order Description - 412590 - PSPM | PSPM | 1 | 261474 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 412594 | Work Order Description - 412594 - PSPM | PSPM | 1 | 261475 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-06-11 | 2019-05-11 | 2019-05-11 | 1 | INTEGRITY | MECHANICAL | 5
2019-03-31 | 412598 | Work Order Description - 412598 - PSPM | PSPM | 1 | 261476 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | INTEGRITY | MECHANICAL | 3
2019-03-31 | 412602 | Work Order Description - 412602 - PSPM | PSPM | 1 | 361269 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-05-30 | 2019-04-29 | 2019-04-29 | 1 | INTEGRITY | MECHANICAL | 8
2019-03-31 | 412604 | Work Order Description - 412604 - PSPM | PSPM | 1 | 361270 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-08-05 | 2019-07-05 | 2019-07-05 | 1 | INTEGRITY | MECHANICAL | 8
2019-03-31 | 412606 | Work Order Description - 412606 - PSPM | PSPM | 1 | 248674 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-05-31 | 2019-04-30 | 2019-04-30 | 1 | INTEGRITY | MECHANICAL | 8
2019-03-31 | 412608 | Work Order Description - 412608 - PSPM | PSPM | 1 | 261525 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-08-08 | 2019-07-08 | 2019-07-08 | 1 | INTEGRITY | MECHANICAL | 8
2019-03-31 | 412610 | Work Order Description - 412610 - PSPM | PSPM | 1 | 248676 | WSCHD | EQUIP-ISOL | 2019-03-31 | 2019-04-13 | 2019-04-13 | 2019-04-13 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 412612 | Work Order Description - 412612 - PSPM | PSPM | 1 | 261511 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2019-08-06 | 2019-07-06 | 2019-07-06 | 1 | INTEGRITY | MECHANICAL | 8
2019-03-31 | 412614 | Work Order Description - 412614 - PRJ | PRJ | 3 | 375638 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-09-12 | 2019-04-13 | 2019-04-24 | 3 | MAINTENANCE | ELECTRICAL | 82
2019-03-31 | 412616 | Work Order Description - 412616 - PSPM | PSPM | 1 | 261505 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2022-08-01 | 2022-07-01 | 2022-07-01 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 412618 | Work Order Description - 412618 - PSPM | PSPM | 1 | 261038 | WPLAN | EQUIP-ISOL | 2019-03-13 | 2020-08-01 | 2020-07-01 | 2020-07-01 | 1 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 412626 | Work Order Description - 412626 - CM | CM | 1 | 481656 | WPLAN | NORM-OPS | 2019-03-16 | 2019-09-12 | 2019-06-12 | 2019-06-12 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 412627 | Work Order Description - 412627 - PSCM | PSCM | 1 | 481656 | SCHD | NORM-OPS | 2019-03-29 | 2021-03-11 | 2021-01-27 | 2021-01-27 | 4 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 412629 | Work Order Description - 412629 - CM | CM | 1 | 481656 | WRISKQ | NORM-OPS | 2019-03-16 | 2019-04-11 |  |  | 2 | MAINTENANCE | ELECTRICAL | 15
2019-03-31 | 412649 | Work Order Description - 412649 - BR | BR | 3 | 499246 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-06-06 | 2019-04-06 | 2019-04-06 | 2 | MAINTENANCE | MECHANICAL | 72
2019-03-31 | 412693 | Work Order Description - 412693 - PRJ | PRJ | 4 | 527967 | SCHD | NORM-OPS | 2019-03-18 | 2021-03-11 | 2021-01-27 | 2021-01-27 | 4 | ENGINEERING | SERVICES | 48
2019-03-31 | 412716 | Work Order Description - 412716 - BR | BR | 3 | 19011 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-09-16 | 2019-04-13 | 2019-04-13 | 3 | INTEGRITY | OPERATIONS | 7
2019-03-31 | 412717 | Work Order Description - 412717 - PRJ | PRJ | 4 | 216028 | WPLAN | SYS-ISOL | 2019-03-16 | 2021-03-11 | 2021-01-28 | 2021-02-01 | 4 | ENGINEERING | CONSTRUCTION | 70
2019-03-31 | 412730 | Work Order Description - 412730 - PRJ | PRJ | 4 | 661008 | SCHD | NORM-OPS | 2019-03-25 | 2020-03-12 | 2019-03-30 | 2019-03-30 | 3 | ENGINEERING | INSPECTION | 85
2019-03-31 | 412747 | Work Order Description - 412747 - PM | PM | 4 | 680977 | WSCHD | NORM-OPS | 2019-03-14 | 2019-08-12 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 412749 | Work Order Description - 412749 - PM | PM | 4 | 400460 | WSCHD | EQUIP-ISOL | 2019-03-14 | 2019-08-12 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 412751 | Work Order Description - 412751 - PM | PM | 4 | 353512 | WSCHD | NORM-OPS | 2019-03-14 | 2019-08-12 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 412753 | Work Order Description - 412753 - PM | PM | 4 | 680976 | WSCHD | NORM-OPS | 2019-03-14 | 2019-08-12 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 412755 | Work Order Description - 412755 - PM | PM | 4 | 680977 | WSCHD | NORM-OPS | 2019-03-14 | 2019-08-12 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 412757 | Work Order Description - 412757 - PM | PM | 4 | 680977 | WSCHD | NORM-OPS | 2019-03-14 | 2019-08-12 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 412759 | Work Order Description - 412759 - PM | PM | 4 | 680977 | WSCHD | NORM-OPS | 2019-03-14 | 2019-08-12 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 412761 | Work Order Description - 412761 - PM | PM | 4 | 666262 | WSCHD | NORM-OPS | 2019-03-14 | 2019-08-12 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 412763 | Work Order Description - 412763 - PM | PM | 4 | 51530 | WSCHD | NORM-OPS | 2019-03-14 | 2019-08-12 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 412767 | Work Order Description - 412767 - PM | PM | 4 | 357145 | WSCHD | NORM-OPS | 2019-03-14 | 2019-08-12 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 412771 | Work Order Description - 412771 - PM | PM | 4 | 680977 | WSCHD | NORM-OPS | 2019-03-14 | 2019-08-12 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 412773 | Work Order Description - 412773 - PM | PM | 4 | 680977 | WSCHD | NORM-OPS | 2019-03-14 | 2019-08-12 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 412775 | Work Order Description - 412775 - PM | PM | 4 | 680977 | WSCHD | NORM-OPS | 2019-03-14 | 2019-08-12 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 412777 | Work Order Description - 412777 - PM | PM | 4 | 51202 | WSCHD | NORM-OPS | 2019-03-14 | 2019-08-12 | 2019-06-30 | 2019-06-30 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 412779 | Work Order Description - 412779 - PSPM | PSPM | 1 | 580769 | WSCHD | NORM-OPS | 2019-03-14 | 2019-08-12 | 2019-07-12 | 2019-07-12 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 412781 | Work Order Description - 412781 - PSPM | PSPM | 1 | 679716 | WSCHD | EQUIP-ISOL | 2019-03-14 | 2019-08-12 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 412783 | Work Order Description - 412783 - PM | PM | 2 | 321115 | WPLAN | PACK-ISOL | 2019-03-14 | 2019-09-05 | 2019-08-08 | 2019-08-08 | 2 | MAINTENANCE | INSTRUMENTS | 69
2019-03-31 | 412787 | Work Order Description - 412787 - PSPM | PSPM | 1 | 519760 | WSCHD | NORM-OPS | 2019-03-14 | 2019-08-12 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 412789 | Work Order Description - 412789 - PSPM | PSPM | 1 | 546068 | WPLAN | NORM-OPS | 2019-03-14 | 2019-08-12 | 2019-06-30 | 2019-06-30 | 1 | MAINTENANCE | SERVICES | 30
2019-03-31 | 412791 | Work Order Description - 412791 - PM | PM | 4 | 308482 | WPLAN | EQUIP-ISOL | 2019-03-14 | 2019-09-05 | 2019-08-08 | 2019-08-08 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 412793 | Work Order Description - 412793 - PM | PM | 4 | 671792 | WPLAN | EQUIP-ISOL | 2019-03-14 | 2019-09-05 | 2019-08-08 | 2019-08-08 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 412795 | Work Order Description - 412795 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-12 | 2019-07-12 | 2019-07-12 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 412797 | Work Order Description - 412797 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-12 | 2019-07-12 | 2019-07-12 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 412799 | Work Order Description - 412799 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-12 | 2019-07-12 | 2019-07-12 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 412801 | Work Order Description - 412801 - PM | PM | 4 | 451323 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-12 | 2019-07-12 | 2019-07-12 | 2 | INTEGRITY | INSPECTION | 2
2019-03-31 | 412803 | Work Order Description - 412803 - PSPM | PSPM | 1 | 528211 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-12 | 2019-07-12 | 2019-07-12 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 412805 | Work Order Description - 412805 - PSPM | PSPM | 1 | 663164 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-12 | 2019-07-12 | 2019-07-12 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 412807 | Work Order Description - 412807 - PM | PM | 3 | 105849 | SCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-12 | 2019-07-12 | 2019-07-12 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 412809 | Work Order Description - 412809 - PM | PM | 4 | 450958 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-12 | 2019-07-12 | 2019-07-12 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 412811 | Work Order Description - 412811 - PSPM | PSPM | 1 | 450984 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-12 | 2019-07-12 | 2019-07-12 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 412813 | Work Order Description - 412813 - PM | PM | 4 | 80349 | SCHD | PACK-ISOL | 2019-03-29 | 2019-09-05 | 2019-07-12 | 2019-07-12 | 2 | OPERATIONS | MECHANICAL | 7
2019-03-31 | 412815 | Work Order Description - 412815 - PM | PM | 4 | 450541 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-12 | 2019-07-12 | 2019-07-12 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 412817 | Work Order Description - 412817 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-12 | 2019-07-12 | 2019-07-14 | 3 | MAINTENANCE | MEDIC | 21
2019-03-31 | 412922 | Work Order Description - 412922 - BR | BR | 4 | 672561 | WPLAN | EQUIP-ISOL | 2019-03-17 | 2021-03-12 | 2019-06-15 | 2019-06-15 | 4 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 412931 | Work Order Description - 412931 - PRJ | PRJ | 4 | 216028 | WPLAN | SYS-ISOL | 2019-03-16 | 2021-03-12 | 2021-01-28 | 2021-02-04 | 4 | ENGINEERING | CONSTRUCTION | 100
2019-03-31 | 412942 | Work Order Description - 412942 - CM | CM | 1 | 78211 | SCHD | EQUIP-ISOL | 2019-03-18 | 2021-03-12 | 2021-01-28 | 2021-01-28 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 412956 | Work Order Description - 412956 - BR | BR | 3 | 249466 | WSCHD | PACK-ISOL | 2019-03-15 | 2019-09-13 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 412958 | Work Order Description - 412958 - PM | PM | 4 | 361286 | WPLAN | PACK-ISOL | 2019-03-14 | 2019-05-27 | 2019-04-14 | 2019-04-14 | 1 | INTEGRITY | CONSTRUCTION | 6
2019-03-31 | 412965 | Work Order Description - 412965 - PSPM | PSPM | 1 | 261121 | WPLAN | PACK-ISOL | 2019-03-14 | 2019-05-12 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 412983 | Work Order Description - 412983 - PM | PM | 4 | 383111 | SCHD | SYS-ISOL | 2019-03-15 | 2020-04-30 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 413017 | Work Order Description - 413017 - BR | BR | 4 | 438720 | INPRG | EQUIP-ISOL | 2019-03-18 | 2021-03-12 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 135
2019-03-31 | 413023 | Work Order Description - 413023 - BR | BR | 3 | 546302 | WSCHD | PACK-ISOL | 2019-03-16 | 2020-03-13 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 48
2019-03-31 | 413027 | Work Order Description - 413027 - PM | PM | 4 | 262746 | SCHD | NORM-OPS | 2019-03-15 | 2019-10-09 | 2019-09-08 | 2019-09-08 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 413029 | Work Order Description - 413029 - PM | PM | 4 | 262746 | SCHD | NORM-OPS | 2019-03-15 | 2019-10-09 | 2019-09-08 | 2019-09-08 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 413034 | Work Order Description - 413034 - PSPM | PSPM | 1 | 361188 | WPLAN | EQUIP-ISOL | 2019-03-14 | 2019-05-13 | 2019-04-27 | 2019-04-27 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 413036 | Work Order Description - 413036 - PSPM | PSPM | 1 | 361197 | WPLAN | EQUIP-ISOL | 2019-03-14 | 2019-06-11 | 2019-04-29 | 2019-04-29 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 413038 | Work Order Description - 413038 - PSPM | PSPM | 1 | 261213 | WPLAN | EQUIP-ISOL | 2019-03-14 | 2019-06-06 | 2019-04-24 | 2019-04-24 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 413040 | Work Order Description - 413040 - PSPM | PSPM | 1 | 399831 | WPLAN | EQUIP-ISOL | 2019-03-14 | 2019-05-13 | 2019-04-24 | 2019-04-24 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 413042 | Work Order Description - 413042 - PSPM | PSPM | 1 | 361200 | WPLAN | EQUIP-ISOL | 2019-03-14 | 2019-05-13 | 2019-04-24 | 2019-04-24 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 413044 | Work Order Description - 413044 - PSPM | PSPM | 1 | 248357 | WPLAN | EQUIP-ISOL | 2019-03-14 | 2019-06-01 | 2019-04-19 | 2019-04-19 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 413046 | Work Order Description - 413046 - PSPM | PSPM | 1 | 248361 | WPLAN | EQUIP-ISOL | 2019-03-14 | 2019-04-14 | 2019-04-20 | 2019-04-20 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 413059 | Work Order Description - 413059 - PRJ | PRJ | 4 | 228839 | SCHD | NORM-OPS | 2019-03-18 | 2021-03-12 | 2021-01-28 | 2021-01-28 | 4 | ENGINEERING | CONSTRUCTION | 221.25
2019-03-31 | 413080 | Work Order Description - 413080 - CM | CM | 4 | 461006 | SCHD | EQUIP-ISOL | 2019-03-29 | 2021-03-13 | 2021-01-29 | 2021-01-29 | 4 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 413085 | Work Order Description - 413085 - PM | PM | 4 | 314186 | WSCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 413087 | Work Order Description - 413087 - PM | PM | 4 | 357106 | WSCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 413089 | Work Order Description - 413089 - PM | PM | 4 | 308005 | WSCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 413091 | Work Order Description - 413091 - PM | PM | 4 | 410635 | WSCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 413093 | Work Order Description - 413093 - PM | PM | 4 | 546053 | WSCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413095 | Work Order Description - 413095 - PM | PM | 4 | 314186 | WSCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 413097 | Work Order Description - 413097 - PM | PM | 4 | 314186 | WSCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 413099 | Work Order Description - 413099 - PM | PM | 4 | 314186 | WSCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 413101 | Work Order Description - 413101 - PM | PM | 4 | 314186 | WSCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 413103 | Work Order Description - 413103 - PM | PM | 4 | 408390 | WSCHD | EQUIP-ISOL | 2019-03-15 | 2019-08-13 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 413105 | Work Order Description - 413105 - PM | PM | 2 | 480203 | WSCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-01 | 2019-07-01 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 413107 | Work Order Description - 413107 - PSPM | PSPM | 1 | 321203 | WSCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 413109 | Work Order Description - 413109 - PSPM | PSPM | 1 | 321218 | WSCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 413111 | Work Order Description - 413111 - PM | PM | 4 | 138073 | WSCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 413113 | Work Order Description - 413113 - PSPM | PSPM | 1 | 138073 | WSCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 413115 | Work Order Description - 413115 - PM | PM | 4 | 666204 | WSCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413117 | Work Order Description - 413117 - PM | PM | 4 | 294916 | WSCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-01 | 2019-07-01 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 413119 | Work Order Description - 413119 - PM | PM | 4 | 475799 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 2 | DRILLING | DRILLING | 8
2019-03-31 | 413121 | Work Order Description - 413121 - PM | PM | 4 | 482054 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 2 | DRILLING | DRILLING | 8
2019-03-31 | 413123 | Work Order Description - 413123 - PSPM | PSPM | 1 | 499149 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 413125 | Work Order Description - 413125 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 413129 | Work Order Description - 413129 - PM | PM | 4 | 668433 | WPLAN | PACK-ISOL | 2019-03-15 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 413133 | Work Order Description - 413133 - PM | PM | 4 | 450984 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 413135 | Work Order Description - 413135 - PM | PM | 4 | 450692 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 1 | OPERATIONS | SAFETY | 1
2019-03-31 | 413137 | Work Order Description - 413137 - PM | PM | 2 | 126821 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-08-10 | 2019-08-10 | 2 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 413139 | Work Order Description - 413139 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413141 | Work Order Description - 413141 - PSPM | PSPM | 1 | 80092 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 413143 | Work Order Description - 413143 - PSPM | PSPM | 1 | 80093 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 413145 | Work Order Description - 413145 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 413147 | Work Order Description - 413147 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2019-03-15 | 2019-08-13 | 2019-07-13 | 2019-07-13 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 413341 | Work Order Description - 413341 - CM | CM | 1 | 128958 | SCHD | NORM-OPS | 2019-03-29 | 2019-06-08 | 2019-04-26 | 2019-04-27 | 2 | INTEGRITY | FABRIC | 448
2019-03-31 | 413342 | Work Order Description - 413342 - CM | CM | 3 | 670468 | WRISKQ | PACK-ISOL | 2019-03-27 | 2019-04-13 | 2019-04-22 | 2019-04-22 | 2 | MAINTENANCE | FABRIC | 11
2019-03-31 | 413349 | Work Order Description - 413349 - CM | CM | 4 | 663478 | SCHD | NORM-OPS | 2019-03-18 | 2019-09-14 | 2019-06-14 | 2019-06-14 | 3 | INTEGRITY | INSPECTION | 3
2019-03-31 | 413353 | Work Order Description - 413353 - PM | PM | 4 | 411443 | SCHD | NORM-OPS | 2019-03-15 | 2019-11-11 | 2019-10-11 | 2019-10-11 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 413355 | Work Order Description - 413355 - BR | BR | 4 | 35977 | WMATL | PACK-ISOL | 2019-03-20 | 2020-03-14 | 2019-09-13 | 2019-09-13 | 3 | MAINTENANCE | DRILLING | 8
2019-03-31 | 413365 | Work Order Description - 413365 - CM | CM | 3 | 448717 | SCHD | EQUIP-ISOL | 2019-03-18 | 2021-03-13 | 2021-01-29 | 2021-01-29 | 4 | WELLS | WELLS | 286
2019-03-31 | 413366 | Work Order Description - 413366 - PRJ | PRJ | 4 | 670468 | SCHD | NORM-OPS | 2019-03-18 | 2019-06-08 | 2019-04-26 | 2019-04-26 | 2 | MAINTENANCE | MECHANICAL | 140
2019-03-31 | 413373 | Work Order Description - 413373 - PRJ | PRJ | 4 | 267676 | SCHD | NORM-OPS | 2019-03-26 | 2021-03-13 | 2019-03-30 | 2019-03-30 | 4 | ENGINEERING | OPERATIONS | 72
2019-03-31 | 413385 | Work Order Description - 413385 - BR | BR | 4 | 313998 | WSCHD | EQUIP-ISOL | 2019-03-22 | 2019-09-14 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | MECHANICAL | 23
2019-03-31 | 413389 | Work Order Description - 413389 - BR | BR | 4 | 436678 | WMATL | NORM-OPS | 2019-03-18 | 2019-09-15 | 2019-06-15 | 2019-06-15 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413393 | Work Order Description - 413393 - CM | CM | 1 | 266597 | WPLAN | PACK-ISOL | 2019-03-23 | 2020-03-20 | 2019-10-05 | 2019-10-05 | 3 | MAINTENANCE | MECHANICAL | 68
2019-03-31 | 413395 | Work Order Description - 413395 - PRJ | PRJ | 4 | 35143 | WSCHD | NORM-OPS | 2019-03-15 | 2019-09-14 | 2019-05-11 |  | 3 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 413399 | Work Order Description - 413399 - BR | BR | 4 | 35976 | WMATL | PACK-ISOL | 2019-03-20 | 2020-03-14 | 2019-09-13 | 2019-09-13 | 3 | MAINTENANCE | DRILLING | 12
2019-03-31 | 413404 | Work Order Description - 413404 - BR | BR | 4 | 465173 | WMATL | PACK-ISOL | 2019-03-27 | 2020-03-14 | 2019-09-13 | 2019-09-13 | 3 | MAINTENANCE | DRILLING | 12
2019-03-31 | 413415 | Work Order Description - 413415 - BR | BR | 3 | 74939 | WPLAN | TPS | 2019-03-18 | 2019-09-14 | 2019-07-14 | 2019-07-14 | 3 | INTEGRITY | INSTRUMENTS | 3
2019-03-31 | 413449 | Work Order Description - 413449 - CM | CM | 4 | 680732 | WSCHD | NORM-OPS | 2019-03-16 | 2020-03-14 | 2019-09-13 | 2019-09-13 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 413459 | Work Order Description - 413459 - CM | CM | 3 | 671640 | WPLAN | EQUIP-ISOL | 2019-03-16 | 2020-03-14 | 2019-05-04 | 2019-05-04 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 413461 | Work Order Description - 413461 - PSCM | PSCM | 1 | 305651 | WPLAN | EQUIP-ISOL | 2019-03-16 | 2021-03-14 | 2019-06-08 | 2019-06-08 | 4 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 413463 | Work Order Description - 413463 - CM | CM | 1 | 411258 | WSCHD | NORM-OPS | 2019-03-17 | 2020-03-14 | 2019-06-01 | 2019-06-01 | 3 | INTEGRITY | FABRIC | 23
2019-03-31 | 413464 | Work Order Description - 413464 - BR | BR | 3 | 656290 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-09-14 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | MECHANICAL | 82
2019-03-31 | 413466 | Work Order Description - 413466 - PSCM | PSCM | 1 | 363634 | SCHD | NORM-OPS | 2019-03-16 | 2019-04-13 | 2019-05-04 | 2019-05-04 | 2 | INTEGRITY | INSTRUMENTS | 1
2019-03-31 | 413470 | Work Order Description - 413470 - BR | BR | 4 | 499126 | SCHD | NORM-OPS | 2019-03-29 | 2019-09-14 | 2019-03-30 | 2019-03-30 | 3 | MAINTENANCE | MECHANICAL | 328
2019-03-31 | 413471 | Work Order Description - 413471 - BR | BR | 3 | 674253 | WSCHD | EQUIP-ISOL | 2019-03-15 | 2020-03-14 |  |  | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 413480 | Work Order Description - 413480 - PRJ | PRJ | 4 | 216028 | WSCHD | NORM-OPS | 2019-03-15 | 2020-03-14 |  |  | 3 | ENGINEERING | CONSTRUCTION | 0
2019-03-31 | 413483 | Work Order Description - 413483 - PRJ | PRJ | 4 | 216028 | WPLAN | NORM-OPS | 2019-03-16 | 2020-03-14 | 2020-03-14 | 2020-03-14 | 3 | ENGINEERING | CONSTRUCTION | 21
2019-03-31 | 413500 | Work Order Description - 413500 - BR | BR | 1 | 34156 | SCHD | EQUIP-ISOL | 2019-03-29 | 2021-03-13 | 2021-01-29 | 2021-01-29 | 4 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 413504 | Work Order Description - 413504 - BR | BR | 1 | 475916 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-06-08 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 413508 | Work Order Description - 413508 - BR | BR | 1 | 98208 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-06-08 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 413512 | Work Order Description - 413512 - BR | BR | 1 | 458055 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-06-08 | 2019-06-01 | 2019-06-01 | 2 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 413516 | Work Order Description - 413516 - BR | BR | 1 | 445660 | SCHD | EQUIP-ISOL | 2019-03-29 | 2020-03-14 | 2019-09-13 | 2019-09-13 | 3 | MAINTENANCE | ELECTRICAL | 50
2019-03-31 | 413573 | Work Order Description - 413573 - PSPM | PSPM | 1 | 18982 | WSCHD | NORM-OPS | 2019-03-16 | 2019-08-14 | 2019-07-02 | 2019-07-02 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 413575 | Work Order Description - 413575 - PSPM | PSPM | 1 | 361642 | WSCHD | NORM-OPS | 2019-03-16 | 2019-08-14 | 2019-07-02 | 2019-07-02 | 1 | INTEGRITY | INSPECTION | 30
2019-03-31 | 413577 | Work Order Description - 413577 - PM | PM | 2 | 572308 | WSCHD | NORM-OPS | 2019-03-16 | 2019-08-14 | 2019-07-02 | 2019-07-02 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 413579 | Work Order Description - 413579 - PM | PM | 4 | 310452 | WSCHD | NORM-OPS | 2019-03-16 | 2019-08-14 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 413581 | Work Order Description - 413581 - PM | PM | 4 | 310477 | WSCHD | NORM-OPS | 2019-03-16 | 2019-08-14 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 413583 | Work Order Description - 413583 - PSPM | PSPM | 4 | 361642 | WSCHD | NORM-OPS | 2019-03-16 | 2019-08-14 | 2019-07-02 | 2019-07-02 | 1 | INTEGRITY | INSPECTION | 30
2019-03-31 | 413585 | Work Order Description - 413585 - PM | PM | 4 | 315510 | WSCHD | NORM-OPS | 2019-03-16 | 2019-08-14 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 413587 | Work Order Description - 413587 - PM | PM | 4 | 580762 | WSCHD | NORM-OPS | 2019-03-16 | 2019-08-14 | 2019-07-02 | 2019-07-02 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 413589 | Work Order Description - 413589 - PSPM | PSPM | 1 | 547298 | WSCHD | NORM-OPS | 2019-03-16 | 2019-08-14 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 413591 | Work Order Description - 413591 - PSPM | PSPM | 1 | 50765 | WPLAN | SUBSYS-ISOL | 2019-03-16 | 2019-08-14 | 2019-07-02 | 2019-07-02 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 413593 | Work Order Description - 413593 - PSPM | PSPM | 1 | 399829 | WPLAN | EQUIP-ISOL | 2019-03-16 | 2019-08-14 | 2019-07-02 | 2019-07-02 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 413595 | Work Order Description - 413595 - PSPM | PSPM | 1 | 315750 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413597 | Work Order Description - 413597 - PSPM | PSPM | 1 | 315750 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413599 | Work Order Description - 413599 - PSPM | PSPM | 1 | 256829 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413601 | Work Order Description - 413601 - PSPM | PSPM | 1 | 544962 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413603 | Work Order Description - 413603 - PSPM | PSPM | 1 | 556432 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413605 | Work Order Description - 413605 - PSPM | PSPM | 1 | 556432 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413607 | Work Order Description - 413607 - PSPM | PSPM | 1 | 556432 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413609 | Work Order Description - 413609 - PSPM | PSPM | 1 | 556432 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413612 | Work Order Description - 413612 - PSPM | PSPM | 1 | 463680 | SCHD | TPS | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | MECHANICAL | 43
2019-03-31 | 413620 | Work Order Description - 413620 - PSPM | PSPM | 1 | 309194 | SCHD | TPS | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | MECHANICAL | 71
2019-03-31 | 413628 | Work Order Description - 413628 - PM | PM | 4 | 489981 | SCHD | TPS | 2019-03-29 | 2019-09-07 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 413630 | Work Order Description - 413630 - PM | PM | 4 | 544405 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-09-07 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413632 | Work Order Description - 413632 - PSPM | PSPM | 1 | 487752 | SCHD | TPS | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | MECHANICAL | 31
2019-03-31 | 413638 | Work Order Description - 413638 - PM | PM | 4 | 487597 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413641 | Work Order Description - 413641 - PM | PM | 4 | 492091 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413644 | Work Order Description - 413644 - PM | PM | 4 | 487598 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413647 | Work Order Description - 413647 - PM | PM | 4 | 487555 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 413649 | Work Order Description - 413649 - PM | PM | 3 | 491977 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413652 | Work Order Description - 413652 - PM | PM | 3 | 188480 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413655 | Work Order Description - 413655 - PM | PM | 4 | 492090 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413658 | Work Order Description - 413658 - PM | PM | 4 | 188500 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413661 | Work Order Description - 413661 - PM | PM | 4 | 324916 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413664 | Work Order Description - 413664 - PM | PM | 4 | 188502 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413667 | Work Order Description - 413667 - PM | PM | 4 | 188501 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413670 | Work Order Description - 413670 - PM | PM | 4 | 188503 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413673 | Work Order Description - 413673 - PM | PM | 4 | 188506 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413676 | Work Order Description - 413676 - PM | PM | 4 | 487594 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413679 | Work Order Description - 413679 - PM | PM | 4 | 487595 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413682 | Work Order Description - 413682 - PM | PM | 4 | 487626 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413685 | Work Order Description - 413685 - PM | PM | 4 | 492094 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413688 | Work Order Description - 413688 - PM | PM | 4 | 324940 | SCHD | TPS | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413691 | Work Order Description - 413691 - PM | PM | 4 | 188507 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413694 | Work Order Description - 413694 - PM | PM | 4 | 324941 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413697 | Work Order Description - 413697 - PM | PM | 4 | 324941 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413700 | Work Order Description - 413700 - PM | PM | 4 | 324941 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413703 | Work Order Description - 413703 - PM | PM | 4 | 324942 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413706 | Work Order Description - 413706 - PM | PM | 4 | 492093 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413709 | Work Order Description - 413709 - PM | PM | 4 | 487599 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413712 | Work Order Description - 413712 - PM | PM | 4 | 487600 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413715 | Work Order Description - 413715 - PM | PM | 4 | 188504 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413718 | Work Order Description - 413718 - PM | PM | 4 | 492142 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413721 | Work Order Description - 413721 - PM | PM | 4 | 487601 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413724 | Work Order Description - 413724 - PM | PM | 4 | 491980 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413727 | Work Order Description - 413727 - PM | PM | 4 | 487622 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413730 | Work Order Description - 413730 - PM | PM | 4 | 188505 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413733 | Work Order Description - 413733 - PM | PM | 4 | 324943 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413736 | Work Order Description - 413736 - PM | PM | 4 | 492143 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413739 | Work Order Description - 413739 - PM | PM | 4 | 324944 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413742 | Work Order Description - 413742 - PM | PM | 4 | 324945 | SCHD | TPS | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413745 | Work Order Description - 413745 - PM | PM | 4 | 487623 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413748 | Work Order Description - 413748 - PM | PM | 4 | 188496 | SCHD | TPS | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 25
2019-03-31 | 413752 | Work Order Description - 413752 - PM | PM | 4 | 324915 | SCHD | TPS | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 25
2019-03-31 | 413756 | Work Order Description - 413756 - PSPM | PSPM | 1 | 256301 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 413758 | Work Order Description - 413758 - PSPM | PSPM | 1 | 256300 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 413760 | Work Order Description - 413760 - PSPM | PSPM | 1 | 256299 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 413762 | Work Order Description - 413762 - PSPM | PSPM | 1 | 304643 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413764 | Work Order Description - 413764 - PSPM | PSPM | 1 | 30720 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413766 | Work Order Description - 413766 - PSPM | PSPM | 1 | 408906 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413768 | Work Order Description - 413768 - PSPM | PSPM | 1 | 408907 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413770 | Work Order Description - 413770 - PSPM | PSPM | 1 | 401262 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413772 | Work Order Description - 413772 - PSPM | PSPM | 1 | 320534 | SCHD | TPS | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | SUBSEA | 14
2019-03-31 | 413774 | Work Order Description - 413774 - PM | PM | 4 | 303805 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413776 | Work Order Description - 413776 - PM | PM | 2 | 501751 | SCHD | TPS | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 144
2019-03-31 | 413778 | Work Order Description - 413778 - PSPM | PSPM | 1 | 259531 | SCHD | TPS | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 413780 | Work Order Description - 413780 - PM | PM | 3 | 188489 | SCHD | TPS | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 22
2019-03-31 | 413786 | Work Order Description - 413786 - PSPM | PSPM | 1 | 653509 | SCHD | TPS | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 413788 | Work Order Description - 413788 - PSPM | PSPM | 1 | 259533 | SCHD | TPS | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 413790 | Work Order Description - 413790 - PSPM | PSPM | 1 | 259536 | SCHD | TPS | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 413792 | Work Order Description - 413792 - PSPM | PSPM | 1 | 477571 | SCHD | TPS | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 413794 | Work Order Description - 413794 - PSPM | PSPM | 1 | 447441 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 413796 | Work Order Description - 413796 - PM | PM | 1 | 446516 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 413798 | Work Order Description - 413798 - PSPM | PSPM | 1 | 401553 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413800 | Work Order Description - 413800 - PSPM | PSPM | 1 | 303896 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413802 | Work Order Description - 413802 - PSPM | PSPM | 1 | 401573 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413804 | Work Order Description - 413804 - PSPM | PSPM | 1 | 303897 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413806 | Work Order Description - 413806 - PSPM | PSPM | 4 | 408462 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-13 | 2019-07-13 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413808 | Work Order Description - 413808 - PSPM | PSPM | 4 | 409227 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413810 | Work Order Description - 413810 - PSPM | PSPM | 1 | 409269 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 413812 | Work Order Description - 413812 - PSPM | PSPM | 1 | 409272 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413814 | Work Order Description - 413814 - PSPM | PSPM | 1 | 304103 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413816 | Work Order Description - 413816 - PSPM | PSPM | 1 | 304104 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413818 | Work Order Description - 413818 - PSPM | PSPM | 1 | 409350 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413820 | Work Order Description - 413820 - PSPM | PSPM | 1 | 408485 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413822 | Work Order Description - 413822 - PSPM | PSPM | 1 | 30547 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-05-04 | 2019-05-04 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413824 | Work Order Description - 413824 - PM | PM | 3 | 409424 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-13 | 2019-07-14 | 2019-07-14 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413826 | Work Order Description - 413826 - PM | PM | 4 | 490496 | SCHD | PACK-ISOL | 2019-03-29 | 2019-09-07 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413828 | Work Order Description - 413828 - PM | PM | 3 | 409531 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-13 | 2019-07-14 | 2019-07-14 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413830 | Work Order Description - 413830 - PM | PM | 3 | 408679 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-13 | 2019-07-14 | 2019-07-14 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413832 | Work Order Description - 413832 - PM | PM | 3 | 30613 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-13 | 2019-07-14 | 2019-07-14 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413834 | Work Order Description - 413834 - PM | PM | 4 | 475851 | SCHD | EQUIP-ISOL | 2019-03-29 | 2020-07-09 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 413836 | Work Order Description - 413836 - PM | PM | 3 | 408686 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-13 | 2019-07-14 | 2019-07-14 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413838 | Work Order Description - 413838 - PM | PM | 3 | 408699 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-13 | 2019-07-14 | 2019-07-14 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413840 | Work Order Description - 413840 - PM | PM | 3 | 408700 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-10-13 | 2019-07-14 | 2019-07-14 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413842 | Work Order Description - 413842 - PSPM | PSPM | 1 | 543913 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413844 | Work Order Description - 413844 - PSPM | PSPM | 1 | 30623 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413846 | Work Order Description - 413846 - PSPM | PSPM | 1 | 30625 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413848 | Work Order Description - 413848 - PSPM | PSPM | 1 | 543965 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413850 | Work Order Description - 413850 - PM | PM | 4 | 30652 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413852 | Work Order Description - 413852 - PM | PM | 4 | 304352 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413854 | Work Order Description - 413854 - PM | PM | 4 | 544000 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413856 | Work Order Description - 413856 - PM | PM | 4 | 408814 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413858 | Work Order Description - 413858 - PM | PM | 4 | 408873 | SCHD | PACK-ISOL | 2019-03-29 | 2019-09-07 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413860 | Work Order Description - 413860 - PM | PM | 4 | 304580 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413862 | Work Order Description - 413862 - PM | PM | 4 | 544186 | SCHD | PACK-ISOL | 2019-03-29 | 2019-09-07 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413864 | Work Order Description - 413864 - PM | PM | 4 | 30706 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413866 | Work Order Description - 413866 - PM | PM | 4 | 30707 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413868 | Work Order Description - 413868 - PSPM | PSPM | 1 | 30684 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413870 | Work Order Description - 413870 - PSPM | PSPM | 1 | 304512 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-05-18 | 2019-05-18 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413872 | Work Order Description - 413872 - PSPM | PSPM | 1 | 408893 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413874 | Work Order Description - 413874 - PSPM | PSPM | 1 | 176736 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413876 | Work Order Description - 413876 - PSPM | PSPM | 1 | 304614 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413878 | Work Order Description - 413878 - PM | PM | 4 | 183600 | SCHD | SYS-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413880 | Work Order Description - 413880 - PSPM | PSPM | 1 | 409020 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413882 | Work Order Description - 413882 - PM | PM | 4 | 556432 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413884 | Work Order Description - 413884 - PM | PM | 4 | 555551 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413886 | Work Order Description - 413886 - PM | PM | 4 | 555567 | SCHD | PACK-ISOL | 2019-03-29 | 2019-09-07 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413888 | Work Order Description - 413888 - PM | PM | 4 | 303803 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413890 | Work Order Description - 413890 - PM | PM | 4 | 303804 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413892 | Work Order Description - 413892 - PM | PM | 4 | 409031 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413894 | Work Order Description - 413894 - PM | PM | 4 | 303828 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413896 | Work Order Description - 413896 - PM | PM | 4 | 408677 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413898 | Work Order Description - 413898 - PSPM | PSPM | 1 | 180459 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 413900 | Work Order Description - 413900 - PSPM | PSPM | 1 | 30688 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413902 | Work Order Description - 413902 - PM | PM | 3 | 491405 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-13 | 2019-07-14 | 2019-07-14 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413904 | Work Order Description - 413904 - PM | PM | 3 | 494962 | SCHD | EQUIP-ISOL | 2019-03-29 | 2020-01-11 | 2019-07-14 | 2019-07-14 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413906 | Work Order Description - 413906 - PM | PM | 4 | 491540 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413908 | Work Order Description - 413908 - PM | PM | 4 | 262572 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413910 | Work Order Description - 413910 - PM | PM | 4 | 325568 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413912 | Work Order Description - 413912 - PM | PM | 4 | 30179 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-09-07 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413914 | Work Order Description - 413914 - PM | PM | 4 | 408672 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413916 | Work Order Description - 413916 - PM | PM | 4 | 408673 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413918 | Work Order Description - 413918 - PSPM | PSPM | 1 | 401238 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413920 | Work Order Description - 413920 - PM | PM | 4 | 256575 | SCHD | PACK-ISOL | 2019-03-29 | 2019-09-25 | 2019-07-14 | 2019-07-14 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 413922 | Work Order Description - 413922 - PSPM | PSPM | 1 | 408872 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 413924 | Work Order Description - 413924 - PM | PM | 4 | 30426 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-09-07 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413926 | Work Order Description - 413926 - PSPM | PSPM | 1 | 256580 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 413928 | Work Order Description - 413928 - PSPM | PSPM | 4 | 256584 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413930 | Work Order Description - 413930 - PSPM | PSPM | 4 | 408895 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413932 | Work Order Description - 413932 - PM | PM | 4 | 401440 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413934 | Work Order Description - 413934 - PM | PM | 4 | 30468 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413936 | Work Order Description - 413936 - PM | PM | 4 | 30469 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413938 | Work Order Description - 413938 - PM | PM | 4 | 401441 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413940 | Work Order Description - 413940 - PM | PM | 4 | 303766 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413942 | Work Order Description - 413942 - PM | PM | 4 | 401442 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413944 | Work Order Description - 413944 - PM | PM | 4 | 303767 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413946 | Work Order Description - 413946 - PM | PM | 4 | 303768 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413948 | Work Order Description - 413948 - PM | PM | 4 | 303769 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413950 | Work Order Description - 413950 - PSPM | PSPM | 4 | 401444 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413952 | Work Order Description - 413952 - PM | PM | 4 | 401446 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413954 | Work Order Description - 413954 - PM | PM | 4 | 303834 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413956 | Work Order Description - 413956 - PM | PM | 4 | 30495 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 413958 | Work Order Description - 413958 - PM | PM | 4 | 303835 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413960 | Work Order Description - 413960 - PM | PM | 4 | 401506 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413962 | Work Order Description - 413962 - PM | PM | 4 | 303861 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413964 | Work Order Description - 413964 - PM | PM | 4 | 401507 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413966 | Work Order Description - 413966 - PM | PM | 4 | 30490 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413968 | Work Order Description - 413968 - PM | PM | 4 | 409060 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413970 | Work Order Description - 413970 - PM | PM | 4 | 303863 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413972 | Work Order Description - 413972 - PM | PM | 4 | 401510 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413974 | Work Order Description - 413974 - PM | PM | 4 | 30499 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413976 | Work Order Description - 413976 - PM | PM | 4 | 409065 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413978 | Work Order Description - 413978 - PM | PM | 4 | 303865 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413980 | Work Order Description - 413980 - PM | PM | 4 | 409067 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413982 | Work Order Description - 413982 - PM | PM | 4 | 409088 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413984 | Work Order Description - 413984 - PM | PM | 4 | 30502 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413986 | Work Order Description - 413986 - PSPM | PSPM | 1 | 401530 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 413988 | Work Order Description - 413988 - PM | PM | 4 | 555972 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 42
2019-03-31 | 413990 | Work Order Description - 413990 - PM | PM | 4 | 215925 | SCHD | TPS | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 72
2019-03-31 | 413992 | Work Order Description - 413992 - PM | PM | 3 | 478664 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-09-07 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 413994 | Work Order Description - 413994 - PSPM | PSPM | 1 | 408999 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 413996 | Work Order Description - 413996 - PSPM | PSPM | 1 | 408966 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 413998 | Work Order Description - 413998 - PSPM | PSPM | 1 | 30709 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414000 | Work Order Description - 414000 - PSPM | PSPM | 1 | 255799 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 414002 | Work Order Description - 414002 - PSPM | PSPM | 1 | 304156 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414004 | Work Order Description - 414004 - PSPM | PSPM | 1 | 30686 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414006 | Work Order Description - 414006 - PSPM | PSPM | 1 | 36442 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414008 | Work Order Description - 414008 - PSPM | PSPM | 1 | 30703 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414010 | Work Order Description - 414010 - PSPM | PSPM | 1 | 409194 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414012 | Work Order Description - 414012 - PSPM | PSPM | 1 | 304486 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414014 | Work Order Description - 414014 - PM | PM | 4 | 59061 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 414016 | Work Order Description - 414016 - PM | PM | 4 | 59062 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 414018 | Work Order Description - 414018 - PM | PM | 4 | 309009 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 414020 | Work Order Description - 414020 - PM | PM | 4 | 309321 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 414022 | Work Order Description - 414022 - PM | PM | 4 | 24898 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 414024 | Work Order Description - 414024 - PM | PM | 4 | 24899 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 414026 | Work Order Description - 414026 - PM | PM | 4 | 486889 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 414028 | Work Order Description - 414028 - PM | PM | 4 | 180502 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 414030 | Work Order Description - 414030 - PM | PM | 4 | 487974 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 414032 | Work Order Description - 414032 - PM | PM | 4 | 59087 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 414034 | Work Order Description - 414034 - PM | PM | 4 | 309323 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 414036 | Work Order Description - 414036 - PM | PM | 4 | 309015 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 414038 | Work Order Description - 414038 - PM | PM | 4 | 59090 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 414040 | Work Order Description - 414040 - PM | PM | 4 | 24886 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 414042 | Work Order Description - 414042 - PM | PM | 4 | 59059 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 414044 | Work Order Description - 414044 - PM | PM | 4 | 309008 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 414046 | Work Order Description - 414046 - PM | PM | 4 | 309320 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 5
2019-03-31 | 414048 | Work Order Description - 414048 - PSPM | PSPM | 1 | 556432 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 414050 | Work Order Description - 414050 - PM | PM | 4 | 543907 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414052 | Work Order Description - 414052 - PSPM | PSPM | 1 | 320534 | SCHD | TPS | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 414054 | Work Order Description - 414054 - PSPM | PSPM | 1 | 304613 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414056 | Work Order Description - 414056 - PM | PM | 4 | 183602 | SCHD | SYS-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414058 | Work Order Description - 414058 - PM | PM | 4 | 304263 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414060 | Work Order Description - 414060 - PSPM | PSPM | 1 | 304261 | SCHD | PACK-ISOL | 2019-03-29 | 2019-09-07 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414062 | Work Order Description - 414062 - PSPM | PSPM | 1 | 30608 | SCHD | PACK-ISOL | 2019-03-29 | 2019-09-07 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414064 | Work Order Description - 414064 - PM | PM | 4 | 491404 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 414066 | Work Order Description - 414066 - PM | PM | 4 | 478627 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 414068 | Work Order Description - 414068 - PM | PM | 4 | 263181 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 414070 | Work Order Description - 414070 - PSPM | PSPM | 1 | 408910 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414072 | Work Order Description - 414072 - PSPM | PSPM | 1 | 408965 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414074 | Work Order Description - 414074 - PSPM | PSPM | 1 | 304583 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414076 | Work Order Description - 414076 - PSPM | PSPM | 1 | 304584 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414078 | Work Order Description - 414078 - PM | PM | 3 | 265830 | SCHD | PACK-ISOL | 2019-03-29 | 2020-02-16 | 2019-07-14 | 2019-07-14 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 414080 | Work Order Description - 414080 - PM | PM | 4 | 490496 | SCHD | PACK-ISOL | 2019-03-29 | 2020-02-16 | 2019-07-14 | 2019-07-14 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 414082 | Work Order Description - 414082 - PM | PM | 4 | 491543 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2020-02-16 | 2019-07-14 | 2019-07-14 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 414084 | Work Order Description - 414084 - PM | PM | 4 | 491544 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2020-02-16 | 2019-07-14 | 2019-07-14 | 3 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 414086 | Work Order Description - 414086 - PM | PM | 4 | 29701 | SCHD | PACK-ISOL | 2019-03-29 | 2020-02-16 | 2019-07-14 | 2019-07-14 | 3 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 414088 | Work Order Description - 414088 - PSPM | PSPM | 1 | 304585 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414090 | Work Order Description - 414090 - PSPM | PSPM | 1 | 544187 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414092 | Work Order Description - 414092 - PSPM | PSPM | 1 | 408967 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414094 | Work Order Description - 414094 - PSPM | PSPM | 1 | 304586 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414096 | Work Order Description - 414096 - PSPM | PSPM | 1 | 304609 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414098 | Work Order Description - 414098 - PSPM | PSPM | 1 | 408990 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414100 | Work Order Description - 414100 - PSPM | PSPM | 1 | 408991 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414102 | Work Order Description - 414102 - PSPM | PSPM | 1 | 408992 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414104 | Work Order Description - 414104 - PSPM | PSPM | 1 | 408993 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414106 | Work Order Description - 414106 - PSPM | PSPM | 1 | 30708 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414108 | Work Order Description - 414108 - PSPM | PSPM | 1 | 304612 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414110 | Work Order Description - 414110 - PSPM | PSPM | 1 | 408996 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414112 | Work Order Description - 414112 - PSPM | PSPM | 1 | 30710 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414114 | Work Order Description - 414114 - PSPM | PSPM | 1 | 304615 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414116 | Work Order Description - 414116 - PSPM | PSPM | 1 | 30711 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414118 | Work Order Description - 414118 - PSPM | PSPM | 1 | 304617 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414120 | Work Order Description - 414120 - PSPM | PSPM | 1 | 544189 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414122 | Work Order Description - 414122 - PSPM | PSPM | 1 | 409019 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414124 | Work Order Description - 414124 - PSPM | PSPM | 1 | 544190 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414126 | Work Order Description - 414126 - PSPM | PSPM | 1 | 30713 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414128 | Work Order Description - 414128 - PSPM | PSPM | 1 | 30715 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414130 | Work Order Description - 414130 - PSPM | PSPM | 1 | 30712 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414132 | Work Order Description - 414132 - PSPM | PSPM | 1 | 409048 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414134 | Work Order Description - 414134 - PSPM | PSPM | 1 | 409049 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414136 | Work Order Description - 414136 - PM | PM | 4 | 265668 | SCHD | SYS-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414138 | Work Order Description - 414138 - PM | PM | 3 | 323646 | SCHD | PACK-ISOL | 2019-03-29 | 2019-09-07 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 414140 | Work Order Description - 414140 - PSPM | PSPM | 1 | 556432 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | MECHANICAL | 600
2019-03-31 | 414142 | Work Order Description - 414142 - PM | PM | 4 | 556432 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | MECHANICAL | 144
2019-03-31 | 414146 | Work Order Description - 414146 - PM | PM | 4 | 556432 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 414149 | Work Order Description - 414149 - PSPM | PSPM | 1 | 408908 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414151 | Work Order Description - 414151 - PSPM | PSPM | 1 | 477531 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414153 | Work Order Description - 414153 - PM | PM | 4 | 30472 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414155 | Work Order Description - 414155 - PM | PM | 4 | 556432 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 414158 | Work Order Description - 414158 - PM | PM | 2 | 481988 | SCHD | TPS | 2019-03-29 | 2019-09-07 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | MECHANICAL | 22
2019-03-31 | 414162 | Work Order Description - 414162 - PM | PM | 2 | 324680 | SCHD | TPS | 2019-03-29 | 2019-09-07 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 414166 | Work Order Description - 414166 - PM | PM | 4 | 30504 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414168 | Work Order Description - 414168 - PSPM | PSPM | 1 | 30687 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414170 | Work Order Description - 414170 - PM | PM | 4 | 256383 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414172 | Work Order Description - 414172 - PSPM | PSPM | 1 | 409091 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414174 | Work Order Description - 414174 - PSPM | PSPM | 1 | 409007 | SCHD | SYS-ISOL | 2019-03-29 | 2019-09-07 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 414176 | Work Order Description - 414176 - PM | PM | 4 | 409090 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414178 | Work Order Description - 414178 - PM | PM | 4 | 401552 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414180 | Work Order Description - 414180 - PM | PM | 4 | 409093 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 414182 | Work Order Description - 414182 - PM | PM | 4 | 409268 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414184 | Work Order Description - 414184 - PM | PM | 4 | 409066 | SCHD | PACK-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414186 | Work Order Description - 414186 - PM | PM | 4 | 30508 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414188 | Work Order Description - 414188 - PM | PM | 4 | 30471 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414190 | Work Order Description - 414190 - PSPM | PSPM | 1 | 30420 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414192 | Work Order Description - 414192 - PSPM | PSPM | 1 | 408869 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414194 | Work Order Description - 414194 - PM | PM | 4 | 30602 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414196 | Work Order Description - 414196 - PM | PM | 4 | 256578 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-10-31 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 414198 | Work Order Description - 414198 - PM | PM | 4 | 408676 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414200 | Work Order Description - 414200 - PM | PM | 4 | 408682 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414202 | Work Order Description - 414202 - PM | PM | 4 | 543908 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414204 | Work Order Description - 414204 - PSPM | PSPM | 1 | 30618 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414206 | Work Order Description - 414206 - PSPM | PSPM | 1 | 30620 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414208 | Work Order Description - 414208 - PM | PM | 4 | 543881 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414210 | Work Order Description - 414210 - PM | PM | 4 | 30609 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414212 | Work Order Description - 414212 - PM | PM | 4 | 30610 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414214 | Work Order Description - 414214 - PM | PM | 4 | 543882 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414216 | Work Order Description - 414216 - PM | PM | 4 | 543884 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414218 | Work Order Description - 414218 - PM | PM | 4 | 30612 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414220 | Work Order Description - 414220 - PM | PM | 4 | 408681 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414222 | Work Order Description - 414222 - PM | PM | 4 | 543904 | WRISKQ | PACK-ISOL | 2019-03-23 | 2019-08-14 | 2019-08-13 | 2019-08-13 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414224 | Work Order Description - 414224 - PM | PM | 4 | 543906 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414226 | Work Order Description - 414226 - PM | PM | 4 | 30617 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414228 | Work Order Description - 414228 - PM | PM | 2 | 462658 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-09-07 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 414230 | Work Order Description - 414230 - PM | PM | 3 | 503331 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414232 | Work Order Description - 414232 - PM | PM | 3 | 494178 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414234 | Work Order Description - 414234 - PM | PM | 3 | 465837 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 414236 | Work Order Description - 414236 - PM | PM | 3 | 465838 | SCHD | SYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 414238 | Work Order Description - 414238 - PM | PM | 4 | 544162 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414240 | Work Order Description - 414240 - PM | PM | 4 | 544163 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414242 | Work Order Description - 414242 - PSPM | PSPM | 1 | 544267 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414244 | Work Order Description - 414244 - PSPM | PSPM | 1 | 544268 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414248 | Work Order Description - 414248 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | SAFETY | 7
2019-03-31 | 414250 | Work Order Description - 414250 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 414252 | Work Order Description - 414252 - PSPM | PSPM | 1 | 669726 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 414254 | Work Order Description - 414254 - PM | PM | 2 | 445036 | SCHD | EQUIP-ISOL | 2019-03-18 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 414256 | Work Order Description - 414256 - PM | PM | 2 | 178962 | SCHD | EQUIP-ISOL | 2019-03-18 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414258 | Work Order Description - 414258 - PM | PM | 2 | 99599 | SCHD | EQUIP-ISOL | 2019-03-18 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414260 | Work Order Description - 414260 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 414262 | Work Order Description - 414262 - PM | PM | 4 | 238227 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 2 | INTEGRITY | INSPECTION | 4
2019-03-31 | 414264 | Work Order Description - 414264 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 414267 | Work Order Description - 414267 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-14 | 2019-07-14 | 2019-07-14 | 3 | MAINTENANCE | ELECTRICAL | 0.5
2019-03-31 | 414438 | Work Order Description - 414438 - BR | BR | 4 | 266597 | WPLAN | EQUIP-ISOL | 2019-03-23 | 2019-09-15 | 2019-04-26 | 2019-04-26 | 3 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 414440 | Work Order Description - 414440 - CM | CM | 3 | 36117 | WRISKQ | PACK-ISOL | 2019-03-16 | 2020-03-15 |  |  | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 414446 | Work Order Description - 414446 - BR | BR | 4 | 705974 | WMATL | PACK-ISOL | 2019-03-18 | 2019-06-09 | 2019-06-08 | 2019-06-08 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 414458 | Work Order Description - 414458 - BR | BR | 4 | 705985 | WMATL | PACK-ISOL | 2019-03-18 | 2019-06-09 | 2019-05-18 | 2019-05-18 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 414465 | Work Order Description - 414465 - BR | BR | 3 | 312683 | SCHD | EQUIP-ISOL | 2019-03-16 | 2019-06-09 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 414467 | Work Order Description - 414467 - BR | BR | 4 | 705972 | WMATL | PACK-ISOL | 2019-03-18 | 2019-06-09 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 414471 | Work Order Description - 414471 - BR | BR | 4 | 705973 | WMATL | PACK-ISOL | 2019-03-18 | 2019-06-09 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 414482 | Work Order Description - 414482 - BR | BR | 3 | 44601 | WPLAN | EQUIP-ISOL | 2019-03-17 | 2020-03-16 | 2019-07-27 | 2019-07-27 | 3 | MAINTENANCE | CONSTRUCTION | 96
2019-03-31 | 414502 | Work Order Description - 414502 - CM | CM | 4 | 292440 | WSCHD | NORM-OPS | 2019-03-18 | 2020-03-15 | 2019-04-13 | 2019-04-13 | 3 | INTEGRITY | FABRIC | 561
2019-03-31 | 414509 | Work Order Description - 414509 - CM | CM | 3 | 375795 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-09-20 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 58
2019-03-31 | 414524 | Work Order Description - 414524 - BR | BR | 3 | 657770 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2021-03-14 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 414537 | Work Order Description - 414537 - CM | CM | 4 | 243680 | SCHD | EQUIP-ISOL | 2019-03-29 | 2021-03-14 | 2021-01-30 | 2021-01-30 | 4 | MAINTENANCE | DRILLING | 5
2019-03-31 | 414539 | Work Order Description - 414539 - CM | CM | 4 | 552898 | SCHD | EQUIP-ISOL | 2019-03-29 | 2021-03-14 | 2021-01-30 | 2021-01-30 | 4 | MAINTENANCE | DRILLING | 5
2019-03-31 | 414541 | Work Order Description - 414541 - CM | CM | 4 | 216480 | SCHD | EQUIP-ISOL | 2019-03-29 | 2021-03-14 | 2021-01-30 | 2021-01-30 | 4 | MAINTENANCE | DRILLING | 5
2019-03-31 | 414543 | Work Order Description - 414543 - CM | CM | 4 | 479506 | SCHD | EQUIP-ISOL | 2019-03-29 | 2021-03-14 | 2021-01-30 | 2021-01-30 | 4 | MAINTENANCE | DRILLING | 5
2019-03-31 | 414545 | Work Order Description - 414545 - CM | CM | 4 | 552899 | SCHD | EQUIP-ISOL | 2019-03-29 | 2021-03-14 | 2021-01-30 | 2021-01-30 | 4 | MAINTENANCE | DRILLING | 5
2019-03-31 | 414551 | Work Order Description - 414551 - CM | CM | 4 | 216481 | SCHD | EQUIP-ISOL | 2019-03-29 | 2021-03-14 | 2021-01-30 | 2021-01-30 | 4 | MAINTENANCE | DRILLING | 5
2019-03-31 | 414556 | Work Order Description - 414556 - PRJ | PRJ | 4 | 216029 | WPLAN | SYS-ISOL | 2019-03-19 | 2020-03-15 | 2020-03-14 | 2020-03-17 | 3 | ENGINEERING | CONSTRUCTION | 63
2019-03-31 | 414562 | Work Order Description - 414562 - BR | BR | 3 | 546271 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-09-16 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414567 | Work Order Description - 414567 - BR | BR | 4 | 705971 | WMATL | PACK-ISOL | 2019-03-18 | 2019-06-09 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | DRILLING | 6
2019-03-31 | 414571 | Work Order Description - 414571 - BR | BR | 4 | 705981 | WMATL | PACK-ISOL | 2019-03-18 | 2019-06-09 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 414576 | Work Order Description - 414576 - CM | CM | 4 | 217862 | SCHD | NORM-OPS | 2019-03-18 | 2019-06-09 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414579 | Work Order Description - 414579 - BR | BR | 4 | 705982 | WMATL | NORM-OPS | 2019-03-18 | 2019-06-09 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 414583 | Work Order Description - 414583 - BR | BR | 4 | 705969 | WMATL | NORM-OPS | 2019-03-18 | 2019-06-09 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 414585 | Work Order Description - 414585 - BR | BR | 4 | 705983 | WMATL | NORM-OPS | 2019-03-18 | 2019-06-09 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 414587 | Work Order Description - 414587 - BR | BR | 4 | 705975 | WMATL | NORM-OPS | 2019-03-18 | 2019-06-09 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 414589 | Work Order Description - 414589 - BR | BR | 4 | 705970 | WMATL | NORM-OPS | 2019-03-18 | 2019-06-09 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | OPERATIONS | 16
2019-03-31 | 414593 | Work Order Description - 414593 - BR | BR | 4 | 705979 | WMATL | NORM-OPS | 2019-03-18 | 2019-06-09 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | OPERATIONS | 2
2019-03-31 | 414598 | Work Order Description - 414598 - BR | BR | 4 | 705962 | WMATL | EQUIP-ISOL | 2019-03-18 | 2019-06-09 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | DRILLING | 6
2019-03-31 | 414602 | Work Order Description - 414602 - BR | BR | 4 | 705980 | WMATL | PACK-ISOL | 2019-03-18 | 2019-06-09 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | OPERATIONS | 4
2019-03-31 | 414613 | Work Order Description - 414613 - BR | BR | 4 | 705963 | WMATL | PACK-ISOL | 2019-03-18 | 2019-06-09 | 2019-05-11 | 2019-05-11 | 2 | MAINTENANCE | OPERATIONS | 6
2019-03-31 | 414619 | Work Order Description - 414619 - CM | CM | 4 | 243651 | SCHD | EQUIP-ISOL | 2019-03-27 | 2021-03-15 | 2021-01-31 | 2021-01-31 | 4 | MAINTENANCE | DRILLING | 4
2019-03-31 | 414621 | Work Order Description - 414621 - CM | CM | 4 | 216438 | WSCHD | EQUIP-ISOL | 2019-03-29 | 2021-03-15 | 2020-03-15 | 2020-03-15 | 4 | MAINTENANCE | DRILLING | 2
2019-03-31 | 414628 | Work Order Description - 414628 - PSPM | PSPM | 1 | 679155 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 414631 | Work Order Description - 414631 - PSPM | PSPM | 1 | 541314 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 414633 | Work Order Description - 414633 - PM | PM | 4 | 18317 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414635 | Work Order Description - 414635 - PM | PM | 4 | 18316 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414637 | Work Order Description - 414637 - PM | PM | 4 | 666316 | WPLAN | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414640 | Work Order Description - 414640 - PM | PM | 4 | 417521 | WPLAN | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414642 | Work Order Description - 414642 - PM | PM | 4 | 50099 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414644 | Work Order Description - 414644 - PM | PM | 4 | 50098 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414646 | Work Order Description - 414646 - PM | PM | 4 | 411571 | WSCHD | NORM-OPS | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414648 | Work Order Description - 414648 - PM | PM | 4 | 358159 | WSCHD | NORM-OPS | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414650 | Work Order Description - 414650 - PM | PM | 4 | 540667 | WSCHD | NORM-OPS | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414652 | Work Order Description - 414652 - PM | PM | 4 | 678551 | WSCHD | NORM-OPS | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 414654 | Work Order Description - 414654 - PM | PM | 3 | 357058 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 414656 | Work Order Description - 414656 - PM | PM | 3 | 246496 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 414658 | Work Order Description - 414658 - PSPM | PSPM | 1 | 657680 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 414660 | Work Order Description - 414660 - PSPM | PSPM | 1 | 671558 | WPLAN | NORM-OPS | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | SERVICES | 40
2019-03-31 | 414662 | Work Order Description - 414662 - PSPM | PSPM | 1 | 307984 | WPLAN | NORM-OPS | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | SERVICES | 60
2019-03-31 | 414664 | Work Order Description - 414664 - PM | PM | 3 | 408229 | WSCHD | NORM-OPS | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 414666 | Work Order Description - 414666 - PSPM | PSPM | 1 | 677996 | WSCHD | NORM-OPS | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 414668 | Work Order Description - 414668 - PM | PM | 4 | 498622 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 414670 | Work Order Description - 414670 - PM | PM | 4 | 318578 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 414672 | Work Order Description - 414672 - PM | PM | 4 | 520388 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 414674 | Work Order Description - 414674 - PM | PM | 4 | 520389 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 414676 | Work Order Description - 414676 - PM | PM | 4 | 520390 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 414678 | Work Order Description - 414678 - PM | PM | 4 | 520391 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 414680 | Work Order Description - 414680 - PM | PM | 4 | 498623 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 414682 | Work Order Description - 414682 - PSPM | PSPM | 1 | 318579 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 414684 | Work Order Description - 414684 - PM | PM | 4 | 354360 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 414686 | Work Order Description - 414686 - PM | PM | 4 | 498643 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 414688 | Work Order Description - 414688 - PM | PM | 4 | 498644 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 414690 | Work Order Description - 414690 - PM | PM | 4 | 520393 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 414692 | Work Order Description - 414692 - PM | PM | 4 | 318580 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 414694 | Work Order Description - 414694 - PM | PM | 4 | 498646 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 414696 | Work Order Description - 414696 - PM | PM | 4 | 354363 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 414698 | Work Order Description - 414698 - PSPM | PSPM | 1 | 470877 | WSCHD | NORM-OPS | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 414700 | Work Order Description - 414700 - PSPM | PSPM | 1 | 672199 | WSCHD | NORM-OPS | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | OPERATIONS | SAFETY | 2
2019-03-31 | 414702 | Work Order Description - 414702 - PM | PM | 4 | 360243 | WSCHD | NORM-OPS | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 414704 | Work Order Description - 414704 - PM | PM | 3 | 361952 | WSCHD | NORM-OPS | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | INTEGRITY | INSPECTION | 1
2019-03-31 | 414706 | Work Order Description - 414706 - PSPM | PSPM | 1 | 546068 | WSCHD | NORM-OPS | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | SERVICES | 6
2019-03-31 | 414708 | Work Order Description - 414708 - PSPM | PSPM | 1 | 652220 | WSCHD | NORM-OPS | 2019-03-17 | 2019-08-15 | 2019-07-03 | 2019-07-03 | 1 | MAINTENANCE | SERVICES | 6
2019-03-31 | 414710 | Work Order Description - 414710 - PM | PM | 4 | 555977 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 414712 | Work Order Description - 414712 - PSPM | PSPM | 1 | 216927 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | OPERATIONS | MEDIC | 4
2019-03-31 | 414714 | Work Order Description - 414714 - PM | PM | 4 | 481636 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 3 | OPERATIONS | SAFETY | 35
2019-03-31 | 414716 | Work Order Description - 414716 - PM | PM | 4 | 481637 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 3 | OPERATIONS | SAFETY | 14
2019-03-31 | 414718 | Work Order Description - 414718 - PSPM | PSPM | 1 | 128338 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | OPERATIONS | OPERATIONS | 4
2019-03-31 | 414720 | Work Order Description - 414720 - PM | PM | 4 | 556260 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 414722 | Work Order Description - 414722 - PM | PM | 2 | 216011 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 414724 | Work Order Description - 414724 - PM | PM | 4 | 320026 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 414726 | Work Order Description - 414726 - PM | PM | 4 | 216158 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 414728 | Work Order Description - 414728 - PM | PM | 4 | 567819 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 414730 | Work Order Description - 414730 - PM | PM | 4 | 74216 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 414734 | Work Order Description - 414734 - PSPM | PSPM | 1 | 686523 | WPLAN | NORM-OPS | 2019-03-17 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | INTEGRITY | INSPECTION | 2
2019-03-31 | 414736 | Work Order Description - 414736 - PSPM | PSPM | 1 | 686524 | WPLAN | NORM-OPS | 2019-03-17 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | INTEGRITY | INSPECTION | 2
2019-03-31 | 414738 | Work Order Description - 414738 - PM | PM | 3 | 266661 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 2 | MAINTENANCE | MECHANICAL | 54
2019-03-31 | 414740 | Work Order Description - 414740 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 414742 | Work Order Description - 414742 - PSPM | PSPM | 1 | 659055 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | OPERATIONS | SAFETY | 7
2019-03-31 | 414744 | Work Order Description - 414744 - PSPM | PSPM | 1 | 106086 | SCHD | EQUIP-ISOL | 2019-03-18 | 2019-11-01 | 2019-07-15 | 2019-07-15 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 414746 | Work Order Description - 414746 - PSPM | PSPM | 1 | 99897 | SCHD | EQUIP-ISOL | 2019-03-18 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 414748 | Work Order Description - 414748 - PM | PM | 4 | 228239 | SCHD | NORM-OPS | 2019-03-18 | 2019-09-08 | 2019-07-15 | 2019-07-15 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 414750 | Work Order Description - 414750 - PSPM | PSPM | 1 | 659511 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 414752 | Work Order Description - 414752 - PSPM | PSPM | 1 | 659511 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 414754 | Work Order Description - 414754 - PM | PM | 4 | 277314 | SCHD | EQUIP-ISOL | 2019-03-18 | 2019-11-01 | 2019-07-15 | 2019-07-15 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 414756 | Work Order Description - 414756 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 414758 | Work Order Description - 414758 - PSPM | PSPM | 1 | 659561 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 414760 | Work Order Description - 414760 - PSPM | PSPM | 1 | 127752 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 414762 | Work Order Description - 414762 - PM | PM | 4 | 112923 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 414764 | Work Order Description - 414764 - PM | PM | 4 | 670525 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 414766 | Work Order Description - 414766 - PM | PM | 4 | 375852 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 414768 | Work Order Description - 414768 - PSPM | PSPM | 1 | 99434 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-15 | 2019-07-15 | 2019-07-15 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 415588 | Work Order Description - 415588 - PSCM | PSCM | 1 | 671829 | WSCHD | EQUIP-ISOL | 2019-03-17 | 2020-03-16 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 67
2019-03-31 | 415602 | Work Order Description - 415602 - CM | CM | 1 | 314584 | WSCHD | NORM-OPS | 2019-03-17 | 2019-09-16 | 2019-11-02 | 2019-11-02 | 3 | MAINTENANCE | ELECTRICAL | 10
2019-03-31 | 415603 | Work Order Description - 415603 - BR | BR | 4 | 671829 | WPLAN | EQUIP-ISOL | 2019-03-17 | 2020-03-16 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 207
2019-03-31 | 415633 | Work Order Description - 415633 - CM | CM | 3 | 357276 | WPLAN | EQUIP-ISOL | 2019-03-18 | 2020-03-16 | 2019-04-27 | 2019-04-27 | 3 | MAINTENANCE | MECHANICAL | 302
2019-03-31 | 415654 | Work Order Description - 415654 - CM | CM | 3 | 674810 | WPLAN | EQUIP-ISOL | 2019-03-18 | 2020-03-16 | 2019-05-11 | 2019-05-11 | 3 | MAINTENANCE | MECHANICAL | 228
2019-03-31 | 415656 | Work Order Description - 415656 - PRJ | PRJ | 4 | 216029 | SCHD | NORM-OPS | 2019-03-29 | 2021-03-16 | 2021-02-01 | 2021-02-01 | 4 | ENGINEERING | MECHANICAL | 4
2019-03-31 | 415684 | Work Order Description - 415684 - CM | CM | 1 | 378843 | WPLAN | NORM-OPS | 2019-03-23 | 2019-04-15 | 2019-03-31 | 2019-03-31 | 2 | INTEGRITY | CONSTRUCTION | 160
2019-03-31 | 415695 | Work Order Description - 415695 - CM | CM | 3 | 672691 | WPLAN | SYS-ISOL | 2019-03-18 | 2019-09-16 | 2019-06-16 | 2019-06-16 | 3 | MAINTENANCE | MECHANICAL | 120
2019-03-31 | 415725 | Work Order Description - 415725 - CM | CM | 1 | 411258 | WSCHD | TPS | 2019-03-24 | 2020-03-16 | 2019-06-01 | 2019-06-01 | 3 | INTEGRITY | FABRIC | 240
2019-03-31 | 415731 | Work Order Description - 415731 - BR | BR | 2 | 262784 | WPLAN | NORM-OPS | 2019-03-19 | 2019-09-16 | 2019-06-17 | 2019-06-17 | 3 | INTEGRITY | OPERATIONS | 12
2019-03-31 | 415735 | Work Order Description - 415735 - BR | BR | 3 | 127842 | WPLAN | NORM-OPS | 2019-03-23 | 2019-06-11 | 2019-04-29 | 2019-04-29 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 415737 | Work Order Description - 415737 - PSPM | PSPM | 1 | 540544 | WSCHD | EQUIP-ISOL | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 415741 | Work Order Description - 415741 - PSPM | PSPM | 1 | 540551 | WSCHD | EQUIP-ISOL | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 415743 | Work Order Description - 415743 - PSPM | PSPM | 1 | 540576 | WSCHD | EQUIP-ISOL | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 415745 | Work Order Description - 415745 - PSPM | PSPM | 1 | 595879 | WSCHD | EQUIP-ISOL | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 415747 | Work Order Description - 415747 - PSPM | PSPM | 1 | 540579 | WSCHD | EQUIP-ISOL | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 415749 | Work Order Description - 415749 - PSPM | PSPM | 1 | 678472 | WSCHD | EQUIP-ISOL | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 415751 | Work Order Description - 415751 - PSPM | PSPM | 1 | 595880 | WSCHD | EQUIP-ISOL | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 415753 | Work Order Description - 415753 - PSPM | PSPM | 1 | 541339 | WSCHD | EQUIP-ISOL | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 415755 | Work Order Description - 415755 - PM | PM | 3 | 314190 | WSCHD | NORM-OPS | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 415757 | Work Order Description - 415757 - PM | PM | 2 | 314195 | WSCHD | NORM-OPS | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 415759 | Work Order Description - 415759 - PSPM | PSPM | 1 | 18946 | WSCHD | NORM-OPS | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 415761 | Work Order Description - 415761 - PM | PM | 4 | 314186 | WSCHD | NORM-OPS | 2019-03-18 | 2019-09-09 | 2019-07-28 | 2019-07-28 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 415763 | Work Order Description - 415763 - PM | PM | 4 | 314186 | WSCHD | NORM-OPS | 2019-03-18 | 2019-09-09 | 2019-07-28 | 2019-07-28 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 415765 | Work Order Description - 415765 - PM | PM | 3 | 308030 | WSCHD | EQUIP-ISOL | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 415767 | Work Order Description - 415767 - PSPM | PSPM | 1 | 531756 | WSCHD | NORM-OPS | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 415769 | Work Order Description - 415769 - PM | PM | 3 | 410689 | WSCHD | EQUIP-ISOL | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 415771 | Work Order Description - 415771 - PM | PM | 3 | 314190 | WSCHD | NORM-OPS | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 415773 | Work Order Description - 415773 - PM | PM | 3 | 314190 | WSCHD | NORM-OPS | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 415775 | Work Order Description - 415775 - PSPM | PSPM | 1 | 50931 | WSCHD | EQUIP-ISOL | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 415777 | Work Order Description - 415777 - PM | PM | 4 | 651607 | WSCHD | NORM-OPS | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 2 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 415779 | Work Order Description - 415779 - PSPM | PSPM | 1 | 676296 | WPLAN | PACK-ISOL | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 415781 | Work Order Description - 415781 - PM | PM | 2 | 363762 | WPLAN | NORM-OPS | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 2 | MAINTENANCE | MECHANICAL | 37.5
2019-03-31 | 415783 | Work Order Description - 415783 - PSPM | PSPM | 1 | 18946 | WPLAN | EQUIP-ISOL | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 415785 | Work Order Description - 415785 - PSPM | PSPM | 1 | 531756 | WPLAN | EQUIP-ISOL | 2019-03-18 | 2019-08-16 | 2019-07-04 | 2019-07-04 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 415787 | Work Order Description - 415787 - PM | PM | 4 | 481609 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-16 | 2019-07-16 | 2019-07-16 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 415789 | Work Order Description - 415789 - PSPM | PSPM | 1 | 462436 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-16 | 2019-07-16 | 2019-07-16 | 1 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 415791 | Work Order Description - 415791 - PM | PM | 4 | 476154 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-16 | 2019-07-16 | 2019-07-16 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 415793 | Work Order Description - 415793 - PSPM | PSPM | 1 | 265465 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-16 | 2019-07-16 | 2019-07-16 | 1 | INTEGRITY | INSPECTION | 8
2019-03-31 | 415795 | Work Order Description - 415795 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-16 | 2019-07-16 | 2019-07-16 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 415799 | Work Order Description - 415799 - PM | PM | 4 | 482752 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-16 | 2019-07-16 | 2019-07-16 | 2 | MAINTENANCE | MECHANICAL | 30
2019-03-31 | 415801 | Work Order Description - 415801 - PSPM | PSPM | 4 | 403503 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-16 | 2019-07-16 | 2019-07-16 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 415803 | Work Order Description - 415803 - PM | PM | 4 | 451337 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-16 | 2019-07-16 | 2019-07-16 | 2 | INTEGRITY | INSPECTION | 8
2019-03-31 | 415805 | Work Order Description - 415805 - PM | PM | 4 | 451439 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-16 | 2019-07-16 | 2019-07-16 | 1 | OPERATIONS | OPERATIONS | 14
2019-03-31 | 415807 | Work Order Description - 415807 - PM | PM | 4 | 228839 | WPLAN | NORM-OPS | 2019-03-18 | 2019-08-16 | 2019-07-16 | 2019-07-16 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 415809 | Work Order Description - 415809 - PSPM | PSPM | 1 | 659511 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-16 | 2019-07-16 | 2019-07-16 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 415811 | Work Order Description - 415811 - PSPM | PSPM | 1 | 450984 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-16 | 2019-08-12 | 2019-08-12 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 415813 | Work Order Description - 415813 - PSPM | PSPM | 1 | 392215 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-16 | 2019-07-16 | 2019-07-16 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 415815 | Work Order Description - 415815 - PSPM | PSPM | 1 | 659511 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-16 | 2019-07-16 | 2019-07-16 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 415817 | Work Order Description - 415817 - PSPM | PSPM | 1 | 387827 | SCHD | NORM-OPS | 2019-03-18 | 2019-08-16 | 2019-07-16 | 2019-07-16 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 416034 | Work Order Description - 416034 - CM | CM | 1 | 378847 | WPLAN | NORM-OPS | 2019-03-23 | 2020-03-17 | 2019-09-16 | 2019-09-16 | 3 | INTEGRITY | CONSTRUCTION | 280
2019-03-31 | 416060 | Work Order Description - 416060 - BR | BR | 1 | 408298 | WSCHD | EQUIP-ISOL | 2019-03-18 | 2021-03-16 |  |  | 4 | MAINTENANCE | ELECTRICAL | 0
2019-03-31 | 416085 | Work Order Description - 416085 - BR | BR | 3 | 72132 | SCHD | NORM-OPS | 2019-03-22 | 2020-03-17 | 2020-03-16 | 2020-03-16 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 416087 | Work Order Description - 416087 - PRJ | PRJ | 4 | 267676 | WSCHD | NORM-OPS | 2019-03-22 | 2021-03-16 | 2019-05-08 | 2019-05-08 | 4 | ENGINEERING | SAFETY | 18
2019-03-31 | 416089 | Work Order Description - 416089 - CM | CM | 1 | 411258 | WSCHD | NORM-OPS | 2019-03-24 | 2021-03-16 | 2020-03-16 | 2020-03-16 | 4 | INTEGRITY | FABRIC | 100
2019-03-31 | 416097 | Work Order Description - 416097 - BR | BR | 2 | 128091 | SCHD | SYS-ISOL | 2019-03-29 | 2019-04-16 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | SUBSEA | 30
2019-03-31 | 416102 | Work Order Description - 416102 - CM | CM | 1 | 247357 | WSCHD | NORM-OPS | 2019-03-19 | 2020-03-06 | 2019-09-05 | 2019-09-05 | 3 | INTEGRITY | SERVICES | 7
2019-03-31 | 416106 | Work Order Description - 416106 - PM | PM | 4 | 540691 | WSCHD | NORM-OPS | 2019-03-19 | 2019-08-17 | 2019-07-05 | 2019-07-05 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 416108 | Work Order Description - 416108 - PM | PM | 4 | 678547 | WPLAN | EQUIP-ISOL | 2019-03-19 | 2019-09-10 | 2019-08-13 | 2019-08-13 | 2 | MAINTENANCE | INSTRUMENTS | 26
2019-03-31 | 416111 | Work Order Description - 416111 - PM | PM | 4 | 481470 | WSCHD | NORM-OPS | 2019-03-19 | 2019-08-17 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 416113 | Work Order Description - 416113 - PM | PM | 4 | 361243 | WPLAN | EQUIP-ISOL | 2019-03-19 | 2019-08-17 | 2019-07-05 | 2019-07-05 | 1 | INTEGRITY | CONSTRUCTION | 9
2019-03-31 | 416115 | Work Order Description - 416115 - PSPM | PSPM | 1 | 361799 | WSCHD | NORM-OPS | 2019-03-19 | 2019-08-17 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 416117 | Work Order Description - 416117 - PSPM | PSPM | 1 | 652220 | WPLAN | NORM-OPS | 2019-03-19 | 2019-08-17 | 2019-07-05 | 2019-07-05 | 1 | MAINTENANCE | SERVICES | 12
2019-03-31 | 416119 | Work Order Description - 416119 - PM | PM | 4 | 51697 | WPLAN | PACK-ISOL | 2019-03-19 | 2019-08-17 | 2019-07-20 | 2019-07-20 | 2 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 416121 | Work Order Description - 416121 - PM | PM | 4 | 99579 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-17 | 2019-07-17 | 2019-07-17 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 416123 | Work Order Description - 416123 - PM | PM | 4 | 460846 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-17 | 2019-07-17 | 2019-07-17 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 416137 | Work Order Description - 416137 - PSPM | PSPM | 1 | 527317 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-17 | 2019-07-17 | 2019-07-17 | 1 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 416139 | Work Order Description - 416139 - PM | PM | 4 | 441876 | SCHD | EQUIP-ISOL | 2019-03-22 | 2019-09-10 | 2019-07-17 | 2019-07-17 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 416141 | Work Order Description - 416141 - PSPM | PSPM | 1 | 179119 | SCHD | PACK-ISOL | 2019-03-29 | 2019-08-17 | 2019-07-17 | 2019-07-17 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 416284 | Work Order Description - 416284 - PRJ | PRJ | 4 | 501084 | SCHD | NORM-OPS | 2019-03-22 | 2021-03-17 | 2019-04-13 | 2019-04-13 | 4 | ENGINEERING | INSTRUMENTS | 92
2019-03-31 | 416294 | Work Order Description - 416294 - BR | BR | 3 | 72132 | WPLAN | NORM-OPS | 2019-03-23 | 2019-09-18 | 2019-06-18 | 2019-06-18 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 416295 | Work Order Description - 416295 - PRJ | PRJ | 3 | 468115 | WPLAN | EQUIP-ISOL | 2019-03-24 | 2020-03-18 | 2019-09-17 | 2019-09-17 | 3 | WELLS | WELLS | 4104
2019-03-31 | 416297 | Work Order Description - 416297 - CM | CM | 1 | 481746 | WPLAN | NORM-OPS | 2019-03-19 | 2020-03-18 | 2019-09-17 | 2019-09-18 | 3 | INTEGRITY | CONSTRUCTION | 24
2019-03-31 | 416311 | Work Order Description - 416311 - PRJ | PRJ | 3 | 580017 | WPLAN | EQUIP-ISOL | 2019-03-24 | 2020-03-18 | 2019-09-17 | 2019-09-17 | 3 | WELLS | WELLS | 4104
2019-03-31 | 416318 | Work Order Description - 416318 - PRJ | PRJ | 4 | 479486 | SCHD | NORM-OPS | 2019-03-29 | 2021-03-17 | 2021-02-02 | 2021-02-02 | 4 | ENGINEERING | CONSTRUCTION | 720
2019-03-31 | 416334 | Work Order Description - 416334 - PRJ | PRJ | 3 | 320396 | SCHD | NORM-OPS | 2019-03-19 | 2021-03-17 |  |  | 4 | ENGINEERING | INSPECTION | 23
2019-03-31 | 416341 | Work Order Description - 416341 - BR | BR | 3 | 654014 | WSCHD | EQUIP-ISOL | 2019-03-19 | 2020-03-18 |  |  | 3 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 416352 | Work Order Description - 416352 - CM | CM | 3 | 411258 | WSCHD | NORM-OPS | 2019-03-24 | 2021-03-17 | 2019-06-01 | 2019-06-01 | 4 | INTEGRITY | FABRIC | 12
2019-03-31 | 416363 | Work Order Description - 416363 - CM | CM | 4 | 407910 | WSCHD | NORM-OPS | 2019-03-24 | 2021-03-17 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | ELECTRICAL | 96
2019-03-31 | 416374 | Work Order Description - 416374 - BR | BR | 4 | 676326 | WMATL | EQUIP-ISOL | 2019-03-27 | 2019-09-18 | 2019-06-18 | 2019-06-18 | 3 | INTEGRITY | ELECTRICAL | 180
2019-03-31 | 416392 | Work Order Description - 416392 - PSCM | PSCM | 1 | 128767 | WMATL | SYS-ISOL | 2019-03-25 | 2020-03-18 | 2019-09-17 | 2019-09-17 | 3 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 416420 | Work Order Description - 416420 - PRJ | PRJ | 4 | 670509 | SCHD | PACK-ISOL | 2019-03-22 | 2019-09-20 | 2019-06-20 | 2019-06-20 | 3 | MAINTENANCE | MECHANICAL | 186
2019-03-31 | 416427 | Work Order Description - 416427 - BR | BR | 3 | 313939 | WSCHD | TPS | 2019-03-20 | 2020-03-19 |  |  | 3 | MAINTENANCE | MECHANICAL | 48
2019-03-31 | 416428 | Work Order Description - 416428 - PM | PM | 4 | 261575 | WPLAN | PACK-ISOL | 2019-03-20 | 2019-08-18 | 2019-07-06 | 2019-07-06 | 1 | INTEGRITY | CONSTRUCTION | 8
2019-03-31 | 416430 | Work Order Description - 416430 - PM | PM | 4 | 660951 | WSCHD | NORM-OPS | 2019-03-20 | 2019-08-18 | 2019-07-06 | 2019-07-06 | 3 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 416434 | Work Order Description - 416434 - PM | PM | 4 | 457377 | WPLAN | TPS | 2019-03-20 | 2019-08-18 | 2019-07-21 | 2019-07-21 | 2 | INTEGRITY | INSPECTION | 0.033333
2019-03-31 | 416437 | Work Order Description - 416437 - PM | PM | 4 | 256187 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-18 | 2019-07-18 | 2019-07-18 | 1 | INTEGRITY | INSPECTION | 7
2019-03-31 | 416439 | Work Order Description - 416439 - PSPM | PSPM | 1 | 123510 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-18 | 2019-07-18 | 2019-07-18 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 416443 | Work Order Description - 416443 - PSPM | PSPM | 1 | 659511 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-18 | 2019-07-18 | 2019-07-18 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 416445 | Work Order Description - 416445 - PSPM | PSPM | 1 | 42961 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-18 | 2019-07-18 | 2019-07-18 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 416447 | Work Order Description - 416447 - PSPM | PSPM | 4 | 99232 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-18 | 2019-07-18 | 2019-07-18 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 416449 | Work Order Description - 416449 - PSPM | PSPM | 1 | 126920 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-18 | 2019-07-18 | 2019-07-18 | 1 | MAINTENANCE | ELECTRICAL | 1.5
2019-03-31 | 416451 | Work Order Description - 416451 - PM | PM | 4 | 126984 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-18 | 2019-07-18 | 2019-07-18 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 416453 | Work Order Description - 416453 - PM | PM | 4 | 110878 | SCHD | PACK-ISOL | 2019-03-22 | 2019-09-11 | 2019-07-18 | 2019-07-18 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 416455 | Work Order Description - 416455 - PM | PM | 4 | 110822 | SCHD | PACK-ISOL | 2019-03-22 | 2019-09-11 | 2019-07-18 | 2019-07-18 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 416457 | Work Order Description - 416457 - PM | PM | 4 | 383919 | SCHD | PACK-ISOL | 2019-03-22 | 2019-09-11 | 2019-07-18 | 2019-07-18 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 416657 | Work Order Description - 416657 - BR | BR | 3 | 674414 | WSCHD | PACK-ISOL | 2019-03-26 | 2020-03-19 | 2019-09-18 | 2019-09-18 | 3 | MAINTENANCE | MECHANICAL | 40
2019-03-31 | 416659 | Work Order Description - 416659 - PSCM | PSCM | 1 | 669702 | WMATL | PACK-ISOL | 2019-03-22 | 2019-09-19 | 2019-06-19 | 2019-06-19 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 416669 | Work Order Description - 416669 - BR | BR | 3 | 387711 | WPLAN | NORM-OPS | 2019-03-23 | 2019-09-19 | 2019-06-19 | 2019-06-19 | 3 | INTEGRITY | INSTRUMENTS | 28
2019-03-31 | 416676 | Work Order Description - 416676 - BR | BR | 4 | 180131 | WPLAN | NORM-OPS | 2019-03-20 | 2021-03-18 | 2021-02-03 | 2021-02-03 | 4 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 416685 | Work Order Description - 416685 - PRJ | PRJ | 4 | 481746 | WPLAN | NORM-OPS | 2019-03-25 | 2020-03-19 | 2019-09-18 | 2019-09-21 | 3 | INTEGRITY | CONSTRUCTION | 51
2019-03-31 | 416689 | Work Order Description - 416689 - PRJ | PRJ | 4 | 127594 | SCHD | NORM-OPS | 2019-03-29 | 2020-03-19 | 2019-04-02 | 2019-04-02 | 3 | ENGINEERING | MECHANICAL | 200
2019-03-31 | 416703 | Work Order Description - 416703 - CM | CM | 4 | 319157 | WSCHD | NORM-OPS | 2019-03-24 | 2020-03-19 | 2019-05-25 | 2019-05-25 | 3 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 416704 | Work Order Description - 416704 - PSCM | PSCM | 4 | 361896 | WSCHD | NORM-OPS | 2019-03-24 | 2021-03-18 | 2019-10-05 | 2019-10-05 | 4 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 416729 | Work Order Description - 416729 - BR | BR | 3 | 183827 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-06-13 | 2019-05-01 | 2019-05-01 | 2 | MAINTENANCE | ELECTRICAL | 32
2019-03-31 | 416734 | Work Order Description - 416734 - CM | CM | 4 | 368279 | WSCHD | NORM-OPS | 2019-03-22 | 2020-03-19 | 2019-06-01 | 2019-06-01 | 3 | INTEGRITY | INSPECTION | 56
2019-03-31 | 416777 | Work Order Description - 416777 - CM | CM | 4 | 179514 | WPLAN | NORM-OPS | 2019-03-23 | 2019-06-13 | 2019-05-01 | 2019-05-01 | 2 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 416785 | Work Order Description - 416785 - BR | BR | 3 | 392144 | WPLAN | PACK-ISOL | 2019-03-27 | 2021-03-18 | 2019-07-13 | 2019-07-13 | 4 | MAINTENANCE | MECHANICAL | 60
2019-03-31 | 416789 | Work Order Description - 416789 - BR | BR | 3 | 392259 | SCHD | PACK-ISOL | 2019-03-29 | 2021-03-18 | 2020-03-18 | 2020-03-18 | 4 | MAINTENANCE | MECHANICAL | 60
2019-03-31 | 416790 | Work Order Description - 416790 - PRJ | PRJ | 4 | 176866 | SCHD | NORM-OPS | 2019-03-29 | 2021-03-18 | 2020-03-18 | 2020-03-18 | 4 | MAINTENANCE | ELECTRICAL | 96
2019-03-31 | 416792 | Work Order Description - 416792 - PRJ | PRJ | 4 | 527177 | SCHD | NORM-OPS | 2019-03-29 | 2021-03-18 | 2019-04-09 | 2019-04-09 | 4 | ENGINEERING | ELECTRICAL | 108
2019-03-31 | 416805 | Work Order Description - 416805 - BR | BR | 3 | 114063 | SCHD | NORM-OPS | 2019-03-29 | 2019-06-13 | 2019-05-01 | 2019-05-01 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 416807 | Work Order Description - 416807 - BR | BR | 3 | 308494 | WSCHD | NORM-OPS | 2019-03-22 | 2020-03-20 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 416812 | Work Order Description - 416812 - PM | PM | 4 | 51202 | WSCHD | NORM-OPS | 2019-03-21 | 2019-08-19 | 2019-07-07 | 2019-07-07 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 416814 | Work Order Description - 416814 - PSPM | PSPM | 1 | 580769 | WSCHD | NORM-OPS | 2019-03-21 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 416816 | Work Order Description - 416816 - PM | PM | 4 | 246173 | WSCHD | NORM-OPS | 2019-03-21 | 2019-08-19 | 2019-07-07 | 2019-07-07 | 1 | INTEGRITY | SERVICES | 2
2019-03-31 | 416818 | Work Order Description - 416818 - PM | PM | 4 | 546030 | WSCHD | NORM-OPS | 2019-03-21 | 2019-08-19 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 416820 | Work Order Description - 416820 - PM | PM | 4 | 652482 | WSCHD | NORM-OPS | 2019-03-21 | 2019-08-19 | 2019-07-07 | 2019-07-07 | 1 | INTEGRITY | SERVICES | 2
2019-03-31 | 416822 | Work Order Description - 416822 - PSPM | PSPM | 1 | 294959 | WSCHD | NORM-OPS | 2019-03-21 | 2019-08-19 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | INSTRUMENTS | 5
2019-03-31 | 416824 | Work Order Description - 416824 - PSPM | PSPM | 1 | 675037 | WSCHD | NORM-OPS | 2019-03-21 | 2019-08-19 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 416826 | Work Order Description - 416826 - PSPM | PSPM | 1 | 671829 | WSCHD | NORM-OPS | 2019-03-21 | 2019-08-19 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 416828 | Work Order Description - 416828 - PSPM | PSPM | 1 | 547275 | WPLAN | NORM-OPS | 2019-03-21 | 2019-08-19 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 416830 | Work Order Description - 416830 - PSPM | PSPM | 1 | 547276 | WPLAN | NORM-OPS | 2019-03-21 | 2019-08-19 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 416832 | Work Order Description - 416832 - PSPM | PSPM | 1 | 519760 | WPLAN | NORM-OPS | 2019-03-21 | 2019-08-19 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 416834 | Work Order Description - 416834 - PSPM | PSPM | 1 | 410324 | WPLAN | NORM-OPS | 2019-03-21 | 2019-08-19 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 416836 | Work Order Description - 416836 - PSPM | PSPM | 1 | 361798 | WPLAN | NORM-OPS | 2019-03-21 | 2019-08-19 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 416838 | Work Order Description - 416838 - PM | PM | 4 | 292836 | WSCHD | NORM-OPS | 2019-03-21 | 2019-08-19 | 2019-07-07 | 2019-07-07 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 416840 | Work Order Description - 416840 - PSPM | PSPM | 1 | 403503 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | MAINTENANCE | INSTRUMENTS | 5.5
2019-03-31 | 416842 | Work Order Description - 416842 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 416844 | Work Order Description - 416844 - PSPM | PSPM | 1 | 27535 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 416846 | Work Order Description - 416846 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 416848 | Work Order Description - 416848 - PSPM | PSPM | 1 | 567452 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 416850 | Work Order Description - 416850 - PSPM | PSPM | 1 | 184667 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 416852 | Work Order Description - 416852 - PSPM | PSPM | 1 | 567562 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 416854 | Work Order Description - 416854 - PSPM | PSPM | 1 | 584883 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 416856 | Work Order Description - 416856 - PSPM | PSPM | 1 | 567646 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 416858 | Work Order Description - 416858 - PM | PM | 4 | 316451 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 2 | DRILLING | DRILLING | 4
2019-03-31 | 416860 | Work Order Description - 416860 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 416862 | Work Order Description - 416862 - PM | PM | 4 | 499149 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 416868 | Work Order Description - 416868 - PM | PM | 4 | 228835 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 416870 | Work Order Description - 416870 - PSPM | PSPM | 1 | 663164 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 416872 | Work Order Description - 416872 - PSPM | PSPM | 1 | 74875 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | WELLS | WELLS | 8
2019-03-31 | 416874 | Work Order Description - 416874 - PSPM | PSPM | 1 | 74947 | SCHD | EQUIP-ISOL | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | WELLS | WELLS | 8
2019-03-31 | 416876 | Work Order Description - 416876 - PSPM | PSPM | 1 | 127776 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | WELLS | WELLS | 4
2019-03-31 | 416878 | Work Order Description - 416878 - PSPM | PSPM | 1 | 218111 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | WELLS | WELLS | 8
2019-03-31 | 416880 | Work Order Description - 416880 - PSPM | PSPM | 1 | 74876 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | WELLS | WELLS | 8
2019-03-31 | 416882 | Work Order Description - 416882 - PSPM | PSPM | 1 | 375692 | SCHD | EQUIP-ISOL | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | WELLS | WELLS | 8
2019-03-31 | 416884 | Work Order Description - 416884 - PSPM | PSPM | 1 | 74871 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | WELLS | WELLS | 8
2019-03-31 | 416886 | Work Order Description - 416886 - PSPM | PSPM | 1 | 74948 | SCHD | EQUIP-ISOL | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | WELLS | WELLS | 8
2019-03-31 | 416888 | Work Order Description - 416888 - PSPM | PSPM | 1 | 128022 | SCHD | EQUIP-ISOL | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | WELLS | WELLS | 8
2019-03-31 | 416890 | Work Order Description - 416890 - PSPM | PSPM | 1 | 74946 | SCHD | EQUIP-ISOL | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | WELLS | WELLS | 8
2019-03-31 | 416892 | Work Order Description - 416892 - PSPM | PSPM | 1 | 218107 | SCHD | PACK-ISOL | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | WELLS | WELLS | 8
2019-03-31 | 416894 | Work Order Description - 416894 - PSPM | PSPM | 1 | 74949 | SCHD | EQUIP-ISOL | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | WELLS | WELLS | 8
2019-03-31 | 416896 | Work Order Description - 416896 - PSPM | PSPM | 1 | 74945 | SCHD | EQUIP-ISOL | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | WELLS | WELLS | 8
2019-03-31 | 416898 | Work Order Description - 416898 - PSPM | PSPM | 1 | 392100 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 416900 | Work Order Description - 416900 - PSPM | PSPM | 1 | 179515 | WPLAN | NORM-OPS | 2019-03-21 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 416902 | Work Order Description - 416902 - PM | PM | 4 | 237971 | SCHD | EQUIP-ISOL | 2019-03-22 | 2019-09-12 | 2019-07-19 | 2019-07-19 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 416904 | Work Order Description - 416904 - PSPM | PSPM | 1 | 527315 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 416906 | Work Order Description - 416906 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-19 | 2019-07-19 | 2019-07-19 | 3 | MAINTENANCE | MEDIC | 21
2019-03-31 | 417016 | Work Order Description - 417016 - BR | BR | 3 | 357148 | WSCHD | NORM-OPS | 2019-03-24 | 2020-03-20 | 2019-05-18 | 2019-05-18 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 417053 | Work Order Description - 417053 - BR | BR | 1 | 127787 | SCHD | NORM-OPS | 2019-03-22 | 2021-03-19 | 2021-02-04 | 2021-02-04 | 4 | OPERATIONS | SAFETY | 2
2019-03-31 | 417055 | Work Order Description - 417055 - BR | BR | 3 | 376243 | SCHD | EQUIP-ISOL | 2019-03-22 | 2019-09-20 | 2019-06-20 | 2019-06-20 | 3 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 417075 | Work Order Description - 417075 - CM | CM | 1 | 392109 | WSCHD | SYS-ISOL | 2019-03-21 | 2019-09-20 |  |  | 3 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 417086 | Work Order Description - 417086 - PRJ | PRJ | 4 | 55937 | WSCHD | NORM-OPS | 2019-03-21 | 2021-03-19 |  |  | 4 | ENGINEERING | CONSTRUCTION | 0
2019-03-31 | 417089 | Work Order Description - 417089 - BR | BR | 3 | 493502 | WSCHD | SYS-ISOL | 2019-03-21 | 2020-03-20 |  |  | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 417092 | Work Order Description - 417092 - PRJ | PRJ | 1 | 375637 | SCHD | NORM-OPS | 2019-03-27 | 2021-03-19 | 2019-03-23 | 2019-03-23 | 4 | MAINTENANCE | MECHANICAL | 293
2019-03-31 | 417103 | Work Order Description - 417103 - PRJ | PRJ | 3 | 482715 | SCHD | PACK-ISOL | 2019-03-29 | 2021-03-19 | 2019-05-14 | 2019-05-14 | 4 | INTEGRITY | CONSTRUCTION | 1578
2019-03-31 | 417104 | Work Order Description - 417104 - BR | BR | 4 | 671828 | WSCHD | EQUIP-ISOL | 2019-03-22 | 2021-03-19 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 75
2019-03-31 | 417160 | Work Order Description - 417160 - CM | CM | 4 | 403920 | WPLAN | NORM-OPS | 2019-03-30 | 2020-03-26 | 2019-09-25 | 2019-09-27 | 3 | INTEGRITY | CONSTRUCTION | 14
2019-03-31 | 417188 | Work Order Description - 417188 - PRJ | PRJ | 4 | 375932 | SCHD | NORM-OPS | 2019-03-22 | 2019-06-14 | 2019-03-25 | 2019-03-25 | 2 | ENGINEERING | MECHANICAL | 204
2019-03-31 | 417190 | Work Order Description - 417190 - PRJ | PRJ | 3 | 668447 | SCHD | PACK-ISOL | 2019-03-22 | 2019-06-14 | 2019-05-13 | 2019-05-13 | 2 | MAINTENANCE | MECHANICAL | 31
2019-03-31 | 417191 | Work Order Description - 417191 - PRJ | PRJ | 3 | 668445 | SCHD | PACK-ISOL | 2019-03-22 | 2019-06-14 | 2019-05-13 | 2019-05-13 | 2 | MAINTENANCE | MECHANICAL | 51
2019-03-31 | 417199 | Work Order Description - 417199 - CM | CM | 3 | 179454 | WPLAN | NORM-OPS | 2019-03-23 | 2020-03-20 | 2019-09-20 | 2019-09-20 | 3 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 417208 | Work Order Description - 417208 - PM | PM | 1 | 671558 | WSCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 417210 | Work Order Description - 417210 - PM | PM | 1 | 671558 | WSCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | SERVICES | 6
2019-03-31 | 417212 | Work Order Description - 417212 - PM | PM | 1 | 671558 | WSCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | SERVICES | 9
2019-03-31 | 417214 | Work Order Description - 417214 - PSPM | PSPM | 1 | 541345 | WSCHD | EQUIP-ISOL | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 417216 | Work Order Description - 417216 - PSPM | PSPM | 1 | 541349 | WSCHD | EQUIP-ISOL | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 417218 | Work Order Description - 417218 - PSPM | PSPM | 1 | 541349 | WSCHD | EQUIP-ISOL | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 417220 | Work Order Description - 417220 - PSPM | PSPM | 1 | 541349 | WSCHD | EQUIP-ISOL | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 417222 | Work Order Description - 417222 - PSPM | PSPM | 1 | 541349 | WSCHD | EQUIP-ISOL | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 417224 | Work Order Description - 417224 - PSPM | PSPM | 1 | 355568 | WSCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 417226 | Work Order Description - 417226 - PSPM | PSPM | 1 | 51688 | WSCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 417228 | Work Order Description - 417228 - PSPM | PSPM | 1 | 545266 | WSCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 417230 | Work Order Description - 417230 - PSPM | PSPM | 1 | 321203 | WSCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 417232 | Work Order Description - 417232 - PSPM | PSPM | 1 | 321218 | WSCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 417234 | Work Order Description - 417234 - PM | PM | 4 | 323340 | WSCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | INTEGRITY | INSPECTION | 2
2019-03-31 | 417236 | Work Order Description - 417236 - PM | PM | 4 | 547276 | WPLAN | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 417238 | Work Order Description - 417238 - PSPM | PSPM | 1 | 547276 | WSCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 417240 | Work Order Description - 417240 - PM | PM | 4 | 293029 | WSCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | OPERATIONS | SAFETY | 13
2019-03-31 | 417242 | Work Order Description - 417242 - PM | PM | 4 | 260753 | WSCHD | NORM-OPS | 2019-03-22 | 2019-09-13 | 2019-08-16 | 2019-08-16 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 417244 | Work Order Description - 417244 - PM | PM | 4 | 64906 | WSCHD | NORM-OPS | 2019-03-22 | 2019-09-13 | 2019-08-16 | 2019-08-16 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 417246 | Work Order Description - 417246 - PM | PM | 4 | 294916 | WSCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-08 | 2019-07-08 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 417248 | Work Order Description - 417248 - PSPM | PSPM | 1 | 216946 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-20 | 2019-07-20 | 2019-07-20 | 1 | OPERATIONS | SAFETY | 4
2019-03-31 | 417250 | Work Order Description - 417250 - PSPM | PSPM | 1 | 29041 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-20 | 2019-07-20 | 2019-07-20 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 417252 | Work Order Description - 417252 - PSPM | PSPM | 1 | 462436 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-20 | 2019-07-20 | 2019-07-20 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 417254 | Work Order Description - 417254 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-20 | 2019-07-20 | 2019-07-20 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 417256 | Work Order Description - 417256 - PSPM | PSPM | 1 | 122617 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-20 | 2019-07-20 | 2019-07-20 | 1 | OPERATIONS | SAFETY | 7
2019-03-31 | 417262 | Work Order Description - 417262 - PM | PM | 4 | 527375 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-20 | 2019-07-20 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 417264 | Work Order Description - 417264 - PM | PM | 4 | 659575 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-20 | 2019-07-20 | 1 | MAINTENANCE | SAFETY | 7
2019-03-31 | 417266 | Work Order Description - 417266 - PM | PM | 4 | 659576 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-20 | 2019-07-20 | 1 | MAINTENANCE | SAFETY | 7
2019-03-31 | 417268 | Work Order Description - 417268 - PM | PM | 4 | 527399 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-20 | 2019-07-20 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 417270 | Work Order Description - 417270 - PM | PM | 4 | 450998 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-20 | 2019-07-20 | 1 | OPERATIONS | SAFETY | 1
2019-03-31 | 417272 | Work Order Description - 417272 - PM | PM | 4 | 450999 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-20 | 2019-07-20 | 1 | OPERATIONS | SAFETY | 1
2019-03-31 | 417274 | Work Order Description - 417274 - PSPM | PSPM | 1 | 378467 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-20 | 2019-07-20 | 1 | MAINTENANCE | ELECTRICAL | 16
2019-03-31 | 417276 | Work Order Description - 417276 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-20 | 2019-07-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 417278 | Work Order Description - 417278 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-20 | 2019-07-20 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 417280 | Work Order Description - 417280 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2019-03-22 | 2019-08-20 | 2019-07-20 | 2019-07-20 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 417437 | Work Order Description - 417437 - BR | BR | 1 | 125261 | WSCHD | EQUIP-ISOL | 2019-03-22 | 2021-03-20 |  |  | 4 | MAINTENANCE | ELECTRICAL | 0
2019-03-31 | 417445 | Work Order Description - 417445 - PRJ | PRJ | 4 | 659516 | SCHD | EQUIP-ISOL | 2019-03-22 | 2021-03-20 | 2021-02-05 | 2021-02-05 | 4 | ENGINEERING | ELECTRICAL | 1
2019-03-31 | 417486 | Work Order Description - 417486 - PRJ | PRJ | 1 | 127636 | SCHD | NORM-OPS | 2019-03-22 | 2021-03-20 | 2020-03-20 | 2020-03-20 | 4 | ENGINEERING | INSTRUMENTS | 1
2019-03-31 | 417487 | Work Order Description - 417487 - BR | BR | 4 | 685304 | SCHD | NORM-OPS | 2019-03-22 | 2021-03-20 | 2019-03-30 | 2019-04-27 | 4 | MAINTENANCE | SERVICES | 477.5
2019-03-31 | 417495 | Work Order Description - 417495 - CM | CM | 3 | 137600 | WSCHD | EQUIP-ISOL | 2019-03-24 | 2019-06-15 | 2019-05-03 | 2019-05-03 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 417499 | Work Order Description - 417499 - CM | CM | 3 | 601863 | SCHD | TPS | 2019-03-29 | 2020-03-21 | 2019-06-16 | 2019-06-16 | 3 | INTEGRITY | OPERATIONS | 360
2019-03-31 | 417500 | Work Order Description - 417500 - CM | CM | 3 | 307769 | WSCHD | EQUIP-ISOL | 2019-03-24 | 2019-06-15 | 2019-05-03 | 2019-05-03 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 417503 | Work Order Description - 417503 - BR | BR | 2 | 111134 | WSCHD | PACK-ISOL | 2019-03-22 | 2021-03-20 |  |  | 4 | MAINTENANCE | MECHANICAL | 0
2019-03-31 | 417504 | Work Order Description - 417504 - CM | CM | 3 | 499092 | WPLAN | EQUIP-ISOL | 2019-03-23 | 2019-09-21 | 2019-06-21 | 2019-06-21 | 3 | MAINTENANCE | INSTRUMENTS | 14
2019-03-31 | 417512 | Work Order Description - 417512 - PRJ | PRJ | 3 | 601744 | SCHD | TPS | 2019-03-29 | 2019-09-21 | 2019-06-21 | 2019-06-21 | 3 | INTEGRITY | OPERATIONS | 336
2019-03-31 | 417557 | Work Order Description - 417557 - PRJ | PRJ | 1 | 484754 | WSCHD | NORM-OPS | 2019-03-24 | 2019-09-21 | 2019-06-21 | 2019-06-21 | 3 | ENGINEERING | INSPECTION | 588
2019-03-31 | 417559 | Work Order Description - 417559 - PRJ | PRJ | 1 | 74878 | SCHD | TPS | 2019-03-29 | 2019-09-21 | 2019-07-07 | 2019-07-07 | 3 | ENGINEERING | OPERATIONS | 384
2019-03-31 | 417572 | Work Order Description - 417572 - PRJ | PRJ | 1 | 375637 | WSCHD | NORM-OPS | 2019-03-29 | 2021-03-20 | 2019-04-02 | 2019-04-02 | 4 | MAINTENANCE | CONSTRUCTION | 60
2019-03-31 | 417573 | Work Order Description - 417573 - BR | BR | 4 | 81260 | WPLAN | EQUIP-ISOL | 2019-03-29 | 2019-04-27 | 2019-04-12 | 2019-04-12 | 2 | MAINTENANCE | MECHANICAL | 28
2019-03-31 | 417577 | Work Order Description - 417577 - CM | CM | 4 | 652220 | WSCHD | EQUIP-ISOL | 2019-03-24 | 2020-03-21 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | MECHANICAL | 468
2019-03-31 | 417623 | Work Order Description - 417623 - PM | PM | 4 | 177242 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-11-08 | 2019-05-29 | 2019-05-29 | 2 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 417625 | Work Order Description - 417625 - PM | PM | 4 | 499117 | SCHD | TPS | 2019-03-29 | 2019-09-07 | 2019-07-14 | 2019-07-14 | 2 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 417627 | Work Order Description - 417627 - PSPM | PSPM | 1 | 472948 | SCHD | SUBSYS-ISOL | 2019-03-29 | 2019-05-21 | 2019-04-20 | 2019-04-20 | 1 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 417629 | Work Order Description - 417629 - PM | PM | 4 | 243160 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-07-02 | 2019-06-01 | 2019-06-01 | 2 | DRILLING | ELECTRICAL | 4
2019-03-31 | 417631 | Work Order Description - 417631 - PM | PM | 4 | 479007 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 2 | DRILLING | ELECTRICAL | 4
2019-03-31 | 417633 | Work Order Description - 417633 - PM | PM | 4 | 243162 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-06-01 | 2019-05-01 | 2019-05-01 | 2 | DRILLING | ELECTRICAL | 4
2019-03-31 | 417635 | Work Order Description - 417635 - PM | PM | 4 | 303719 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-07 | 2019-04-20 | 2019-04-20 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 417638 | Work Order Description - 417638 - PSPM | PSPM | 1 | 450947 | SCHD | PACK-ISOL | 2019-03-29 | 2019-05-22 | 2019-04-21 | 2019-04-21 | 1 | MAINTENANCE | ELECTRICAL | 360
2019-03-31 | 417684 | Work Order Description - 417684 - PM | PM | 4 | 362462 | SCHD | NORM-OPS | 2019-03-29 | 2019-10-20 | 2019-03-30 | 2019-04-18 | 2 | OPERATIONS | SAFETY | 9
2019-03-31 | 417694 | Work Order Description - 417694 - PM | PM | 4 | 246092 | WPLAN | NORM-OPS | 2019-03-22 | 2019-10-20 | 2019-04-06 | 2019-04-06 | 2 | OPERATIONS | SAFETY | 9
2019-03-31 | 417706 | Work Order Description - 417706 - PM | PM | 4 | 545943 | SCHD | NORM-OPS | 2019-03-29 | 2019-10-20 | 2019-03-30 | 2019-04-18 | 2 | OPERATIONS | SAFETY | 9
2019-03-31 | 417716 | Work Order Description - 417716 - PM | PM | 4 | 411122 | WPLAN | NORM-OPS | 2019-03-22 | 2019-10-20 | 2019-04-06 | 2019-04-06 | 2 | OPERATIONS | SAFETY | 9
2019-03-31 | 417726 | Work Order Description - 417726 - PM | PM | 4 | 246094 | WPLAN | NORM-OPS | 2019-03-22 | 2019-10-20 | 2019-04-13 | 2019-04-13 | 2 | OPERATIONS | SAFETY | 9
2019-03-31 | 417732 | Work Order Description - 417732 - PM | PM | 4 | 362465 | SCHD | NORM-OPS | 2019-03-29 | 2019-10-26 | 2019-03-30 | 2019-04-18 | 2 | OPERATIONS | SAFETY | 1
2019-03-31 | 417826 | Work Order Description - 417826 - CM | CM | 4 | 675037 | WPLAN | EQUIP-ISOL | 2019-03-25 | 2021-03-21 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | MECHANICAL | 242
2019-03-31 | 417828 | Work Order Description - 417828 - CM | CM | 4 | 80136 | WPLAN | NORM-OPS | 2019-03-23 | 2019-06-15 | 2019-04-27 | 2019-04-27 | 2 | MAINTENANCE | MECHANICAL | 126
2019-03-31 | 417829 | Work Order Description - 417829 - CM | CM | 1 | 128898 | WSCHD | NORM-OPS | 2019-03-22 | 2021-03-20 |  |  | 4 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 417832 | Work Order Description - 417832 - CM | CM | 1 | 472760 | WSCHD | NORM-OPS | 2019-03-22 | 2020-03-21 |  |  | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 417861 | Work Order Description - 417861 - PM | PM | 4 | 540851 | WPLAN | EQUIP-ISOL | 2019-03-23 | 2019-09-14 | 2019-07-21 | 2019-07-21 | 2 | MAINTENANCE | INSTRUMENTS | 36
2019-03-31 | 417866 | Work Order Description - 417866 - PM | PM | 4 | 51662 | WSCHD | NORM-OPS | 2019-03-23 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 417868 | Work Order Description - 417868 - PM | PM | 2 | 572308 | WSCHD | NORM-OPS | 2019-03-23 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 417870 | Work Order Description - 417870 - PM | PM | 4 | 18972 | WSCHD | NORM-OPS | 2019-03-23 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 417872 | Work Order Description - 417872 - PM | PM | 4 | 355546 | WSCHD | NORM-OPS | 2019-03-23 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 417874 | Work Order Description - 417874 - PM | PM | 4 | 18973 | WSCHD | NORM-OPS | 2019-03-23 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 417876 | Work Order Description - 417876 - PM | PM | 4 | 355547 | WSCHD | NORM-OPS | 2019-03-23 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 417878 | Work Order Description - 417878 - PM | PM | 4 | 18985 | WSCHD | NORM-OPS | 2019-03-23 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 417880 | Work Order Description - 417880 - PM | PM | 4 | 355548 | WSCHD | NORM-OPS | 2019-03-23 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 417882 | Work Order Description - 417882 - PM | PM | 4 | 362466 | WSCHD | NORM-OPS | 2019-03-23 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 2 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 417884 | Work Order Description - 417884 - PM | PM | 4 | 246109 | WSCHD | NORM-OPS | 2019-03-23 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 2 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 417886 | Work Order Description - 417886 - PM | PM | 4 | 400005 | WPLAN | EQUIP-ISOL | 2019-03-23 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 1 | INTEGRITY | CONSTRUCTION | 9
2019-03-31 | 417888 | Work Order Description - 417888 - PM | PM | 4 | 267676 | WSCHD | NORM-OPS | 2019-03-23 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 2 | OPERATIONS | SAFETY | 2
2019-03-31 | 417890 | Work Order Description - 417890 - PM | PM | 4 | 580762 | WSCHD | NORM-OPS | 2019-03-23 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 417892 | Work Order Description - 417892 - PM | PM | 4 | 363762 | WPLAN | NORM-OPS | 2019-03-23 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 2 | MAINTENANCE | MECHANICAL | 65
2019-03-31 | 417894 | Work Order Description - 417894 - PSPM | PSPM | 1 | 481467 | WPLAN | NORM-OPS | 2019-03-23 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 1 | OPERATIONS | OPERATIONS | 15
2019-03-31 | 417896 | Work Order Description - 417896 - PM | PM | 1 | 446516 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 417898 | Work Order Description - 417898 - PSPM | PSPM | 1 | 29041 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 417900 | Work Order Description - 417900 - PM | PM | 4 | 527365 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 2 | MAINTENANCE | SAFETY | 7
2019-03-31 | 417902 | Work Order Description - 417902 - PM | PM | 4 | 96159 | SCHD | NORM-OPS | 2019-03-29 | 2019-11-07 | 2019-07-21 | 2019-07-21 | 2 | MAINTENANCE | MECHANICAL | 12
2019-03-31 | 417904 | Work Order Description - 417904 - PM | PM | 4 | 392396 | WPLAN | PACK-ISOL | 2019-03-23 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 2 | INTEGRITY | MECHANICAL | 4
2019-03-31 | 417906 | Work Order Description - 417906 - PSPM | PSPM | 1 | 451271 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 1 | MAINTENANCE | ELECTRICAL | 6
2019-03-31 | 417908 | Work Order Description - 417908 - PM | PM | 4 | 659870 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 2 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 417910 | Work Order Description - 417910 - PSPM | PSPM | 1 | 659059 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 1 | MAINTENANCE | SAFETY | 2
2019-03-31 | 417912 | Work Order Description - 417912 - PM | PM | 4 | 85066 | SCHD | NORM-OPS | 2019-03-29 | 2019-09-14 | 2019-07-21 | 2019-07-21 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 417914 | Work Order Description - 417914 - PM | PM | 4 | 659501 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 4 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 417916 | Work Order Description - 417916 - PM | PM | 4 | 659053 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 417918 | Work Order Description - 417918 - PSPM | PSPM | 1 | 669726 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 417920 | Work Order Description - 417920 - PM | PM | 3 | 664434 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 1 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 417922 | Work Order Description - 417922 - PM | PM | 4 | 448593 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-21 | 2019-07-21 | 2019-07-21 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 418192 | Work Order Description - 418192 - PSCM | PSCM | 1 | 409814 | WSCHD | NORM-OPS | 2019-03-24 | 2020-03-22 | 2019-09-21 | 2019-09-21 | 3 | INTEGRITY | FABRIC | 14
2019-03-31 | 418258 | Work Order Description - 418258 - BR | BR | 3 | 95307 | SCHD | EQUIP-ISOL | 2019-03-28 | 2020-03-22 | 2019-03-30 | 2019-03-31 | 3 | MAINTENANCE | MECHANICAL | 114
2019-03-31 | 418263 | Work Order Description - 418263 - BR | BR | 1 | 527313 | SCHD | NORM-OPS | 2019-03-29 | 2019-06-16 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 418265 | Work Order Description - 418265 - BR | BR | 3 | 438720 | WMATL | SYS-ISOL | 2019-03-25 | 2019-06-16 | 2019-07-13 | 2019-07-13 | 2 | MAINTENANCE | MECHANICAL | 68
2019-03-31 | 418278 | Work Order Description - 418278 - BR | BR | 3 | 671293 | WPLAN | PACK-ISOL | 2019-03-24 | 2019-09-23 | 2019-06-23 | 2019-06-23 | 3 | MAINTENANCE | MECHANICAL | 38
2019-03-31 | 418279 | Work Order Description - 418279 - BR | BR | 1 | 527313 | SCHD | NORM-OPS | 2019-03-29 | 2019-06-16 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 418280 | Work Order Description - 418280 - BR | BR | 1 | 494338 | WPLAN | PACK-ISOL | 2019-03-24 | 2020-03-22 | 2019-06-23 | 2019-06-23 | 3 | MAINTENANCE | MECHANICAL | 24
2019-03-31 | 418287 | Work Order Description - 418287 - BR | BR | 1 | 527313 | SCHD | NORM-OPS | 2019-03-29 | 2019-06-16 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 418297 | Work Order Description - 418297 - BR | BR | 1 | 527313 | SCHD | NORM-OPS | 2019-03-29 | 2019-06-16 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 418298 | Work Order Description - 418298 - BR | BR | 1 | 527313 | SCHD | NORM-OPS | 2019-03-29 | 2019-06-16 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 418300 | Work Order Description - 418300 - BR | BR | 3 | 658816 | WPLAN | EQUIP-ISOL | 2019-03-24 | 2019-06-16 | 2019-05-25 | 2019-05-25 | 2 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 418302 | Work Order Description - 418302 - BR | BR | 1 | 227866 | SCHD | NORM-OPS | 2019-03-29 | 2019-06-16 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 418306 | Work Order Description - 418306 - BR | BR | 1 | 527313 | SCHD | NORM-OPS | 2019-03-29 | 2019-06-16 | 2019-05-04 | 2019-05-04 | 2 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 418317 | Work Order Description - 418317 - BR | BR | 3 | 321894 | WPLAN | PACK-ISOL | 2019-03-24 | 2021-03-21 | 2019-09-22 | 2019-09-22 | 4 | MAINTENANCE | MECHANICAL | 98
2019-03-31 | 418344 | Work Order Description - 418344 - BR | BR | 3 | 326849 | WSCHD | EQUIP-ISOL | 2019-03-23 | 2019-09-22 |  |  | 3 | MAINTENANCE | MECHANICAL | 0
2019-03-31 | 418361 | Work Order Description - 418361 - BR | BR | 3 | 551113 | SCHD | PACK-ISOL | 2019-03-29 | 2021-03-22 | 2020-03-22 | 2020-03-22 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 418362 | Work Order Description - 418362 - PM | PM | 4 | 18317 | WSCHD | EQUIP-ISOL | 2019-03-24 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418364 | Work Order Description - 418364 - PM | PM | 4 | 18316 | WSCHD | EQUIP-ISOL | 2019-03-24 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418366 | Work Order Description - 418366 - PM | PM | 4 | 666316 | WPLAN | EQUIP-ISOL | 2019-03-24 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418368 | Work Order Description - 418368 - PM | PM | 4 | 417521 | WPLAN | EQUIP-ISOL | 2019-03-24 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418370 | Work Order Description - 418370 - PM | PM | 4 | 50099 | WSCHD | EQUIP-ISOL | 2019-03-24 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 418372 | Work Order Description - 418372 - PM | PM | 4 | 50098 | WSCHD | EQUIP-ISOL | 2019-03-24 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 418374 | Work Order Description - 418374 - PM | PM | 4 | 411571 | WSCHD | NORM-OPS | 2019-03-24 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418376 | Work Order Description - 418376 - PM | PM | 4 | 358159 | WSCHD | NORM-OPS | 2019-03-24 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418378 | Work Order Description - 418378 - PM | PM | 4 | 540667 | WSCHD | NORM-OPS | 2019-03-24 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 418380 | Work Order Description - 418380 - PM | PM | 4 | 678551 | WSCHD | NORM-OPS | 2019-03-24 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 418382 | Work Order Description - 418382 - PM | PM | 3 | 674189 | WSCHD | EQUIP-ISOL | 2019-03-24 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 418384 | Work Order Description - 418384 - PM | PM | 3 | 400409 | WSCHD | EQUIP-ISOL | 2019-03-24 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 418386 | Work Order Description - 418386 - PM | PM | 3 | 553673 | WSCHD | NORM-OPS | 2019-03-24 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418388 | Work Order Description - 418388 - PM | PM | 4 | 547429 | WSCHD | NORM-OPS | 2019-03-24 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | SERVICES | 2
2019-03-31 | 418390 | Work Order Description - 418390 - PSPM | PSPM | 1 | 470877 | WSCHD | NORM-OPS | 2019-03-24 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | MECHANICAL | 5
2019-03-31 | 418392 | Work Order Description - 418392 - PSPM | PSPM | 1 | 671828 | WSCHD | NORM-OPS | 2019-03-24 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 418394 | Work Order Description - 418394 - PM | PM | 4 | 360243 | WSCHD | NORM-OPS | 2019-03-24 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 2 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 418396 | Work Order Description - 418396 - PSPM | PSPM | 1 | 189054 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | OPERATIONS | OPERATIONS | 3
2019-03-31 | 418399 | Work Order Description - 418399 - PSPM | PSPM | 1 | 325633 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 418401 | Work Order Description - 418401 - PSPM | PSPM | 1 | 81212 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 418403 | Work Order Description - 418403 - PSPM | PSPM | 1 | 447441 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 418405 | Work Order Description - 418405 - PSPM | PSPM | 1 | 632455 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 418407 | Work Order Description - 418407 - PM | PM | 3 | 189054 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 2 | MAINTENANCE | MECHANICAL | 4.25
2019-03-31 | 418409 | Work Order Description - 418409 - PM | PM | 4 | 556260 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 2 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 418411 | Work Order Description - 418411 - PM | PM | 2 | 216011 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 3 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 418413 | Work Order Description - 418413 - PM | PM | 4 | 320026 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 2 | DRILLING | DRILLING | 10
2019-03-31 | 418415 | Work Order Description - 418415 - PM | PM | 4 | 216158 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 2 | DRILLING | DRILLING | 6
2019-03-31 | 418417 | Work Order Description - 418417 - PM | PM | 4 | 74216 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 418425 | Work Order Description - 418425 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 418427 | Work Order Description - 418427 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 418429 | Work Order Description - 418429 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 418431 | Work Order Description - 418431 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 418433 | Work Order Description - 418433 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 418435 | Work Order Description - 418435 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 418437 | Work Order Description - 418437 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 418439 | Work Order Description - 418439 - PM | PM | 4 | 450961 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 3 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 418441 | Work Order Description - 418441 - PSPM | PSPM | 1 | 527373 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 418443 | Work Order Description - 418443 - PSPM | PSPM | 1 | 378695 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 418445 | Work Order Description - 418445 - PSPM | PSPM | 1 | 378816 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 3 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 418447 | Work Order Description - 418447 - PSPM | PSPM | 1 | 451327 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 3 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 418449 | Work Order Description - 418449 - PSPM | PSPM | 1 | 528139 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 3 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 418451 | Work Order Description - 418451 - PSPM | PSPM | 4 | 527365 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 418453 | Work Order Description - 418453 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 418455 | Work Order Description - 418455 - PSPM | PSPM | 1 | 450986 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 418457 | Work Order Description - 418457 - PSPM | PSPM | 1 | 99232 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-22 | 2019-07-22 | 2019-07-22 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 418668 | Work Order Description - 418668 - CM | CM | 3 | 463283 | WPLAN | SYS-ISOL | 2019-03-25 | 2021-03-22 | 2020-03-22 | 2020-03-22 | 4 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 418681 | Work Order Description - 418681 - BR | BR | 3 | 321895 | WPLAN | PACK-ISOL | 2019-03-25 | 2020-03-23 | 2019-09-22 | 2019-09-22 | 3 | MAINTENANCE | MECHANICAL | 60
2019-03-31 | 418683 | Work Order Description - 418683 - CM | CM | 4 | 54216 | WSCHD | EQUIP-ISOL | 2019-03-25 | 2021-03-22 | 2019-05-18 | 2019-05-18 | 4 | MAINTENANCE | INSTRUMENTS | 34
2019-03-31 | 418695 | Work Order Description - 418695 - CM | CM | 1 | 680808 | WSCHD | NORM-OPS | 2019-03-25 | 2020-03-23 | 2019-09-22 | 2019-09-22 | 3 | MAINTENANCE | MECHANICAL | 34
2019-03-31 | 418696 | Work Order Description - 418696 - BR | BR | 3 | 33695 | WPLAN | PACK-ISOL | 2019-03-25 | 2020-03-23 | 2019-09-22 | 2019-09-22 | 3 | MAINTENANCE | MECHANICAL | 64
2019-03-31 | 418703 | Work Order Description - 418703 - CM | CM | 3 | 491792 | SCHD | TPS | 2019-03-29 | 2021-03-22 | 2020-03-22 | 2020-03-22 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 418705 | Work Order Description - 418705 - CM | CM | 3 | 554762 | SCHD | TPS | 2019-03-29 | 2021-03-22 | 2020-03-22 | 2020-03-22 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 418707 | Work Order Description - 418707 - CM | CM | 1 | 531852 | WSCHD | NORM-OPS | 2019-03-24 | 2019-09-23 | 2019-06-23 | 2019-06-23 | 3 | INTEGRITY | FABRIC | 355
2019-03-31 | 418711 | Work Order Description - 418711 - BR | BR | 3 | 663650 | SCHD | EQUIP-ISOL | 2019-03-29 | 2020-03-23 | 2019-09-22 | 2019-09-22 | 3 | MAINTENANCE | ELECTRICAL | 0
2019-03-31 | 418724 | Work Order Description - 418724 - BR | BR | 3 | 326849 | WPLAN | PACK-ISOL | 2019-03-25 | 2020-03-23 | 2019-09-22 | 2019-09-22 | 3 | MAINTENANCE | MECHANICAL | 78
2019-03-31 | 418743 | Work Order Description - 418743 - CM | CM | 4 | 484460 | WRISKREV | NORM-OPS | 2019-03-26 | 2021-03-22 |  |  | 4 | INTEGRITY | DRILLING | 144
2019-03-31 | 418746 | Work Order Description - 418746 - PSCM | PSCM | 1 | 541305 | WSCHD | EQUIP-ISOL | 2019-03-25 | 2021-03-22 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | INSTRUMENTS | 20
2019-03-31 | 418794 | Work Order Description - 418794 - BR | BR | 4 | 472798 | SCHD | NORM-OPS | 2019-03-29 | 2019-06-17 | 2019-05-05 | 2019-05-05 | 2 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 418820 | Work Order Description - 418820 - PM | PM | 4 | 400438 | WSCHD | EQUIP-ISOL | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 418822 | Work Order Description - 418822 - PM | PM | 4 | 545527 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 418824 | Work Order Description - 418824 - PM | PM | 2 | 314195 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418826 | Work Order Description - 418826 - PM | PM | 4 | 356946 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418828 | Work Order Description - 418828 - PM | PM | 4 | 356946 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418830 | Work Order Description - 418830 - PM | PM | 4 | 356946 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418832 | Work Order Description - 418832 - PM | PM | 4 | 356946 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418834 | Work Order Description - 418834 - PM | PM | 4 | 356946 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418836 | Work Order Description - 418836 - PM | PM | 4 | 671290 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418838 | Work Order Description - 418838 - PM | PM | 4 | 666260 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418840 | Work Order Description - 418840 - PM | PM | 4 | 666263 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418842 | Work Order Description - 418842 - PM | PM | 4 | 666261 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418844 | Work Order Description - 418844 - PM | PM | 4 | 356946 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 418846 | Work Order Description - 418846 - PM | PM | 4 | 356946 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418848 | Work Order Description - 418848 - PM | PM | 2 | 314195 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1.5
2019-03-31 | 418850 | Work Order Description - 418850 - PM | PM | 2 | 51289 | WPLAN | EQUIP-ISOL | 2019-03-25 | 2019-09-16 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 418853 | Work Order Description - 418853 - PM | PM | 2 | 308036 | WSCHD | EQUIP-ISOL | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 418855 | Work Order Description - 418855 - PSPM | PSPM | 1 | 457538 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 418857 | Work Order Description - 418857 - PM | PM | 2 | 262208 | WSCHD | EQUIP-ISOL | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 418859 | Work Order Description - 418859 - PM | PM | 3 | 359313 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418861 | Work Order Description - 418861 - PM | PM | 2 | 314195 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418863 | Work Order Description - 418863 - PM | PM | 2 | 321115 | WSCHD | NORM-OPS | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 418865 | Work Order Description - 418865 - PSPM | PSPM | 1 | 595631 | WSCHD | EQUIP-ISOL | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 1 | MAINTENANCE | INSTRUMENTS | 48
2019-03-31 | 418867 | Work Order Description - 418867 - PSPM | PSPM | 1 | 399802 | WPLAN | EQUIP-ISOL | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 1 | INTEGRITY | CONSTRUCTION | 5
2019-03-31 | 418869 | Work Order Description - 418869 - PM | PM | 4 | 545299 | WPLAN | PACK-ISOL | 2019-03-25 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 418871 | Work Order Description - 418871 - PM | PM | 4 | 481609 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 418873 | Work Order Description - 418873 - PM | PM | 4 | 476154 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418875 | Work Order Description - 418875 - PM | PM | 4 | 457792 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 1 | MAINTENANCE | MECHANICAL | 7
2019-03-31 | 418879 | Work Order Description - 418879 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 1 | MAINTENANCE | INSTRUMENTS | 30
2019-03-31 | 418889 | Work Order Description - 418889 - PM | PM | 4 | 97634 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 418891 | Work Order Description - 418891 - PM | PM | 4 | 527315 | SCHD | NORM-OPS | 2019-03-29 | 2019-09-16 | 2019-07-23 | 2019-07-23 | 2 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 418893 | Work Order Description - 418893 - PM | PM | 4 | 450692 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 1 | OPERATIONS | SAFETY | 2
2019-03-31 | 418895 | Work Order Description - 418895 - PSPM | PSPM | 1 | 527365 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 418897 | Work Order Description - 418897 - PSPM | PSPM | 1 | 392215 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 418899 | Work Order Description - 418899 - PM | PM | 2 | 450548 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-23 | 2019-07-23 | 2019-07-23 | 3 | OPERATIONS | OPERATIONS | 4
2019-03-31 | 418941 | Work Order Description - 418941 - BR | BR | 3 | 55873 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-04-02 | 2019-03-28 | 2019-03-28 | 1 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 418944 | Work Order Description - 418944 - CM | CM | 3 | 409871 | WSCHD | NORM-OPS | 2019-03-25 | 2019-06-18 | 2019-05-06 | 2019-05-06 | 2 | INTEGRITY | FABRIC | 36
2019-03-31 | 418945 | Work Order Description - 418945 - PRJ | PRJ | 1 | 626120 | SCHD | NORM-OPS | 2019-03-25 | 2020-03-24 | 2019-09-23 | 2019-09-23 | 3 | INTEGRITY | FABRIC | 9.5
2019-03-31 | 418946 | Work Order Description - 418946 - CM | CM | 4 | 363599 | WSCHD | NORM-OPS | 2019-03-25 | 2021-03-23 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | DRILLING | 39
2019-03-31 | 418955 | Work Order Description - 418955 - CM | CM | 3 | 409871 | WPLAN | TPS | 2019-03-25 | 2021-03-23 | 2020-05-02 | 2020-05-02 | 4 | INTEGRITY | CONSTRUCTION | 90
2019-03-31 | 418958 | Work Order Description - 418958 - BR | BR | 1 | 490539 | WPLAN | EQUIP-ISOL | 2019-03-27 | 2021-03-23 | 2020-03-23 | 2020-03-23 | 4 | INTEGRITY | INSTRUMENTS | 20
2019-03-31 | 419055 | Work Order Description - 419055 - BR | BR | 3 | 325186 | WRISKREV | EQUIP-ISOL | 2019-03-30 | 2019-06-23 |  |  | 2 | MAINTENANCE | INSTRUMENTS | 50
2019-03-31 | 419065 | Work Order Description - 419065 - BR | BR | 4 | 123937 | SCHD | NORM-OPS | 2019-03-29 | 2021-03-23 | 2019-03-28 | 2019-03-28 | 4 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 419067 | Work Order Description - 419067 - PRJ | PRJ | 4 | 255841 | WSCHD | NORM-OPS | 2019-03-29 | 2021-03-23 | 2020-03-23 | 2020-03-23 | 4 | MAINTENANCE | CONSTRUCTION | 60
2019-03-31 | 419089 | Work Order Description - 419089 - CM | CM | 4 | 436043 | SCHD | NORM-OPS | 2019-03-29 | 2021-03-23 | 2019-04-22 | 2019-04-22 | 4 | INTEGRITY | INSPECTION | 61
2019-03-31 | 419096 | Work Order Description - 419096 - CM | CM | 4 | 34879 | WPLAN | EQUIP-ISOL | 2019-03-30 | 2019-04-28 | 2019-04-13 | 2019-04-13 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 419097 | Work Order Description - 419097 - PRJ | PRJ | 4 | 312568 | WPLAN | NORM-OPS | 2019-03-26 | 2021-03-23 | 2020-03-23 | 2020-03-23 | 4 | ENGINEERING | ELECTRICAL | 40
2019-03-31 | 419098 | Work Order Description - 419098 - BR | BR | 3 | 98069 | SCHD | SYS-ISOL | 2019-03-29 | 2020-03-24 | 2019-09-23 | 2019-09-23 | 3 | INTEGRITY | MECHANICAL | 22
2019-03-31 | 419106 | Work Order Description - 419106 - CM | CM | 3 | 578830 | WRISKREV | NORM-OPS | 2019-03-25 | 2019-04-28 |  |  | 2 | WELLS | INSTRUMENTS | 1
2019-03-31 | 419120 | Work Order Description - 419120 - CM | CM | 3 | 540747 | WPLAN | NORM-OPS | 2019-03-26 | 2021-03-23 | 2020-03-23 | 2020-03-23 | 4 | MAINTENANCE | ELECTRICAL | 24
2019-03-31 | 419147 | Work Order Description - 419147 - BR | BR | 3 | 546184 | WSCHD | NORM-OPS | 2019-03-26 | 2020-03-25 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 419149 | Work Order Description - 419149 - BR | BR | 3 | 51130 | SCHD | NORM-OPS | 2019-03-26 | 2020-03-25 | 2019-03-30 | 2019-03-30 | 3 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 419151 | Work Order Description - 419151 - CM | CM | 4 | 352342 | WPLAN | EQUIP-ISOL | 2019-03-28 | 2021-03-24 | 2019-10-04 | 2019-10-04 | 4 | MAINTENANCE | INSTRUMENTS | 8
2019-03-31 | 419152 | Work Order Description - 419152 - PSPM | PSPM | 1 | 679146 | WSCHD | EQUIP-ISOL | 2019-03-26 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 419154 | Work Order Description - 419154 - PSPM | PSPM | 1 | 679146 | WSCHD | EQUIP-ISOL | 2019-03-26 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 419156 | Work Order Description - 419156 - PSPM | PSPM | 1 | 51902 | WSCHD | EQUIP-ISOL | 2019-03-26 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 419158 | Work Order Description - 419158 - PM | PM | 4 | 540691 | WSCHD | NORM-OPS | 2019-03-26 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 419160 | Work Order Description - 419160 - PSPM | PSPM | 1 | 355558 | WSCHD | NORM-OPS | 2019-03-26 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 419162 | Work Order Description - 419162 - PM | PM | 4 | 481470 | WSCHD | NORM-OPS | 2019-03-26 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 1 | MAINTENANCE | MECHANICAL | 16
2019-03-31 | 419164 | Work Order Description - 419164 - PSPM | PSPM | 1 | 650444 | WSCHD | NORM-OPS | 2019-03-26 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 1 | OPERATIONS | OPERATIONS | 15
2019-03-31 | 419166 | Work Order Description - 419166 - PSPM | PSPM | 1 | 675036 | WSCHD | NORM-OPS | 2019-03-26 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 1 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 419168 | Work Order Description - 419168 - PSPM | PSPM | 1 | 519759 | WSCHD | NORM-OPS | 2019-03-26 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 419170 | Work Order Description - 419170 - PM | PM | 4 | 212354 | WSCHD | NORM-OPS | 2019-03-26 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 2 | INTEGRITY | INSPECTION | 2
2019-03-31 | 419172 | Work Order Description - 419172 - PM | PM | 4 | 460846 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 1 | MAINTENANCE | MECHANICAL | 14
2019-03-31 | 419176 | Work Order Description - 419176 - PM | PM | 4 | 100182 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-09-17 | 2019-07-24 | 2019-07-24 | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 419178 | Work Order Description - 419178 - PSPM | PSPM | 1 | 528213 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 1 | OPERATIONS | SAFETY | 3
2019-03-31 | 419180 | Work Order Description - 419180 - PSPM | PSPM | 1 | 659551 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 419182 | Work Order Description - 419182 - PSPM | PSPM | 1 | 227791 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 419184 | Work Order Description - 419184 - PSPM | PSPM | 1 | 659338 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 419186 | Work Order Description - 419186 - PSPM | PSPM | 1 | 659339 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 419188 | Work Order Description - 419188 - PSPM | PSPM | 1 | 450926 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 1 | MAINTENANCE | MECHANICAL | 3
2019-03-31 | 419190 | Work Order Description - 419190 - PSPM | PSPM | 1 | 668570 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 419192 | Work Order Description - 419192 - PM | PM | 4 | 227826 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 2 | MAINTENANCE | ELECTRICAL | 100
2019-03-31 | 419194 | Work Order Description - 419194 - PSPM | PSPM | 1 | 227941 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-24 | 2019-07-24 | 2019-07-24 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 419317 | Work Order Description - 419317 - BR | BR | 3 | 26565 | WPLAN | NORM-OPS | 2019-03-29 | 2020-03-25 | 2019-09-24 | 2019-09-24 | 3 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 419346 | Work Order Description - 419346 - BR | BR | 1 | 238186 | WSCHD | EQUIP-ISOL | 2019-03-26 | 2020-03-25 |  |  | 3 | MAINTENANCE | ELECTRICAL | 0
2019-03-31 | 419351 | Work Order Description - 419351 - PRJ | PRJ | 4 | 481746 | WSCHD | NORM-OPS | 2019-03-26 | 2021-03-24 |  |  | 4 | INTEGRITY | CONSTRUCTION | 0
2019-03-31 | 419359 | Work Order Description - 419359 - CM | CM | 4 | 481746 | WRISKQ | NORM-OPS | 2019-03-29 | 2021-03-24 |  |  | 4 | INTEGRITY | CONSTRUCTION | 28
2019-03-31 | 419362 | Work Order Description - 419362 - BR | BR | 3 | 50763 | WSCHD | EQUIP-ISOL | 2019-03-26 | 2019-06-19 | 2019-04-06 | 2019-04-06 | 2 | INTEGRITY | MECHANICAL | 136
2019-03-31 | 419404 | Work Order Description - 419404 - CM | CM | 4 | 677472 | WSCHD | NORM-OPS | 2019-03-28 | 2020-03-25 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | ELECTRICAL | 8
2019-03-31 | 419405 | Work Order Description - 419405 - CM | CM | 4 | 247501 | WSCHD | NORM-OPS | 2019-03-28 | 2021-03-24 | 2020-03-24 | 2020-03-24 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 419406 | Work Order Description - 419406 - CM | CM | 4 | 314210 | WSCHD | NORM-OPS | 2019-03-28 | 2019-09-25 | 2019-06-25 | 2019-06-25 | 3 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 419461 | Work Order Description - 419461 - CM | CM | 3 | 272751 | WPLAN | NORM-OPS | 2019-03-28 | 2021-03-24 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | MECHANICAL | 23
2019-03-31 | 419469 | Work Order Description - 419469 - PM | PM | 4 | 295957 | WPLAN | EQUIP-ISOL | 2019-03-27 | 2019-08-25 | 2019-07-25 | 2019-07-25 | 2 | MAINTENANCE | OPERATIONS | 4
2019-03-31 | 419471 | Work Order Description - 419471 - PM | PM | 2 | 312718 | WPLAN | PACK-ISOL | 2019-03-27 | 2019-08-25 | 2019-07-25 | 2019-07-25 | 2 | MAINTENANCE | MECHANICAL | 11
2019-03-31 | 419475 | Work Order Description - 419475 - PM | PM | 4 | 99579 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-25 | 2019-07-25 | 2019-07-25 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 419477 | Work Order Description - 419477 - PSPM | PSPM | 1 | 632581 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-25 | 2019-07-25 | 2019-07-25 | 1 | OPERATIONS | SAFETY | 5
2019-03-31 | 419479 | Work Order Description - 419479 - PM | PM | 4 | 601923 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-25 | 2019-07-25 | 2019-07-25 | 2 | OPERATIONS | OPERATIONS | 60
2019-03-31 | 419491 | Work Order Description - 419491 - PSPM | PSPM | 1 | 123510 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-25 | 2019-07-25 | 2019-07-25 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 419493 | Work Order Description - 419493 - PM | PM | 4 | 266136 | WPLAN | PACK-ISOL | 2019-03-27 | 2019-08-25 | 2019-07-25 | 2019-07-25 | 2 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 419497 | Work Order Description - 419497 - PM | PM | 4 | 387912 | WPLAN | EQUIP-ISOL | 2019-03-27 | 2019-08-25 | 2019-07-25 | 2019-07-25 | 2 | MAINTENANCE | MECHANICAL | 9
2019-03-31 | 419503 | Work Order Description - 419503 - PM | PM | 4 | 668417 | WPLAN | EQUIP-ISOL | 2019-03-27 | 2019-08-25 | 2019-07-25 | 2019-07-25 | 2 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 419505 | Work Order Description - 419505 - PSPM | PSPM | 1 | 74979 | WPLAN | NORM-OPS | 2019-03-27 | 2019-08-25 | 2019-07-25 | 2019-07-25 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 419507 | Work Order Description - 419507 - PM | PM | 4 | 375597 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-10-06 | 2019-07-25 | 2019-07-25 | 3 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 419509 | Work Order Description - 419509 - PSPM | PSPM | 1 | 42961 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-25 | 2019-07-25 | 2019-07-25 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 419511 | Work Order Description - 419511 - PM | PM | 3 | 106085 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-11-11 | 2019-07-25 | 2019-07-25 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 419513 | Work Order Description - 419513 - PM | PM | 3 | 78465 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-11-11 | 2019-07-25 | 2019-07-25 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 419515 | Work Order Description - 419515 - PSPM | PSPM | 4 | 99434 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-25 | 2019-07-25 | 2019-07-25 | 1 | MAINTENANCE | SERVICES | 8
2019-03-31 | 419517 | Work Order Description - 419517 - PSPM | PSPM | 1 | 126920 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-25 | 2019-07-25 | 2019-07-25 | 1 | MAINTENANCE | ELECTRICAL | 1.5
2019-03-31 | 419519 | Work Order Description - 419519 - PM | PM | 4 | 126984 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-25 | 2019-07-25 | 2019-07-25 | 3 | INTEGRITY | OPERATIONS | 4
2019-03-31 | 419521 | Work Order Description - 419521 - PM | PM | 4 | 179063 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-25 | 2019-07-25 | 2019-07-25 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 419523 | Work Order Description - 419523 - PM | PM | 4 | 669999 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-25 | 2019-07-25 | 2019-07-25 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 419647 | Work Order Description - 419647 - BR | BR | 2 | 322668 | SCHD | EQUIP-ISOL | 2019-03-29 | 2021-03-25 | 2019-03-30 | 2019-03-30 | 4 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 419649 | Work Order Description - 419649 - BR | BR | 1 | 547508 | WPLAN | PACK-ISOL | 2019-03-28 | 2020-03-27 | 2019-09-26 | 2019-09-26 | 3 | MAINTENANCE | WELLS | 64
2019-03-31 | 419656 | Work Order Description - 419656 - CM | CM | 3 | 320440 | SCHD | SYS-ISOL | 2019-03-29 | 2019-04-25 | 2019-04-10 | 2019-04-11 | 2 | INTEGRITY | CONSTRUCTION | 13
2019-03-31 | 419662 | Work Order Description - 419662 - CM | CM | 1 | 685304 | SCHD | NORM-OPS | 2019-03-29 | 2021-03-25 | 2019-03-30 | 2019-03-30 | 4 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 419665 | Work Order Description - 419665 - CM | CM | 1 | 685304 | WSCHD | NORM-OPS | 2019-03-27 | 2021-03-25 | 2019-04-06 | 2019-04-06 | 4 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 419668 | Work Order Description - 419668 - CM | CM | 1 | 685304 | WSCHD | NORM-OPS | 2019-03-27 | 2021-03-25 | 2019-04-13 | 2019-04-13 | 4 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 419670 | Work Order Description - 419670 - CM | CM | 1 | 685304 | WSCHD | NORM-OPS | 2019-03-27 | 2021-03-25 | 2019-04-20 | 2019-04-20 | 4 | MAINTENANCE | INSTRUMENTS | 10
2019-03-31 | 419671 | Work Order Description - 419671 - PRJ | PRJ | 4 | 292661 | WRISKREV | EQUIP-ISOL | 2019-03-27 | 2021-03-25 |  |  | 4 | ENGINEERING | INSPECTION | 84
2019-03-31 | 419680 | Work Order Description - 419680 - CM | CM | 3 | 363683 | WRISKREV | NORM-OPS | 2019-03-27 | 2019-09-26 |  |  | 3 | INTEGRITY | FABRIC | 20
2019-03-31 | 419693 | Work Order Description - 419693 - CM | CM | 1 | 685304 | SCHD | NORM-OPS | 2019-03-29 | 2020-03-26 | 2019-03-30 | 2019-03-30 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 419695 | Work Order Description - 419695 - CM | CM | 1 | 685304 | WSCHD | NORM-OPS | 2019-03-27 | 2020-03-26 | 2019-04-06 | 2019-04-06 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 419702 | Work Order Description - 419702 - CM | CM | 1 | 685304 | WSCHD | NORM-OPS | 2019-03-27 | 2020-03-26 | 2019-04-13 | 2019-04-13 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 419704 | Work Order Description - 419704 - CM | CM | 1 | 685304 | WSCHD | NORM-OPS | 2019-03-27 | 2020-03-26 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 419712 | Work Order Description - 419712 - PSCM | PSCM | 1 | 357581 | WRISKREV | EQUIP-ISOL | 2019-03-27 | 2020-03-26 |  |  | 3 | MAINTENANCE | INSTRUMENTS | 54
2019-03-31 | 419716 | Work Order Description - 419716 - PM | PM | 4 | 567872 | WPLAN | PACK-ISOL | 2019-03-27 | 2019-05-28 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 419718 | Work Order Description - 419718 - PM | PM | 4 | 567872 | WPLAN | PACK-ISOL | 2019-03-27 | 2019-06-27 | 2019-05-27 | 2019-05-27 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 419720 | Work Order Description - 419720 - PM | PM | 4 | 567872 | WPLAN | PACK-ISOL | 2019-03-27 | 2019-07-28 | 2019-06-27 | 2019-06-27 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 419741 | Work Order Description - 419741 - BR | BR | 3 | 520416 | SCHD | EQUIP-ISOL | 2019-03-27 | 2020-03-26 | 2019-03-30 | 2019-03-30 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 419743 | Work Order Description - 419743 - CM | CM | 3 | 50471 | WRISKREV | NORM-OPS | 2019-03-27 | 2019-06-20 |  |  | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 419758 | Work Order Description - 419758 - BR | BR | 4 | 476716 | WRISKQ | NORM-OPS | 2019-03-29 | 2021-03-25 |  |  | 4 | MAINTENANCE | INSPECTION | 8
2019-03-31 | 419759 | Work Order Description - 419759 - PSPM | PSPM | 1 | 411321 | WSCHD | NORM-OPS | 2019-03-27 | 2021-01-01 | 2020-12-01 | 2020-12-01 | 1 | INTEGRITY | INSPECTION | 4
2019-03-31 | 419764 | Work Order Description - 419764 - PSPM | PSPM | 1 | 361166 | WSCHD | NORM-OPS | 2019-03-27 | 2021-01-01 | 2020-12-01 | 2020-12-01 | 1 | INTEGRITY | INSPECTION | 30
2019-03-31 | 419767 | Work Order Description - 419767 - CM | CM | 1 | 50470 | WRISKREV | NORM-OPS | 2019-03-27 | 2019-06-20 |  |  | 2 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 419772 | Work Order Description - 419772 - CM | CM | 1 | 315442 | WRISKREV | NORM-OPS | 2019-03-27 | 2020-03-26 |  |  | 3 | MAINTENANCE | ELECTRICAL | 110
2019-03-31 | 419793 | Work Order Description - 419793 - BR | BR | 3 | 72612 | WMATL | TPS | 2019-03-29 | 2019-09-26 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 140
2019-03-31 | 419794 | Work Order Description - 419794 - BR | BR | 3 | 444558 | WMATL | TPS | 2019-03-29 | 2019-09-26 | 2019-07-13 | 2019-07-13 | 3 | MAINTENANCE | MECHANICAL | 100
2019-03-31 | 419795 | Work Order Description - 419795 - CM | CM | 1 | 320745 | WRISKREV | SUBSYS-ISOL | 2019-03-27 | 2019-06-20 |  |  | 2 | DRILLING | DRILLING | 10
2019-03-31 | 419797 | Work Order Description - 419797 - BR | BR | 3 | 189101 | WPLAN | PACK-ISOL | 2019-03-29 | 2020-03-28 | 2019-09-27 | 2019-09-27 | 3 | MAINTENANCE | MECHANICAL | 6
2019-03-31 | 419799 | Work Order Description - 419799 - PM | PM | 4 | 650444 | WSCHD | NORM-OPS | 2019-03-28 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 3 | MAINTENANCE | ELECTRICAL | 3
2019-03-31 | 419801 | Work Order Description - 419801 - PM | PM | 4 | 51202 | WSCHD | NORM-OPS | 2019-03-28 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 419803 | Work Order Description - 419803 - PSPM | PSPM | 1 | 580769 | WSCHD | NORM-OPS | 2019-03-28 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 1 | MAINTENANCE | OPERATIONS | 8
2019-03-31 | 419805 | Work Order Description - 419805 - PM | PM | 4 | 48164 | WSCHD | EQUIP-ISOL | 2019-03-28 | 2019-09-19 | 2019-07-26 | 2019-07-26 | 2 | MAINTENANCE | MECHANICAL | 26
2019-03-31 | 419807 | Work Order Description - 419807 - PM | PM | 4 | 547429 | WSCHD | EQUIP-ISOL | 2019-03-28 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 1 | MAINTENANCE | SERVICES | 14
2019-03-31 | 419809 | Work Order Description - 419809 - PSPM | PSPM | 1 | 361803 | WPLAN | NORM-OPS | 2019-03-28 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 1 | MAINTENANCE | MECHANICAL | 8
2019-03-31 | 419811 | Work Order Description - 419811 - PSPM | PSPM | 1 | 546068 | WPLAN | NORM-OPS | 2019-03-28 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 1 | MAINTENANCE | SERVICES | 10
2019-03-31 | 419813 | Work Order Description - 419813 - PM | PM | 4 | 476155 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 2 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 419815 | Work Order Description - 419815 - PSPM | PSPM | 1 | 460846 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 1 | MAINTENANCE | MECHANICAL | 10
2019-03-31 | 419817 | Work Order Description - 419817 - PM | PM | 4 | 472552 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 1 | MAINTENANCE | ELECTRICAL | 14
2019-03-31 | 419819 | Work Order Description - 419819 - PM | PM | 4 | 403503 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 1 | MAINTENANCE | INSTRUMENTS | 11.5
2019-03-31 | 419821 | Work Order Description - 419821 - PM | PM | 4 | 320150 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 1 | MAINTENANCE | SAFETY | 1
2019-03-31 | 419825 | Work Order Description - 419825 - PM | PM | 4 | 74899 | WSCHD | PACK-ISOL | 2019-03-30 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 419827 | Work Order Description - 419827 - PM | PM | 4 | 451323 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 2 | INTEGRITY | INSPECTION | 2
2019-03-31 | 419829 | Work Order Description - 419829 - PSPM | PSPM | 1 | 663164 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 1 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 419831 | Work Order Description - 419831 - PM | PM | 4 | 527339 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 2 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 419833 | Work Order Description - 419833 - PSPM | PSPM | 1 | 527364 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 1 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 419835 | Work Order Description - 419835 - PSPM | PSPM | 1 | 527364 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 419837 | Work Order Description - 419837 - PSPM | PSPM | 1 | 527364 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 419839 | Work Order Description - 419839 - PSPM | PSPM | 1 | 527364 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 419841 | Work Order Description - 419841 - PM | PM | 4 | 398470 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 2 | MAINTENANCE | INSTRUMENTS | 49
2019-03-31 | 419843 | Work Order Description - 419843 - PM | PM | 4 | 659081 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-26 | 2019-07-26 | 2019-07-26 | 3 | MAINTENANCE | MEDIC | 21
2019-03-31 | 419910 | Work Order Description - 419910 - CM | CM | 3 | 189050 | WPLAN | NORM-OPS | 2019-03-30 | 2020-03-28 | 2019-09-27 | 2019-09-27 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 419911 | Work Order Description - 419911 - BR | BR | 4 | 247361 | WSCHD | NORM-OPS | 2019-03-30 | 2021-03-26 | 2019-04-13 | 2019-04-13 | 4 | INTEGRITY | SERVICES | 14
2019-03-31 | 419931 | Work Order Description - 419931 - BR | BR | 4 | 359983 | SCHD | NORM-OPS | 2019-03-29 | 2021-03-26 | 2019-03-30 | 2019-03-30 | 4 | MAINTENANCE | MECHANICAL | 20
2019-03-31 | 419947 | Work Order Description - 419947 - CM | CM | 4 | 237450 | WRISKREV | NORM-OPS | 2019-03-28 | 2020-03-27 |  |  | 3 | INTEGRITY | FABRIC | 75
2019-03-31 | 419948 | Work Order Description - 419948 - BR | BR | 1 | 97583 | WSCHD | NORM-OPS | 2019-03-28 | 2021-03-26 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 419951 | Work Order Description - 419951 - CM | CM | 1 | 237450 | WRISKREV | NORM-OPS | 2019-03-28 | 2020-03-27 |  |  | 3 | INTEGRITY | CONSTRUCTION | 200
2019-03-31 | 419959 | Work Order Description - 419959 - BR | BR | 1 | 536247 | WPLAN | NORM-OPS | 2019-03-30 | 2021-03-26 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 28
2019-03-31 | 419969 | Work Order Description - 419969 - BR | BR | 1 | 407683 | WSCHD | NORM-OPS | 2019-03-30 | 2021-03-26 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | INSTRUMENTS | 18
2019-03-31 | 419975 | Work Order Description - 419975 - CM | CM | 4 | 482038 | WSCHD | PACK-ISOL | 2019-03-28 | 2019-06-21 |  |  | 2 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 419976 | Work Order Description - 419976 - BR | BR | 1 | 535849 | WPLAN | NORM-OPS | 2019-03-30 | 2020-03-27 | 2019-04-20 | 2019-04-20 | 3 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 419989 | Work Order Description - 419989 - CM | CM | 3 | 463378 | WPLAN | EQUIP-ISOL | 2019-03-29 | 2019-09-27 | 2019-06-27 | 2019-06-27 | 3 | MAINTENANCE | INSTRUMENTS | 1
2019-03-31 | 419998 | Work Order Description - 419998 - BR | BR | 1 | 325841 | WPLAN | NORM-OPS | 2019-03-30 | 2021-03-26 | 2019-05-04 | 2019-05-04 | 4 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 420010 | Work Order Description - 420010 - BR | BR | 1 | 677817 | WSCHD | NORM-OPS | 2019-03-28 | 2021-03-26 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 24
2019-03-31 | 420035 | Work Order Description - 420035 - BR | BR | 1 | 657136 | WSCHD | NORM-OPS | 2019-03-28 | 2021-03-26 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 16
2019-03-31 | 420036 | Work Order Description - 420036 - BR | BR | 3 | 409744 | WPLAN | NORM-OPS | 2019-03-30 | 2019-04-26 | 2019-04-20 | 2019-04-21 | 2 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 420089 | Work Order Description - 420089 - PSPM | PSPM | 1 | 30652 | WPLAN | PACK-ISOL | 2019-03-28 | 2019-08-04 | 2019-07-04 | 2019-07-04 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 420109 | Work Order Description - 420109 - BR | BR | 4 | 98743 | WSCHD | TPS | 2019-03-28 | 2021-03-26 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 420111 | Work Order Description - 420111 - CM | CM | 1 | 266185 | WRISKREV | NORM-OPS | 2019-03-28 | 2019-09-27 |  |  | 3 | MAINTENANCE | MECHANICAL | 21
2019-03-31 | 420113 | Work Order Description - 420113 - BR | BR | 4 | 98725 | WSCHD | TPS | 2019-03-28 | 2021-03-26 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 420114 | Work Order Description - 420114 - BR | BR | 4 | 98775 | WSCHD | TPS | 2019-03-28 | 2021-03-26 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 420116 | Work Order Description - 420116 - BR | BR | 4 | 668792 | WSCHD | TPS | 2019-03-28 | 2021-03-26 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 420117 | Work Order Description - 420117 - BR | BR | 4 | 98698 | WSCHD | TPS | 2019-03-28 | 2021-03-26 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 420121 | Work Order Description - 420121 - PRJ | PRJ | 1 | 80451 | SCHD | NORM-OPS | 2019-03-29 | 2021-03-26 | 2019-03-29 | 2019-03-29 | 4 | MAINTENANCE | CONSTRUCTION | 224
2019-03-31 | 420130 | Work Order Description - 420130 - PSPM | PSPM | 1 | 661008 | WSCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 1 | OPERATIONS | OPERATIONS | 6
2019-03-31 | 420132 | Work Order Description - 420132 - PM | PM | 4 | 666261 | WSCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 420134 | Work Order Description - 420134 - PM | PM | 4 | 595820 | WSCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 420136 | Work Order Description - 420136 - PM | PM | 4 | 246173 | WSCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 1 | MAINTENANCE | SERVICES | 14
2019-03-31 | 420138 | Work Order Description - 420138 - PM | PM | 4 | 272070 | WSCHD | EQUIP-ISOL | 2019-03-29 | 2019-11-13 | 2019-07-27 | 2019-07-27 | 2 | MAINTENANCE | ELECTRICAL | 9
2019-03-31 | 420140 | Work Order Description - 420140 - PM | PM | 4 | 672639 | WSCHD | EQUIP-ISOL | 2019-03-29 | 2019-11-13 | 2019-07-27 | 2019-07-27 | 2 | MAINTENANCE | ELECTRICAL | 9
2019-03-31 | 420142 | Work Order Description - 420142 - PSPM | PSPM | 1 | 321203 | WSCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 420144 | Work Order Description - 420144 - PSPM | PSPM | 1 | 321218 | WSCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 1 | MAINTENANCE | ELECTRICAL | 4
2019-03-31 | 420146 | Work Order Description - 420146 - PM | PM | 4 | 267676 | WSCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 2 | MAINTENANCE | SAFETY | 4
2019-03-31 | 420148 | Work Order Description - 420148 - PM | PM | 4 | 666204 | WSCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 1 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 420150 | Work Order Description - 420150 - PM | PM | 4 | 294916 | WSCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 1 | MAINTENANCE | ELECTRICAL | 5
2019-03-31 | 420152 | Work Order Description - 420152 - PM | PM | 4 | 98009 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 1 | MAINTENANCE | MECHANICAL | 4
2019-03-31 | 420154 | Work Order Description - 420154 - PSPM | PSPM | 1 | 499149 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 1 | OPERATIONS | OPERATIONS | 2
2019-03-31 | 420156 | Work Order Description - 420156 - PSPM | PSPM | 1 | 99577 | SCHD | NORM-OPS | 2019-03-29 | 2019-07-21 | 2019-06-20 | 2019-06-20 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 420158 | Work Order Description - 420158 - PSPM | PSPM | 1 | 450481 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 1 | MAINTENANCE | ELECTRICAL | 2
2019-03-31 | 420160 | Work Order Description - 420160 - PM | PM | 4 | 567872 | WPLAN | PACK-ISOL | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 4 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 420166 | Work Order Description - 420166 - PM | PM | 4 | 528141 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 2 | INTEGRITY | INSPECTION | 8
2019-03-31 | 420168 | Work Order Description - 420168 - PSPM | PSPM | 1 | 527364 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 1 | MAINTENANCE | INSTRUMENTS | 4
2019-03-31 | 420170 | Work Order Description - 420170 - PM | PM | 4 | 452962 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 2 | MAINTENANCE | INSTRUMENTS | 2
2019-03-31 | 420172 | Work Order Description - 420172 - PM | PM | 4 | 670506 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 3 | MAINTENANCE | MECHANICAL | 2
2019-03-31 | 420174 | Work Order Description - 420174 - PSPM | PSPM | 1 | 375737 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 420176 | Work Order Description - 420176 - PSPM | PSPM | 1 | 74970 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 420178 | Work Order Description - 420178 - PSPM | PSPM | 1 | 375738 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 1 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 420180 | Work Order Description - 420180 - PM | PM | 4 | 449202 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 4 | MAINTENANCE | INSTRUMENTS | 7
2019-03-31 | 420182 | Work Order Description - 420182 - PM | PM | 4 | 387984 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 420184 | Work Order Description - 420184 - PM | PM | 4 | 96111 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 420186 | Work Order Description - 420186 - PM | PM | 4 | 375764 | SCHD | EQUIP-ISOL | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 2 | MAINTENANCE | MECHANICAL | 1
2019-03-31 | 420188 | Work Order Description - 420188 - PSPM | PSPM | 1 | 128057 | SCHD | NORM-OPS | 2019-03-29 | 2019-08-27 | 2019-07-27 | 2019-07-27 | 1 | OPERATIONS | OPERATIONS | 10
2019-03-31 | 420288 | Work Order Description - 420288 - BR | BR | 3 | 671528 | WRISKREV | EQUIP-ISOL | 2019-03-29 | 2020-03-28 |  |  | 3 | MAINTENANCE | ELECTRICAL | 12
2019-03-31 | 420290 | Work Order Description - 420290 - BR | BR | 2 | 51070 | WRISKREV | NORM-OPS | 2019-03-29 | 2021-03-27 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 12
2019-03-31 | 420297 | Work Order Description - 420297 - BR | BR | 3 | 95502 | SCHD | PACK-ISOL | 2019-03-29 | 2019-09-28 | 2019-06-28 | 2019-06-28 | 3 | MAINTENANCE | ELECTRICAL | 1
2019-03-31 | 420342 | Work Order Description - 420342 - BR | BR | 1 | 536293 | WRISKREV | NORM-OPS | 2019-03-29 | 2021-03-27 |  |  | 4 | MAINTENANCE | INSTRUMENTS | 3
2019-03-31 | 420370 | Work Order Description - 420370 - CM | CM | 4 | 66559 | WRISKREV | NORM-OPS | 2019-03-29 | 2021-03-27 |  |  | 4 | DRILLING | DRILLING | 27
2019-03-31 | 420376 | Work Order Description - 420376 - PRJ | PRJ | 3 | 76032 | WSCHD | NORM-OPS | 2019-03-30 | 2021-03-27 | 2019-03-29 | 2019-03-29 | 4 | INTEGRITY | CONSTRUCTION | 82
2019-03-31 | 420379 | Work Order Description - 420379 - PRJ | PRJ | 3 | 76032 | WSCHD | NORM-OPS | 2019-03-30 | 2021-03-27 | 2019-03-29 | 2019-03-29 | 4 | INTEGRITY | CONSTRUCTION | 70
2019-03-31 | 420381 | Work Order Description - 420381 - PRJ | PRJ | 3 | 76032 | WSCHD | NORM-OPS | 2019-03-30 | 2021-03-27 | 2019-03-29 | 2019-03-29 | 4 | INTEGRITY | CONSTRUCTION | 70
2019-03-31 | 420383 | Work Order Description - 420383 - PRJ | PRJ | 3 | 375637 | WSCHD | NORM-OPS | 2019-03-30 | 2021-03-27 | 2019-03-29 | 2019-03-29 | 4 | MAINTENANCE | CONSTRUCTION | 80
2019-03-31 | 420386 | Work Order Description - 420386 - PRJ | PRJ | 3 | 375637 | WSCHD | NORM-OPS | 2019-03-30 | 2021-03-27 | 2019-03-29 | 2019-03-29 | 4 | MAINTENANCE | CONSTRUCTION | 50
2019-03-31 | 420406 | Work Order Description - 420406 - PSCM | PSCM | 1 | 567376 | WPLAN | NORM-OPS | 2019-03-30 | 2019-09-28 | 2019-06-28 | 2019-06-28 | 3 | MAINTENANCE | INSTRUMENTS | 6
2019-03-31 | 420417 | Work Order Description - 420417 - PM | PM | 4 | 216009 | WSCHD | NORM-OPS | 2019-03-29 | 2019-05-25 | 2019-04-24 | 2019-04-24 | 3 | INTEGRITY | INSPECTION | 2
2019-03-31 | 420438 | Work Order Description - 420438 - PSCM | PSCM | 1 | 568548 | WPLAN | NORM-OPS | 2019-03-30 | 2019-09-28 | 2019-06-28 | 2019-06-28 | 3 | MAINTENANCE | INSTRUMENTS | 0
2019-03-31 | 420447 | Work Order Description - 420447 - BR | BR | 4 | 657993 | WSCHD | NORM-OPS | 2019-03-30 | 2021-03-27 | 2019-04-27 | 2019-04-27 | 4 | MAINTENANCE | FABRIC | 90
2019-03-31 | 420464 | Work Order Description - 420464 - CM | CM | 4 | 262786 | WRISKQ | NORM-OPS | 2019-03-29 | 2021-03-27 | 2019-04-01 | 2019-04-02 | 4 | INTEGRITY | OPERATIONS | 20